## NCRs
Número NCR | SBR | Disciplina | Data Criação | Nível | COS | CTE | Status | Descrição | Crítico | CEDOC Closure Data | Tipo de Produto | Tipo de Anomalia | Motivo da Anomalia | Deliberação N1 | Deliberação N2 | Deliberação N3 | Autor | Especialista 2.1 | Tempo de Tramitação | Especialista TA | Bigramas | NCR Original | NG added recommendations N2 | NG added recommendations N3 | Motivo da rejeição TA 2.2 Specialist | Data da rejeição TA 2.2 Specialist | Especialista responsável pela rejeição TA 2.2 Specialist | Motivo da rejeição TA 7.2 | Data da rejeição TA 7.2 | Especialista responsável pela rejeição TA 7.2 | Responsável TA 7.2
NCR-ICN-UFEM-12-0508-2019 | 53B | INTEGRATION EQUIPMENT | 2019-05-23 18:46 |  | COS-SMB-319737 |  | CEDOC Closure | During fitting on board of FQ00200, it was verified that the fastening elements were smaller than the necessary. It would have 40mm, but the received is 30mm lenght. ICN production team proposes to replace the received screws (CMD 32VI110D008000 - 30mm lenght) for 32VI110D00802 (40mm lenght). | Não |  |  |  |  | Replace the screws | Change screws by new more long (40mm). Opening of NCR MAT to supply new screws and update documentation. |  | Hellen Cristina Vieira Paes | Osvaldo Luiz de Moura Filho | 920 Dias |  |  |  | NO | [5 empty] | 2021-02-11 18:09 | Christophe Marret | Philippe Falquerho
NCR-ICN-UFEM-12-0510-2019 | 53B | PIPES | 2019-05-30 12:21 |  | COS-SMB-200470 |  | CEDOC Closure | The tube P4148809 will have to be modified for closure in the penetration piece AC34039. | Não |  |  |  |  | The pipe must be remanufactured according to the model. | Repair solution proposed by ICN will be accepted as far as trade and proximity rules are complied. Spool manufactured must pass through all controls predicted for P4148809 |  | Paulo Jose Lopes Almeida | Paulo Jose Lopes Almeida | 914 Dias |  |  |  | NO |  |  | 2019-11-01 16:27 | Frederic Pavic |  |  |  | Christophe Marret
NCR-ICN-UFEM-12-0511-2019 | 53B | ACOUSTIC DISCRETION | 2019-05-31 13:02 |  | COS-SMB-319720 | CTE00784506 | CEDOC Closure | Resilient mount compression is out of tolerance according to SMB-200949_E. See attached CTE00784506. | Não |  |  |  |  | Check the positioning of the equipment and resize the shims. | Maximum out of tolerance it's +0,9mm. | This concerns decoupling washers MN03-40 type for an auxiliary fitted decoupled on a suspended cradle on hull (room A130). Accept as is. | Marcos Aurelio Correa Abrantes | Rogerio Milani | 913 Dias |  | EM |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0512-2019 | 53B | SEATING | 2019-05-31 17:10 |  | COS-SMB-200386 |  | CEDOC Closure | During the final assembly of the seating P4021531, it has been found that the fasteners paid are smaller than necessary. See Annex 1. CMD: 32VI110D00830 - SCREW H M16X60X60 CLASS 8.8. | Não |  |  |  |  | We propose to use 32VI110D00832 (SCREW H M16X80X80 CLASS 8.8) as 1.2 mentioned. | Rework the screw H M16X60X60 CL8.8 FLZN mentioned are correct. use it. |  | Hellen Cristina Vieira Paes | Luiz Felipe Silva Moreira | 912 Dias |  |  |  | NO | [5 empty] | 2021-02-25 15:21 | Franciellen da Silva Braga | Philippe Falquerho
NCR-ICN-UFEM-12-0514-2019 | 53B | SEATING | 2019-06-10 19:27 |  | COS-SMB-200414 |  | CEDOC Closure | The seating P4024683 was welded according to the coordinate as shown in SBH.4C20.SAD.004523_D , but does not meet pipeclamp position due to deviation in pipe installation. | Não |  |  |  |  | Rework according to item 1.2 | Repair, remove the seating P4024683. Rework a new one and weld in the mirror view to match with teh clpipe clamp. |  | Hellen Cristina Vieira Paes | Rodrigo Altomare de Carvalho | 902 Dias | Alain Lamy |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-UFEM-12-0515-2019 | 53B | PIPES | 2019-06-11 13:56 |  | COS-SMB-206089 |  | CEDOC Closure | os spools P4156638 e P4176145 estão com o sistema e pressão de teste diferente um do outro, sendo que eles não estão sujetos a mesma pressão a montante da HP50003U. | Não |  |  |  |  | the spools P4176145 and P4156638 should both be tested with a pressure of 3.5 Bar which is the same test pressure as tube P4156638. | For construction purposes, please apply applicable isometrics. For SBR3 and 4 Naval Group will update TDP. |  | Paulo Jose Lopes Almeida | Paulo Jose Lopes Almeida | 902 Dias | Franck Rubis |  |  | NO |  |  | 2019-07-11 18:49 | Frederic Pavic |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0005-2019 | 53B | RESISTANT STRUCTURE | 2019-07-16 12:58 |  | COS-SMB-341062 |  | CEDOC Closure | Due to a problem in the power generator, two defects were verified in the machining of the male soft patch, according to the attached files. Defect Aft / Portside - width 18mm / Depth 2mm; Aft / Starboard - width 15mm / Depth 1mm. | Sim |  |  |  |  | Surfacing affected areas with TIG using procedure described in IT21-02-10 S11.2.3. | Rework as per annex. |  | Charles Douglas de Oliveira | Felipe Trigueiros Silveira | 867 Dias | Hugues Bourget |  |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0526-2019 | 53B | INTEGRATION EQUIPMENT | 2019-08-07 14:40 | Nível 2 | COS-SMB-319693 |  | CEDOC Closure | During the B01 test the drain valve KT03415 (P0113778) leaked. When the valve was removed it was found that the valve belzone coating broke (Annex 01). | Não |  |  |  |  | Redo Belzona and do CTE00939475 / 1 again If you have the SBR3 valve in stock, order and replace with the SBR2. | CMX: 18RT010D00716 Serial number: ???? The valve will be change by a new one. The serial number of the valve with the defect one have to be mentionned inside this NCR. All tracability document will be updated, control and pressure tests carry out again. The belzona will be repair in respect of rules of repairing. | Why did you send this NCR in level 3, the answer is made in level 2. The serial number of the valve is 154C268 as mentioned in one of the attachments. | Osvaldo Luiz de Moura Filho | Osvaldo Luiz de Moura Filho | 845 Dias | Patrick Daliguet |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0527-2019 | 53B | NON RESISTANT STRUCTURE | 2019-08-07 19:41 | Nível 2 | COS-SMB-200627 |  | CEDOC Closure | After finishing the GRP lamination process on the stern starboard hydroplane blade DP00252 – CMD 21SA000D00007, it was detected an absent machined recess on the pintle solid part. See annex 1. Product: DP00252 – STERN STARBOARD HYDROPLANE BLADE; Location: D111; Drawing: MAT214-1515. | Não |  |  |  |  | In accordance with production team, perform machining and repair the GRP lamination on the region according described in annex 2. | Rework, Carry out the modification as per annex 2 |  | Bruno Marcel Lima Ferreira Amancio | Bruno Marcel Lima Ferreira Amancio | 844 Dias | Hugues Bourget |  |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0008-2019 | 53B | ACOUSTIC DISCRETION | 2019-08-14 11:16 | Nível 1 | COS-SMB-200542 | CTE00931610, CTE00931608 | CEDOC Closure | 1 - EJ00003 and EJ00007 pumps are reversed on board SBR2. 2 - The EJ00003 pump nameplate has been lost, see attached photo. Note 1: EJ00003 PUMP: CMD 12GH000D00005, electric motor 2014489039 and serial number is 338/11-04. Note 2: EJ00007 PUMP: CMD 12PC000D00017 and serial number 087/13-03. | Não | 2021-03-15 19:36 |  |  |  | Follow according to deliberation. | NCR LEVEL 1 |  | Rogerio Milani | Rogerio Milani | 838 Dias |  | EJ |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0529-2019 | 53B | NON RESISTANT STRUCTURE | 2019-08-14 14:10 | Nível 2 | COS-SMB-200109 |  | CEDOC Closure | Problem 1 - A part of the equipment EX00040 was not considered by the design on the 3D mock up resulting on an interference between this item (chain guide) and the aft chain guide tube. See annex 1. Problem 2 - There is no way to tighten the fixing screws of the aft chain guide tube, as there is no access inside the support SC4-CV2-ST03. See annex 2. Product: SC4-CV2-TU-A – AFT CHAIN GUIDE TUBES Location: D240 Drawing: SMB-600060 | Não |  |  |  |  | Follow action 1.2 | Repair using the annex 4 and 5. | According to paragraph 2.2, repair according annex 4 and 5. Application of a coating type Adekit A210 on the cutted area to avoid corrosion between the steel and the vulcanization of the tube. Paint recovery on the cutted area. This decision is applicable on SBR2 only and should not be extended to other SBRs. | Osvaldo Luiz de Moura Filho | Osvaldo Luiz de Moura Filho | 838 Dias | Hugues Bourget |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0009-2019 | 53B | INTEGRATION EQUIPMENT | 2019-08-20 13:03 | Nível 2 | COS-SMB-319737 |  | CEDOC Closure | Hole diameters are outside tolerance H7. Pin diameters are out of tolerance F6. See CTE00943220 and CTE00943219. | Não |  |  |  |  | The bolt and hole have the largest diameters, but their adjustments are within tolerance H7 / f6 (See annex01). Accept as is. | The gap betwwen holes and screws are minimum 0mm and maximum 0,03mm. Theoretical gap is 0,025/0,066. | For the fitted screws n° 8 et 10, reduce the diameter in order to reach a minimum gap of 0,025 mm. See document FA255370 in annex. | Osvaldo Luiz de Moura Filho | Osvaldo Luiz de Moura Filho | 832 Dias | Patrick Daliguet |  |  | NO | NO |  |  |  |  | 2020-09-21 14:40 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0010-2019 | 53B | INTEGRATION EQUIPMENT | 2019-08-27 13:30 | Nível 2 | COS-SMB-319705 |  | CEDOC Closure | According the drawing MTSI205100100EXP, see notes in the drawing in annex, it is necessary to make an upward offset of 3 mm is applied in order to take account the wear of the fitting. During the machining of the internal bush, production team made a mistake and made an upward offset of 1.5mm. To reach 3mm in the radius the operator should have had put 6mm in the diameter. | Não |  |  |  |  | 1) Replace the Aft Immersed Bush (MB00005 - P0104799 - 14CO100D00003) from SBR 2 by SBR 4 (available in warehouse) and machine the external diameter respecting the clearance of 0/+0,04 mm according onboard machined dimensions, see Annex 1 (inspection sheet CTE00687337.2). 2) For the upward offset of 3 mm in the inner diameter, the operation must be following by TA Naval Group, ICN engineer and CQ Inspector to validate and authorize the machining. All operations must be done according documents MTSI205100100EXP_A and TAF-TA-2017-0822. | Agree with the proposed solution 1 Continue the installation of the shaft-line with this bearing , in thies conditions 2 Wait of the confirmation by NG Design to accept as it is. The feedback on this material permite to accept as it is. | REWORK : machine a new internal bush. Internal bush NGD 0930930013869 (quantity 2) have been delivered to Itaguai on 14/04/2020 through batch SMB-RMS-CUR-DB35/01. | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 825 Dias |  | MB |  | NO | NO |  | 2019-09-13 14:04 | Beatriz Branco Braz de Castro |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0011-2019 | 53B | PAINTING | 2019-08-30 17:57 | Nível 1 | COS-SMB-319316 | CTE100000145 | CEDOC Closure | According to the report COR-2019-903769 of Light Materials Specialist Anne-Camille, it was detected an irregularity in item I: Dust. SMB-326399 of CTE100000143. | Não |  |  |  |  | Perform rework as described in NCR-ICN-UFEM-11-897-2018. | NCR LEVEL 1 |  | Bruno Marcel Lima Ferreira Amancio | Bruno Marcel Lima Ferreira Amancio | 821 Dias |  |  |  | NO | [5 empty] | 2021-06-07 13:04 | Frederic Pavic | Christophe Marret
NCR-ICN-ESC-12-0027-2019 | 53B | PIPES | 2019-11-20 19:06 | Nível 2 | COS-SMB-206076 |  | CEDOC Closure | Catch screws of the system P4165367/EG50100G1 (from SBR2), to replace and finalize the fresh water system KT50231J3/P4122084 and KT50232J1/P4121749 (SBR1). | Não |  |  |  |  | It is necessary to take the bolting from SBR2 on EG50100G1 Type 2 lenght 80 dto do the mounting. | follow the decision 2.1 |  | Camila Fagundes de Paula Guedes | Sharles Gomes Silveira | 739 Dias | Franck Rubis | EG |  | NO | [7 empty] | Christophe Marret
NCR-ICN-UFEM-12-0531-2019 | 53B | NON RESISTANT STRUCTURE | 2019-09-13 14:12 | Nível 2 | COS-SMB-343995 | CTE00959820, CTE00959826 | CEDOC Closure | Dimensions are not according to drawing, see attached the following CTEs: CTE00959826.3 / CTE00959826.2 / CTE00959825.1 / CTE00959820.3 / CTE00959820.2 | Não |  |  |  |  | Accept as it is. See comments in document attached "2.1 ICN SOLUTION". | accept to realyze key wit a T profil |  | Rogerio Milani | Joao Paulo Schneider Gonzaga | 808 Dias | Charles Boucher |  |  | NO |  |  | 2019-10-21 12:48 | Philippe Falquerho |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0014-2019 | 53B | RESISTANT STRUCTURE | 2019-09-16 12:24 | Nível 2 | COS-SMB-349505 |  | CEDOC Closure | During onboard adjustment of the female Soft Patch with the male Soft Patch, the following anomalies were detected: 1) A misalignment of 10 mm was detected between the flat bars of the male Soft Patch and the female Soft Patch. Note: D82-41 template drawing SMB-327127_F that was used for flat bar mounting and inspection has a design error. 2) Due to deformation in the hull it is not possible to use the measuring tool to control the neutral fiber alignment of the hull. | Não |  |  |  |  | 1) Follow to level 2 decision. 2) Use optical mesurement to define the adjustment between male and female softpatch. | 1- Six parts was grinded to have a real inspection ( see annex). After analysis NV/TA proposes to continue the process because the worst gap founded is 10mm so the rest will be 15mm and we know that the male soft patch must me going down about 0,5 or 1mm to achieve the blue matching. 2- ok to use 3D inspection insteed of wooden template. See complemantary informations in annex | This problem is link with the NCR-ICN-ESC-12-0035-2019. Rework according decision of NCR-ICN-ESC-12-0035-2019. | Silvio Fonseca de Paiva | Felipe Trigueiros Silveira | 805 Dias | Hugues Bourget |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0015-2019 | 53B | INTEGRATION EQUIPMENT | 2019-09-20 18:44 | Nível 2 | COS-SMB-319719, COS-SMB-331842, COS-SMB-339470, COS-SMB-321710, COS-SMB-321709 |  | CEDOC Closure | All mobile parts of the attachment will be disassembled to be followed by the painting procedure. How will they be assembled as per SMB-002525. | Não |  |  |  |  | Run painting of mobile parts as described in DEI-200153-63120-12-002. | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. To remonte as indicated in Level 2, it is necessary to check the aspect of bolting which can be used only if it is not damaged and if we are sure that the torque value used is the value required in SMB-002465. If there is a doubt, the bolting need to be change. The gasket and the lock washers need to be change - it is not allowed to re-use them. The re-mounting of mobile parts need to follow SMB-200960 requirement and new inspections B06 or B11 (depending of the kind of mobile part) need to be redone. | Lucas Rosa de Sousa | Bruno Marcel Lima Ferreira Amancio | 800 Dias | Patrick Daliguet | AC | NCR-ICN-REGRESS-12-0006-2019 | NO | NO |  | 2019-10-09 19:14 | Hugues Bourget |  |  |  | Frederic Pavic
NCR-ICN-UFEM-12-0534-2019 | 53B | PIPES | 2019-10-18 11:55 | Nível 2 | COS-SMB-327471 |  | CEDOC Closure | During mounting on board was detected that the diameter of the passagem piece AF31558 and the spool P4165275 are incompatable | Não |  |  |  |  | Use the same solution as the attached NCR-ICN-UFEM-11-630-2017 that was applied to SBR1. | REPAIR with the same solution of the SBR1 for SBR 2 /3/4 refere to the FTG -6167 |  | Paulo Jose Lopes Almeida | Paulo Jose Lopes Almeida | 773 Dias | Franck Rubis |  |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0020-2019 | 53B | ACOUSTIC DISCRETION | 2019-10-23 18:36 | Nível 1 | COS-SMB-200569 | CTE00789691 | CEDOC Closure | There are no tilt sensors glued and the shock sensors were damaged on DA0004, see attached picture. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 |  | Luisa Kubrusly | Rogerio Milani | 767 Dias |  | DA |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0032-2019 | 53B | PIPES | 2019-12-09 17:57 | Nível 2 | COS-SMB-206089 |  | CEDOC Closure | During inspection on board it was identified the impossibility of correct assembly of the straub union between pipes P4140160 and P4125601. To avoid the simple remanufacture of the pipe, production team kindle suggest to add a niple and increase the pipe lenght at the cost of one aditional weld not foreseen in the project. | Não |  |  |  |  | To dictate the necessary length to get out of the interference, it will be necessary to create a CTEPROD.. This subject should be addressed directly at NCR.. | REPAIR Add a nipple to respect the fitting conformity of the STRAUB |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 720 Dias | Franck Rubis | BH |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0022-2019 | 53B | PIPES | 2019-11-05 11:50 | Nível 2 | COS-SMB-200444 |  | CEDOC Closure | The spool EJ500371J (P4134339) has no PR-ADDENDUM only has the isometric and is in revision "E" and it is necessary to adjust the spool. The flexible hose that connect to the spool is large. | Não |  |  |  |  | The spool EJ50037J1 (P4134339) should be adjusted as per board. | Decision: REPAIR Repair solution applied to SBR-2 will be acceptable. BO has been alerted about the problem in order to update isometric drawings and avoid the problem for the other SBR's. |  | Vladimir Gianotti Lopes | Paulo Jose Lopes Almeida | 755 Dias | Franck Rubis | EJ |  | NO |  |  | 2019-11-21 16:42 | Philippe Falquerho |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0023-2019 | 53B | PIPES | 2019-11-12 12:13 | Nível 1 | COS-SMB-206070 |  | CEDOC Closure | The whole construction process was performed according to the project, but the determined fit for the piping (P4148951 and P4148969) is not sufficient to compensate for the tolerances of the other structures. The pipe team asks you to supply a pipe with the same characteristics with a: -10 degree bend and 100mm overlenght for each side; -Display on board and mark the mounting position of the curve; -Create a Prod joint for control. | Não |  |  |  |  | Make a template for closing the pipe with the valve. This pipe has to be adjusted on board as it is in the junction area. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Paulo Jose Lopes Almeida | 748 Dias |  | EG |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0024-2019 | 53B | ELETRIC | 2019-11-14 16:49 | Nível 2 | COS-SMB-200434 | CTE00896515 | CEDOC Closure | Cannot open a RM12515P instrument cover by tube interference as per attached photos | Não |  |  |  |  | Wait for NG orientation | See FTG-8334 |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 745 Dias | Stéphane Patrick Philippe Rideau | RM |  | NO |  |  | 2020-03-03 19:12 | Philippe Falquerho |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0026-2019 | 53B | ACOUSTIC DISCRETION | 2019-11-19 13:23 | Nível 1 | COS-SMB-200716 | CTE00976176 | CEDOC Closure | During MS01-1 inspection was checked resilient mount compression out of tolerance. See attached CTE00976176 (record sheet). | Não |  |  |  |  | Make the necessary adjustments to obtain shim compression according to SMB-200965. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 741 Dias |  | BF |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0028-2019 | 53B | ACOUSTIC DISCRETION | 2019-11-21 18:39 | Nível 1 | COS-SMB-200716 | CTE00937373 | CEDOC Closure | During MS01 inspection on BF02540 was detected resilient mount compression out of tolerance. See attached CTE00937373 (inspection sheet) | Não |  |  |  |  | Its not in accordance with SMB-200965_D item 9.2.1.2 Rule for the compression of the MN45 mounts. Rework. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 738 Dias |  | BF |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0029-2019 | 53B | PIPES | 2019-12-05 17:36 | Nível 2 | COS-SMB-200444 |  | CEDOC Closure | As discussed with GIR as reported below Production, for connection to flexible hoses 18FH101D00060, the CMD 18RO220D00958 provided in the documentation is not compatible, but the CMD 18RO220D00054. This applies to 16 spools of the PR Addendum SMB-TDP-PR-5490640. De: 18RO220D00958 (THREATED CONNECT STAINSTEEL OD10, 2X1,6) + 44JO304D00001 (O-RING, METAL 8X22,8X2,6) Para: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10,2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | Não |  |  |  |  | Await NG definition. | Proposition to be validated in level 3. | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 724 Dias | Franck Rubis | EV |  | NO | NO |  | 2019-12-09 13:47 | Philippe Falquerho |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0031-2019 | 53B | STW | 2019-12-06 18:23 | Nível 2 | COS-SMB-200271 | CTE00841470 | CEDOC Closure | I inform that "HP SUPPLY HOSE / KE20021 / P0113082 / 18FH203D00062 / 18FH000C4712" is missing. | Não |  |  |  |  | The line "HP SUPPLY HOSE / KE20021 / P0113082 / 18FH203D00062 / 18FH000C4712" in reference needs to be found. If not found, replace by new one from SBR02 / SBR03 / SBR04. | These pipes have been delivered, but unfortunately ICN do not where there are. So it is necessary to write a NCR MAT in order to order some new. |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 723 Dias | Paul Fosse | KE |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0034-2019 | 53B | ELETRIC | 2019-12-10 19:30 | Nível 2 | COS-SMB-319321 |  | CEDOC Closure | As agreed with Mr. ERIC FOUGEROUSE, we are opening this NCR to solve the defected sensors of DEVELEC for the OAB. At least, we have counting a total of 57 damaged sensors and we need them to activate the batteries SBR 2. | Não |  |  |  |  | Buy new DEVELEC sensors. | 57 sensors are in defect on the OAB - 24 manufacturer failure - 33 ICN failure (preservation) => Replace these sensors | follow decision LVL3 in annex | Paulo Roberto de Souza | Paulo Roberto de Souza | 719 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO | NO |  | 2019-12-17 19:11 | Philippe Falquerho |  | 2020-12-15 18:41 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0035-2019 | 53B | MACHINING | 2019-12-19 16:00 | Nível 2 | COS-SMB-349505 | CTE00954300 | CEDOC Closure | During the adjustment of the male soft patch with the female after grinding machining for neutral fiber alignment it was detected that the thickness reached the minimum allowable limit and the Prussian blue did not reach 20% contact on the Fwd and Aft faces. | Não |  |  |  |  | Send to level 2.2. | To be decided by Naval Group back office after new measurement , gap between soft patch new thickness on both sof patch and blue machine on the face done last months C BOUCHER | Rework to be carried out according to TAF-1095. Stop point following the final positioning of the male soft patch with associated CTE. Following the analysis of this CTE, the resumption of work is authorized for the adjustment of the joint cover plates, however a new NCR must be issued for the carrying situation (The carrying criterias (20% + homogeneous distribution on each side) is deemed acquired on Bd and Td sides but not acquired on the Forward and Aft sides. Naval Group asks ICN to declare a new NCR (to be sent in level 3) about inspection CTE00954297 -SBR2-D59-05 which should not be considered "compliant" concerning the Forward and Aft sides mentioned above. Additional answer on 24/09/2020 : Deviations which have been reported by ICN on thickness of soft patch roundings have been validated by calculation by the design authority . | Silvio Fonseca de Paiva | Ernanes de Souza | 711 Dias | Charles Boucher |  |  | NO | NO |  |  |  |  | 2020-11-24 10:52 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0036-2020 | 53B | PAINTING | 2020-01-07 19:14 | Nível 1 | COS-SMB-319300 |  | CEDOC Closure | During inspection by the Brazilian Navy, we observed the difference between the paintings of SBR2 (PHOTO: A130_SBR2) and SBR3 (PHOTO: A130_SBR3) regarding the height of the buff painting in the bilge area. | Não |  |  |  |  | The height difference of the F1 scheme can be accepted in the state as there is anticorrosive paint applied in part of the area that should have the finishing paint. | NCR LEVEL 1 |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 691 Dias |  |  |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0037-2020 | 53B | ACOUSTIC DISCRETION | 2020-01-16 16:54 | Nível 2 | COS-SMB-200542 | CTE00978486, CTE00978496 | CEDOC Closure | After mounting the pumps DT00201 and DT00301 hoses and electric cables, resilient mounts compression out of tolerance was checked, in disagreement with SMB-200965_D. The NCR ICN-UFEM-12-469/2019 reports that the compression values were below the minimum value before mounting the hoses and electrical cables. See CTE00978496 and CTE00978486 in annex. | Não |  |  |  |  | Based on NCR-ICN-UFEM-12-469-2019 of SBR-1 with the same type of anomaly presented in SBR-2, we suggest accepting as is. | The maximum out of tolerance is 1,9mm. Accept as it is | Agreement to accept assembly as is. The analysis of controls A04 (Control of suspension frequencies) then the upstream / downstream vibration measurements (SHIP11C) on these auxiliaries will enable us to decide on these studs. | Marcos Aurelio Correa Abrantes | Rogerio Milani | 682 Dias | Patrick Daliguet | DT |  | NO | NO |  |  |  |  | 2020-07-09 18:45 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-ESC-12-0038-2020 | 53B | NON RESISTANT STRUCTURE | 2020-01-30 12:57 | Nível 2 | COS-SMB-324572 |  | CEDOC Closure | As seen error in the of the ballast in the battery spaces of (AR) the DG02130 refering to TIR-GGQ-2019-0068 it was necessary to remove the plates for the possible correction of the solid ballast safes. | Não |  |  |  |  | For deliberation by NG. | Rework. Remove the plates,Rectify the plates Correct the lead position. Reweld as per original |  | Luis Carlos da Costa Diniz | Sergio André Telles Soares | 669 Dias | Hugues Bourget | DG |  | NO |  |  | 2020-01-31 12:12 | Franciellen da Silva Braga |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0039-2020 | 53B | NON RESISTANT STRUCTURE | 2020-01-31 12:21 | Nível 2 | COS-SMB-200709 |  | CEDOC Closure | As seen error in the of the ballast in the battery spaces of (AV) the DG04100 refering to TIR-GGQ-2019-0120 it was necessary to remove the plates for the possible correction of the solid ballast safes. | Não |  |  |  |  | For deliberation by NG | Rework. Remove the lead in the wrong position Re install in a good position. Take the load Correct the plates shape Reweld the plates |  | Luis Carlos da Costa Diniz | Sergio André Telles Soares | 668 Dias | Hugues Bourget | DG |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0041-2020 | 53B | PRESERVATION | 2020-02-04 19:01 | Nível 2 | COS-SMB-206044, COS-SMB-200452 |  | CEDOC Closure | Swivel Hoses EM21002 and EN20015 were installed with the storage deadline exceeded. | Não |  |  |  |  | Wait for NG orientation | For EM21002 serial number: 18LF100D00003-25806-5259905: The storage limit date is 28/02/2018 and the date removal from storage is before. (14/07/2017) No problem for this swivel hose, the 8 years to use start the 14/07/2017. For EN20015 serial number: 18LF100D00003-24614-5259905: The storage limit date is 10/2017 and the date removal from storage is after. (20/02/2018) I propose for this swivel hose, the 8 years to use start the 10/2017 (storage limit date) | 1 / Keep on-board as they are the swivel hoses CMD 18LF100D00003. Consider that the equipment operational lifetime starts once the limit storage date has passed. 2 / Provide a precise statement of which swivel hoses are fitted on which boat for traceability and maintenance purposes. (non-respect of Naval Group's assignment requests) 3 / Adapt the maintenance schedule accordingly. (Ex : premature intervention on these swivel hoses while SRA) | Leonardo Andrade Gama | Sergio André Telles Soares | 663 Dias | Patrick Daliguet | EN |  | NO | NO |  |  |  |  | 2020-12-15 18:43 | Frederic Pavic | Christophe Marret
NCR-ICN-ESC-12-0045-2020 | 53B | NON RESISTANT STRUCTURE | 2020-02-14 16:34 | Nível 2 | COS-SMB-341403 |  | CEDOC Closure | During assembly, interference has been detected that impossibilities the correct positioning of the plates ST300. | Não |  |  |  |  | Do the propose in 1.2 as accorded with TA. After the positioning of ST300 weld again the piece that was cutted and inspect 100% VT ,100% PT or MT. | Repair, agreed with the proposal. Cut a 100mm plate weld with a correct gap as per SMB-200853 Carry out 100%VT 100% MT or PT |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 653 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0042-2020 | 53B | ELETRIC | 2020-02-06 13:10 | Nível 2 | COS-SMB-200240 |  | CEDOC Closure | As per attached email. There is a request to replace the BF02502 CVT2 equipment of the SBR2. The FORWARD converter SBR2 (001186-IV91-01-005) is normally the AFT converter of SBR3. ICN must be remove it and set up the converter 001186-IV91-01-004. It is necessary that the Naval Group provide the serial numbers of each converter for the correct installation in the respective Submarines. | Não | 2021-06-09 13:18 |  |  |  | The FWD SBR2 converter (001186-IV91-01-005) is the AFT converter of the SBR3. It is necessary to replace the converter 001186-IV91-01-004. | All the informations are in the document SMB-002931 |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 662 Dias | Stéphane Patrick Philippe Rideau | BF |  | NO | [5 empty] | 2020-09-04 14:13 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0059-2020 | 53B | ELETRIC | 2020-05-12 10:38 | Nível 2 | COS-SMB-319731 | CTE00799379 | CEDOC Closure | Damaged DA1 OFF button protection found on panel BF02505. | Não |  |  |  |  | Open NCRMAT, supply new | Open a NCR-MAT to supply and replace the RED protection by a new one : Supplier : MAFELEC 22 VCRED NGD 5930143490618 The breakage of the Mafelec shutter does not prevent the continuation of the tests and trials |  | Fabricio Duarte Ramos | Claudio Marcelo Guedes da Silva | 566 Dias | Stéphane Patrick Philippe Rideau | BF |  | NO | [5 empty] | 2020-10-23 12:58 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0043-2020 | 53B | NON RESISTANT STRUCTURE | 2020-02-12 13:44 | Nível 2 | COS-SMB-319115 |  | CEDOC Closure | A 70X70 CUT EAS MADE ON THE CL11-EL055 SHEET TO FACILITATE WELDING ACCESS ON THE PT-SL-225 SHEET. | Não |  |  |  |  | Do the cut of 70X70 in CI11-EL055-PLATE as in the annex. Following instructions from Naval Group. | Rework Rework as per original. Change the PLate CL11-EL055. Reweld and carry out all the inspection required. |  | Camila Fagundes de Paula Guedes | Luiz Felipe Silva Moreira | 656 Dias | Hugues Bourget |  |  | NO | [5 empty] | 2020-08-20 12:40 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0046-2020 | 53B | NON RESISTANT STRUCTURE | 2020-02-19 11:21 | Nível 2 | COS-SMB-319116, COS-SMB-321681 |  | CEDOC Closure | According TA guindance, the AF36006 cable gland should be replaced in A150 compartment. The correct cable is described in MAT-697-0034_A, page 15 of 36, divided into 04 CMD's: 11TE170D00063 11TE170D00070 11TE170D00075 11TE170D00098 | Não |  |  |  |  | Wait for guidance from NG. | Rework, Remove the passage AF396006 Build-up all around with TIG ( W42) Carry out the required inspection of IT21-02-10E 100%VT , 100%RT , 100%MT Machine with the good Diameter re-install a passageAF36006 |  | Charles Douglas de Oliveira | Sharles Gomes Silveira | 649 Dias | Hugues Bourget | AF |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0047-2020 | 53B | ELETRIC | 2020-02-20 12:25 | Nível 2 | COS-SMB-319321 |  | CEDOC Closure | The BMS computer it is not working. There ir a problem of initialization in the disk and the battery it isn't charging. | Não | [5 empty] | Naval Group confirms once again that this console must be replaced and that ICN can use that of the SBR3 or SBR4 while awaiting its replacement. Naval Group informs that the replacement of the BS02505 console is currently in progress and its arrival is imminent. For information, Naval Group has temporarily "repaired" the BIOS of the SBR2 console, but once again reminds you that it must be switched off correctly at each end of use so as not to lose the configuration. Finally, if this has not already been done, Naval Group reminds that ICN must open an NCR-MAT to formalize the replacement request. "There was no maintenance on the laptop during its storage. The battery on the motherboard is unloaded and the bios has lost its configuration. While waiting the replacement of the laptop (CMD 86VX000D00015), ICN can use the SBR3´s Laptop. Naval Group will not only have to replace the Laptop but specify in the PHST MS-01-b the maintenance in storage to be performed (power up every 6 months for 2h / battery´s replacement of the motherboard every 3 years) Sending to L3 for analysis." | Please take PHST SMB-322212_D into account ICN can use the SBR03 or SBR04 BMS maintenance PC as a temporary solution | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 648 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0060-2020 | 53B | SEATING | 2020-05-12 11:20 | Nível 2 | COS-SMB-200542 | CTE00759001 | CEDOC Closure | Interference in opening the EW03002 motor connection box with piping support. | Não |  |  |  |  | The seating is P4031085. According to the job orders CC-319644-18111-12-001_C and CC-319645-18111-12-001_B the drawning for it are updated and correct. Check the drawnings SBH.PLM.3B10.000457_G and SBH.PLM.3B10.002376_H if there ia a problem on board. | On SBR2 the seating EW00011C is conform to TDP (SBH.PLM.3B10.000457-G) and to 3 Model, The seating is designed to be dismounted, in order to access to the motor of pump EW0002. It is not necessary to modify this seating. |  | Fabricio Duarte Ramos | Luiz Felipe Silva Moreira | 566 Dias |  | EW |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0060-2017 | 53B | SEATING | 2017-06-29 03:00 |  | COS-SMB-200122 |  | CEDOC Closure | It was necessary to remove the 8 seating pads already welding on the seating ( mount 12, 24 , 14 , 13 , 23, 15 , 17 and 19 drawing SMB- 104293). | Não |  |  |  |  | REMOVE THE 8 SEATING PADS ALREADY WELDING ON THE SEATING 12,24,14,13,23,15,17 AND 19; ON THESE 8 SEATING MAKE THE FLATNESS BY BLUE MATCHING; IN WORKSHOP PREPARE 25 SHIMS ACCORDING SEE DRAWING SMB-104291 (THICKNESS 20). ON EACH SHIMS PREPARE 5 FACES, THE TOP ONE WILL BE MAHINE AFTER THICKNESS CALCULATION; MACHINE THE 25 SHIMS AND WELD EACH ON THE CORRESPONDED SEATING. (WELD BEAD A=3). | #AGREES WITH PARAGRAPHE 2.1 REWORK | flow error. Never been treated in L3. | System |  | 1614 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0106-2018 | 53B | PIPES | 2018-02-09 02:00 | Nível 2 | COS-SMB-206112, COS-SMB-206114 |  | CEDOC Closure | The spools P4503093-P4503092-P4503091-P4503090-P4503089 were manufactured and pre-installed in rev A, but there was a revision B in the design and the thickness of the tubes was modified. | Não |  |  |  |  | REWORK DECISION: REWORK SEE ATTACHED INFALT'S. | As ICN did not respect the first decision given in 2018 , by force new decision is accept as it is first decision was REWORK THE SPOOLS P4503087 / P4503088 / P4503089 / P4503090 / P4503091 / P4503092 / /4503093 IN STEEL 048,3 THICKNESS 2,6 AS PER TDP-IS. | N/A | System |  | 1389 Dias | Alain Lamy |  |  | NO | NO |  | 2020-05-04 14:54 | Frederic Pavic |  |  |  | Christophe Marret
NCR-ICN-UFEM-12-0152-2018 | 53B | NON RESISTANT STRUCTURE | 2018-03-27 03:00 |  | COS-SMB-200542 | CTE00758978 | CEDOC Closure | It was detected during the test (M09 - Equipment fitting) that it is impossible to carry out the test through port R (Inlet) because the grease returns to the tank, according to the diagram of the page 6/14 of the MAT524-0202. | Não |  |  |  |  | NG to deliberate | NG/TA ANALYSIS: PMS EXIGIBLE FOR INTER AND OUTLET OF THE HP GREASE PRODUCTION UNIT: R= 10 BARS P= 56 BARS DECISION: NG MUST UPDATE THE PROCEDURE MAT524-0202_A. | DOCUMENT BDM-00078969_B / MAT524-0202 HAVE BEEN UPDATED IN TDP-IS TO REVISION B. | System |  | 1343 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0221-2018 | 53B | NON RESISTANT STRUCTURE | 2018-07-10 03:00 |  | COS-SMB-321800 |  | CEDOC Closure | The passage pieces AF35035, AF35018, AF35063 and AF35075 were missed, so it will be necessary to manufacture new pieces for SBR2. | Não |  |  |  |  | SEE PROPOSAL IN THE ANNEX1. DECISION: SEE ANNEX1. |  | N/A | System |  | 1238 Dias |  |  |  |  | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0242-2018 | 53B | MECHANICAL | 2018-07-30 03:00 |  | COS-SMB-331842 |  | CEDOC Closure | According to the PR-Addendum (SMB-TDP-PR-5607948) the studs required for the assembly of the mobile part AC41019 would be 95mm in length (CMD: 32VI220D00161), but with this length it is not possible shown the 2 threads required to be accordance with SMB- | Não |  |  |  |  | WAIT NG DECISION. IF IT WILL BE NECESSARY CHANGE THE STUD AND JOINT, NG PLEASE INFORM THE NEW NUMBER OF THE NEW PR. DECISION: TO BE FORWARDED TO EXPERT LEVEL 2. | DECISION: APPLY FTG-5839. | N/A | System |  | 1218 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0258-2018 | 53B | MECHANICAL | 2018-09-03 03:00 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | CEDOC Closure | During the dismantling of the adjustable bolts there was detachment of material due to burrs generated by the machining process of the 40H7 hole of the Removable Shaft (MB00002) of the propeller shaft. | Não |  |  |  |  | Repair according to solution 1 (see annex 1). | Agree to repair according to the proposed solution and accept. Decision: repair and machining the bolt (from SBR3) accordinly. (Charles Boucher). | N/A | System | Joao Paulo Schneider Gonzaga | 1183 Dias | Charles Boucher | MB |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0279-2018 | 53B | ELETRIC | 2018-08-24 03:00 |  | COS-SMB-200494, COS-SMB-348462 |  | CEDOC Closure | The cable HX62511R is not long as necessary to fit the design route. Current lenght 8,3m / Lenght required 12,0m. | Não |  |  |  |  | WAIT FOR NG ORIENTATION. DECISION: TO BE FORWRDED TO EXPERT LEVEL 2. | REPLACE THE CABLE HX625IIR OF 8,3M BY ONE OF 12M. (SEE THE FTG-5749). THE ROUTING CABLE FILE WILL BE UP DAHED )SMB-330521). DECICION: REWORK. | N/A | System |  | 1193 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0306-2018 | 53B | PIPES | 2018-09-25 03:00 |  | COS-SMB-200443 |  | CEDOC Closure | The spool P4134328 according to its conformation can not be installed because interfere with the exchanger which is permanently installed. We will have to cut the spool and add ruch fittings and make a fixture in place, adding a seating and clamp (OD36). | Não |  |  |  |  | REWORK THE SPOOLAS ATTACHED. APPLICATION ONLY FOR SBR2. | All nuts turn of 5° when it was tighet at the torque valve. Decision: Accept as it is. | After the observation of the rotation of 5º of the nuts, it was asked to wait for 16 additional hours and to redo a pass (which is not specify in this NCR). After that there was no new rotation, so no evolution of creep. On this basis, accept as it is. Ho | System |  | 1161 Dias |  |  |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0317-2018 | 53B | PIPES | 2018-10-03 03:00 |  | COS-SMB-206071 |  | CEDOC Closure | Clamp P4155911 interferes with tube P4130261, since the clamp P4130262 has a port deviation of + 10mm. | Não |  |  |  |  | REWORK THE SPOOL USING THE COORDINATES DEFINED IN THE PROJECT. DECISION: REWORK. | REFERE TO THE FTG-5777. DECISION: REWORK. | N/A | System |  | 1153 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0318-2018 | 53B | PIPES | 2018-10-04 03:00 |  | COS-SMB-206061 |  | CEDOC Closure | The tubes P4108425, P4108536, P4108417 and P4108421 rudder carbon steel galvanizing has problems and outside the criterion of acceptance of SMB-0030500 (STF 33-04-16E). | Não |  |  |  |  | Use solution described in NCR-ICN-UFEM-11-346-2015. | Paint the pipe for SBR-2. For the other SBR. Try the valvanisation external orientation without internal + painting. Decision: Repair. | N/A | System |  | 1152 Dias |  |  |  | NO | NO |  |  |  |  | 2020-04-21 13:13 | Frederic Pavic | Christophe Marret
NCR-ICN-UFEM-12-0325-2018 | 53B | PIPES | 2018-10-10 03:00 |  | COS-SMB-206071 |  | CEDOC Closure | the tube P4154302 rev A for the closing with the valve P0120052 was missing 50mm, because the valve came with different dimension. | Não |  |  |  |  | ADD 50MM IN THE PIPER, AS THE VALVES SUPPLIED ARE DIFFERENT FROM THAT PROVIDED IN THE DESIGN DECISION: SEE ATTACHED THE LIST OF PRODUCTS IMPACTED BY THE | REFERE TO THE FTG-6024. | N/A | System |  | 1146 Dias |  |  |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0331-2018 | 53B | INTEGRATION EQUIPMENT | 2018-10-15 03:00 |  | COS-SMB-319719 |  | CEDOC Closure | During the fitting of the mobile part (AC41020) and the spools (P4162647 and P4162648), it was noted that the screws, which make the mobile coupling (32VI220D00171 - PITCH DIAMETER ROD M18-126 EQ (X05T)) damage the copper pipes , according to the attached | Não |  |  |  |  | WAIT FOR NG DECISION. | AGREE WITH PROPOSED SOLUTION. DECISION: -REPLACE STUD ROD M18X126(X05T)32VI220D00171 BY STUD ROD M18X116(X05T) 32VI220D00170. -UPDATE DOCUMENTATION. -TO BE FORWARDED TO EXPERT LEVEL 3. | AGREE WITH DECISION: STUD ROD TYPE HAVE TO BE CHANGED. MODIFICATIONS SENT TO ICN VIA PR ADDENDUM SMB-TDP-PR-5707115. | System |  | 1141 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0354-2018 | 53B | SEATING | 2018-11-19 02:00 |  | COS-SMB-319496 |  | CEDOC Closure | During SBR2 Diesel Cradle Pressure Transmitters fitting, it was verified that the manufacturing and installation of the seating was correct, however the equipment P0135338 and P0135339 that ICN production team received was smaller in relation to the seati | Não |  |  |  |  | MANUFACTURE A NEW BLACKET ACCORDING TO THE EQUIPMENT. DECISION: NG MUST CORRECT THE PROJECT. | NG/TA don't have information. To be sent to level 3. | It is necessary to mount sensors in 62 mm (those of 38 mm to not correspond to the definition) and to keep the provided seating. The configuration must be identical on all boats. Check if there was not na error in the storage of the ICN store because only | System |  | 1106 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0361-2018 | 53B | PIPES | 2018-11-23 02:00 |  | COS-SMB-206096 |  | CEDOC Closure | At LMA-04B202-S2AFM03-CE-12-003_C you are paying CMD 18PA000D00039 for RP P0115970. As spec asks us to use a plug CMD 44BO230D00137 and join 44JO303D00036. | Não |  |  |  |  | UNFOUNDED, A RIDA WILL BE CREATED. DECISION: UNFOUNDED | REFERE TO TEH FTG-6017. DECISION: REWORK. | N/A | System |  | 1102 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0367-2018 | 53B | SEATING | 2018-11-30 02:00 |  | COS-SMB-200733 |  | CEDOC Closure | Seating P4029064 parts where the mounts will seat are not well squared preventing the equipment FC00530 from being fitted. Remove items 023, 025, 031, 032, 033, 035, 036, 037, 049, 050, 051, 052, 054, 055 e 058 (See annex 1) and reinstall using a mock u | Não |  |  |  |  | Wait for NG orientation about 1.2 | REMOVE THE ELEMENTS (ITENS) 23;25;31;32;33;35;36;37;49;50;51;52;54;55; AND 58. USE A MACKUP, CHECK THE HORIZONTALITY AND REWELD A NEW ELEMENTS. | N/A | System |  | 1095 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0378-2018 | 53B | MECHANICAL | 2018-12-17 02:00 |  | COS-SMB-200581 |  | CEDOC Closure | During fitting of DB0004, it was verified that there was an interference in the position detection device because the drilling, as shown in annex (pages 1 and 2), the part only allows the cable gland to be turned forward, but there was interference with t | Não |  |  |  |  | WAIT FOR NVG DECISION. SEE 1.2 DECISION: TO BE FORWARDED TO EXPERT LEVEL 2. | DB00004 AND DB00001 ARE INVOLVED ON ALL SMB. CATEGORY 2: MAJOR. DECISION: -DEFINE A NEW SUPPORT FOR DB00001 AND DB00004 SWITCH. -UPDATE DOCUMENTATIONS AND LAUNCH HE NEW SUPPORTS. TO BE FORWARDED TO EXPERT LEVEL 3. | ICN PROPOSAL IS NOT ACCEPTABLE. ICN HAVE TO WAIT FR UNTERFACE PIECE MODIFICATION THAT NAVAL GROUP WILL SEND VIA PR ADDENDUM. PR-5915755 OM103888 | System |  | 1078 Dias |  |  |  | NO | NO |  |  |  |  | 2021-02-04 16:48 | Christophe Marret | Christophe Marret
NCR-ICN-UFEM-12-0382-2018 | 53B | INTEGRATION EQUIPMENT | 2018-12-20 02:00 |  | COS-SMB-319771 |  | CEDOC Closure | According to part list, the ICN mechanical team received the coated screws M14x100 CL8.8 (32VI110D01174), but during assembly of the equipment (FQ00804), it was verified that the screws need to be replaced by M14x90 (stainless steel) and it is necessary t | Não | 2021-07-20 13:29 |  |  |  | WAIT FOR NG POSITION ABOUT THE PROPOSAL IN ITEMS 1.1 AND 1.2. DECISION: IF NG AGREES WITHE THE PROPOSAL, THE PROJECT AND THE TDP-IS MUST BE MODIFIED. | THE MOUNTING IS NOT CONFORM AS INDICATED ON DRAWING (SBH.2D31.SMD-006445). THE BOLTS AND HUTS DEFINED ON THE NOMENCLATURE ARE NOT COMPATIBLE WITH THIS CASE. HOLE DAMETERS OF SHIMS ARE NOT COMPATIBLE WITH THE DIAMETER OF SCREWS. REPLACE FIXING SCREW ON DEE | THE NUTS AND BOLTS MENTIONED ARE NOT THE RIGHT ONES. SEE PR ADDENDUM SMB-TDP-6027759: 6 LACES 32VI220D00516 (M14X100X05T) / 12 NUTS 32VI320D00013 (M14X05T) / 12 ANGLE BRAKES 32VI420D00030(DN14X6CRNITI18-10). THESE 3 CMD HAVE BEEN DELIVERED TO ICN IN QUANT | System |  | 1075 Dias |  |  |  | NO | NO |  |  |  |  | 2020-12-07 17:11 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-UFEM-12-0392-2019 | 53B | ACOUSTIC DISCRETION | 2019-01-15 02:00 |  | COS-SMB-200542 |  | CEDOC Closure | During installation of Air Conditioning FC00526 were checked the following non conformities: a) According to SMB-200949_D (item 6.1.2), Annex 1, equipment support thickness must be 15mm to enable the assembly of the MN03 resilient mount. It was checked eq | Não |  |  |  |  | a) Machining of 6 washers with external diameter 60 mm, internal diameter 21 mm and thickness 5 mm, and assembly the mounts with these washers attached to equipment support; b) Carry out a review of the drawing SBH.3B10.SAD.004151_A in order to change th |  | N/A | System |  | 1049 Dias |  |  |  |  | NO |  |  |  |  | 2020-12-07 18:28 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-UFEM-12-0395-2019 | 53B | MECHANICAL | 2019-01-22 02:00 |  | COS-SMB-345144, COS-SMB-345144 | CTE00895167, CTE00895167 | CEDOC Closure | During inspection of the threaded holes in the faces of the upper rudder DP00155 and the lower rudder DP00156 problems were detected in the threads M16 and position of the holes. See D63-11_CTE00895161 / 1 and D63-11_CTE00895167 / 2. | Não |  |  |  |  | FOLLOW ANNEX 1. | AGREE TO REPARE AS PER THE FOLLOWING ANNEX. DECISION: REPAIR AND MAKE NEW HOLES ACCORDING THE PROPOSED SOLUTION. | N/A | System |  | 1042 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0400-2019 | 53B | HVAC | 2019-01-28 02:00 |  | COS-SMB-206202 |  | CEDOC Closure | The rivet would be assemble in the filter (500 x 700 x 100) but they are in the filter frame, therefore it is not possible to assemble the two elements. The holes highlighted in the photo nº 1 needs to be displaced, because they coincide with the bars of | Não |  |  |  |  | Manufacture new filter frama as MAT 853-0237 FL.7, without rivets. Drill new holes for the ones indicated in green on photo number 1 attached. The holes must not be coincident wih the support bars of the filter. The rivets must be fixed on filter box as t | REFERE TO THE FTG-6273 DECISION: REPAIR | N/A | System |  | 1036 Dias |  |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0433-2019 | 53B | RESISTANT STRUCTURE | 2019-02-22 03:00 |  | COS-SMB-319096, COS-SMB-319096 | CTE00963959, CTE00963959 | CEDOC Closure | DURING DIMENSIONAL INSPECTION, IT HAS BEEN VERIFIED THAT SOME MEASURES ARE IN DISAGREE WITH THE PROJECT, AS INDICATED IN THE DRAWING SMB-104831 IN ANNEX. | Não |  |  |  |  | DECISION: SEE ANNEX 1. TO BE FORWARDED TO EXPERT LEVEL 2. | SCRAP REWORK ANEXX PICCES THE SBR4 ELEMENTS CAN BE USE IF NECESSARY OPEN A NEW NCR | N/A | System |  | 1011 Dias |  |  |  | NO | NO |  |  |  |  | 2021-04-30 13:19 | Frederic Pavic | Frederic Pavic
NCR-ICN-UFEM-12-0443-2019 | 53B | PIPES | 2019-03-11 03:00 |  | COS-SMB-321801 |  | CEDOC Closure | the tube P4157955 is isometric with the height of the flange in disagreement with the connecting hose. | Não |  |  |  |  | DESPITE THE SPOOL CONFIGURATION INCLUED IN THE LAST VERSION OF THE 3D MODEL AND THE NEW HOSE DEFINED, ICN WILL KEEP THE LAST SPOOL SSUED IN THE SOB ORDER SBH.2A21.P4157955_DAD02 (SEE ANNEX 1) DECISION: ACCEPT AS IT IS | FOLLOW NAVAL GROUP DECISION GIVEN IN ANSWER SHEET FTG-6856 ATTACHED. | N/A | System |  | 994 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0446-2019 | 53B | SEATING | 2019-03-13 03:00 |  | COS-SMB-200396 |  | CEDOC Closure | The seating P4114592 was welded with dimensions according to the drawing SBH.4D30.SAD.003363_D, but during assembly of the ER00063 (P0120987) equipment, it has been verified that the holes were in disagreement. See annex 1. ICN production team proposes t | Não |  |  |  |  | REMOVE ACCORDING TO ANNEX 1 AND REINSTALL ACCORDING 1.2. PERFORM: 100% VT 100% MT OR PT DECISION: TO BE FORWARDED TO EXPERT LEVEL 2. | AGREE WITH PROPOSAL. | N/A | System |  | 992 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0458-2019 | 53B | SEATING | 2019-03-28 03:00 |  | COS-SMB-319571, COS-SMB-206044, COS-SMB-319579, COS-SMB-321780 |  | CEDOC Closure | During analysis and preparation for boarding of the AM00003C AM00005C in SBR2, ICN production team has verified that it is necessary to remove some seatings and pipe clamps which have been welded in the correct positions but needs to be installed only aft | Não |  |  |  |  | WAIT NG POSITION ABOUT 1.2 PROPOSAL | NG/TA AGREES WITH PROPOSAL THE REWORK MUST BE IMMEDIATLY AFTER THE ENBARK | N/A | System |  | 977 Dias |  |  |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0466-2019 | 53B | SEATING | 2019-04-09 03:00 |  | COS-SMB-319453 |  | CEDOC Closure | The seating P4175877 was welded with dimensions according to the drawing, but during assembly of the bulkhead 61 (cool room), it was verified that it is necessary to remove and reinstall 2 elements of the seating welded on frame 61, as shown in annex 2. | Não |  |  |  |  | In order to solve the problem, ICN production team proposes to remove 2 elements of the seating according to annex 1, reinstall after bulkhead been installed and perform 100%VT and 100%MT/PT. | REWORK: REMOVE AND REPIT AFTER WELDING OF BULTHEAD. CARRY OUT NDT 100% VT 100% MT/PT. | N/A | System |  | 965 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0470-2019 | 53B | PIPES | 2019-04-11 03:00 |  | COS-SMB-206071 |  | CEDOC Closure | The tube P4154488 presents difficulty for the alignment of the holes with the valve P0146505, For the tube P4154490 that connects on the other side of the valve and fixed flange. | Não |  |  |  |  | Replace the CMD flange 18RO120D00030 to 18RO120D00005. Take advantage of the flange of tube P4154302 which had to be changed to fixed flange because of spacing. | SEE FTG-6855. DECISION: REPAIR - MODIFICATION ALREADY DONE SEE PRETUSE FOLLOWING FTG-6855. | N/A | System |  | 963 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0479-2019 | 53B | INTEGRATION EQUIPMENT | 2019-04-26 03:00 |  | COS-SMB-200512 |  | CEDOC Closure | As shown attached, the bolts paid for mounting the UL00002 are short. The installation shown in the photo is without the washers and only 2 threads remain (which will decrease after inclusion of the washers in the final assembly). The screw paid is CMD | Não |  |  |  |  | WAIT NG ABOUT 1.2 PROPOSAL. | See PR-6028284. Decision: Rework. | N/A | System |  | 948 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0489-2019 | 53B | NON RESISTANT STRUCTURE | 2019-05-03 03:00 |  | COS-SMB-200108 |  | CEDOC Closure | 1.1 A shape defect was detected on both acoustic recesses (Starboard and Portside) of the Forward Framework, preventing the GRP to fit in the recess properly and causing a discontinuity between GRP and the framework structure. See annex 1. | Não |  |  |  |  | Remove the stiffener from the inside to allow the correct forming of the angle bar. Reinstall new stiffeners afterwards. See annex 2 Parts of the Starboard stiffener to be removed: CV2-EL1111-RENFORT LONGI TD AV EN ABORD CV2-EL1113-SEMELLE AV DU REP 407 | -REWORK NEW ELEMENTS. -FORM AS PER MOCK UP. -RE-INSTALL AS PER ORIGINAL. -CARRY OUT WELDING INSPECTION REQUIRED. | N/A | System |  | 941 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-UFEM-12-0498-2019 | 53B | INTEGRATION EQUIPMENT | 2019-05-09 03:00 |  | COS-SMB-319718 |  | CEDOC Closure | During installation of the equipment EX00025 and EX00026 the screws planned in project ( H M16X40X40 CLASS 8.8) - CMD 32VI110D00826 are left without the two threads provided by the design, as shown in the picture. | Não |  |  |  |  | In order to solve the problem, we will change the screw- SCREW H M16X60X60 CLASS 8.8).CMD (32VI110D00830 ) | Agree with solution proposed: replace by screws HM16X60X60 class 8.8 Modification of parts list (action NVG). Done by NCR-MAT-648-2019. | N/A | System |  | 935 Dias |  |  |  | NO | NO |  |  |  |  | 2020-03-06 12:46 | Philippe Falquerho | Frederic Pavic
NCR-ICN-UFEM-12-0500-2019 | 53B | SEATING | 2019-05-14 03:00 |  | COS-SMB-319613, COS-SMB-321768 |  | CEDOC Closure | During the embarkation of the electric cradle, the seatings P4141381 and P4161047 presented interference with the resistant hull, having to be removed. | Não |  |  |  |  | Remove the seatings according to annex 1 and reinstall after embarkation of the eletric cradle. Perform 100%VT (both seatings) and 100%MT/PT (only for P4141381). | REWORK. | N/A | System |  | 930 Dias |  |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0049-2020 | 53B | PIPES | 2020-03-10 15:26 | Nível 2 | COS-SMB-200551 |  | CEDOC Closure | There is a incoherence between the connections of FH10106Q and the pipe line. To apply the connectors foreseen in FH device we must create a new pipe to braze with the connectors and crimp on the other side to fit pipes. Attached the solution applied for SBR1, used as model for SBR2. There is no need of manufacturing, the 4 new pipes are already on board in final configuration. | Não |  |  |  |  | Wait for NG orientation. | Apply the same solution than the SBR 1 for all the SBR, refere to the FTG-5620 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 629 Dias | Franck Rubis | FH |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0050-2020 | 53B | INTEGRATION EQUIPMENT | 2020-03-13 10:09 | Nível 2 | COS-SMB-317392 |  | CEDOC Closure | During the assembly of the BH00004 equipment, it was observed that the AC30050 coamming was damaged as shown in annex. | Não |  |  |  |  | Send to TA Hugues Bourget. | -Open a cavity to remove the defetc and to have a good shape with ''spoon'' on each side ( as per WPS). -Carry out 100% VT and 100% DP. - if the depth is less than 2mm,Build up using WPS 141/9-6/5RP.A1. - if the depth is more than 2mm, stop point. -The welder must be qualified as per SMB-030502-B para.15.4 -Carry out 100%VT and 100% DP. -smooth grinding with sand paper and JIG ( anel) to ajust the good shape. -Carry out flatness inspection on the coaming face | the depth of the defects being less than 2mm repair by welding is possible. follow recomandation gave by TA | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 626 Dias | Hugues Bourget | BH |  | NO | NO |  | 2020-06-09 17:55 | Frederic Pavic |  | 2020-08-18 16:32 | Frederic Pavic | Christophe Marret
NCR-ICN-ESC-12-0052-2020 | 53B | PIPES | 2020-04-20 15:15 | Nível 2 | COS-SMB-200470 |  | CEDOC Closure | We request authorization to use 07 units of CMD 01PM300D00007 of SBR4 in SBR2, due to the fact that 05 units have not been received, and 02 units have been used in SBR1. (P0107799; P0107803; P0107807; P0107802; P0107804; P0107805; P0107806) Please see NCR-ICN-ESC-11-808-2020 and NCR-ICN-ESC-11-674-2019. | Não |  |  |  |  | NG, please guide the production how to proceed. See attached document. | 5 DV NRV of SBR2 were arrived from France and are conform to mount on SBR2. Serial number of these valves: 17/010 - 17/011 - 17/012 - 17/013 - 17/014 2 DV NRV of SBR2 will be send to Issartel do Brazil to change mushroom inside and carry out pressure test. The 2 new mushrooms were delivered by NG. Serial number of these valves: 17/008 - 17/009 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 588 Dias | Patrick Daliguet | N/A |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0054-2020 | 53B | PIPES | 2020-05-05 17:12 | Nível 2 | COS-SMB-200435 |  | CEDOC Closure | Modify tubing EZ51023 (P4178063 and P4177025) according to FTG-5193 which has interference with the EW0001 tank, this tubing will be altered or remanufactured according to the template, see photo in annex. | Não |  |  |  |  | Remove and Repair, Modifique a tubulação EZ51023 (P4178063 e P4177025) de acordo com o FTG-5193, | Agree to modify the pipe EZ51023 or manufacture a new one. Following the FTG-8870 and the inspections requied REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 572 Dias | Franck Rubis | EZ |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0056-2020 | 53B | NON RESISTANT STRUCTURE | 2020-05-08 12:34 | Nível 2 | COS-SMB-200120 |  | CEDOC Closure | Distance between pillars are not conform, as shown in annex “Forward battery measures”. During squareness measurement, it was identified a deviation in the vertical bars BT1-PD-EL116, BT1-PD-EL112, BT1-PD-EL111, BT1-PD-EL115, BT1-PD-EL105, BT1-PD-EL101, BT1-PD-EL102, BT1-PD-EL106. | Não |  |  |  |  | Do the correction treated with Naval Group mentioned in 1.2. Use CTE´s C24 e G01 to do the inspections. The correct measures have to consider the SMB-600108, the annex of 53B_CTE00595157 and the measures of the frames from the section 4. | Rework, Remove the element C and E of RE16 RE17 RE18 and RE19. Rework a new element and install in a good position. rectify is necessary. carry out welding inspection C24 Carry out a new G01. |  | Lucas Rosa de Sousa | Luiz Felipe Silva Moreira | 570 Dias | Hugues Bourget |  |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0062-2020 | 53B | ELETRIC | 2020-05-15 10:40 | Nível 2 | COS-SMB-327472 | CTE00897035 | CEDOC Closure | Broken electrical connection pin, as attached. | Não |  |  |  |  | Wait for NG response | Take a DJ00010 available in stock Open an NCR-MAT to supply a new one Protect the valve to avoid a new breakage Check all the protection in the submarine |  | Geraldo Alves Simoes Filho | Claudio Marcelo Guedes da Silva | 563 Dias | Stéphane Patrick Philippe Rideau | DJ |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0061-2020 | 53B | PIPES | 2020-05-14 18:05 | Nível 2 | COS-SMB-321785, COS-SMB-200457 |  | CEDOC Closure | It was identified a difference in the distance of pipe intake point and tank bottom (C101, C102, C111, C112 and C121) . PRODUCT NORM REAL P4035479 100mm 105mm P4035503 100mm 110mm P4035483 101mm 95mm P4035538 84mm 90mm P4035485 101mm 115mm P4180649 55mm 45mm P4035490 96mm 120mm | Não |  |  |  |  | ICN request evaluation to accept as it is. | Proposal TA 2.2 specialst decision is, to accept as it is the spools on board. Decision to be validated by Expert level 3. | Accepted as is. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 563 Dias | Franck Rubis | KT |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0063-2020 | 53B | MECHANICAL | 2020-05-19 10:57 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | The ELECTRIC PUMP CONTROL UNIT - EV03500 CMD-11CD300D00009 of the SBR-2 was used in the SBR-1 according to guidance n°: NCR-ICN-ESC-11-210 / 2018. I request authorization to use the ELECTRIC PUMP CONTROL UNIT - EV03500 / CMD-11CD300D00009 from another submarine for application in the SBR-2. | Não | [5 empty] | Agree to use a disponisible pump from aanother SBR Raised a NCR MAT to order a new one. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 559 Dias | Stéphane Patrick Philippe Rideau |  |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0066-2020 | 53B | STW | 2020-05-26 11:39 | Nível 2 | COS-SMB-200244, COS-SMB-200544 |  | CEDOC Closure | The PLC cabinet OO02534 (AUX 1/2/3) of the S-BR02 has two power supply QUINT 24VDC/10A Output (Ref. Manufacture: 2866763) missing applied on S-BR01 due to the problems declared on the NCR-MAT-000596-2019 and NCR-MAT-000600-2019. | Não |  |  |  |  | Forward to Naval Group. | Naval Group asks ICN to Pick up these two devices in the OO02534 cabinet of SBR3 |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 552 Dias | Serge Meyer | OO |  | NO |  |  | 2020-06-02 16:42 | Frederic Pavic |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0067-2020 | 53B | PIPES | 2020-05-29 15:37 | Nível 2 | COS-SMB-206095, COS-SMB-337192 |  | CEDOC Closure | There is a proximity rule NCR betwee pipe EG50303M3 and FH20201. | Não |  |  |  |  | NG. please advise how to proceed. | Decision: REPAIR ICN must weld the spools EG50303M3 (P4169228) with EG50303M4 (P4169231) instead of connecting them by flange. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 549 Dias |  | EG |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0069-2020 | 53B | ELETRIC | 2020-06-03 13:10 | Nível 2 | COS-SMB-319326 |  | CEDOC Closure | According to the attached evidence, we can see that the BS02510 (CMD05SE100D00092) charger is not charging the batteries BS02508. | Não |  |  |  |  | Please forward to TA Benoit Cuquemelle. | It seems that the transformer has defect CMD 05SE100D00092 The equipment have to be return to the supplier ADELCO Note, the transformer must return complete with CMD 05SE100D00091 , charger bloc CMD 05SE100D00092 and battery bloc CMD 05SE100D00093. Open a NCR MAT for this Take SBR 4 AFT part complete and install on SBR2 B CUQUEMELLE |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 544 Dias | Benoit Guillaume Pierre Cuquemelle | BS |  | NO | [5 empty] | 2020-09-17 16:13 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0074-2020 | 53B | PIPES | 2020-06-08 18:32 | Nível 2 | COS-SMB-206084 |  | CEDOC Closure | A curve was added to the project, adjusted on board. | Não |  |  |  |  | NG, please analyze the solution taken for the problem encountered on board. | agree with the ICN decision and accept the modificatilon made , ACCEPT AS IT IS. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 538 Dias | Franck Rubis | EG |  | NO |  |  | 2020-07-31 15:49 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0075-2020 | 53B | PIPES | 2020-06-08 18:43 | Nível 1 | COS-SMB-200455 |  | CEDOC Closure | The pipe was damaged on board during the work. For copper pipes we do not have allowed repair solutions, so we ask a new manufacture of it. | Não |  |  |  |  | Manufacture Spools according to the design issued by the design. use the issued templates. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 538 Dias |  | EF |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0072-2020 | 53B | ELETRIC | 2020-06-08 12:45 | Nível 2 | COS-SMB-319326 |  | CEDOC Closure | According to NCR-ICN-ESC-11-0849-2020, ICN needed to install the BS02509 battery charger ahead of SBR2 in SBR1. ICN requests that the Naval Group authorize the maintenance of the installation of the BS02509 battery charger of the SBR2 in the SBR1 definitively, so it will be necessary to change the traceability of the battery charger. Below is the current scenario of the BS02509 battery charger installations: SBR1 It's installed BS02509 do SBR2 SBR2 It's installed BS02509 do SBR4 SBR3 Does not change traceability SBR4 Awaiting repair of BS02509 do SBR1 | Não | [5 empty] | ICN must complete the NCR with the following informations : - CMD - Serial number - CTE01 with the CMD and serial number used on each SBR Naval Group wants the charger BS02507 (05SE 100D000090) and BS02509 (905SE100D000089) of the SBR4 to be mounted on the SBR2 upon its return of repair open a NCR MAT for the repair |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 539 Dias | Benoit Guillaume Pierre Cuquemelle | BS |  | NO |  |  | 2020-06-17 18:09 | Stéphane Patrick Philippe Rideau |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0073-2020 | 53B | STW | 2020-06-08 16:59 | Nível 2 | COS-SMB-339822 |  | CEDOC Closure | In alignment with Naval Group FO, the hydraulic flushing for the systems BH (M04_BHZ0001) and RM (M04_RMZ0003, M04_RMZ0004 e M04_RMZ0005) has been executed according to the description below: - Each operation was carried out during 4 hours as maximum time. After this established time, the respective operation has changed independently of the result on the laser particles counter; - In the end of the process a sample was taken to validate the inspection. The summary table of the operations is in attachment. | Não |  |  |  |  | Forward to Naval Group level to Accept as It is. | We can observe that the redoing of the flushing operations gave a good result: the analyses from the laboratory confirmed that the Fhari’s quality respects the cleanness criterias. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 539 Dias | Gildas Le Goff | DR, RM, BH |  | NO |  |  | 2020-06-10 17:42 | Frederic Pavic |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0077-2020 | 53B | STW | 2020-06-09 13:39 | Nível 2 | COS-SMB-200258 |  | CEDOC Closure | Please checking, The valve EV02117 / CMD 18SA000D00020 e EV02115 / CMD 18SA000D00020, presented leak. Check for the need for repair or replacement. | Não |  |  |  |  | Please checking, The valve EV02117 / CMD 18SA000D00020 e EV02115 / CMD 18SA000D00020, presented leak. Check for the need for repair or replacement. | Following the answer of the NCR-ICN-ESC-11-0922-2020, we can temporarly (before replacement) machine the “clapet moulé” to put it in good condition. The safety valves need to be test and calibrate in workshop. Must add the report in the NCR. | 1 / acceptance by repair by remanufacturing the valve 2 / Replacing the valves with new ones when they arrive in Brazil BATCH SMB-RAW-DB394. | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 538 Dias | Gildas Le Goff | EV |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0079-2020 | 53B | STW | 2020-06-10 15:37 | Nível 2 | COS-SMB-200287 |  | CEDOC Closure | During inspection F03 RMZ0002, valve RM00971/29OU000D00155 was found to be leaking and thus need to be replaced. | Não |  |  |  |  | Openned to be in place of NCR-ICN-ESC-11-0910-2020. Send this to Herve | Action: After replaced the Nitrogen filling Valve of SBR1 by the same from SBR2, it was noted that Pin is damaged inside (see attached pictures). The reason can be: Hand tightening is required, without torque or any other tool. Tracability: The serial number seems to be: 30/16/7035 the CMD = 29OU000D00155 See attached picture. open a NCR MAT to order new spare |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 537 Dias | Herve Gerard de Backer | RM |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0080-2020 | 53B | PIPES | 2020-06-10 17:54 | Nível 1 | COS-SMB-206094 |  | CEDOC Closure | Inconsistency of the central draining tank display at the IPMS : quick decreasing of the level at the begin of the draining sequence. | Não |  |  |  |  | Follow the attached TAF | NCR LEVEL 1 |  | Bruno Vicente Fernandes | Sharles Gomes Silveira | 536 Dias |  | DA |  | NO | [5 empty] | 2020-09-18 18:27 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0081-2020 | 53B | ELETRIC | 2020-06-10 18:41 | Nível 2 | COS-SMB-200240 |  | CEDOC Closure | During verification of functional pre-tests on CVT BF02501 SBR2, we identified that the panel is not getting "READY" and therefore it is not possible to operate the panel. Attached are images captured from the faults presented by the panel. | Não |  |  |  |  | Request specialized technical assistance from the supplier | Naval Group didn´t see the problem on the CVT1 of SBR2. Naval Group suggests a supplier intervention to diagnose the source of the problem. NCR sent in L3 to organize a supplier intervention Answer 22/07/2020 : According to the ADELCO´s report on 02/07/2020 about the CVT1 BF02502 of SBR2, PCB15 board (2 power resistors faulty) and PCB03 board (fuse F9 out of service) must be changed. 1) Open NCR-MAT to replace PCB03 and PCB15 2) Take PCB03 and PCB15 on CVT1 BF02502 of SBR4 until new cards are delivered |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 536 Dias | Benoit Guillaume Pierre Cuquemelle | BF |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0082-2020 | 53B | TRACEABILITY | 2020-06-18 14:20 | Nível 2 | COS-SMB-319079 |  | CEDOC Closure | During NG auditory mission carried by Fabien Bris in March / April (2019)as reported in COR-2019-902249, it was verified a lack of traceability of the elements 53B-SC2-BR2-SU2-EL3 / EL4-WELD (CTC00670546) and 53B-SC2-BR2-SU2-EL1 / EL2-WELD (CTC00670492) in the welding parameters and also a lack of traceability of the element 53B-SC2-BR2-CO46 / BO1-WELD (CTC00844749) no shimming to ensure welded joint compliance. | Não |  |  |  |  | Attached find the Shimming plan in the documentaitons of the Softpatch Male. CTE 00844750 - C046 / BO1 | Accept as it is. must be sent to level 3 | Accept as it is. The modifications or additional information made in the traceability files are consistent with the expectations. | Charles Douglas de Oliveira | Luiz Antonio da Silva | 529 Dias | Hugues Bourget |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0084-2020 | 53B | PIPES | 2020-06-19 15:34 | Nível 2 | COS-SMB-206111, COS-SMB-200430, COS-SMB-200429 |  | CEDOC Closure | There was an interference between the CO60 and between the spool straub P4171688. The straub was replaced by a weld in the P4163393 / P4171688 spool (see photos in annex). | Não |  |  |  |  | ICN requests that NG accept the modifications applied on board as such. | Apply the solution given by TA in annex Franck RUBIS |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 528 Dias | Alain Lamy | EW |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0083-2020 | 53B | NON RESISTANT STRUCTURE | 2020-06-19 15:13 | Nível 2 | COS-SMB-319098 |  | CEDOC Closure | Distance between pillars are not conform, as shown in annex “Aft battery measures”. During squareness measurement, it was identified a deviation in the vertical bars BTAR-EP-EL403, BTAR-EP-EL402, BTAR-EP-EL408 e BTAR-EP-EL409. | Não |  |  |  |  | Do the correction treated with Naval Group mentioned in 1.2. Use CTE´s C24 e G01a nnexed to do the inspections. The correct measures have to consider the SMB-600316, the annex of 53B_CTE00616201.2 and the measures of the frames from the section 2A. | Repair, Rework some part of pilares (see annex) exchange the old one and correct the position. To have a enough space between pilares, conform o SMB-104624 ; SMB-600317 Carry out inspection required in IT21-02-10E. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 528 Dias | Hugues Bourget |  |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-UFER-12-0139-2020 | 53B | MACHINING | 2020-06-25 11:24 | Nível 2 | COS-SMB-319078 |  | CEDOC Closure | For machining the drilling of the SBR2 female soft patch, the drawing SMB-104055_B was used, as it was the last revision in the system. The Inspection D81_37 was approved based on the measurements in drawing SMB-104055_B. The document was revised for revision C, with some changes in the tolerance of drilling: (Rev_B _ tolerance 0/-0.5 / Rev_C_ tolerance 0/-0.1). To Female Soft Patch SBR2 - ICN asks to accept as it is. To Male Soft Patch - ICN suggests mapping the holes in the female, and drilling the Male using the holes in the female as a reference. | Não |  |  |  |  | Accept as it is. Drill the Male Soft Patch holes using the holes in the female as a reference. | The hole of all the male soft patch will be machined in correspondence with the hole of the female. During the adjustment on board it will be not necessary to achieve the diamater of 65 mm. The reaming will be stop as soon as the diamater on the both soft patch will be perfect ( for example 64,5). The share bolt will be machined in accordance. |  | Charles Douglas de Oliveira | Joao Paulo Schneider Gonzaga | 522 Dias | Charles Boucher | N/A |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0088-2020 | 53B | ELETRIC | 2020-06-25 19:05 | Nível 2 | COS-SMB-319321 |  | CEDOC Closure | One of the two Data concentrator of BMS system in OAB (Activation workshop) is damaged. It is possible to monitor 180 battery elements using the good data concentrator and the 5 optical loops. It is also missing 200 meters of fiber optical. The one deliverd for SBR1 it is broken/damaged not possible to use. | Não |  |  |  |  | Please forward to Sebastien Jacquin management. | Naval Group has sent a new RCU card and 200ml of fiber optical to perform the activation of the batteries of the SBR2 |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 521 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO |  |  | 2020-08-13 16:57 | Frederic Pavic |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0089-2020 | 53B | ELETRIC | 2020-06-26 17:18 | Nível 2 | COS-SMB-319323 |  | CEDOC Closure | The BE02000 Panel (11TD200D00322) of the SBR2 is without the insulation meter, this device was installed in the SBR1 panel according to the decision of NCR-ICN-ESC-11-0488-2019 and NCR-MAT-000739-2019. The replacement insulation meter on the BE02000 panel (11TD200D00322) of the SBR2 has not been provided so far through the NCRs described above to meet the safety milestone J1 of the SBR2. I request clearance to use the SBR4 panel insulation meter. | Não |  |  |  |  | Take the insulation measurement device of the BE panel (11TD200D00322) of the SBR4 and install this device in the BE02000 panel (11TD200D00322) of the SBR2. | Take the insulation measurement device of the BE panel (11TD200D00322) of the SBR4 and install this device in the BE02000 panel (11TD200D00322) of the SBR2 No need to open an NCR-MAT, because the device is already purchased following NCR-MAT-000739-2019 Check if traceability on those item |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 520 Dias | Yann Jaouen | BE |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0090-2020 | 53B | ACOUSTIC DISCRETION | 2020-06-30 18:04 | Nível 1 | COS-SMB-319712 | CTE00960243 | CEDOC Closure | During MS01 inspection on BE00001 we observed the lack of two upper resilient mounts. | Não |  |  |  |  | The equipment must have complete assemblies, resilient mount, completion of the seatings and electrical cables. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 516 Dias |  | BE |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0091-2020 | 53B | ELETRIC | 2020-07-02 14:39 | Nível 2 | COS-SMB-319323 |  | CEDOC Closure | This NCR is being opened to address the problem that was raised at NCR-ICN-ESC-12-0051-2020, but NCR-ICN-ESC-12-0051-2020 was closed with the wrong information (UNFOUNDED). Below the description of the problem: An internal inversion was identified in the connections of the transformers of the bigram BE, the internal identifications are exchanged (H1-H2 / X1-X2). For the correct transformation ratio of the transformers, it will be necessary to change the identifications and connections of the interconnection cables of the primary and secondary of the transformer. This change is similar to the changes handled in NCR-ICN-ESC-11-0555-2019 regarding the BT bigram. | Não |  |  |  |  | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | As explained in the NCR-ICN-11-0555-2019 and purposed by ICN, NG is agree to modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 515 Dias | Stéphane Patrick Philippe Rideau | BE |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0092-2020 | 53B | PIPES | 2020-07-06 12:01 | Nível 2 | COS-SMB-206070, COS-SMB-206055 |  | CEDOC Closure | Due to the lack of space to braze, ICN request to change the connection as below: P4153841 CTE #003 - #005 – 18RO230D00567 P4153950 CTE #003 - #005 – 18RO230D00593 This way we change the male and female making possible to braze. As used between spool's P4153950 and P4141259, both are with female connection (18RO230F00237), we ask to replace connection P4153950 # 007 from 18RO230F00237 to 18RO230D00593 | Não |  |  |  |  | Invert the connections due to lack of space to weld. | In order to get enough space for brasing, Invert the connection male-female on the assembly of the spools P4153841 and P4153950. See FTG-9103. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 511 Dias |  | EZ |  | NO |  |  | 2020-10-29 12:39 | Felipe Gonçalves Sequeira |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0093-2020 | 53B | PIPES | 2020-07-07 18:35 | Nível 1 | COS-SMB-200455 |  | CEDOC Closure | During the S02 test it was identified a damage to pipe P4107184 (EF50012O1), probably it occurs during trolley test in battery compartiment. ICN request a manufacture of a new pipe. | Não |  |  |  |  | Manufacture a new tube according to the issued drawing. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 509 Dias |  | EF |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0094-2020 | 53B | PIPES | 2020-07-08 17:35 | Nível 2 | COS-SMB-206089, COS-SMB-206090 |  | CEDOC Closure | There is an incoherence between the pipe P4127221 connection with hose P0107649, due to the fact that the male connection is smaller than the hose female. For SBR1 this subject was solved by NCR-ICN-ESC-11-0512-2019, according to FTG-7187 made by GIR NG team. Please confirm the same solution applied for SBR1 to be placed over SBR2. | Não |  |  |  |  | ICN suggests applying the same decision made through NCR-ICN-ESC-11-0512-2019, FTG-7187. | REPAIR Apply FTG-7187 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 508 Dias |  | HP |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0095-2020 | 53B | RESISTANT STRUCTURE | 2020-07-08 18:48 | Nível 2 | COS-SMB-349505 |  | CEDOC Closure | After analyzing the inspection D59_5 - INSPECTION OF BEARING SURFACE AFTER ADJUSTMENT by the BO of the Naval Group, it was found that it did not comply with the homogeneity criterion (FWD FACE AND AFT FACE). ** Opening of NCR as requested by TA Hugues Bourget (see attached email). | Não |  |  |  |  | Send to level 2. | Accept as it is , To be forwarded to level 3 | Accept as it is | Neimar Mayrink da Silva | Luiz Felipe Silva Moreira | 508 Dias | Hugues Bourget |  |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0096-2020 | 53B | PIPES | 2020-07-09 11:21 | Nível 2 | COS-SMB-206083, COS-SMB-321784 |  | CEDOC Closure | ICN is out of stock for CMD 18RO220D01172, so we request authorization to manufacture the correspondent CMD from 0930930278974 (X2CrNiMo 17-12-2 Dia 45mm). We need 2 pieces for each product. | Não |  |  |  |  | ICN requests that NG authorizes the manufacture of CMD 18RO220D01172, as it is not available in stock. | REWORK, NG doesn't autorize the manufacture of the pieces because they will be supply week 32 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 508 Dias | Franck Rubis | ES |  | NO |  |  | 2020-07-27 17:59 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0097-2020 | 53B | STW | 2020-07-13 11:47 | Nível 2 | COS-SMB-200247, COS-SMB-319698, COS-SMB-200716 |  | CEDOC Closure | According to the action performed through the NCR-ICN-ESC-11-0962-2020, Naval Group shall provide the following o-rings in order to repair the defected valves DY01031 and DY01032 or new valves (CMD: 18RT150D00005): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS | Não |  |  |  |  | Forward to Naval Group to provide the necessary material in order to repair and mount on S-BR02. | Before remount on SBR2, ICN to repair in workshop the both valves DY01031 and DY01032, needs to create a spare part request to take in the RMS the items below (rep 4 and 5 of the SBR-ETM-00000M0001, page: 3849): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS If the RMS stock is not available, need to replenish with a safety stock (the consumption of these kinds of O-RING is very common. I suggest a replenishment threshold of 50 units). |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 504 Dias | Gildas Le Goff | DY |  | NO |  |  | 2020-08-04 12:01 | Felipe Gonçalves Sequeira |  | 2021-04-30 13:06 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0098-2020 | 53B | MACHINING | 2020-07-13 12:44 | Nível 2 | COS-SMB-200792 | CTE00620771 | CEDOC Closure | 1. During the inspection of the final machining of the DP00355 and DP00356 of the forward rudder, deviation was detected in disagreement with the design tolerance. (See attached D47-10_CTE00620771). 2. Due a problem of excentration after final machining of DP00355 and DP00356, the center diameter (theoretical Ø280 - MAT214-1394) between the Ø270 and the Ø275 was machined (see detail in annex 1). The actual dimensions of the center diameter is: • Starboard: Ø289,10 • Portside: Ø287,77 | Não |  |  |  |  | 1. There is an angle of 89°58’35.5” between the Machined Axis of FWD Hydroplane Holes and the Vertical Axis (see Machining Report - FL 3). Then, the Transmission Axis is not perpendicular for a tolerance of 90° ±1’ according SMB-200974. ACCEPT AS IT IS. 2. The Straightness and concentricity must be confirmed through piano wire inspection. 3. The Vertical Axis was shifted at Y = 0,35 mm to portside to follow the machined axis of AC34027 (see Machining Report – FL 4 and detail in FL 7). The distances C and D (for both sides) must be updated according new values after shifting of vertical axis: DP00356 • C = 203,47 • D = 814,72 DP00355 • C = 204,18 • D = 816,10 The ADJUSTING HALF-SHIM (2x Ref: 18) and THRUST WASHER (Ref: 26) will be machined accordingly. 4. The center diamenter was machined and the excentricity was corrected. Accept as it is. SEND TO LEVEL 2 ANALYSIS. | Due to the exentration it was necesary to machine the diameter in the center of the bushes. Accept as it is. |  | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 504 Dias | Charles Boucher |  |  | NO |  |  | 2020-07-29 11:34 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0099-2020 | 53B | ACOUSTIC DISCRETION | 2020-07-14 10:52 | Nível 1 | COS-SMB-319713 |  | CEDOC Closure | Torque values applied in resilient mounts screws of the Diesel Cradles AM00003 and AM00005 were in disagreement with issue "D" of SMB-200965. The torque values applied are lower than those specified in revision "D". See attached CTE00963340 and CTE00963761. | Não |  |  |  |  | Rework according to SMB-200965_D | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 503 Dias |  | AM |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0101-2020 | 53B | PIPES | 2020-07-14 18:48 | Nível 1 | COS-SMB-206113 |  | CEDOC Closure | During inspection it was identified a thickness reduction not conform on the pipe as per quality inspection. | Não | 2020-10-15 16:42 |  |  |  | Manufactures the spool according to the issued drawing. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 502 Dias |  | ER |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0104-2020 | 53B | ELETRIC | 2020-07-21 11:31 | Nível 2 | COS-SMB-200544 |  | CEDOC Closure | The block X37 and X38 terminal of equipment OO02534 is damaged. | Não |  |  |  |  | Wait for NG orientation | Take module X37 and X38 in the OO02534 on SBR4 Open MAT to replenish them See drawing attached Module Phoenix contact MCR REPEATER POWER SUPPLIES Manufacturer reference 2864752 |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 496 Dias | Serge Meyer | OO |  | NO | [7 empty] | Christophe Marret
NCR-ICN-UFEM-12-0539-2020 | 53B | MACHINING | 2020-07-24 10:45 | Nível 2 | COS-SMB-343994, COS-SMB-345808 | CTE00933385, CTE00933383, CTEPROV34399403, CTEPROV34399404 | CEDOC Closure | During the inspection of the machining of the solid blocks of the forward rudder (Port and starboard) , deviations were detected in disagreement with the project. See attachments: G06_CTE00933385-1, G06_CTE00933385-2, G06_CTE00933385-3, G06_CTE00933385-5, G06_CTE00933385-6, D52-20_CTE00933383-1, D52-20_CTE00933383-2, D52-21_CTEPROV34399403 and D52-21_CTEPROV34399404. | Não | 2021-04-13 13:18 |  |  |  | Accept the machining as it is. See comments in document attached "2.1 ICN SOLUTION". | Agree with the proposal solution to solve all the defauts.(Charles Boucher) |  | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 493 Dias | Charles Boucher |  |  | NO |  |  | 2020-08-06 13:16 | Felipe Gonçalves Sequeira |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0105-2020 | 53B | STW | 2020-07-23 21:53 | Nível 2 | COS-SMB-200276, COS-SMB-319731 |  | CEDOC Closure | It was verified the lower fitting of the door for the equipment OO02531 is damaged in S-BR02. Check the photos in attachment. | Não |  |  |  |  | Forward to Naval Group. | The door was removed to be transfered to SBR1 (first door damaged). NVG has to purchase a new door for SBR2 PLC OO02531 | Please open a NCR MAT in order to purchase a new door for SBR2 PLC OO02531. | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 493 Dias | Serge Meyer | OO |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0107-2020 | 53B | ELETRIC | 2020-07-27 13:06 | Nível 2 | COS-SMB-200240 |  | CEDOC Closure | During a functional test on the SBR2 panel BF02505, an electrical fault was identified in the U5 power supply. | Não |  |  |  |  | Replace the U5 power supply with a new one. | Take on sbr4 the power supply U5 in BC02660 because the U5 of sbr4 on BF02505 has been already canibalysed for sbr1. Open NCR MAT to replenish it. PHOENIX CONTACT. SUPPLY DC/DC 28VDC 20A. Manufacturer Ref:2320102. BDM-00077872 |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 490 Dias | Benoit Guillaume Pierre Cuquemelle | BF |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0108-2020 | 53B | ELETRIC | 2020-07-28 14:19 | Nível 2 | COS-SMB-319738 | CTE00874218 | CEDOC Closure | For equipment FH02625, 04 buttons and 01 lamp are missing, as identified in the annexes. | Não |  |  |  |  | Wait for NG orientation | Pegar o SBR4 os itens abaixo: 4 itens rep 40 1 itens rep 43 1 itens rep 46 1 itens rep 42 BDM-00060105 BDM-00060109 Abra o NCR MAT para reconstituir itens canibalizados |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 489 Dias | Etienne Alexandre Sebastien Rene Berot | FH |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0109-2020 | 53B | NON RESISTANT STRUCTURE | 2020-07-30 16:25 | Nível 2 | COS-SMB-337192 |  | CEDOC Closure | As discussed with TA during the assembly of the joints FH20033, FH20035 e FH20031 was checked on board and the fixing the some screws are short, without access for replacement. | Não |  |  |  |  | It was proposed by ICN, to accept as it is. | ACCEPT AS IS only for SBR 2 |  | Renato da Silva Goncalves | Sharles Gomes Silveira | 487 Dias | Franck Rubis | FH |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0110-2020 | 53B | PIPES | 2020-07-30 17:10 | Nível 1 | COS-SMB-206041 |  | CEDOC Closure | During bench inspection it was identified damage in the spools reduction. Probably due to smash by foot on board. | Não |  |  |  |  | REMOVE AND REWORK | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 486 Dias |  | MB |  | NO
NCR-ICN-ESC-12-0112-2020 | 53B | STW | 2020-08-03 14:03 | Nível 2 | COS-SMB-200258, COS-SMB-200444 |  | CEDOC Closure | The flexible EV22018 / 18FH101D00617 was damaged on board. Please authorize replacement. | Não |  |  |  |  | Please authorize replacement. | Following the drawing MAT166-0637 (BDM-00017642 sheet 17), the only difference between the 2 CMX 18FH101D00051 and 18FH101D00617 is the length (0.45m and 0.79m). How the curvature of the flexible is better with the CMX 18FH101D00051 (NGD: 0930930261600), I agree to use this CMX. | Agree with paragraph 2.2 : replacement of the flexible 18FH101D00617 by the 18FH101D00051 for SBR2. | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 483 Dias | Gildas Le Goff | EV | NCR-ICN-REGRESS-12-0010-2020 | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0150-2020 | 53B | ELETRIC | 2020-09-02 20:06 | Nível 2 | COS-SMB-200542 | CTE00931538 | CEDOC Closure | Scorched equipment door, as attached photo. | Não |  |  |  |  | Repainting according parameters described in Appendix 1 and inspection template. If the color is different one, entire lay can be applied. | According to the paint specification SMB-002345, ICN must rework the painting with a RAL7038 |  | Geraldo Alves Simoes Filho | Bruno Marcel Lima Ferreira Amancio | 452 Dias | Hugues Bourget | DM |  | NO | [5 empty] | 2021-05-11 15:47 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0114-2020 | 53B | ELETRIC | 2020-08-05 18:18 | Nível 2 | COS-SMB-319724 |  | CEDOC Closure | Problems found on the EM02500 panel: - Two Broken lamp; - Broken button; - Broken protective cover; - damaged ventilation cover. | Não |  |  |  |  | Change the broken parts | Check RMS stock or take on EM02500on sbr4 the items below: -BIPOLAR 2-POSITION FLIP SWITCH 3A SERIES 160UN01 WITH LOCK YELLOW TERMINATION Rep 65>>>5930930151289 -INDICATOR LAMP SERIES 330B WITH RED LENS WITHOUT BULB Rep67>>>6210930150643 -VENTING FILTER Rep25>>>4130930237303 Open NCR MAT to replenish |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 480 Dias | Etienne Alexandre Sebastien Rene Berot | EM |  | NO |  |  | 2020-09-10 19:16 | Franciellen da Silva Braga |  | 2020-10-14 14:44 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0113-2020 | 53B | STW | 2020-08-05 17:39 | Nível 2 | COS-SMB-200281 |  | CEDOC Closure | During test B01 RMZ0057, it was verified that the lipseals of RM00237 were slightly damaged which resulted in a consistent leakage throught the hull bearing. | Não |  |  |  |  | As discussed with Anthony Grel, the bearing can be replaced with the one from SBR3 and the damaged bearing fixed in the workshop. | remove the damaged hull bearing SBR2 for repair in work shop. define and order (NCRMAT)the spares to perform the repair. i suggest to mount in place of hull bearing SBR2 the hull bearing from SBR3 ( ensure the tracability) | Rework according to SMB-TDP-PR6650333 and SMB-TDP-PR-6650334. | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 480 Dias | Paul Fosse | RM |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0118-2020 | 53B | PIPES | 2020-08-11 17:44 | Nível 2 | COS-SMB-206092, COS-SMB-327464 |  | CEDOC Closure | During CSPI inspection it was identified a non-conformity in the assembly of pipe KT53714M1 (P4123601) with valve KT01114 (P0116263). | Não |  |  |  |  | NG, please advise how to proceed. | REWORK Dismounting the pipe Cleaning the flanges Realize a test 52,5 bars Reassemble in conforme the pipe on board |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 474 Dias | Franck Rubis | KT |  | NO | [5 empty] | 2020-10-16 13:51 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0116-2020 | 53B | ELETRIC | 2020-08-10 16:34 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | Damaged terminal inside panel DT04310. | Não |  |  |  |  | Change the terminal. NG should inform the NGD | Take module Z02 in the DT04310 on SBR4 Open MAT to replenish it Rep 42 of drawing attached in annex NGD: 6620930195387 |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 476 Dias | Gildas Le Goff | DT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0117-2020 | 53B | MACHINING | 2020-08-11 16:02 | Nível 2 | COS-SMB-345144, COS-SMB-200792 |  | CEDOC Closure | After execution of NCR-ICN-ESC-11-1012-2020 and NCR-ICN-ESC-12-0098-2020 and discussion with TA Charles Boucher (see e-mail attached), the lubrication groove (center diameter) of all bushes of DP system (stern steering gear and bow hydroplane) must be machined to avoid any problem of lubrication after final assembly. See reports attached for SBR 2 and SBR 3. | Não |  |  |  |  | Machining 0,5 mm (radius) or as less as possible to achieve values bigger than the theoretical gap (7,5 mm): • The coaming first in priority; • The bush after if for the coaming it’s too late, but take care because on this diameter there is the traceability; • Record the traceability and after machining, stamp back. | Agree with the proposed solution, the thickness of the grooves should be respected between the bush and the sleeve. Machining the bush if necessary. ( Charles Boucher) |  | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 475 Dias | Charles Boucher | DP |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0121-2020 | 53B | PIPES | 2020-08-12 13:47 | Nível 2 | COS-SMB-200441 |  | CEDOC Closure | There is no M10 forecast to braze the flowmeter hose connector to pipe P4127155 (FH50105H1). | Não |  |  |  |  | Wait for NG orientation. | REWORK The assembly is compliant Add the CTE for brazing |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 474 Dias | Franck Rubis | FH | NCR-ICN-REGRESS-12-0012-2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0123-2020 | 53B | ELETRIC | 2020-08-13 12:22 | Nível 2 | COS-SMB-319724 |  | CEDOC Closure | Broken button on the EM02501 panel door. | Não |  |  |  |  | NG inform the NGD | Due of no RMS stock ,take on EM02501on sbr4 the item below: -BIPOLAR 2-POSITION FLIP SWITCH 3A SERIES 160UN01 WITH LOCK YELLOW TERMINATION 5930930151289 Open NCR MAT to replenish |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 473 Dias | Etienne Alexandre Sebastien Rene Berot | EM |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0124-2020 | 53B | ELETRIC | 2020-08-13 12:24 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | Piping interference in the opening radius of the panel door. | Não |  |  |  |  | Adjust the position of the pipe. NG should define a new configuration. | -Do not apply the FTG-8990 -Reposition the electric cabinet ES02500 with the original xyz coordinates in accordance with the mounting plan . -Not modify the pipes P4128989 and P4128983 ( CSPI) conform with the plan and with the position correctly on board. |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 473 Dias | Franck Rubis | ES |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0125-2020 | 53B | ELETRIC | 2020-08-14 16:15 | Nível 2 | COS-SMB-200542 | CTE00758499 | CEDOC Closure | Lack of the local / remote button, as per annex 1. | Não |  |  |  |  | NG inform the NGD | The commutator local/remote is inside the panel as per picture attached. This NCR is unfounded. |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 472 Dias | Stéphane Patrick Philippe Rideau | EV |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0126-2020 | 53B | ELETRIC | 2020-08-14 16:17 | Nível 2 | COS-SMB-200542 | CTE00758540 | CEDOC Closure | Lack of the local / remote button, as per annex 1. | Não |  |  |  |  | Ng should inform the NGD | The commutator local/remote is inside the panel as per picture attached. This NCR is unfounded. |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 472 Dias | Stéphane Patrick Philippe Rideau | EV |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0127-2020 | 53B | STW | 2020-08-14 18:00 | Nível 2 | COS-SMB-200240 |  | CEDOC Closure | I opened NCR-ICN-ESC-12-0081-2020 to deal with the problems we had identified to start SBR2's CVT1 (READY). The treatment of this problem was the replacement of two boards (PCB03 and PCB15) internal to the panel, according to the decision of NCR-ICN-ESC-12-0081-2020. After replacing the plates, we managed to connect the CVT1, which had other operational failures, as we can see in the attached report by ADELCO. CVT2 (BF02502) of SBR2 is presenting the same problems identified in CVT1 (BF02501) of SBR2. The failures identified in the CVTs (BF02501 and BF02502) of the SBR2, do not allow the operation of the BF system from the converters, however the converters are prerequisites for the safety milestone J1 and J3 of the SBR2. | Não |  |  |  |  | Technical assistance from the converter manufacturer is required. | 1) For CVT2 - BF02502 The ADELCO report shows internal wiring problems which were resolved . => It is nevertheless necessary to open an NCR MAT to replenish the H2 lamp which was taken from the CVT2 - SBR4. 2) For CVT1 - BF02501 After further investigations, it was found that the components and cables connections were defective. => Open an NCR MAT in order to replenish: - 1 PCB02 card because the adjustabled resistor "RP4" was missing S / N 131002506241A Note that it has been replaced by that of CVT2 SBR1 S / N 131002502988A repaired by Naval Group on a provisional basis. - 2 fans M41 and M42 because they were out of order. Note that they have been replaced by those of the CVT2 SBR4. See attached annex. Send to level 3. | Rework according to paragraph 2.2 use the material from SBR04. | Paulo Roberto de Souza | Paulo Roberto de Souza | 471 Dias | Benoit Guillaume Pierre Cuquemelle | BF |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0129-2020 | 53B | PIPES | 2020-08-17 19:46 | Nível 2 | COS-SMB-206090 |  | CEDOC Closure | In face of the advanced assembly conditions, dimension and geometry of BH50052M1. ICN request NG authorization to perform B01 and B02 relative to valves BH00102 and BH00105 with the pipe in place. | Não |  |  |  |  | ICN requests authorization from NG to execute B01 and B02 in relation to BH00102 and BH00105 valves with the pipe installed. | Exceptionally B01 and B02 can be carry out with pipe mounted It will be important to check the quantity of leak with difference of water quantity before and after the test inside the pump tank | n accordance with level 2.2 proposal but the time for the pressure test has to be increased at minimum 15 min. David BERNEDE | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 468 Dias | Patrick Daliguet | BH | NCR-ICN-REGRESS-12-0063-2021 | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0128-2020 | 53B | MECHANICAL | 2020-08-17 13:32 | Nível 2 | COS-SMB-321710 |  | CEDOC Closure | It was verified in the inspection of B07 that the equipment: AC43060 (CMD: 11TE141D00110 - P0152060 and AC43058 (11TE141D00109 - P0151763) were in exchanged positions on board. | Não | 2020-10-16 17:09 |  |  |  | Put in a correct positiond and re do the inspections | Dismount and remount in the good location with new gasket and lock washers. The new mounting will be followed by a new B06. |  | Emanuela Lucia Justino dos Santos | Sergio André Telles Soares | 469 Dias | Patrick Daliguet | AC |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0132-2020 | 53B | MACHINING | 2020-08-18 16:09 | Nível 2 | COS-SMB-200228 |  | CEDOC Closure | During the D95_04 inspection (CTE00933936) it was detected that the diameter 20 H7 is outside allowable tolerance. See attached CTE. Durante a inspeção D95_04 (CTE00933936) foi detectado que o diâmetro 20 H7 está fora da tolerância permitida. Veja CTE em anexo. | Não |  |  |  |  | Accept as it is. Machine a new pin accordingly the hole dimensions respecting the tolerance H7. | Adjust the size in order to be in tolerances H7 |  | Neimar Mayrink da Silva | Joao Paulo Schneider Gonzaga | 468 Dias | Paul Fosse | RM |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0131-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-18 16:06 | Nível 2 | COS-SMB-321703 |  | CEDOC Closure | The mobile part AF35350 (MAT169-0199) is not compatible with drilling the DA12510N tank level (BDM-00036934). | Não |  |  |  |  | Send to level 2. | See FTG-8992 |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 468 Dias | Patrick Daliguet | DA |  | NO |  |  | 2020-09-03 12:56 | Felipe Gonçalves Sequeira |  | 2021-03-23 18:58 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0133-2020 | 53B | STW | 2020-08-19 18:42 | Nível 2 | COS-SMB-200239, COS-SMB-200560 |  | CEDOC Closure | During inspection F01_BCZ0035 of the SBR2, it was identified that the SINEAX V604s U3 of the BC02660 panel is not working. The problem was verified in conjunction with TA NG Benoit Cuquemelle. | Não |  |  |  |  | Replace the SINEAX V604s with a new one. | Take on sbr4 Open NCR MAT to replenish: GMC INSTRUMENTS PROGRAMMABLE MULTIFUNCTIONAL TRANSMITTER SINEAX V604s Manufacturer Ref:168 329 BDM-00077875 |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 466 Dias | Etienne Alexandre Sebastien Rene Berot | BC | NCR-ICN-REGRESS-12-0017-2020 | NO |  |  | 2020-09-24 14:33 | Franciellen da Silva Braga |  |  |  | Christophe Marret
NCR-ICN-UFEM-12-0541-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-24 18:38 | Nível 2 | COS-SMB-200762, COS-SMB-321706, COS-SMB-321707, COS-SMB-321708, COS-SMB-321698, COS-SMB-319772, COS-SMB-339471, COS-SMB-321701, COS-SMB-200767 |  | CEDOC Closure | nodes 1Z, 2Z and 4Z have CP1 inspection for painting with epoxy paint on the face of the anode in contact with the hull according to SMB-002081. However, the anodes received by ICN have already been painted from the manufacturer, and it is not possible to carry out the inspection by ICN. | Sim |  |  |  |  | This products received painted. Its not possible to inspect. Attached are receipt documents received by ICN without painting certificates and other documents, see NCR-MAT-00585-2019. | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 461 Dias | Hugues Bourget | AZ |  | NO |  |  | 2020-09-01 18:41 | Hugues Bourget |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0134-2020 | 53B | ELETRIC | 2020-08-20 13:22 | Nível 2 | COS-SMB-319738 | CTE00874218 | CEDOC Closure | Scratch in the painting of the equipment, according to the attachment "PHOTO FH02625_1". | Não |  |  |  |  | Touch-up according parameters described in Annex 1 and inspection template. | Repair Repair as per comments of para 1.2. If the color is diferent one entire lay can be applied |  | Geraldo Alves Simoes Filho | Bruno Marcel Lima Ferreira Amancio | 466 Dias | Hugues Bourget | FH |  | NO | [5 empty] | 2020-10-05 19:39 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0135-2020 | 53B | ELETRIC | 2020-08-20 16:32 | Nível 2 | COS-SMB-319760, COS-SMB-200712, COS-SMB-319750 |  | CEDOC Closure | The equipment OO24024 and OO24208 was demaged on board. | Não |  |  |  |  | Change for the new one. NG inform the CMX | ICN damaged on board SBR2 the ASI modules OO024024 and OO024208. Naval Group recall ICN to install the individual cover protection for each external module ASi according with the mandatory TAF_SBR_2018_903. ICN has to create a NCR-MAT on SBR3 to purchase these ASI module |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 466 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO | [5 empty] | 2020-10-15 18:50 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0137-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-24 13:38 | Nível 2 | COS-SMB-319693 |  | CEDOC Closure | Some problems were found during the assembly at the KT greasing point. For TLT 1-2-3-4: TLT 1: The depth of holes Ø9 is 90mm instead of 95mm +/- 1: KT03611; TLT 2: The external door detection position assembly is missing, not possible to check: no action; TLT 3 : The hole Ø4 of the adaptor rep: M40 is not at the good position when it’s tight correctly: KT03613; TLT 4: OK no problem: no action; TLT 5: The hole Ø4 of the adaptor rep:M40 is not at the good position when it’s tight correctly : KT03615; TLT 6: The hole Ø4 of the adaptor rep: M40 is not at the good position when it’s tight correctly : KT03616. | Não |  |  |  |  | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 (David Bernerde) | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 462 Dias | Patrick Daliguet | KT |  | NO | NO |  | 2020-12-16 14:30 | Felipe Gonçalves Sequeira |  | 2021-06-08 15:10 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0138-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-24 13:38 | Nível 2 | COS-SMB-319693 |  | CEDOC Closure | On all external door, the control axle (rep: 4) have two hole partially drilled. | Não | 2021-05-04 11:57 |  |  |  | Send to leval 2 to validate the modification. | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | Rework the drillings according to the drawing. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 462 Dias | Patrick Daliguet | KT |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0139-2020 | 53B | MECHANICAL | 2020-08-26 11:25 | Nível 2 | COS-SMB-200563 |  | CEDOC Closure | Leveling deviation on the chockfast resin at fwd battery room, detected by optical measurement as per annex 1. In order to correct the leveling, the resin surfaces were grinded using specific tools and new measurements were taken. The results are shown in annex 2. | Não |  |  |  |  | Accept as it is. Send to level 2 to validate. | The grinding process is updated and this process not increase the temperature. According to the results in annex the floor is not aceptable as it is. The solution to repair: - mark on the ground each position of the batterie; - check the planeity one by one square (500x360); -check the horizontability; -take optic measurement to validate the rectification send to level 3 (Charles Boucher) Additional comments on 14/09/2020 by JACQUIN.S: Based on the annex 2 measurements, an analysis has been done following the aft battery connections in order to ensure a proper connection between the accumulators (SMB-000737). A repair proposal has been done on some identified seatings in order to respect as much as possible the tolerances of the batteries connectors. Annex”20200903-C100 - Etat avant reprise”: The cells to be reworked are in red background, and in orange background are highlighted the gap >1mm compared to the nominal high of each floors Upon rework done, new measurements have been taken and reported: Annex”20200904-C100 - Etat après reprise”. Based on these new measurements, the tolerance reported are within the connector tolerances. We would like to propose to accept as it is. | Agreement with 2.2 proposed solution of chocking rework. A specific follow-up with Electrical TA et Mechanical TA is required in order to ensure that all electrical connections can be mounted without any deviation to the required gap, namely : - each electrical connection between battery elements - battery head connection Open a new NCR in case of discrepancie regarding the electrical connection mounting gap or battery theorical height. V2 du 01/10/2020: Following the V2 of this NCR received on 15/09/2020 after chocking rework and last measurements done, decision to Accept as is. V2 du 01/10/2020: Following the V2 of this NCR received on 15/09/2020 after chocking rework and last measurements done, decision to Accept as is. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 460 Dias | Sebastien Jacquin | BB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0140-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-26 15:07 | Nível 2 | COS-SMB-338262, COS-SMB-319750 |  | CEDOC Closure | Regarding the Launching Command Box UP02800 (P0132142) CMD: 11BR000D00021 there is not Test Device Cable installed in SBR2. Please provide it | Não |  |  |  |  | The missing cable is part of this product. | The Launching Command Box UP02800 (P0132142) CMD: 11BR000D00021 was deliverred to SBR1 & SBR2 with its UP dummy Probes. The Dummy Probe of SBR1 was lost by ICN. Naval Group inquires to order and deliver a new UP dummy probe. Naval Group requests ICN to regulate the movement of mateial by editing a NCR MAT. | Please create an NCR MAT for the replenishment of the material. | Ana Paula Bernardes de Araujo | Ana Paula Bernardes de Araujo | 460 Dias | Herve Gerard de Backer | UP |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0142-2020 | 53B | PIPES | 2020-08-27 15:06 | Nível 2 | COS-SMB-200273, COS-SMB-206092 | CTE00897455, CTE00897456, CTE00897435, CTE00897436 | CEDOC Closure | After blowing of TLT1 hydraulic block, it was checked that the hydraulic lines connected at points "A1 / KT50581R" (SMB-000667_N) and "A2 / KT50481R" (SMB-000667_N) of the hydraulic passage "KT40001" of the TLT1 / SBR2 were connected inverted. In other words, the line that is connected at the point "A1" should be connected at the point "A2", and vice versa. That is, the lines in reference need to be reversed. | Não |  |  |  |  | Please, send the NCR in reference to TA Patrick Daligue. | Agree with the ICN analysis : -the pipes KT50581R and KT50481R must be reversed after the valves P0114089 and P0114100 on the hydraulic passage KT40001 -KT50581R with A2 -KT50481R with A1 -REPAIR with manufacture news pipes |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 459 Dias | Franck Rubis | KT | NCR-ICN-REGRESS-12-0018-2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0141-2020 | 53B | ELETRIC | 2020-08-26 18:51 | Nível 2 | COS-SMB-200239 |  | CEDOC Closure | The BC32500 panel's U3 + P3D power supply was defective during panel operation. Attached is the drawing of the panel indicating the point of installation of the power supply and photos of the problem presented. | Não |  |  |  |  | Replace the U3 + P3D power supply on the BC02500 panel. | Take on sbr4 in BC02500 the power supply U3 Open NCR MAT to replenish: MARTEK POWER 24VDC/230V 50Hz SUPPLY 600W Manufacturer Ref: ACR750 (B) BDM-00077867 |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 459 Dias | Etienne Alexandre Sebastien Rene Berot | BC |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0156-2020 | 53B | MECHANICAL | 2020-09-08 19:31 | Nível 2 | COS-SMB-200792, COS-SMB-200535 | CTE00866017 | CEDOC Closure | During the dimensional inspection (CTE00866017_D85_2) of the M12 holes in the forward rudder, deviation of rotation and perpendicularity of the holes was detected. See attached | Não | 2020-10-22 18:17 |  |  |  | Accept as it is. The production team already performed the adjustment of the hole bushes and assembly the screws temporarily. It was not found any problem in the mounting. | If you have already arrive to tight the bush on the coaming , accept as it is. (Charles Boucher) |  | Neimar Mayrink da Silva | Joao Paulo Schneider Gonzaga | 446 Dias | Charles Boucher | DP |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0149-2020 | 53B | PIPES | 2020-09-02 13:39 | Nível 2 | COS-SMB-200439 |  | CEDOC Closure | During the final assembly of pipe P4157124 (BH50050M4) it was identified that the adjust was not done correctly in 2019. To adjust this we suggest to redo 3 welds. One in already forecast in the flange to adjust the drill position, on in x axis, and another for z axis. See cut proposal attached picture. | Não |  |  |  |  | ICN suggested redoing 3 welds. One already provided on the flange to adjust the drill position, on the x axis, and another for the z axis. See the photo of the proposal cut in the attachment ” | -solution accepted for SBR 2 -but it is preferable to add the minimum of welds on a pipe category "A" -REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 453 Dias | Franck Rubis | BH |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0144-2020 | 53B | INTEGRATION EQUIPMENT | 2020-08-31 16:25 | Nível 2 | COS-SMB-319725 |  | CEDOC Closure | Leveling deviation on the chockfast resin at AFT battery room, detected by optical measurement as per annex 1. In order to correct the leveling, the resin surfaces were grinded using specific tools and new measurements were taken. The results are shown in annex. | Não |  |  |  |  | Send to level 2. | Based on the annex 2 measurements, an analysis has been done following the aft battery connections in order to ensure a proper connection between the accumulators (SMB-000736). A repair proposal has been done on some identified seatings in order to respect as much as possible the tolerances of the batteries connectors. Annex”20200903-A150 - Etat avant reprise”: The cells to be reworked are in red background, and in orange background are highlighted the gap >1mm compared to the nominal high of each floors Upon rework done, new measurements have been taken and reported: Annex”20200908-A150 - Etat après reprise”. Based on these new measurements, the tolerance reported are within the connector tolerances. We would like to propose to accept as it is. | Following the chocking rework and last measurements done, decision to Accept as is. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 455 Dias | Sebastien Jacquin | BB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0146-2020 | 53B | NON RESISTANT STRUCTURE | 2020-09-01 18:27 | Nível 2 | COS-SMB-325860 |  | CEDOC Closure | During the adjustment of the thermographic batty, the holes were from item 072 were bilonged. (PR-6114418) - see annex 1. It was necessary to overlap a plate with the correct hurricanes, in order to meet the correct specifications, see annex 2. | Não |  |  |  |  | Follow NG orientation to do the rework in EL072 and EL070. See annex 1 and 2. | Repair, In accord with Mechanical TA . Put a shim a carry ot a correct drilling |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 453 Dias | Hugues Bourget |  |  | NO |  |  | 2020-09-15 14:58 | Felipe Gonçalves Sequeira |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0147-2020 | 53B | STW | 2020-09-01 19:52 | Nível 2 | COS-SMB-319362 |  | CEDOC Closure | The secondary control box (STL83SB - CMD 11BR000D00028 - HP02506) located in Diesel Room is with bad behavior, since the pins regarding loudspeaker 100V and loudspeaker return are in ground short. It is necessary to replace the equipment. | Não |  |  |  |  | ICN will need to replace the equipment. | According to the last investigation performed by ICN, it seem necessary to replace the actual HP base station (HP02506) on board SBR2 by a new one from SBR3 (If available) and edit a NCR MAT. |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 453 Dias | Herve Gerard de Backer | HP |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-UFEM-12-0542-2020 | 53B | MACHINING | 2020-10-20 15:49 | Nível 2 | COS-SMB-343997 | CTE00962718, CTE00962721, CTE00962720, CTE00962716, CTE00962715, CTE00962719 | CEDOC Closure | During the dimensional inspection of the machining of the upper rudder cones, deviation was detected in disagreement with the design tolerance. Note: The inspections below were not performed due to calibers CAL-115 and CAL-117 being in the company subcontracted by ICN where the cones were machined. G06_CTE00962716-1, G06_CTE00962718-2, D96-15_CTE00962721, D96-15_CTE00962715, D96-03_CTE00962719 e D96-03_CTE00962720. | Não |  |  |  |  | Repair the Blade Solid Cone according 2.1 ICN SOLUTION / DECISION and annex 1. | TA agree with this solution proposed by ICN (scratch the cone of the blade to perform better perpendicularity of the shaft). Make a new inspection and add here to close the NCR. (Charles Boucher) |  | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 405 Dias | Charles Boucher |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0151-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-03 15:59 | Nível 2 | COS-SMB-319705 |  | CEDOC Closure | Damaged material on board, as attached. | Não |  |  |  |  | 1) For SBR 2, replace the Inflatable Seal from SBR 2 by SBR 4 (CMD 15PE000D00003 delivered in batch SMB4-MA16B-DB2). 2) For SBR 4, take the item from SBR 2 and proceed as below: • Remachining the Ø550 of the Inflatable Seal as less as possible until achieve a regular surface; • The minimum acceptable dimension is 549,80 ± 0,05 mm to obtain an extrusion gap less than 0,4 mm; • Perform a G06 dimensional inspection to register the machined diameter (issue CTEPROV); • If the measurement is in accordance, machining the AC30001 coaming according to the project (Ø550H7) respecting the PELA clearances; • If the measurement is not conform, scrap the equipment and raise a NCR-MAT for replacement; Note: The water tightness is achieved by static sealing and there is no risk for extrusion of the seal with a gap which remains smaller than 0.4 mm. See comments in "Annex 1 - 2.1 ICN SOLUTION-DECISION"; 3) Send to level 2, DA and Safety Diving especialist to analysis. | Not agree with the proposed solution by ICN in 2.1. For SBR2 use the inflatable seal provided for SBR2. Using san d paper reduce the stripes on the external diameter. Install the inflatable seal and make the test at 20bar. If the rest is good accept as it is. (Charles Boucher) |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 452 Dias | Charles Boucher | MB |  | NO | [5 empty] | 2020-11-04 14:11 | Christophe Marret | Philippe Falquerho
NCR-ICN-ESC-12-0153-2020 | 53B | NON RESISTANT STRUCTURE | 2020-09-04 12:13 | Nível 2 | COS-SMB-200137 |  | CEDOC Closure | During the assembly of the elements of annex 1, it was noted that the conformations are not in agreement. PS4-EL321, PS4-EL33, PS4-EL317, PS4-EL319 e PS4-EL347C. (SMB-600220). T.A Hugues proposed 2.1. | Não |  |  |  |  | Rework elements: EL317, EL319,EL321 and EL323 (SMB-600217_C F20-F23 / SMB-330061_B);EL347C (SMB-600216_B F46 / SMB-330061_B). Use SMB-600220_B (F17-F18) to make the new assembly for LR-PART2. Use C24 annexed to weld. | Rework, Due to the wrong forming and mounting, Naval-group/Ta proposes to rework some elements described in para1.2 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 451 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0155-2020 | 53B | NON RESISTANT STRUCTURE | 2020-09-08 12:47 | Nível 2 | COS-SMB-200769 |  | CEDOC Closure | According to SMB-104502_C and RAI-SBR2-0133-200149, it will be necessary to make an limber hole in CO59. According to the drawing, the limber hole is made on the portside and the physical one is made on the starboard side. | Não |  |  |  |  | We propose to close the limber hole in accordance with SMB-001386 (Page-39) and IT21-02-10E (Page-77). Use DE-200149-10000-12-026_A to do the correct work. | REPAIR During the work following the SMB-104502 updated rev. C , ICN opened the limber on the wrong side of Frame 59. Portside instead of starbord side. Close the wrong opening following the IT 21-02-10-E and SMB-001386 Carry out all the tests required . 100% VT and 100%MT ( open an NCR/RO to record the welding information) Open the limber Hole on the good side, carry out inspections 100% VT ; 100% MT |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 447 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0154-2020 | 53B | MACHINING | 2020-09-08 11:30 | Nível 2 | COS-SMB-207763 |  | CEDOC Closure | During inspection D59-06 (CTE00964995) visual defects of tool marks from grinding were detected after the machining service was performed. See attached the evidence. Durante inspeção D59-06 (CTE00964995) foram detectados defeitos visuais de marcas de ferramentas provenientes do esmerilhamento após a execução do serviço de usinagem. Veja em anexo as evidencias. | Não |  |  |  |  | Follow to NG level 2. | Rework Rework by surfacing For each defect open an NCR/RO ( HRO) . For the defect 2 open 2 HRO one for each soft patch element.10 HRO must be open. The defect and the solution repair will be discribed in these NCR/RO |  | Joanei Vieira de Sa | Felipe Trigueiros Silveira | 447 Dias | Hugues Bourget | N/A |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0157-2020 | 53B | ELETRIC | 2020-09-09 11:18 | Nível 2 | COS-SMB-200516, COS-SMB-CAB-DA-DY |  | CEDOC Closure | The equipment DA12512N was demaged on board. The connector this cable DA62512R was lost in the construction process. | Não |  |  |  |  | Follow TA 2.2 guidelines. | use the DA12512N (50DD500d00047) of the SBR4 define NGD of the base and the plug provide a new set for repair | Replenishment of the components below to replace the base and the damaged detector socket - fixed connector RECM 10MT 03 -14 : 5935143886814 - plug FEDF 10 MT E123 : 5935144069967 | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 446 Dias | Stéphane Patrick Philippe Rideau | DA |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0158-2020 | 53B | SEATING | 2020-09-10 10:44 | Nível 2 | COS-SMB-319554 |  | CEDOC Closure | During the assembly of the AG00013 hatch, it was noticed that the seating P4164781 was out of position. According to annex 1, the support P4164781 was 28mm more in the assembly. | Não |  |  |  |  | Rework the seating P4164781 removing using Annex 1 and install again using CTE´s and SBH.2D31.SAD.005781_B annexed. | Rework carefully remove the support by grinding. carry out the following inspections, 100% visual, 100% MT and nital attack. Open an NCR / RO if necessary to reconstitute the base metal. Position the new seating in the right place. carry out the inspections requested as per original |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 445 Dias | Hugues Bourget | AG |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0160-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-10 16:43 | Nível 2 | COS-SMB-200569, COS-SMB-200712 |  | CEDOC Closure | The valve KT03517 has a broken Belzona coating and the KT03518 valve has been lost on board (see E-mail annex). | Não |  |  |  |  | Request the SBR4 valves. CMD 18RT010D00834, it the same valve, but with halar coating. Redo the inspections L01, B07, F06 and B06 for KT03517 and KT03518. For the broken valve, need to repair belzona following SMB-333523, do the CP1-1 and CP1-2 inspections. Make sure to put more belzona for the machining areas (greater than or equal to 1000 µm). Machining the valve and respect the tolerances. Do the dimensional inspection. If possible do the leak test in workshop, if you can't do the test, make the test onboard record the B01 and B02 inspections. Make sure the record all process and attach tracebility folder of the equipment. | Raise a NCR MAT to follow the repairing of valve (indicating CMD and serial number). The repairing of Belzona can be carried out by ICN. For the remplacement on board 2 CMD can be use: -18RT010D00726 (Belzona) -18RT010D00834 (Halar) To avoid this kind of problem it's very important to protect flanges of valve and take care of the alignment with the pipe during the mounting. |  | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 445 Dias | Patrick Daliguet | KT |  | NO | [5 empty] | 2021-05-14 18:46 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-ESC-12-0161-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-10 17:22 | Nível 2 | COS-SMB-321696 |  | CEDOC Closure | During the leak test, B01 (paste ID: 10236), a leak was identified in the retainer, MAT 214-1496, REP 10, NG 5330142522535 and CMD: 0930930292400. | Não |  |  |  |  | Proceed according 1.2. Replace by CMD 0930930292400. | replace the seal rep 10 CMD 0930930292400 by the same. Open a NCR-MAT. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 444 Dias | Charles Boucher | DP |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0162-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-10 19:55 | Nível 2 | COS-SMB-206044 |  | CEDOC Closure | The DN00112 valve has a damaged “halar” coating on board. | Não | 2021-07-19 16:52 |  |  |  | Send to level 2. | Not possible to repair at ICN but a supplier in Brazil have the capability. To allow the following of the repairing a NCR MAT have to be raise. | NAVAL GROUP will globally take in charge all hull valves which have a damaged coating. These hull valves will be sent lot by lot to a dedicated supplier for rework. This topic will not be managed by RTE process. No NCR MAT required. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 444 Dias |  | DN |  | NO | NO |  | 2020-12-02 18:32 | Frederic Pavic |  | 2021-03-30 17:27 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0163-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-15 23:30 | Nível 2 | COS-SMB-200763 |  | CEDOC Closure | The DN00212 valve has a damaged “halar” coating on board. | Não |  |  |  |  | Send to level 2. | Not possible to repair at ICN but a supplier in Brazil have the capability. To allow the following of the repairing a NCR MAT have to be raise. Complements of informations done by TA NG, the product mentioned is the hand manover not the valve. Right product is DN00212 Annex with defect added | NAVAL GROUP will globally take in charge all hull valves which have a damaged coating. These hull valves will be sent lot by lot to a dedicated supplier for rework. This topic will not be managed by RTE process. No NCR MAT required. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 439 Dias | Patrick Daliguet | DN |  | NO | NO |  |  |  |  | 2021-03-30 17:28 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0174-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-22 16:08 | Nível 2 | COS-SMB-321697 |  | CEDOC Closure | The material was lost on board (DP00162). Consider items in yellow only (see Annex). | Não |  |  |  |  | Proceed according 1.2. Replace by items described in annex 1. Raise a NCR MAT to supply new spare parts. | ICN should open a NCR-MAT to replace all the items missing. In parallel Naval Group suggest to buy double or triple itens for spare. (Charles Boucher). |  | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 433 Dias | Charles Boucher | DP |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0166-2020 | 53B | PIPES | 2020-09-16 15:24 | Nível 2 | COS-SMB-200551 |  | CEDOC Closure | There is a watertight problem with the material forecast to perform the connection of BB00040. | Não |  |  |  |  | ICN acquisition analysis of NG. | -refere to the FTG 8894 -manufacture of the conection -REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 439 Dias | Franck Rubis | BB |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0168-2020 | 53B | PIPES | 2020-09-16 19:18 | Nível 2 | COS-SMB-321781 |  | CEDOC Closure | It was necessary an adjust on the geometry of pipe not forecast on the project adjust. The pipe is bended, now we need the new connections. The modification was done on the quote marked in red, adjusted for on board requirements. | Não | 2021-05-04 12:03 |  |  |  | ICN asks to adjust the spool as indicated in the annex. | -authorizes the modification of the pipe in accordance with the proposal of ICN -Repair |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 438 Dias | Franck Rubis | DB |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0167-2020 | 53B | PIPES | 2020-09-16 19:01 | Nível 2 | COS-SMB-206080 |  | CEDOC Closure | There is a modification on the flanges of pipes P4153109, P4153110, P4153113 and P4153115. ICN request authorization to invert the fixed flange from P4153110 and P4153115 and use a loose flange, and for P4153109 and P4153113 instead of loose apply the fixed one. This is because we are not going to respect the minimum distance between welds on the point presented in attached drawing (EG). | Não |  |  |  |  | NG, please analyze this problem. | Accept as it is on the SBR 2 Apply the last revision of isometric drawing for the following submarines |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 438 Dias | Franck Rubis | EG | NCR-ICN-REGRESS-12-0011/2020 | NO | [5 empty] | 2020-11-04 11:42 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0175-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-22 16:56 | Nível 2 | COS-SMB-319705, COS-SMB-330822, COS-SMB-330822 |  | CEDOC Closure | Loss on board items 5, 6 and 8 (see attachment). | Não |  |  |  |  | Manufacture or buy in SKF company the missing itens. Raise a NCR MAT to supply spare parts. | Manufacture or buy new items in SKF company ( Charles Boucher) |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 433 Dias | Charles Boucher | MB |  | NO | [5 empty] | 2020-12-14 13:47 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-ESC-12-0188-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-02 14:55 | Nível 2 | COS-SMB-319705 |  | CEDOC Closure | Loss on board item 2 of drawing MTSI20220100EXP (see attachment). | Não |  |  |  |  | The item was already replaced by SBR 3 that was available in workshop; Open a NCR-CQ for SBR 3 to use the item from SBR 4. Raise a NCR-MAT to supply new part or the drawing to manufacture for SBR 4. Remark: According certificate SMB-355803_FL86 (SBR 3), the material of Obturator (ref. 2) is S355NL. Available in ICN. | 1- ICN could manufacture a new piece following NG drawings if raw material in ICN; 2- Order a new spare to NG; 3- Diving safety element ICN must open an NCR for all SBRs; 4- Naval Group Suggest to order spare items 3 and 5 of the drawing MTSI202200100EXP_B for all the submarines. (Charles Boucher) | - Carry out a visual inspection of the bores that do not have a shutter for any signs of corrosion. If necessary remove them by grooming the surfaces. Renew the anti-corrosion protection by spraying a long-lasting protective coating (type Ardrox 3140 or equivalent) inside these shafts. - NCR to be created for SBR3 in order to declare the use of the SBR4 shutter on SBR3 - NCR to be created for SBR4 in order to decide whether or not to manufacture the shutter on site (See if NCR is needed to initiate the request for spare parts: seals and square brake) | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 423 Dias | Charles Boucher | MB |  | NO | NO |  | 2020-10-26 11:10 | Christophe Marret |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0169-2020 | 53B | NON RESISTANT STRUCTURE | 2020-09-17 19:22 | Nível 2 | COS-SMB-200140 |  | CEDOC Closure | During the assembly of the flank array panels, the seating EL082, EL094, EL116, EL110, EL122, EL132, EL138, EL150, EL162, EL164, EL178 e EL190 are out of coordinate. It will be necessary to increase the size of the seating, as the friling is hiyying outside the support, as highlighted in annex 2. | Não | 2020-10-24 14:33 |  |  |  | Follow Naval Group orientation making a repair in the seatings like annex 2 showed. | repair as per annex |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 437 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0172-2020 | 53B | PIPES | 2020-09-21 16:29 | Nível 1 | COS-SMB-206081 |  | CEDOC Closure | During self-inspection over EG00102 it was identified a problem with the length of the screws. The problem was fixed, and the B06 attached was performed to control. | Não |  |  |  |  | follow according to 1.2 | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 434 Dias |  | EG | NCR-ICN-REGRESS-12-0016/2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0173-2020 | 53B | PIPES | 2020-09-21 19:57 | Nível 1 | COS-SMB-206140 |  | CEDOC Closure | EQ00004 18DL100D00003 was not located on board. Production request a new material. | Não |  |  |  |  | Follow according to the document issued. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 433 Dias |  | EQ |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0177-2020 | 53B | ELETRIC | 2020-09-24 15:26 | Nível 2 | COS-SMB-200239 |  | CEDOC Closure | We have a specification divergence between document SMB-002931_I and 2 circuit breakers on the BC02512 panel, we can see these divergences in the attached file. | Não |  |  |  |  | TA NG Etienne Berot and Benoit Cuquemelle are aware of this problem. | Take 2 breakers on sbr 4 BDM-00064080 CIRCUIT BREAKERS NS100DBDC EQUIPED MAGNETOTHERMAL TRIP TM40D Rep:55 NGD:5925145218979 Open NCR MAT to replenish them (Reference range of replacement NSXDC Block of cut: LV438019 Trip TM40D: LV429054) Supply chain action: Put in RMS data base the old breakers: -5925145218980 CIRCUIT BREAKER NS100DBDC TM25D 4P4D -5925145218978 CIRCUIT BREAKER NS100DBDC TM63D 4P4D |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 431 Dias | Etienne Alexandre Sebastien Rene Berot | BC |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0183-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-01 11:21 | Nível 1 | COS-SMB-206090 |  | CEDOC Closure | The valves cited below have the problems: BH00101/BH00104: Stud rods too short for the fixing of BH00101. BH00102/BH00105: Stud rods too short for the fixing of BH00102. BH00103/BH00106: Stud rods too short for the fixing of BH00103. | Não |  |  |  |  | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. It's necessary to redo B06 and open a NCR-REGRESS for the tests B01 and B02. Bigrama Produto CTE Nome BH00101 P0104601 CTE01015965 B06 - INSPECTION OF THE CONFORMITY OF THE PRESSURE HULL... BH00102 P0104602 CTE01015959 B06 - INSPECTION OF THE CONFORMITY OF THE PRESSURE HULL... BH00103 P0104603 CTE01016115 B06 - INSPECTION OF THE CONFORMITY OF THE PRESSURE HULL... BH00104 P0104604 CTE01015957 B06 - INSPECTION OF THE CONFORMITY OF THE PRESSURE HULL... BH00105 P0104605 CTE01016097 B06 - INSPECTION OF THE CONFORMITY OF THE PRESSURE HULL... BH00106 P0104606 CTE00950781 B06_01-INSP MEASUREMENT “PRESSURE HULL BOLTING MATERIAL” | NCR LEVEL 1 |  | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 424 Dias |  | BH | NCR-ICN-REGRESS-12-0021-2020 | NO | [5 empty] | 2021-03-10 16:37 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0189-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-02 15:00 | Nível 2 | COS-SMB-200535 |  | CEDOC Closure | Short screw, with less than 02 threads. | Não |  |  |  |  | Accept as it is. See images in Annex 1. Send to level 2 to validate. | Less than 2 threads but more than 1,5 thread is visible. A modification of the stud rod length should be analysed by NG for other SBR. | Accept as it is for SBR2. This problem was take in account by OM-114819. | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 423 Dias | Patrick Daliguet | DP |  | NO | NO |  |  |  |  | 2021-01-13 19:03 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0193-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-06 16:33 | Nível 2 | COS-SMB-321709, COS-SMB-317388 |  | CEDOC Closure | The AC30070 coaming was found damaged on board. | Não |  |  |  |  | Rework the surface with appropriate tools, like in NCR-ICN-UFEM-12-410-2019. It's necessary to inspect thickness remain and planicity after work. Respect the tolerance indicated in MAT424-0776_D. | Repair ]Map the defect , Clean by grinding and take the depth and map the defect . Carry out 100%VT and 100% DP Stop point to analyse with T.A. After analysis open the defect with a good profile (see WPS)Carry out 100%VT Build up using WPS 141/9-9/RPA2 Carry out 100%Vt and 100%DP Rework the manuel machining using a tool ( marble) |  | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 419 Dias | Hugues Bourget | AC |  | NO | [5 empty] | 2020-12-07 19:38 | Frederic Pavic | Christophe Marret
NCR-ICN-ESC-12-0181-2020 | 53B | NON RESISTANT STRUCTURE | 2020-09-29 20:03 | Nível 2 | COS-SMB-200136, COS-SMB-321680 |  | CEDOC Closure | During the assembly of panel 22 (AH00422), there was interference with the ampoules. According to annex 1, highlighted in ted, it will be necessary to do a roughing (SMB-104308). | Não |  |  |  |  | Wait for Naval group decision. | REPAIR Repair as per ICN proposal annexed |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 425 Dias | Hugues Bourget | AH |  | NO | [5 empty] | 2021-02-03 17:02 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0182-2020 | 53B | STW | 2020-09-30 11:31 | Nível 2 | COS-SMB-200239, COS-SMB-319730 |  | CEDOC Closure | The power supply -U2 + D2A (28Vdc / 230V 50Hz) has the defect led "ON". A check was performed on the power supply together with the TA NG, and the need to replace the power supply was identified, due to problems in the internal components. | Não |  |  |  |  | Replace the power supply. | Take on sbr4 in BC02550 the power supply U2 Open NCR MAT to replenish: MARTEK POWER 24VDC/230V 50Hz SUPPLY 600W Manufacturer Ref: ACR750 (B) BDM-00077872 |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 425 Dias | Etienne Alexandre Sebastien Rene Berot | BC | NCR-ICN-REGRESS-12-0019-2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0184-2020 | 53B | NON RESISTANT STRUCTURE | 2020-10-01 15:08 | Nível 2 | COS-SMB-319146 |  | CEDOC Closure | During the assembly of panel 1, the stanchions highlighted in annex 1 are outside the coordinates (SMB-600522). It will be necessary to modify the stanchions CO33-BD-EP28, CO34-BD-EP32, CO35-BD-EP36, CO33-BD-EP26, CO34-BD-EP30, CO35-BD-EP34, CO36-BD-EP40, CO37-BD-EP46, CO34-TD-EP31, CO35-TD-EP35, CO36-TD-EP41, CO37-TD-EP47, CO32-TD-EP25, CO34-TD-EP33, CO35-TD-EP37 e CO36-TD-EP43 (Annex 1). | Não |  |  |  |  | Remover all the EP´s mentioned using Annex 1 and install again doing 100% VT and 100% LP or PM using SMB-600522_A. | Rework, rework as per original design |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 424 Dias | Hugues Bourget |  |  | NO | [5 empty] | 2021-03-01 13:43 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0185-2020 | 53B | STW | 2020-10-02 10:58 | Nível 2 | COS-SMB-319362 |  | CEDOC Closure | The SBR2 NCO, AMP1 and AMP2, inside PAS CABINET, are not working properly (bigram HP). There is no sound (voice and alarm) coming out the loudspeakers, even the system does not shows any fail in its display. It is necessary to replace the equipment. SBR2 Equipment S/N: NCO: 110137d1 AMP1: 80600f0 AMP2: 80600e3 | Não |  |  |  |  | ICN needs to replace the equipment from another set | NCO, AMP1 and AMP2 inside PAS CABINET SBR2 can be replaced by news from SBR3. Naval Group requests ICN to edit a dedicated NCR-MAT. |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 423 Dias | Herve Gerard de Backer | HP |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0187-2020 | 53B | RESISTANT STRUCTURE | 2020-10-02 12:30 | Nível 2 | COS-SMB-319088 |  | CEDOC Closure | During the assembly of the DSRV, excess material was removed (SMB-104023). According to Annex 1, the items SC2-PT1-G1, SC2-PT1-G4, SC2-PT1-G5 e SC2-PT1-G8 highlighted in red will have to recomposes with weld. | Não |  |  |  |  | Repair by surfacing. Recompose the good profile according IT21-02-10 11.2. Perform C16 inspection. | Rework by surfacing, Open NCR/RO ( HRO) and use C15 file |  | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 423 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0205-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-13 17:32 | Nível 2 | COS-SMB-206092 |  | CEDOC Closure | Valve KT01116 was mounted with error, according to card reprise No. 185. | Não |  |  |  |  | Proceed according sheet nº 185. | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 | Agree with paragraph 2.2 : Rework - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure test B01 and B02 and redo associated documents B11 and B07. Vu David BERNEDE le 04/11/2020. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 411 Dias | Patrick Daliguet | KT | NCR-ICN-REGRESS-12-0015-2020 | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0192-2020 | 53B | PIPES | 2020-10-06 12:40 | Nível 2 | COS-SMB-206092 |  | CEDOC Closure | It was discovered tab washer opened after the B02 on KT01111 and KT01112: The 10/05/2019 for KT01111 and the 06/06/2019 for KT01112 was carried out pressure tests B01 and B02 of these valves. During this pressure test, NG was present and all bending of tab washers were correct. The 23/10/2019 these both valves were verified by NG controller and found correct. Beginning of this week these both valves were verified by ICN controller and found not correct. Like decision for TLT6 it’s necessary: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 Attached the pictures of the tighten torque on the screws. For TLT 1 any other position other than the actual one would generate a new interference. | Não |  |  |  |  | NG, please check the item in question. | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 419 Dias | Patrick Daliguet | KT | NCR-ICN-REGRESS-12-0023-2020 | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0197-2020 | 53B | PIPES | 2020-10-07 12:01 | Nível 2 | COS-SMB-200426 |  | CEDOC Closure | During M05 it was identified the lack of the cap on the pieces KT22347 and KT22548. There is no more of it on ICN warehouse, so we request drawing and authorization to manufacture it here. | Não |  |  |  |  | ICN authorization for the manufacture of the caps of KT22347 and KT22548 | All informations are in the document MAT162-0390. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 418 Dias | Patrick Daliguet | KT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0195-2020 | 53B | STW | 2020-10-06 17:47 | Nível 2 | COS-SMB-319362 |  | CEDOC Closure | The external loudspeaker HP02509 (62AE000D00003, 120119-12001) is not working properly. ICN needs to replace it from one of other set. | Não |  |  |  |  | replace the equipment | Naval Group suggests to replace the loudspeaker HP02509 by a new one from amother boat. Naval Group requests ICN to rise a NCR MAT and to note S/N of both equipment. |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 418 Dias | Herve Gerard de Backer | HP |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0201-2020 | 53B | PIPES | 2020-10-08 13:25 | Nível 2 | COS-SMB-200460 |  | CEDOC Closure | It was identified a bad positiong of the pipes on the seating, making impossible to fit the clamp according to the rules described in SMB-030510. | Não |  |  |  |  | NG, please analyze this problem. | Adjust the pipes P4123516-P4123565-P4123301-P4123291 in the clamp P4164586, in order to respect the following assembly rules SMB030510, if necessary, remanufacture news pipes sections ,to correctly connect the valve KT02111. REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 417 Dias | Franck Rubis | KT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0202-2020 | 53B | ELETRIC | 2020-10-08 13:38 | Nível 2 | COS-SMB-319731 | CTE00947564 | CEDOC Closure | Broken Local / Remote button. | Não |  |  |  |  | Change the broken part (Local / Remote button). | Replace the broken switch with a new one Open an NCR MAT to supply a new BIPOLAR 2-POSITION FLIP SWITCH NGD 5930930151289 |  | Fabio Brito da Silva | Geraldo Alves Simoes Filho | 417 Dias | Stéphane Patrick Philippe Rideau | ES |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0206-2020 | 53B | MECHANICAL | 2020-10-14 10:48 | Nível 2 | COS-SMB-319705, COS-SMB-330822 | CTE01053515 | CEDOC Closure | During inspection B11-07 CTE01053515 it was detected that the requiriment of "minimum 2 stud rod threads protruding" not in conformity according SMB-200960_H (item 8.1). See photo attached. | Não |  |  |  |  | Accept as it is. Send to level 2 and DA to validate the mounting. | Find the cause of the problem, because is good for someones, add all the traceability of the stud in this NCR and rework if necessary respecting the rules (SMB-200960_H).Perform this job before to do the prssure test. ( Charles Boucher). | In accordance with L2 proposal to check the traceability of the studs rods In addition at the other part of the stern gland there is some tab washers wich are nor adapted to the bolting D BERNEDE | Neimar Mayrink da Silva | Ernanes de Souza | 411 Dias | Charles Boucher | MB |  | NO | NO |  |  |  |  | 2021-01-18 13:49 | Christophe Marret | Philippe Falquerho
NCR-ICN-ESC-12-0207-2020 | 53B | MECHANICAL | 2020-10-14 15:56 | Nível 2 | COS-SMB-206090 | CTE00950775 | CEDOC Closure | During the inspection F06_CTE00950775 was detected a falied made by tools in the HALAR coating. It was observed that the damage reached the steel of the piece according to the attached photos. | Não |  |  |  |  | Replace the Valve, take from SBR4 - CMD 18RT010D00830. Redo inspections L01, B07, F06 and B06 for the new valve. The damage valve need repair, raise a NCR-MAT, return it to warehouse and send to a supplier can make repair Halar. ICN is not qualified to repair Halar. | It is necessary to add the traceability number of the valve in the NCR MAT which will be created and in this NCR In accordance with level to take another valve and to redo inspections L1, B07, B06 for mountng and then pressure tests The treacebility of the valve damaged has to be updated with the reference of the NCRs (ESC and MAT) Send to level 3 David BERNEDE | A sectioning recovery campaign will be implemented. They will not be treated individually. | Alexander Vilela Dias | Osvaldo Luiz de Moura Filho | 411 Dias | Patrick Daliguet | BH |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0208-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-14 18:53 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | CEDOC Closure | After the disassembling the SKF coupling (MB00007) some leakeges were found according the imagens below. The problem cause need to be investigated. | Não |  |  |  |  | Send to level 2. | The SKF for SBR02 damaged has been control by photogrametry. The result will show if it is possible to be repaired. Open a NCR-MAT to decide what do if the damaged item. Actually use SKF SBR04 on the shaft SBR02 to finish the installation of the shaft line. As proposed in the mail (06/10/2020) jointed. (Charles Boucher). | 1. Install on SBR2 shaft line the SKF coupling delivered for SBR4. 2. NAVAL GROUP will replenish a new SKF coupling for SBR4. 3. Open a NCR MAT to manage the damaged SKF coupling : scrap or repair in order to reput in stock as RGP. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 410 Dias | Charles Boucher | MB |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0209-2020 | 53B | SEATING | 2020-10-16 10:55 | Nível 2 | COS-SMB-319547 |  | CEDOC Closure | The mounting of the P4164603 seating does not match the panel 1. It will be necessary to make an adjustment on the seating P4164603 due to the elevations not being in accordance with panel 1. | Não |  |  |  |  | Do the repair as mentioned in annex 1. | Rework Due to the wrong fabrication of the seating , it was necessary to correct it before mounting on Board. Cut in 3 parts , build up and ajust in the good position. Carry out all the repairs following the IT21-02-10E rules and SMB-200853 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 409 Dias | Hugues Bourget | EX |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0214-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-16 18:33 | Nível 2 | COS-SMB-200581, COS-SMB-321709 |  | CEDOC Closure | As discussed with mechanical TA, a rework will be performed on the forward capstan (AC44031) together at the stern and bow, as shown in annex 1. The status for this moment: -The red part already dismounted; -The green part will be dismounted. | Não |  |  |  |  | Send to level 2. | -In accordance with level 1.2 -To manufacture new lock washers it will be used "EX lock washer.pdf" ( Patrick Daliguet) | In accordance with levels 1.2 and 2.2 proposal. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 408 Dias | Patrick Daliguet | EX |  | NO | NO |  | 2020-10-19 19:14 | Christophe Marret |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0212-2020 | 53B | MECHANICAL | 2020-10-16 17:19 | Nível 2 | COS-SMB-319719 | CTE00936283 | CEDOC Closure | During the inspection B06_01‐INSP MEASUREMENT “PRESSURE HULL BOLTING MATERIAL (CTE00936283) of mobile part AC42042, was detected that the criterion "length of stud rods L=116mm" isn't in compliance (126mm). See CTE attached. | Não |  |  |  |  | The 116 mm stud is not appropriate for installing the AC42042, it is necessary to change to 126 mm to be accepted with at least two threads. It is necessary to change the CTE00936283 and CC-319718-80500-12-001. | The length of stud rods L=116 mm was replaced by L=126mm after the modification of thickness of lock washers (replace by new design for the lower side) | The use of 126 mm is correct - accepted as it is David Bernede | Adriano Oliveira da Costa | Osvaldo Luiz de Moura Filho | 408 Dias | Patrick Daliguet | AC |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0215-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-19 14:13 | Nível 2 | COS-SMB-330822 |  | CEDOC Closure | The can holder, iten 30 (BDM-00070465), was broken during the pressure test. | Não |  |  |  |  | 1) Replace the damaged parts from SBR 2 by SBR 4; 2) The traceability of the replaced parts of the both Stern Gland must be updated; Pay attention to register the correct serial number of the origin of equipment; For example : Rep 30 broken replaced per Rep 30 from Stern Gland which has traceability reference APXXXXXX. 3) Raise a NCR-MAT to delibery new parts. | Naval Group suggest replace de broken item. Take from SBR4 and replace on SBR2. Take care with the traceability of the items. Add Naval Group suggest: 1) To changes all O-rings, items 29 and 35 of the MAT-422-0109; 2) Open a new NCR MAT to replanishment new items ( O-rings and Came )for SBR04. (Charles Boucher) | In accordance with level 2.2 proposal. The traceability folder of both equipment concerned thhe one damaged and the one from which piece is taken from. 10/03/2021: 1) The displacement of the shaft line caused the spacers to break but may have damaged other parts. It is necessary to check with inspection report (visual, dimensional) with photos and inspection report the parts: - bangle Rep 7 - Ice Rep 5B - Carbon Rep 4B A visual check with photo is to be done for: - cam support Rep 30 - Glass holder Rep 5A - Carbon holder Rep 4A - Key Rep 8 - Key Rep 10 - Boitard Rep 33 Create a new NCR if any of these hardware is damaged 2) - Scrap of the 3 spacers damaged during the pressure tests. - Replacement of the 3 ice cams ref. 41 as well as their O-rings ref. 29 and 35, New items will be restocked (5331145330435-O-RING 41.50X2.65 20A8 CLASS A-N - Qty: 3 and 5331144145869-O-RING 20.00X2.65 20A8 A-N - Qty: 3) If taken by the time, possible sampling of the elements of SBR4, and order to be provided for SBR4 => Add the new compliance elements to the material tracking file. - Perform the pressure tests of the equipment The traceability aspect of parts is important and must be ensured. The reference of the NCR must be mentioned in the 2 traceability files (of the taking material - of the yielding material) | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 406 Dias | Charles Boucher | MB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0216-2020 | 53B | ELETRIC | 2020-10-20 10:51 | Nível 2 | COS-SMB-321703 |  | CEDOC Closure | DA62510R cable connector lost for the construction process. | Não |  |  |  |  | Follow level 2.2 guidelines. | Use the SBR4 connector provided for DA12510N Open an NCR-MAT to supply a new connector JUPITER FED F 10M T03-14 E123 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 405 Dias | Stéphane Patrick Philippe Rideau | DA |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0218-2020 | 53B | STW | 2020-10-21 11:57 | Nível 2 | COS-SMB-200239, COS-SMB-319731 |  | CEDOC Closure | The numerical indicator type C.A 2150-M on the panel BC02500 DAR3 Mark P5 (S2A) is not turning on. | Não |  |  |  |  | Replace the indicator | Take on sbr 4 in BC02500 the NUMERICAL INDICATOR P5 (ENERDIS C.A 2150). Open NCR MAT to replenish it. |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 404 Dias | Etienne Alexandre Sebastien Rene Berot | BC |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0219-2020 | 53B | ACOUSTIC DISCRETION | 2020-10-21 14:12 | Nível 2 | COS-SMB-319712 | CTE00796936 | CEDOC Closure | During MS01 inspection the resilient mount compression was checked out of tolerance in disagreement with SMB-200965_E. When analyzing the drawings and the position of the equipment's center of gravity, we observe that it is displaced aft, where theoretically the mounts with greater load capacity should be positioned, and is the opposite of the positioning specified in the drawing SBH.2A21.SAD.006906. See attached results in CTE, drawings and 3D mockup. We do not know yet about the condition of the mounting of 53A-FC00521, as the NCR ICN-ESC-11-0938 / 2020 has not yet been treated. | Não |  |  |  |  | SUBMITTED FOR ANALYSIS AND REVIEW OF NAVAL GROUP TA | The mounting is not in accordance with SMB-TCP-OR-6748378: 1 x MN45-110 1 x MN45-60 2 x MN45-85. Redo the mounting with the correct elasting mounts and redo the measurement. |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 404 Dias | Patrick Daliguet | FC |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0225-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-22 18:17 | Nível 2 | COS-SMB-200161, COS-SMB-321710 |  | CEDOC Closure | The sealing faces of the FRESH AIR INDUCTION CUPOLA ACCESS COAMING - AC30052 is damaged, see annex. | Não |  |  |  |  | Repair. The same defect was found e treated in NCR-ICN-UFEM-12-410-2019. Follow the steps below: 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. | Rework Agree with para.2.1. Rework as per description stop point with Naval-group/TA |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 402 Dias | Hugues Bourget | AC |  | NO |  |  | 2020-10-23 18:33 | Frederic Pavic |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0221-2020 | 53B | STW | 2020-10-22 13:56 | Nível 2 | COS-SMB-319220, COS-SMB-319217, COS-SMB-200276 |  | CEDOC Closure | Communication errors found were during the inspection of the operation of PLC AUX2AL regarding the DP Profibus bus No.1. | Não |  |  |  |  | ICN recommends to replace the respective cables OO64004B and OO64005B. Forward to next level. | After technical expertise onboard Naval Group confirms that these two cable are corrects. Resume of technicals facts: 1- the cable OO64531B was not connected on input of the CPU Alaux2 connector Profibus but on output. The wiring has been modified. 2- the connecteur Profibus of DY02511 is damaged. No resistor detected and no continuity input A1/B1 with output B2/B2 and it has to be replaced with a NCR. 3- Remarked that the first connector Profibus on CPU ALaux2 and ALaux3 are not the model requiered with an external Subd connector for the connexion of maintenance console . ICN has to check and redo these works. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 403 Dias | Serge Meyer | OO |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0223-2020 | 53B | STW | 2020-10-22 14:55 | Nível 2 | COS-SMB-200276, COS-SMB-319750 |  | CEDOC Closure | The locks of the door for the cabinet OO02533 are missing. | Não |  |  |  |  | ICN suggests to remove the item from a cabinet in storeroom. NCR-MAT to be opened to request the missing item. | ICN used these lock for the door of OO02534 cabinet SBR1. Forward NCR to BO to deliver spare locks for the door of OO02533 cabinet SBR2. The door is not fitted onboard. | Please take the lock of the door from the damaged OO02531 cabinet. | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 403 Dias | Serge Meyer | OO |  | NO | NO |  |  |  |  | 2021-05-04 11:27 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0222-2020 | 53B | ELETRIC | 2020-10-22 14:52 | Nível 2 | COS-SMB-319321 |  | CEDOC Closure | The hose reel BB00061 (FM BB00061 / CMD 12EP003C0001 / CMX 12EP000D00014 / RP P0141256) has its connection plastic broken as we can see in the picture attached. | Não |  |  |  |  | It is necessary to change and create a NCR MAT for reposition. | Replace the BB00061 (12EP000D00014) broken by a new one available in stock Open an NCR MAT to supply a new one |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 403 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0224-2020 | 53B | STW | 2020-10-22 15:04 | Nível 2 | COS-SMB-319750, COS-SMB-200276 |  | CEDOC Closure | It was verified the lower fitting of the door for the equipment OO02532 is damaged in S-BR02. | Não |  |  |  |  | Forward to Naval Group. | Naval Group requests to replace the door of cabinet from SBR4 IPMS Equipment OO02532. ICN has to create a NCR-MAT |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 403 Dias | Serge Meyer | OO |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0232-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-24 12:03 | Nível 2 | COS-SMB-330725, COS-SMB-330663 |  | CEDOC Closure | The machining on the hinge arm is not conform of the drawing: internal machining is not straight but with rounding. | Não |  |  |  |  | Send to level 2. | -This machining can't allow the good movement between the cover and hinge arm. -Dismount the hinge arm and finish the machining in conformity with the drawing. ( Patrick Daliguet) | Rework according to plan MAT424-0871_G. This machining with the NCR reference must be identified in the panel's traceability file. Complete the NCR with the balancing serial number | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 401 Dias | Patrick Daliguet | AG |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0233-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-24 12:05 | Nível 2 | COS-SMB-319693 |  | CEDOC Closure | Axle broken on board. | Não |  |  |  |  | Manufacture the shaft as per drawing attached. The NG must provide the material to be used. | -In accordance with level 2.1 redo the axis with drawing enclosed in material: CuAl10Ni5Fe4 (Patrcik Daliguet) |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 401 Dias | Patrick Daliguet | KT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0236-2020 | 53B | PIPES | 2020-10-26 19:55 | Nível 2 | COS-SMB-206077 |  | CEDOC Closure | The material 10RO110D00822 asssociated to P0141690 was lost. This NCR is to trace the material. | Não |  |  |  |  | ICN requests new material.. | Raise NCR MAT to launch the manufacture of new one. Replace by temporary plug for ceremony | The CMD is 18RO110D00822. In accordance with level 2.2 to raise an NCR MAT to manufacture a new one after confirmation that the equipment can´t be found. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 398 Dias | Patrick Daliguet | EL |  | NO | NO |  |  |  |  | 2021-05-27 15:20 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0235-2020 | 53B | STW | 2020-10-26 14:05 | Nível 2 | COS-SMB-200276, COS-SMB-200526, COS-SMB-319750 |  | CEDOC Closure | In order to attend the NCR-ICN-ESC-11-1076-2020, the following items originally from S-BR02 were applied in S-BR01. OO02505 - CHIEF OF THE WATCH DISPLAY UNIT (CMD 48ES100D00022); OO02533 - THERMAL CUT-OUT 70DEG WITH MANUAL RESET - M4Bl70HP4 (mark by level S01). | Não |  |  |  |  | Forward to Naval Group. | Naval Group request ICN to get from SBR3 IPMS equipments the spare SSO screen OO02500 and the spare thermal cut out from OO02533 ICN has to create a NCR-MAT for each spare taken |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 399 Dias | Serge Meyer | OO |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0237-2020 | 53B | SEATING | 2020-10-26 20:10 | Nível 2 | COS-SMB-319548 |  | CEDOC Closure | Initially during the pre-assembly of the EX00015 and EX00011 bollards, it was noticed that the seatings P4154682 and P4154667 are out of coordinates and the degree inverted. The position were corrected. After it was checked that the seatings P4154689, P4154682 and P4154667 are outside the coordinates of the drawing SBH.2D30.SAD.005739_K. The seatings P4154689, P4154682 and P4154667 to be positioned according to the bollards, had to leave the coordinates of the drawing. Attached are all changes. | Não |  |  |  |  | Accept the new coordenates for the 3 seatings. Use CTe´s annexed for the inspections. | Rework, Initally the support the P4154682, P4154689 , P4154667 and P4164603 were installed wrongly. Remove all, After remotion carry out a nittal attack to remove the austenitic welding. Open an NCR/RO to build up the planking Re-install P4154682, P4154689 , P4154667 in accordance with the position of P4164603. the dimension is out of original position ( 10mm) . It´s acceptable because the equipment will be centralised with the opening of P4164603. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 398 Dias | Hugues Bourget | EX |  | NO |  |  | 2020-11-11 13:34 | Felipe Gonçalves Sequeira |  | 2020-11-27 17:51 | Philippe Falquerho | Christophe Marret
NCR-ICN-ESC-12-0238-2020 | 53B | ACOUSTIC DISCRETION | 2020-10-27 12:53 | Nível 2 | COS-SMB-200542 | CTE00978508 | CEDOC Closure | During MS01 inpection on EV00010S the resilient mount compression was checked out of tolerance in disagreement with SMB-200965_E. Similar non conformity was checked in SBR1 (NCR ICN-ESC-11-0330/2019). See attached CTE00978508 Sheet 3. | Não |  |  |  |  | The compression dimensions are below the minimum recommended in SMB-200965_E. Naval Group TA evaluate a similar case in the SBR1 of the same equipment and make the necessary recommendations for 53B-EV00010S. | The maximum out of tolerance is 2mm. As on SBR1 with NCR-ICN-ESC-11-330-2019 ( maximum out of tolerance: 4,5mm ) can be accept as it is. | Accept as is and continuation of other inspections until SHIP11C, in the event of a deviation from SHIP11C, a new NCR must be issued. | Marcos Aurelio Correa Abrantes | Rogerio Milani | 398 Dias | Patrick Daliguet | EV | NCR ICN-ESC-11-0330/2019 | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0239-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-27 16:46 | Nível 2 | COS-SMB-321710, COS-SMB-200161 |  | CEDOC Closure | The sealing face of the FRESH AIR CUPOLA MANHOLE COAMING - AC30053 is damaged, see annex. | Não |  |  |  |  | Repair. The same defect was found e treated in NCR-ICN-UFEM-12-410-2019. Follow the steps below: 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. | Rework 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 398 Dias | Hugues Bourget | AC | NCR-ICN-ESC-12-0225-2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0244-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-30 15:54 | Nível 2 | COS-SMB-206092 |  | CEDOC Closure | The valves KT01417 and KT01418 were found disassembled on board. | Não |  |  |  |  | Rework. Replace the gasket and check the good condition and cleanliness; Check the condition of the bearing surfaces; Check the integrity of the studs and nuts; Replace the lock tab washer and install the valve according SMB-200960. Note: The valves were already reinstalled onboard, see attached. | Valves were not correctly mounted: -Switch box not in good orientation and support are not in line with the valves. -Dismount completely, cut and replace support at the good location. -Mount the switch box in the good orientation. -Mount valves and redo all inspections ( Patrick Daliguet) | in accordance with L2,1 proposal raise a NCR REGRESS if any inspection was done before this dismounting redo all inspections of mouting, testing traceability D BERNEDE | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 395 Dias | Patrick Daliguet | KT |  | NO | NO |  | 2020-11-13 11:23 | Felipe Gonçalves Sequeira |  | 2021-06-22 14:10 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0252-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-04 14:39 | Nível 2 | COS-SMB-206044 |  | CEDOC Closure | Gasket replacement and washer fixes for EM00007 and EM00008 valves. | Não |  |  |  |  | Send to level 2. | -Valves EM00007 and EM00008 were dismounted. -Gaskets and lock washers will be changed. A new purchase will be launch. -Stud rods can be reuse: there are in good status, the last tightening was in normal value and no hard point between stud and nuts -Raise a NCR REGRESS to redo inspections and test. (Patrcick Daliguet) | In accordance with L2.2 D BERNEDE | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 390 Dias | Patrick Daliguet | EM | NCR-ICN-REGRESS-12-0014/2020 | NO | NO |  |  |  |  | 2021-02-08 19:37 | Christophe Marret | Philippe Falquerho
NCR-ICN-ESC-12-0241-2020 | 53B | MECHANICAL | 2020-10-29 20:21 | Nível 2 | COS-SMB-347362, COS-SMB-321697 |  | CEDOC Closure | The stock removal remaining gugdion (BB, BE, upper and bottom) do not allow the assembly of the pipes, see images. | Não |  |  |  |  | Waiting for Naval Group orientation. | Installation of the gudgeon on board Actually on each gudgeon, it’s impossible to install correctly the greasing pipe due to the shame of the structure of the gudgeon For each gudgeon - Present the gudgeon on board ( connect0 to the stabilizer with the transversal key) - Tracer on the structure , the area that will need to be remove 9 by grinding), to permit the installation of the greasing pipe correctly (radius have to be respect) , see the annex 1 jointed to the NCR. Charles Boucher |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 395 Dias | Charles Boucher |  |  | NO |  |  | 2020-11-04 17:40 | Hugues Bourget |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0243-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-30 13:14 | Nível 2 | COS-SMB-321696, COS-SMB-321697 |  | CEDOC Closure | The seals on the upper rudder seal box were damaged during assembly, see attached items. | Não |  |  |  |  | Replace the items according CMD/NGD showed in annex. | Change the damaged items to finish the correctly assembly in order to success of the pressure test. Open a NCT MAT to replanishment of the dameged items. ( Charles Boucher) |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 395 Dias | Charles Boucher | DP |  | NO | [5 empty] | 2021-05-04 11:58 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0245-2020 | 53B | HVAC | 2020-10-30 16:57 | Nível 2 | COS-SMB-200478 |  | CEDOC Closure | During the assembly of the P0130328 joint, the P4152602 duct was misaligned with the joint. A 40 mm shimi was manufactured and installed inside the duct, according to annex 1, to align the duct P4152602 and the joint P0130328 at the time of bonding. After the P0130328 joint was glued, a fuse sleeve was inserted to avoid the risk of leakage, as shown in annex 2. | Não |  |  |  |  | NG, please validate the solution found by ICN. | Agree with ICN solution in the annex. |  | Renato da Silva Goncalves | Sharles Gomes Silveira | 395 Dias | Franck Rubis | FC |  | NO | [5 empty] | 2021-07-08 19:17 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0311-2021 | 53B | ELETRIC | 2021-01-15 15:12 | Nível 2 | COS-SMB-200502, COS-SMB-CAB-KT-ME |  | CEDOC Closure | Paid cable with a length of 4.6 m, short cable, was found on board. To make the connections at both ends, we need 1.5 m more. | Não |  |  |  |  | Provide a new cable (KT66871D) with a length of 6.5 m. | Provide a new cable 11LS222D00016 with a length of 6.5 m. BO : kindly check and take into account the new length | New length will be taken into account in next revision O of SBR PRODUCTION ROUTING FILE SMB-330521 | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 318 Dias | Stéphane Patrick Philippe Rideau | KT |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0248-2020 | 53B | PIPES | 2020-11-04 11:12 | Nível 2 | COS-SMB-206116, COS-SMB-206042, COS-SMB-327470 |  | CEDOC Closure | During adjust phase it was identified that the forecast overlength is not enough to be conform to SMB-030510. We request the remanufacture of the items according to attached drawing. For item P4123636 a template has been prepared and will be sent for remanufacturing. | Não |  |  |  |  | NG, Please inform which are the two NCR that are dealing with this matter. | NCR LEVEL 1 UNDER RESPONSABILITY ON ICN |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 390 Dias | Christophe Marret | FA |  | NO |  |  | 2021-03-30 12:27 | Franciellen da Silva Braga |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0314-2021 | 53B | ELETRIC | 2021-01-18 11:53 | Nível 2 | COS-SMB-200542 | CTE00765545 | CEDOC Closure | The DT 04100 panel does not comply with the proximity rule, see the annex. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Replace the existing screws with screws 32VI110D01871 "SLOTTED COUNTERSUNK FLAT HEAD SCREW WITH THREAD M6, NOMINAL LENGTH L = 20 AND PROPERTY CLASS 4.8" identical to SBR3 (see annex1) | Replace the screws used (H head with washer) by FHC screws as provided in the definition file, (M6x20x20 CL4.8 - 32VI110D01871) is acceptable. | Fabio Brito da Silva | Jair de Barros Sena de Araujo | 315 Dias | Stéphane Patrick Philippe Rideau | DT |  | NO | NO |  | 2021-02-01 15:31 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0251-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-04 14:26 | Nível 2 | COS-SMB-200763 |  | CEDOC Closure | Occurred in valves DN00311 and DN00312: 1) DN000311 valve: a. The valve (DN00311) was assembled on 27/08/2020 and released for B01, but after the teste B01 (NG) signalized that the screws were in wrong size. b. The valve (DN00311) was disassembled on 28/09/2020. c. The valve (DN00311) was reassembled on 30/09/2020 and finished on 13/10/2020. See the new CTE B06 in annex. 2) DN00312 valve: a. The valve (DN00312) was not disassembled. See the CTE B06 in annex. | Não |  |  |  |  | Accept as it is. | a visual control have to be done B001 and B02 pressure tests will be done after remounting if the mounting is conform and pressure tests without leaks, it is possible to accept as it is DALIGUET P |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 390 Dias | Patrick Daliguet | DN | NCR-ICN-REGRESS-12-0024-2020 | NO |  |  | 2020-11-05 12:27 | Franciellen da Silva Braga |  | 2021-02-26 18:45 | Franciellen da Silva Braga | Philippe Falquerho
NCR-ICN-ESC-12-0256-2020 | 53B | STW | 2020-11-06 16:42 | Nível 2 | COS-SMB-200526, COS-SMB-200276 |  | CEDOC Closure | The DS214 - DIGITAL PANEL METER ICO 514VM [FAQ11 - AOIP] ) of PEDSP OO02500 presented malfunctioning on its display, possibly due a bad contact on its eletronic bus. | Não |  |  |  |  | Forward to Naval Group. | After repaired the welds on DS214 Display naval group FO confirms that this display has a failure (error 0) on the analog Input when it is connected. Replace the Display DS214 from priority SBR4 else SBR3 product. Report on NCR the serial number of these products. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 387 Dias | Serge Meyer | OO |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0257-2020 | 53B | STW | 2020-11-09 18:38 | Nível 2 | COS-SMB-200239, COS-SMB-200560 |  | CEDOC Closure | It was found that the acrylic of the voltmeter (+ D1A -P4) of the BC02660 panel (11TD100D00073) is damaged. See attached image. | Não |  |  |  |  | Replace voltmeter | ICN needs to open an NCR MAT to replace the voltmeter + D1A-P4 of the BC02660 on the SBR2. On the other hand, Naval Group confirms that the voltmeter can be used as is while waiting for its replacement. |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 384 Dias | Etienne Alexandre Sebastien Rene Berot | BC |  | NO |  |  | 2020-11-27 17:20 | Etienne Alexandre Sebastien Rene Berot |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0258-2020 | 53B | ACOUSTIC DISCRETION | 2020-11-11 11:42 | Nível 1 | COS-SMB-319713 | CTE00963339, CTE00963760 | CEDOC Closure | It was checked in Diesel Cradles that the compression of some resilient mounts is out of tolerance in disagreement with SMB-200965_E. See annexes 1 and 3. | Não |  |  |  |  | Rework according to SMB-200965_E | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 383 Dias |  | AM |  | NO
NCR-ICN-ESC-12-0261-2020 | 53B | PIPES | 2020-11-11 13:12 | Nível 2 | COS-SMB-206084 |  | CEDOC Closure | To attempt the manufacturing rules it was necessary to change the flanges from pipe P4152681 from loose to fixed. It was: 18RO11D00011 18RO110D0003 Became: 18RO110D00479 18RO0110D00067 | Não |  |  |  |  | NG, review the order in item 2.1 | Agree with the modification of the pipe . Repair. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 383 Dias | Franck Rubis | DM |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0262-2020 | 53B | PIPES | 2020-11-11 13:21 | Nível 2 | COS-SMB-200451, COS-SMB-200452 |  | CEDOC Closure | During CSPI inspection it was identified a not good practice by TA over the pipe line EN50025M. The pipe P4145049 has it weld with P4148243 located inside the pipe clamp P4145050. However it is not described in the mounting rules it was requested to be treated as non-conformity. | Não |  |  |  |  | NG, review the order in item 2.1 | It is not possible to respect the model ,lack of space for the clamping Study to be done by BO asap Send to level 3 | For SBR2 : Accept as is for the pipe clamp P4145050 mounting. For SBR1: As P4145049 & P4148243 SBR01 pipes were manufactured by ICN under Caderno: CC-200451-80510-11-001, please inform NAVAL GROUP Design Authority on what has be done for mounting the same pipe clamp. No NCR level 3 has been transmitted to NAVAL GROUP Design Authority. Repair action : Please note that the PTRH EN SMB-051113 will be updated to add the request to dismount the pipe clamp P4145050 before pressure and tightness test, in order to check there is no leakage. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 383 Dias | Franck Rubis | EN |  | NO | NO |  |  |  |  | 2021-05-10 13:25 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0263-2020 | 53B | PIPES | 2020-11-11 13:25 | Nível 2 | COS-SMB-206116, COS-SMB-206115 |  | CEDOC Closure | It was impossible to mount the pipes with the original configuration onboard due to the lack of access. To solve the pipes was cutted and crimpred with the same connections defined in the extremities, as per attached drawing. Concerned products: - P4165788 - P4165717 | Não |  |  |  |  | NG, review the order in item 2.1 | REPAIR: Agree with the modification solution proposed by icn. New inspections must be respected. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 383 Dias | Franck Rubis | FA |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0259-2020 | 53B | STW | 2020-11-11 11:54 | Nível 2 | COS-SMB-200258 |  | CEDOC Closure | During flow adjustment of the BB00600 and BB00700 batteries, we identified that the flow indicator are not calibrated. (EV12151Q - 50MD600D00004 and EV12152Q 50MD600D00004). It is necessary to carry out the calibration. To continue with the available system, i request authorization to send the flow indicator we have in stock for calibration, after calibration, perform the replacement with the one installed on board the SBR-2. | Não | 2021-09-29 14:29 |  |  |  | It is necessary to carry out the calibration. To continue with the available system, i request authorization to send the flow indicator we have in stock for calibration, after calibration, perform the replacement with the one installed on board the SBR-2. | Agree to calibrate the flow indicator available in stock before proceed to the standard exchange onboard. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 383 Dias | Gildas Le Goff | EV | NCR-ICN-REGRESS-12-0028-2021 | NO | [5 empty] | 2021-02-08 17:03 | Franciellen da Silva Braga | Christophe Marret
NCR-ICN-ESC-12-0260-2020 | 53B | ELETRIC | 2020-11-11 12:56 | Nível 2 | COS-SMB-319737 |  | CEDOC Closure | The “53B-OO24402” equipment is not supplied with the internal connections of the “53B-OO24307” connected to the internal terminals. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | For the internal FLAT modules ASI type 4 integrated in the cabinet (FQ or IPMS) according with Document SMB-201629 (ASI MODULES DEFINITIONS) You don't need specific connector. For this case, apply the wiring described in BDM-00073622 To connect use rep 36 conductor quoted in this plan |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 383 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO |  |  | 2020-12-01 11:01 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0268-2020 | 53B | PIPES | 2020-11-13 11:26 | Nível 2 | COS-SMB-200440, COS-SMB-206090 | CTE00981437, CTE00951377, CTE00981438, CTE00951378 | CEDOC Closure | Due to the pending material for the HE01202 valve, ICN commissioning team needs to perform partial B01 and B02 tests in HE system. The proposed solution is: - perform B01_HE01201/ B02_HE01201 using the point at the end of line HE5120Y before the HE01202, as a checking point, instead of the point at HE01204 valve; - perform B01_HE01203/ B02_HE01203 using the point at the end of line HE5120Y after the HE01202, as a checking point, instead of the point at HE01201 valve; To ensure the traceability of quality control team, the related reports must be issued with all the relevant observations mentioned in this NCR. After ceremony, these operations, resulting from the pendency of the HE01202 valve, will be ensured in S02_HEZ0008 test, which includes all products in the line. | Não |  |  |  |  | SEND TA 2.2 | In accordance with level 1.1 ( Patrick Daliguet) | Perform only B01,B02 HE01203 using the point at the end of line HE50120Y [Put a plug after the test put also plugs on each connections not mounted outside the pressure hull | Priscilla Felipe de Oliveira Botelho | Sergio Kenji Inoue | 381 Dias | Patrick Daliguet | HE | - | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0269-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-13 12:57 | Nível 2 | COS-SMB-331842, COS-SMB-319719, COS-SMB-321710, COS-SMB-319154, COS-SMB-206081 |  | CEDOC Closure | For mobile parts AC31019, AC32069 and AC34050, the orientation of the mount is not correct, due the short time to the ceremony and all necessary tests were performed, ICN request to fix the orientation after the ceremony. | Não |  |  |  |  | Accept as it is for ceremony. Send to level 2 to validate. | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | In accordance with TA 2.2 | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 381 Dias | Patrick Daliguet | AC |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0270-2020 | 53B | PIPES | 2020-11-13 13:02 | Nível 2 | COS-SMB-206190 |  | CEDOC Closure | For the preparation of the drill on P4168507 it was identified a need to change the position according to attached drawing. | Não |  |  |  |  | NG please analyze the need to change the position according to the attached drawing. | Due to the difficulty to fit the stud in the top of assembly of the zinc flange and the pipe, the position of thewelding piece has to be moved as per the new position shown on the pipe´s isometric |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 381 Dias | Alain Lamy | BQ |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0272-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-13 14:25 | Nível 2 | COS-SMB-319693 |  | CEDOC Closure | For the ceremony, the TLTs are mounted with a provisory lip seal that will be changed after for the official J06. | Não |  |  |  |  | Accept as it is for ceremony. Send to level 2 to validate. | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | IN ACCORDANCE WITH 2.2 | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 381 Dias | Patrick Daliguet | KT |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0271-2020 | 53B | ELETRIC | 2020-11-13 14:16 | Nível 2 | COS-SMB-200549, COS-SMB-200551, COS-SMB-319730 |  | CEDOC Closure | Equipment (BE0B00AD, BE0A00AC and BE0B00AF) damaged in the production process. | Não |  |  |  |  | Equipment (BE0B00AD, BE0A00AC and BE0B00AF) damaged in the production process. | Take on another boat, depending on available stock. Replace only the broken part (the globe) so that no REGRESS will be necessary, avoiding redo the ctrl E01 and STW. Send in lvl 3 to request the NGD of the globe in order to be able to launch an provisioning. Do NCR-MAT to replenish (Stephane Rideau) | Scrap the damaged globe. Naval Group will send a new globe 0930930239565 and the seal 5330930177267. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 381 Dias | Stéphane Patrick Philippe Rideau | BE |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0274-2020 | 53B | ACOUSTIC DISCRETION | 2020-11-16 13:46 | Nível 1 | COS-SMB-208161 | CTE00907175 | CEDOC Closure | Air conditioning unit FC00525 was assembled without the A02 inspection having been carried out in the seating FC00525C. | Não |  |  |  |  | Remove and Rework - Disassemble the FC00525 from the seating, and pipes connected to the seating, to perform A02 acoustic discretion inspection. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 378 Dias |  | FC |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0277-2020 | 53B | PIPES | 2020-11-17 12:31 | Nível 2 | COS-SMB-319638 |  | CEDOC Closure | The document SMB-030510_E sheet 91 shown that the bottle with CMD: 22BA000D00109 is fitted with dip tube for a positioning on board with vertical axis between 45 to 86 degres. But, the real vertical position on board of EQ00101 bottle is 25 degres (See Annex 1). As the real vertical position on board is different to what is mentioned in document SMB-030510_E, do we must keep the dip tube or it would rather to remove it from the bottle? If the dip tube is not required, the document SMB-030510 need to be updated or a new CMD has to be defined for this bottle. | Não |  |  |  |  | NG, analyze whether we should keep the immersion tube or prefer to remove it from the bottle? | Proposal solution: Taken into account the inclinaison ( 25 ° ) of the bottle EQ00101 on board, there is no longer any need for a dip tube inside this air bottle. Then, replace the actual adapter equiped with a dip tube by a new one without dip tube. For information, on SBR1 and SBR2, we have replaced the said adapter equiped with dip tube by an adapter without dip tube retrieved from BX bottles supplied with a wrong fitting. This proposal solution is to be sent to Expert Level 3 for validation. Also, the document SMB-030510 (SHEET 91) is to be modified in order to take into account the new outfitting of bottle 22BA000D00109 but also the new outfitting of bottle 22BA000D00139 due to a wrong supply on BX bottles ( Qty 8 supplied for SBR1 and SBR2) | Accept as is for the modified bottles SBR1 and SBR2 such as displayed by the AT to the level 2 of the NCR. In complement : bottles SBR3 and SBR4 will be modified before sending | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 377 Dias | Alain Lamy | EQ |  | NO | NO | [6 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0275-2020 | 53B | SEATING | 2020-11-16 16:54 | Nível 2 | COS-SMB-200388 |  | CEDOC Closure | During the assembly of the AG00036 equipment, there was a change of dimension in the seating P4019069. It was necessary to remove the support P4019069 for height adjustment. | Não |  |  |  |  | Rework the positioning for the seating P4019069. Use CTE´s annexed. | Rework as per original, cut the seating, to ajust the hight if the gap if below 8mm build up the seating. if it´s more rework new elements After removing carry out a visual and nittal inspection of the hull, open an NCR/RO to build up the hull reinstall a seating. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 377 Dias | Hugues Bourget | AG |  | NO | [5 empty] | 2021-03-04 16:30 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0276-2020 | 53B | PIPES | 2020-11-17 12:25 | Nível 2 | COS-SMB-327470, COS-SMB-200385 |  | CEDOC Closure | During assembly of pipe P4123633 it was identified a miss assembly on clamp P4021224. During further inspection there was more deviation on the following clamps: P4021225, P4021321, P4021221, P4021220 and P4021224. | Não |  |  |  |  | NG, please analyze the problem found on board. | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB -Rework the connected pipes when is necessary. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 377 Dias | Hugues Bourget | KT |  | NO |  |  | 2020-12-08 17:55 | Felipe Gonçalves Sequeira |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0312-2021 | 53B | ELETRIC | 2021-01-15 15:57 | Nível 2 | COS-SMB-200526 |  | CEDOC Closure | Cable connector GV62500I damaged during the construction process. | Não |  |  |  |  | Use the connector "D38999-26-W-G-75-BN (GV02501)" provided for the SBR4. | Use the connector "D38999-26-W-G-75-BN (GV02501)" provided for the SBR4. Open a NCR MAT to supply a new one. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 318 Dias | Stéphane Patrick Philippe Rideau | GV |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0278-2020 | 53B | HVAC | 2020-11-18 12:59 | Nível 2 | COS-SMB-200486, COS-SMB-200561 |  | CEDOC Closure | Interference of the P4160082 duct with the P4172665 piping. it is not possible to assemble the pipe P4172665, according to annex 1, it has an interference with the duct P4160082. | Não |  |  |  |  | NG, please check the problem found. | Proposal solution: Modify the wrong pipe as per requirement on board (use it as dummy). Then, send the new routing of the pipe to UFEM in order to re-bend according to the sample. Give back the new dimensions ( angles, length..) to the GIR or back office in order to update the isometric of the spool P4172665. Answer to be given by expert level 3 | Rework of the pipe according to the bord constraints, acccording to approach provided in paragraph 2.2 and in line with what had to be done on SBR1. (SMB-TDP-PR-6779504 and SMB-TDP-PR-6779503) | Renato da Silva Goncalves | Sharles Gomes Silveira | 376 Dias | Alain Lamy | FH |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0280-2020 | 53B | STW | 2020-11-18 18:35 | Nível 2 | COS-SMB-200246 |  | CEDOC Closure | WAS RECEIVED VIA SMB-TDP-PR-6628357 ON 11/4/2020, REVISION “E” OF DOCUMENT SMB-051174 ADDING INSPECTIONS F02_DWZ0005 (ITEM 8.2.5), F02_DWZ0006 (ITEM 8.2.5), F05_DWZ0002 (ITEM 8.4 .2) AND F05_DWZ0003 (ITEM 8.4.2) IN THE CURRENT COMMISSIONING STAGE OF SBR-01. | Não |  |  |  |  | DUE TO THE CURRENT COMMISSIONING STAGE THAT PREVENTS THE PERFORMANCE OF INSPECTIONS AND AS THE ASSEMBLY AND INSPECTION ACTIVITIES CARRIED OUT IN MAIN HALL WERE ACCOMPANIED BY THE NAVAL GROUP, WE REQUEST TO ADD THE INSPECTIONS ONLY ON SBR-02/03/04. | Regarding the updating time of the doc AIS SMB-051174, and the situation of the SBR1, the new controls requested can be performed only on SBR-02/03/04. |  | Sergio Kenji Inoue | Sergio Kenji Inoue | 375 Dias | Gildas Le Goff | DW | NA | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0281-2020 | 53B | MECHANICAL | 2020-11-18 18:50 | Nível 2 | COS-SMB-321784 | CTE01036496 | CEDOC Closure | During inspection B06 of valvules MB00300 (P0104808) and MB00301 (P0104812) it were detected that the requiriment of "minimum 2 stud rod threads protruding" not in conformity according SMB-200960_H (item 8.1). See photo attached. | Não |  |  |  |  | For analysis by Naval Group. | As there is not enough space between the flange and the body of the valve MB00300, the respect of the rule of "minimum 2 stud rod threads protruding" cannot be applied then the two assemblies MB00300 with MB00301 and MB00300 with MB00003 can be accepted as it is as long as the edge of the studs don´t touch the body of the valve. Answer to be validated by expert level 3 (David BERNEDE) | In accordance with level 2.2 position. ( David Bernerde) | Neimar Mayrink da Silva | Sergio André Telles Soares | 375 Dias | Patrick Daliguet | MB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0284-2020 | 53B | ELETRIC | 2020-11-19 15:32 | Nível 2 | COS-SMB-319721 |  | CEDOC Closure | Broken lamp on the EL02500 panel door. | Não |  |  |  |  | USE THE EL02500 EQUIPMENT LAMP (SBR4), IF APPROVED BY THE NAVAL GROUP. | Take on SBR4 the light rep 50 of BDM-00060857 SIGNAL LAMP UNIT D22 LED BLUE 24V NGD: 6210144901880 Open NCR MAT to replenish it if control to be done open a NCR REGRESS |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 375 Dias | Etienne Alexandre Sebastien Rene Berot | EL |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0283-2020 | 53B | ELETRIC | 2020-11-19 14:37 | Nível 2 | COS-SMB-200526 |  | CEDOC Closure | The electrical connection points of the GV02501 equipment are unviable to guarantee the continuity of the system. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Take out the cabinet , in order to see clearly the issue. clean with scrutiny with a vacuum cleaner all sockets, and close them with a metallic or plastic Caps. In the same time clean the arear and arrange the cables, change the plug broken. and protect the cabinet To perform that provide the following items: Cotton, Silicon grease, WD 40, Electrical contact cleanner spray Vacuum cleaner, Rags Little metallic brush, as toothbrush... Plastic caps (see that with electrical Team). take pictures |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 375 Dias | Stéphane Patrick Philippe Rideau | GV |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0290-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-24 14:33 | Nível 2 | COS-SMB-200532 |  | CEDOC Closure | During the execution of RF B01 and B02 inspections, it was identified that the ball valve (IM: RF00008 ; CODE: 18CR000D00334) was giving water passage. After troubleshooting, it was identified a damage on the the ball of the valve. This valve needs to be changed. | Não |  |  |  |  | Suggestion to change only the ball of the balve. | Take out the ball valve on SBR 4 or SBR 3 from the whare house, check theire ball Valve, If there are OK , in order to avoid to unmount all the valve ball assembly on the SBR 1, unmount ( With TA NG) only the ball assembly on SBR 4 or SBR 3 in this order, and change with this one of SBR 1. Raise an NCR MAT to replace the defective part. | If the valve is not coçpletely dismouted it will be necessary to define and use a specific inspection file for mounting specific test will be also define to check the good fonctionality of the ball alve if it not possible to repair the situation the tool to perform B01 and B02 will be put in place for the ceremony of decembre 2020 D BERNEDE | Matias Lins Maranhão | Matias Lins Maranhão | 370 Dias | Paul Fosse | RF |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0296-2020 | 53B | ELETRIC | 2020-12-07 11:59 | Nível 2 | COS-SMB-200542 | CTE00765545, CTE00765546 | CEDOC Closure | The DT04200 and DT04300 panels do not comply with the proximity rule, see the annex. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Replace the existing screws with screws 32VI110D01871 "SLOTTED COUNTERSUNK FLAT HEAD SCREW WITH THREAD M6, NOMINAL LENGTH L = 20 AND PROPERTY CLASS 4.8" identical to SBR3 (see annex1) | Replace the screws used (H head with washer) by FHC screws as provided in the definition file, (M6x20x20 CL4.8 - 32VI110D01871) is acceptable. | Fabricio Duarte Ramos | Jair de Barros Sena de Araujo | 357 Dias | Stéphane Patrick Philippe Rideau | DT | NCR-ICN-REGRESS-12-0040-2021 | NO | NO |  | 2020-12-08 14:10 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0294-2020 | 53B | STW | 2020-12-01 14:53 | Nível 2 | COS-SMB-200566 |  | CEDOC Closure | The blue part of the valve the valve BB00019 (CMX 18RT000D00143 - CMD 18RM000C0005) is broken as we can see in the picture attached. | Não |  |  |  |  | It is necessary change the valve and open NCR MAT for replenishment. | Need to proceed to a standard exchange of the valve (take in stock or on SBR3 or SBR4). Need to create a NCR-MAT to order a coupling (item 3) following the SBR-ETM-00000M0001 folha 4134 to refund the stock. |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 363 Dias | Gildas Le Goff | BB |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0295-2020 | 53B | PIPES | 2020-12-07 11:11 | Nível 2 | COS-SMB-206140 |  | CEDOC Closure | During the vacuum test it was identified a problem at EQ00027 valve. It is not reaching the end of course. To solve the issue it was proposed the change for a new cmd. (J06 - CEREMONY) | Não |  |  |  |  | To solve the problem, ICN suggests changing to a new cmd. | EQ00027 CMD: 18RT210D00015 will be changed by a new one. NCR MAT will be raise to follow the repair of valve. NCR REGRESS will be raise to carry out new pressure tests and inspection (M05,B01,B02). | In accordance with level 2.2 proposal. Add in the NCR regress the S02 test concerning the circuit. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 357 Dias | Patrick Daliguet | EQ | NCR-ICN-REGRESS-12-0027-2021 | NO | NO |  |  |  |  | 2021-03-25 17:50 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0317-2021 | 53B | MECHANICAL | 2021-01-20 12:52 | Nível 2 | COS-SMB-319712 | CTE00957278 | CEDOC Closure | It was not possible to see traceability of the screw batches. As directed by David Bernede, Ncr was opened to make documentation traceability and, if necessary, to accompany disassembly. | Não |  |  |  |  | Send to level 2 | On B06 of BM00032: - all the tracability of nuts is not possible -Lock washers were bended more than one year after the last tightening (20/07/2020 - 30/01/2019) On BM00031: -Lock washers were bended more than one year after the last tightening (30/07/2020 - 22/01/2019) -F06 was done more than one year after the last tightening (24/07/2020) It's necessary to dismount and remount properly with inspections and tests the two valves A NCR regress will be raise and after B05 updated | In accordance with level 2.2 proposal. It is not possible to know what could be happened between the dates of last tightening and the bending of tab washers. David BERNEDE | Rodolfo Alves de Abreu | Ernanes de Souza | 313 Dias | Patrick Daliguet | BM |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0304-2021 | 53B | ELETRIC | 2021-01-04 13:01 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | The threads of the connecting screws are worn. | Não |  |  |  |  | FOLLOW LEVEL 2 GUIDELINES. | Check if NGD 0930930037510 connector available on SBR3 or 4. Open an NCR-MAT to provision a new connector. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 329 Dias | Stéphane Patrick Philippe Rideau | FR |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0300-2020 | 53B | INTEGRATION EQUIPMENT | 2020-12-16 19:18 | Nível 2 | COS-SMB-200563 |  | CEDOC Closure | There is a leakage in cooling system (P0102195 - BB00700 - 17FR000D00005) in forward battery C100 as highlighted in the annex. | Não |  |  |  |  | It was not necessary to remove the the battery connection BB22511 to access the leakage point. After repair, remount the pipe to perform the leakege test S02BBZ0005. | Agree with proposed solution above in 2.1, but after having located and repaired the leakage in workshop, carry out a pressure test on the PVC element before remount the pipe on board. ( Alain Lamy) |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 347 Dias | Alain Lamy | BB | NCR-ICN-REGRESS-12-0026-2020 | NO |  |  | 2021-01-13 18:30 | Felipe Gonçalves Sequeira |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0301-2020 | 53B | INTEGRATION EQUIPMENT | 2020-12-17 12:23 | Nível 2 | COS-SMB-321696, COS-SMB-321697 |  | CEDOC Closure | During final assembly of the Rudder Blades, Stocks, Yokes and Tilting Arms of Aft Steering Gear some clearances are out of tolerance. See e-mails attached. | Não |  |  |  |  | Rework. Hydroplane Gear: • Dismounting the Hydroplane Blades completely, send to workshop and take new measurements; • Check the referential axis of the steering gear holes and transmission lines onboard by optical; • According results make new calculations and remachining the shims; • Check the cleaning of the coamings (holes) and pipes before installation (flow of the grease and control the quality); • Assembly back the Hydroplane blades, Stocks, Yokes and Tilting Arms; Note: Pay attention during torque applying with Superbolt Nut. Don’t use impact wrench, tight the nut by hand; • Check the clearances and flow of the grease after final mounting. Rudder Gear: • After finishing Hydroplane activities, an analyze must be made to verify if is necessary to dismounting the Rudder Gear completely as done in Hydroplane Gear or a minimum disassembly (for example, removing and machining only the shims). | To solve the problem of the gap on the blade, you will find attached the detail of the work to be carried out Find also, the first measure and calculation of the hydroplane system, with details of the added works The same woks should be perform on the rudder system |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 347 Dias | Charles Boucher | DP |  | NO | [5 empty] | 2021-05-10 15:11 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0302-2020 | 53B | PIPES | 2020-12-17 17:17 | Nível 2 | COS-SMB-206041, COS-SMB-206042 |  | CEDOC Closure | During adjust phase it was identified that the forecast overlength is not enough to be conform to SMB-030510. We request the remanufacture of the items according to attached drawing. | Não |  |  |  |  | Remanufatura dos itens conforme desenho anexo. | -Authorizes the modification of the pipe conforming to the new iso proposed by icn -Associate all M01 manufacturing CTEs ,M10,M05 -REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 346 Dias | Franck Rubis | EM |  | NO | [5 empty] | 2021-03-25 17:33 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0306-2021 | 53B | ELETRIC | 2021-01-13 17:31 | Nível 2 | COS-SMB-200542, COS-SMB-CAB-EF-EZ |  | CEDOC Closure | Connectors of the EF62610F and EF62611F cables lost during the construction process. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | see if the two connectors (NGD : 0930930098682 + 0930930273306 + 5975145548490 + 5975142632291) are available on another boat open an NCR-MAT to supply two new connectors |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 319 Dias | Stéphane Patrick Philippe Rideau | EF |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0315-2021 | 53B | ACOUSTIC DISCRETION | 2021-01-19 17:11 | Nível 1 | COS-SMB-200542 | CTE00756889 | CEDOC Closure | During A06 inspection on EJ00003 pump the lack of 2 tilt sensors and 1 shock sensor 10G was checked. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspection, but its operation should be checked during the STW. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 313 Dias |  | EJ |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0307-2021 | 53B | SEATING | 2021-01-14 19:56 | Nível 2 | COS-SMB-200385 |  | CEDOC Closure | During the assembly of some pipes in the KT system, it was identified that the seating was mounted in the wrong coordinate. According to NCR-ICN-ESC-12-0276-2020, the seatings P4021220, P4021221, P4021224, P4021225 and P4021321 are out of coordination with the pipes, but it was seen on board that the seatings P4021217, P4021218 and P4021219 are also out of the coordinate and it will be necessary to remove all. In annex, there are all the seatings that will be modified. | Não |  |  |  |  | Remove the seatings using Annex 2 and install again using CTE´s and drawning annexed. | Rework, The drilling of the seating were oblonded, so not in accord with the design. Remove the seatings remove the austenic trace carry out nital test , 100%VT, Open NCR/RO for each repair, annex a map defetc and dimension if the depht is less tan 3mm Carry out 100% VT , 100%MT. Re- install the seatings WITH THE VALVES at the therorical position . If any defect depht is more than 3mm carry out 100% RT and 100%UT |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 318 Dias | Hugues Bourget | KT | NCR-ICN-ESC-12-0276/2020 | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0310-2021 | 53B | ACOUSTIC DISCRETION | 2021-01-15 14:16 | Nível 1 | COS-SMB-319667 |  | CEDOC Closure | During MS02 inspection on FC00527 it was checked that one of the support reinforcements (starboard-aft support) of the seating FC00527C was cut. See photo in Annex 1. | Não |  |  |  |  | Redo item 10 of the seating P4031090 on board using sbh.plm.3b10.000441_K and CTE´s annexed. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Luiz Felipe Silva Moreira | 318 Dias |  | FC |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0309-2021 | 53B | PIPES | 2021-01-15 14:03 | Nível 2 | COS-SMB-319331, COS-SMB-206056 |  | CEDOC Closure | VALVE EF00380 MOUNTED INVERTED. | Não |  |  |  |  | Assemble the EF00380 valve according to the project definition. | Mount the valve according the drawing attached. | SMB-000871 will be updated for inversion of the valve symbol with respect to the direction of the fluid. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 318 Dias | Franck Rubis | EF | NCR-ICN-REGRESS-12-0013/2020 | NO | NO |  |  |  |  | 2021-06-29 14:10 | Christophe Marret | Christophe Marret
NCR-ICN-ESC-12-0316-2021 | 53B | ACOUSTIC DISCRETION | 2021-01-19 17:40 | Nível 1 | COS-SMB-200542 | CTE00929541 | CEDOC Closure | After the inspection of the A06, it was found that 02 inclination sensors are missing on the equipment. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspection, but its operation should be checked during the STW. | NCR LEVEL 1 |  | Emanuela Lucia Justino dos Santos | Rogerio Milani | 313 Dias |  | BB |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0319-2021 | 53B | ELETRIC | 2021-01-20 17:49 | Nível 2 | COS-SMB-200526 |  | CEDOC Closure | Cable connector GN62758B damaged during the construction process. | Não |  |  |  |  | Apply the connector provided for the SBR4 and open the "NCR-MAT" for a new supply, description of the connector, 35661 - RPFTV 6M N R&M IDC (Equipment: GN02563). | NG does not authorize taking on another submarine. Spare available with production team. The connector is already repaired by the production team. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 312 Dias | Stéphane Patrick Philippe Rideau | GN |  | NO |  |  | 2021-05-11 18:13 | Stéphane Patrick Philippe Rideau |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0318-2021 | 53B | NON RESISTANT STRUCTURE | 2021-01-20 14:37 | Nível 2 | COS-SMB-319146 |  | CEDOC Closure | Adjustment of the stanchions CO58-TD-EP127, CO60-TD-EP133, CO61-TD-EP135 and CO62-TD-EP139. To adjust the stanchions with GRP, it was necessary to remove and readjust 2mm deep openings. | Não |  |  |  |  | Reinstall all the EP´s mentioned. Use CTE´s annexed. | Rework, The stanchions were not install in accord with the design. Remove the seatings remove the austenic trace carry out nital test , 100%VT, Open NCR/RO for each repair, annex a map defetc and dimension if the depht is less tan 3mm Carry out 100% VT , 100%MT. Re- install the seating at the good location If any defect depht is more than 3mm carry out 100% RT and 100%UT |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 313 Dias | Hugues Bourget |  |  | NO | [5 empty] | 2021-03-24 20:05 | Franciellen da Silva Braga | Philippe Falquerho
NCR-ICN-ESC-12-0321-2021 | 53B | ELETRIC | 2021-01-20 19:40 | Nível 2 | COS-SMB-319724 |  | CEDOC Closure | Panel with missing internal parts, so we were unable to connect the internal cables. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Following the NCR 1271 ,we took the "driver card" on sbr2 to repair the sbr1. In order to be able to start DY02511 on sbr2, we have to take the "driver card" on sbr3 No need to open NCR MAT because normally it has been done after NCR ESC 1271 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 312 Dias | Etienne Alexandre Sebastien Rene Berot | DY |  | NO |  |  | 2021-02-01 15:47 | Christophe Marret |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0324-2021 | 53B | NON RESISTANT STRUCTURE | 2021-01-25 11:40 | Nível 2 | COS-SMB-319088 | CTE00851436 | CEDOC Closure | During the dimensional inspection D95_15 - CTE00851436.1, it was detected that the 700mm dimension is out of tolerance (See attached CTE). | Não |  |  |  |  | Height can be adjusted during machining on board. Accept as it is. | Accept as it is H BOURGET |  | Neimar Mayrink da Silva | Felipe Trigueiros Silveira | 308 Dias | Hugues Bourget | N/A |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0327-2021 | 53B | ELETRIC | 2021-01-29 12:25 | Nível 2 | COS-SMB-200544 |  | CEDOC Closure | The lock for the OO62584B cable connector was damaged during the construction process. | Não |  |  |  |  | Use o conector fornecido para o SBR4 e crie um NCR-MAT. | Naval Group confirms the suggested action by ICN. Create a NCR-MAT to replace on SBR4 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 304 Dias | Serge Meyer | OO |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0396-2021 | 53B | MECHANICAL | 2021-03-23 18:52 | Nível 2 | COS-SMB-319712 |  | CEDOC Closure | The equipament FC00521 damaged during the construction process (see annex). | Não | 2021-06-15 13:19 |  |  |  | Send to level 2. | make the standard exchange of the pieces damaged make NCR Mat |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Frederic Guevel | FC |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0330-2021 | 53B | INTEGRATION EQUIPMENT | 2021-02-03 18:53 | Nível 2 | COS-SMB-330822 |  | CEDOC Closure | NG reported an internal manufacturing problem with the SBR2 hull seal (PELA). | Não |  |  |  |  | Send to level 2. | Change the PELA SBR2 and replace it by the complete PELA of SBR4. NCR send to level 3 in order to inform NG BO about the utilisation of PELA SBR4 for the tracability. | Change the PELA SBR2 and replace it by the complete PELA of SBR3 or SBR4. The PELA SBR2 has to be disassembled to replace the defective GUIDE BEARING (box item 33), with the new one once delivered, and then be mounted on board SBR3 or SBR4. The operations and tests to be carried out are described in document SBR-ETM-000MBM0004-STERNGLAND_B. For disassembly/reassembly operations, please also apply procedure STP-2338_A joined in annex. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 298 Dias | Jean Christophe Laurent | MB |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0333-2021 | 53B | SEATING | 2021-02-04 20:24 | Nível 2 | COS-SMB-319621 |  | CEDOC Closure | P4151674 out of coordinate mounting. During the assembly of the pipes, it was verified that the alignment was getting out. A seating check was made and the seating is 12mm out of coordinate. | Não |  |  |  |  | Remove the seating using annex 1, install again using CTE´s annexed and drawning SBH.2A21.SAD.005074_D. | REWORK Analysis :the seating was installed in wrong position. difference de 6mm Proposition: Correct the position in relation to the design. use the CTE annexed. Due to the small difference of position the new welding will touch the old one. No need to remove the austenitic. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 297 Dias | Hugues Bourget | BQ |  | NO | [5 empty] | 2021-03-25 17:21 | Philippe Falquerho | Philippe Falquerho
NCR-ICN-ESC-12-0331-2021 | 53B | PAINTING | 2021-02-04 19:10 | Nível 2 | COS-SMB-200619, COS-SMB-319300, COS-SMB-319315, COS-SMB-319318, COS-SMB-319304, COS-SMB-319305 |  | CEDOC Closure | According to SMB-002525, in item 6.10, stainless steel and galvanized steel floor plates are not painted. However, in "Appendix 1 - Painting Instructions" to this SMB and in the job orders there was an indication of painting for these regions. | Sim |  |  |  |  | An on-board check must be made on the condition of the paint finish on the floors to be accepted as is or to be replaced. Please TA analyze. | In the SMB-002525 , only the Crude steel floor must be painted. On board the floor of A220 and A230 were painted. Accepted as it is. |  | Bruno Marcel Lima Ferreira Amancio | Bruno Marcel Lima Ferreira Amancio | 297 Dias | Hugues Bourget |  |  | NO |  |  | 2021-02-26 18:47 | Hugues Bourget |  |  |  | Philippe Falquerho
NCR-ICN-ESC-12-0334-2021 | 53B | PIPES | 2021-02-08 17:09 | Nível 2 | COS-SMB-200424 |  | CEDOC Closure | During paint inspection on B110 tank it was identified a non-painted and rusty valve (EJ00211). ICN request authorization to sandblast and paint according to tank schema. | Não |  |  |  |  | ICN request authorization to sandblast and paint according to tank schema. | The steel non return valve, EJ00210 and EJ00211, on suction pipe of tanks EJ01 and EJ03, CMD: 18CR000D00044 / 18CR000C0197 is not intended to be submerged in water tank. These two NRV´s must be replaced as soon as a new CMD will be defined by Naval-Group. Nevertheless, awaiting the delivery of the correct NRV, TA Naval-Group suggest ICN to sandblast and paint the actual wrong NRV´s in order to limit the risk and the pollution of rust inside the tanks B110 and B120. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 293 Dias | Hugues Bourget | EJ |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0335-2021 | 53B | STW | 2021-02-09 13:46 | Nível 2 | COS-SMB-200512, COS-SMB-200259 |  | CEDOC Closure | After energizing the FC02524 panel, there was an internal heating in the FC00524 air conditioning unit and some internal components melted. Attached photos follow | Não | [5 empty] | Dismount FC00524 and put it at the workshop for an expertise. Check the safety thermostat. If too much components are damaged ,take the unit of sbr4. Check in FC02524 that the relay K05 is not by-passed (terminal 2 and 1).BDM-00055058 Update 30/06/2021: Taking into account expertise result, take the unit from SBR4 for remounting on SBR2. To open NCR MAT |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 293 Dias | Gerard Landure | FC |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0336-2021 | 53B | ELETRIC | 2021-02-09 13:47 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | In order to fulfill the requirements for the sea out in SBR1 ICN has to taken some parts of ME converter in SBR 2 as deliberated and described in NCR-ICN-11-1265-2020. But now the ME converter is missing some parts. We need to replace the ones was taken to star the setting to work tests in SBR2. | Não |  |  |  |  | We need to replenish the material removed described in NCR to carry on the tests in SBR2. | To allow starting of STW of ME system on SBR2, please take 2 busbars from SBR4 and install them on SBR2, with help of NVG TA Then, it will necessary to repair the 2 damaged capacity banks on SBR4 by replacing their busbar. Please open a NCR MAT to launch the repair of those parts. Then NVG will order new busbars. Upon delivery in brasil, NVG will organize the repair on SBR4 by Jeumont |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 293 Dias | Etienne Alexandre Sebastien Rene Berot | ME | NCR-ICN-ESC-11-1265-2020 | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0337-2021 | 53B | ACOUSTIC DISCRETION | 2021-02-09 18:50 | Nível 1 | COS-SMB-319724 | CTE00934215 | CEDOC Closure | During A07 inspection on DA00001 pump was checked that the nameplate was missing. Pump traceability could not be performed. See attached photo. | Não |  |  |  |  | Request a new data card and reinstall on the equipment. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Franciellen da Silva Braga | 292 Dias |  | DA |  | NO
NCR-ICN-ESC-12-0338-2021 | 53B | ACOUSTIC DISCRETION | 2021-02-09 18:51 | Nível 1 | COS-SMB-319724 | CTE00785282 | CEDOC Closure | During A06 inspection on DA00001 pump was checked that 1 shock sensor 15G was triggered and 2 tilt sensors were missing. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Franciellen da Silva Braga | 292 Dias |  | DA |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0340-2021 | 53B | ACOUSTIC DISCRETION | 2021-02-10 18:16 | Nível 1 | COS-SMB-200512 | CTE00943863 | CEDOC Closure | During A06 inspection on FC00523 was checked 1 shock sensor 15G and 1 tilt sensor triggered. See attached CTE. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 291 Dias |  | FC |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0341-2021 | 53B | RESISTANT STRUCTURE | 2021-02-11 10:58 | Nível 2 | COS-SMB-319093 |  | CEDOC Closure | During the installation of the pipes in sleeves AC32059, AC32062, AC32063, AC32064 and AC32065, it was detected that the position is not in accordance with the drawing SMB-104509_B. | Não |  |  |  |  | Send to level 2. | For: 1/ AC32060 and AC32061 accept as it is ( symetry of sleeve) 2/ AC32059 an dAC32065: Machine a new sleeves . Machine 2 inside insert pieces weld it to close the wrong sleeves. Drill the DSRV cilinder at the original place, and weld as per original a new manufactured sleeve. 3/ AC 32062 ; AC32063 and AC32064 accept as it is , open a Pipe NCR to adapt the the spool s to the accepted position sleeves. | repair as descibed in attached annex | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 291 Dias | Hugues Bourget |  |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0342-2021 | 53B | PAINTING | 2021-02-12 12:22 | Nível 2 | COS-SMB-201424 |  | CEDOC Closure | After inspection of the B110 tank, areas with mechanical damage were observed (breakage of the film at the ends of the flanges, connections, web junction with shell, among others). Burning points / contamination of the paint film due to hot works carried out internally and externally to the tank. Contamination of the paint film by steel filings, which were not removed after work carried out inside the compartment, in contact with water produces corrosion spots on the paint film (See photos). | Não |  |  |  |  | We suggest repair the tank as follow: 1 - Mapped the bottom, ceiling and connections areas for the repair. 2 - Opening of the anchoring profile with Vacuum Blasting equipment for the Sa 2 ½ standard; 3 - Cleaning and surface preparation inspection Note: Attention to the surface treatment in the transition areas of the old film with the new application. Isolate with tape and break the edges as instructed by the manufacturer. 4 - Stripe Coat in the regions of the welds and sharp edges as shown in the paint scheme; 5 - Application of the E7 scheme; 6 - Final inspection of the tank; | REWORK Rework following the production orientation. |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 290 Dias | Hugues Bourget |  |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0344-2021 | 53B | ELETRIC | 2021-02-12 13:41 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | The drilling related to the equipment (DT04200 / DT04300) for fixing it does not coincide with the holes made in the supports, so it is not possible to perform the complete fixing of the equipment. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Repair Cut the part of seating where the drilling are out of holes equipment, ajust and reweld at a good place. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 290 Dias | Hugues Bourget | DT |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0348-2021 | 53B | INTEGRATION EQUIPMENT | 2021-02-19 12:24 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | CEDOC Closure | During an inspection on board, NG detected a lack of protection and dirt around the main thrust block (see annex). | Não |  |  |  |  | Follow 1.2. | Agree with level 1. Any dust detect inside the thrust block during the buroscopy. Maintain all the holes of the thrust block close and protect the shaft part. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 283 Dias | Jean Christophe Laurent | MB |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0347-2021 | 53B | ACOUSTIC DISCRETION | 2021-02-19 11:39 | Nível 1 | COS-SMB-319737 | CTE00943235 | CEDOC Closure | It is not possible to check the equipment identification plate, because this plate is located behind the seating and it is impossible to view the DA00002 traceability information. | Não |  |  |  |  | Remove and Rework According to the description, the equipment data plate must be fixed in a visible place. | NCR LEVEL 1 |  | Luisa Kubrusly | Rogerio Milani | 283 Dias |  | DA |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0350-2021 | 53B | PIPES | 2021-02-22 17:12 | Nível 2 | COS-SMB-200728 |  | CEDOC Closure | During the presentation phase was identified an impossibility to mount the pipe P4161492 (DV50064Y1) in a single part. So we kindly request authorization to cut and add a new connection point in the area highlighted in the attached file. | Não |  |  |  |  | ICN request authorization to cut and add a new connection point in the area highlighted in the attached file | The configuration on board not allow to mount the pipe P4161492 . AT decision authorizes to cut the pipe P4161492 : - add a conection - realize the associated controls REPAIR Send to level 3 for decision . | It is not up to the designer to modify the design and in particular by particularizing the definition file of a boat, to take into account an assembly anomaly. The Shipyard must correct its error and return to compliance with the definition, as recommended in the designer opinion: - Or by welding on board 2 spools, provided that it is technically possible to weld, to carry out the radio control and other NDT + PEH = 375 bar on board. - Otherwise go back to the configuration (==> dismantling) to allow nominal assembly of the spool. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 279 Dias | Franck Rubis | DV |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0353-2021 | 53B | STW | 2021-02-25 11:58 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | The FC12560T temperature transmitter had a broken cable and stopped working | Não |  |  |  |  | Remover e substituir | CMX:50AM100D00017 Picture attached of damaged wire. Take new one on Sbr4. Open NCR MAT to replenish it. |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 277 Dias | Etienne Alexandre Sebastien Rene Berot | FC |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0354-2021 | 53B | MECHANICAL | 2021-02-26 17:18 | Nível 2 | COS-SMB-331842 |  | CEDOC Closure | On IM AC41018 there is a stud rod in contact with the hull thus not acceptable for the diving and safety demands according to SMB-200960 (p. 12) | Não |  |  |  |  | Remove AC41018, remount according SMB-200960 using new gasket and new tab washers, redo inspection B06 and update B07 Open NCR-REGRESS to invalidate inspections B06 of A41018, B01 and B02 already done of the following pipes and isolating valves: DB50221Y1, DB50231Y1, DB50232Y1, DB50242Y1, DB00121, DB00101, DB00102, DB00122 | In accordance with level 1.2 remove AC41018, remount according SMB-200960 using new gasket and new tab washers, redo inspection B06 and update B07 Open NCR-REGRESS to invalidate inspections B06 of A41018 and to redo pressure test: The link of pipes and mobile part will be verify by a S02_DBZ0001 (DB50221Y1, DB50231Y1, DB50232Y1, DB50242Y1) B05 will be updated | Agree with paragraph 2.2, rework : Disassembly then reassembly of the moving part in accordance with SMB-200960. Change the seal during reassembly. Repeat the traceability and hull integrity inspections then record them in the traceability file. | Renato Trabach da Cunha | Renato Trabach da Cunha | 275 Dias | Patrick Daliguet | AC | Repair Sheet 128 | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0356-2021 | 53B | MECHANICAL | 2021-03-02 17:23 | Nível 2 | COS-SMB-321703 |  | CEDOC Closure | The DA12510N level detector was identified on board with problems. Consult the attached file for problems. | Não |  |  |  |  | The internal part of the equipment must be replaced by another one. Proceed to the decision of the NG specialist. | Use RMS stock NGD:6680930201175 CMX:50DD500D00048 Open NCR MAT to replenish it |  | Rafael Thome da Silva | Rafael Thome da Silva | 271 Dias | Etienne Alexandre Sebastien Rene Berot | DA |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0358-2021 | 53B | STW | 2021-03-03 19:25 | Nível 2 | COS-SMB-200546 |  | CEDOC Closure | GCO would like to ask the installation of the RF00026 - CMD 11CD000D00089 -, initially received for SBR3 (SMB3-COM2A-DB1/02) in SBR2, even though the internal conversor (11CD000D00089_3001) is not working properly since it was used to replace the SBR1 one (as described in NCR-ICN-ESC-11-1407-2021). Besides that, all other RF equipment received in SMB3-COM2A-DB1/02 should be installed in SBR2, since no batch for SBR2 was received by ICN. The equipment in this batch are: 11CD000D00144 (RF00023) 11CD000D00089 (RF00026) 11BJ000D00055 (RF00033) 11TD200D00170 (RF00027) 11CD200D00437 (RF00024) | Não |  |  |  |  | ICN asks to install the SBR3 RF cabinets in SBR2 | The batch pertaining to RF system is arriving in June at Brazil |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 270 Dias | Herve Gerard de Backer | RF |  | NO |  |  | 2021-03-29 19:13 | Frederic Pavic |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0359-2021 | 53B | ELETRIC | 2021-03-04 12:25 | Nível 2 | COS-SMB-200247, COS-SMB-319724 |  | CEDOC Closure | Two junction blocks 1 and 2 (item 90 of BDM-00059883) of DY02511 are damaged. | Não |  |  |  |  | Forward to NG TA | Take 2 new terminal blocks B1and B2 on DY02511 SBR3 Open NCR MAT to replenish them BDM-00059895: Rep 90 NGD:5940144372246 R: BJT23-8 / F: MAFELEC / |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 270 Dias | Etienne Alexandre Sebastien Rene Berot | DY |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0362-2021 | 53B | SEATING | 2021-03-05 11:52 | Nível 2 | COS-SMB-200386, COS-SMB-200385 |  | CEDOC Closure | During dimensional inspection of seatings P4021220, P4021221, P4021225 and P4021321, out-of-tolerance measurements were detected, as annexed. The assembly was carried out following the coordinates of the pipes. | Não |  |  |  |  | For analysis by Naval Group. | Accepted as it is To explain the misalignment, the seatings were positioned in relation to the pipes, the measurements outside tolerances are acceptable because the environment allows it |  | Neimar Mayrink da Silva | Luiz Felipe Silva Moreira | 269 Dias | Hugues Bourget | KT | NCR-ICN-ESC-12-0276-2020 | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0360-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-04 18:19 | Nível 2 | COS-SMB-200221 |  | CEDOC Closure | At the time of the drilling of the upper plate of the bow shutter of the upper TLT number 5 and 6 for the installation of the cylindrical pins diameter 12, we noticed that the hole diameter 12H7 falls into a stiffner of the structure of the bow shutter,and also it crosses the weld (see photos in appendix). ICN requests the expertise of an NG structure specialist to help us find a repair solution. | Não |  |  |  |  | Send to NG structure specialist. | REPAIR Build up the drilling already done using E42 electrodes, grind to have a good profile Carry 100% VT and 100%MT. Carry out a new drilling 10mm aft. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 269 Dias | Hugues Bourget | KT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0363-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-05 12:35 | Nível 2 | COS-SMB-319712 |  | CEDOC Closure | During the mechanical assembly of the hydraulic supply blocks (BQ00017 e BQ00018) of the valves BQ00001, BQ00002, BQ00003, BQ00004, on their respective support of the soft patch, we realized that it would be impossible to dismantle the hydraulic implantation (18RO0230D00125) in the event of a problem without dismantling the blocks on board, because there is an interference between the implantation and the support of the blocks (see on annex). | Não |  |  |  |  | Agree with 1.2. Replace the 18RO230D00135 by 18RO0230D00070. | Agree witl level 1.2. The dismounting of couplings is not possible: interference with support. -Change the CMD:18RO230F00260 (RUCH sqare coupling) and CMD:32FI301D00003 (shim) by 18RO0230D00070 -NCR MAT will be raise to modify the part list |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 269 Dias | Patrick Daliguet | BQ |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0361-2021 | 53B | STW | 2021-03-04 18:54 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | After powering the FC02520 panel, the control card item 59.3 mentioned in sheet 6/9 of the drawing BDM-00053939 has burned and needs to be replaced. | Não |  |  |  |  | Substituir material RMS | Due of the variator message incident "overvoltage bus dc ” It was identifed that the problem is that the thyristor does not close after the capacitors are preloaded Found that the “control board "must be replaced with a new one using RMS stock. NGD:5998145794347 Set the parameter according to SMB-345168 for FC02520. Open NCR MAT to replenish it. |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 269 Dias | Etienne Alexandre Sebastien Rene Berot |  | NCR-ICN-REGRESS-12-0037-2021 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0364-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-05 14:38 | Nível 2 | COS-SMB-330663 |  | CEDOC Closure | The washers received for the EQ00043 equipment do not meet the equipment need (see annex). | Não |  |  |  |  | • The design of the seating does not permit to use Lock Tab washer on the bottom (see details in SBH.2B30.SMD.006130_FL20); • The assembly drawing MAT424-0924 show a different seating profile that permit to install the Lock Tab washer. • Replace the Lock Tab washer by Nord-Lock washer NL10; • Apply torque of 50 Nm (dry condition) for screw M10 class 8.8 according BDM-00033368_A; • Update the hatch drawing and part list. | With the profile of the support it's not possible to bend lock washers: -Replace lock washers (rep:6 of MAT424-1656) by steel Nord-Lock washers. -For the tightening with Nord-Lock washers the document applicable is the SMB-200963 ( in reference to the norme NF E 25-030-1 ). In this case with 8.8 steel it´s better to use grease (Jet Marine) for the mounting: the torque value in accordance with the SMB-200963 for M10 class 8.8 with grease is 37Nm. -A NCR MAT should be raise for the modification of nomenclature | - Acceptance of Nord-Lock washers according to ISSP and designer recommendation. On the other hand, the tightening torque is different from that of NF E 25-030-1 (37Nm): tightening the NL requires a torque increased by 20%, configuration with lubrication, ie 45Nm. - ICN must formalize the situation concerning the mounting for the EQ00043 hatch on SBR1 -> waiting in BO for an NCR LVL3 | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 269 Dias | Patrick Daliguet | EQ |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0368-2021 | 53B | ELETRIC | 2021-03-10 18:12 | Nível 2 | COS-SMB-200569 |  | CEDOC Closure | During the on-board inspection, the damaged DA12515N equipment connector was found. | Não |  |  |  |  | USE THE CONNECTOR PROVIDED FOR THE DA12515N (SBR4) EQUIPMENT. OPEN "NCR-MAT" FOR NEW SUPPLY. | Replace the plug JUPITER (FEDF10MT03-14 E123) by a new one, Codigo: 11CI121D00020, NGD: 5935144069967. Take in stock or canibalize the SBR4 and create a NCR-MAT to refund the stock. | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 263 Dias | Gildas Le Goff | DA |  | NO | NO |  |  |  |  | 2021-08-04 14:36 | Frederic Pavic | Frederic Pavic
NCR-ICN-ESC-12-0372-2021 | 53B | RESISTANT STRUCTURE | 2021-03-12 13:18 | Nível 2 | COS-SMB-200386 |  | CEDOC Closure | During dimensional inspection of seatings P4021217, P4021218, P4021219 and P4021224, out-of-tolerance measurements were detected, as annexed. The assembly was carried out following the coordinates of the pipes. | Não |  |  |  |  | For analysis by Naval Group. | Accepted as it is The seating was installed to be match with the spool, it´s why the coordinates are out of design. Can be accpeted like that no interference in this area. |  | Neimar Mayrink da Silva | Franciellen da Silva Braga | 262 Dias | Hugues Bourget | KT | NCR-ICN-ESC-12-0307-2021 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0377-2021 | 53B | ELETRIC | 2021-03-15 16:12 | Nível 2 | COS-SMB-200763 |  | CEDOC Closure | During the on-board inspection, the damaged EN00013F equipment connector was found. | Não |  |  |  |  | Use the connector provided for EN00010F (SBR4) and open "NCR-MAT" for new supply. | Replace the broken connector (NGD 5935144580825) with a new one. Open a regressed NCR to redo all the associated cable and equipment tests. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 259 Dias | Stéphane Patrick Philippe Rideau | EN |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0390-2021 | 53B | INSULATION | 2021-03-19 13:22 | Nível 2 | COS-SMB-344782 |  | CEDOC Closure | In the B211/B213 compartments of the SBR2, it is necessary to apply MASTIC OTTOSEAL SILICONE WHITE S27-04-C01 01RA400D00001 according to SMB-003084. This material have not in warehouse. ICN requests the replacement of this material by LOCTITE 5970 ALCOXY SILICONE ADHESIVE CARTRIDGE (01RA300D00004). | Não |  |  |  |  | Please TA-NG analyze the possibility of Loctite SI 5970 to be used for this purpose, according to tests carried out on RCQ-UFEM-0242-2021 (attached) in compliance with the requirements of TAF-TA-2017-0790. | REPAIR Use the Loctite 5970 only to stick the GRP floor |  | Annelize Lyra Nobre | Bruno Marcel Lima Ferreira Amancio | 255 Dias | Hugues Bourget |  |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0381-2021 | 53B | HVAC | 2021-03-17 14:36 | Nível 2 | COS-SMB-337192 |  | CEDOC Closure | The joints P0121682 and P0121680 of the ventilation/extraction ducts are torn. It was checked that the joints P0121682 and P0121680 are torn and it will be necessary to change the joints. | Não |  |  |  |  | Get a new joint and create an NCR MAT. | REWORK Change the joint P0121682 and P0121680 with new ones |  | Renato da Silva Goncalves | Sharles Gomes Silveira | 257 Dias | Franck Rubis | FH |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0385-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-18 11:34 | Nível 2 | COS-SMB-319719 |  | CEDOC Closure | According to NCR-ESC-12-0269-2020 the IM AC42069 was in the wrong position, this NCR is to treat the need of remounting the equipment | Não |  |  |  |  | The IM AC42069 is rotated 1 hole from the original position as shown on SBH.2D30.IMZ.006924 (F05) Since is a electric mobile part and here is no problem connecting the electric cable from inside the pressure hull, accept as it is | No cable connection problem Accept as it is |  | Renato Trabach da Cunha | Renato Trabach da Cunha | 256 Dias | Patrick Daliguet | AC | NCR-ESC-12-0269-2020 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0387-2021 | 53B | NON RESISTANT STRUCTURE | 2021-03-18 17:12 | Nível 2 | COS-SMB-200108 |  | CEDOC Closure | During the assembly of the UA06100 and UA06200 sonars, there was an interference in the positioning of the SC4-CV2-NI-TO-T and SC4-CV2-NI-TO-b structure. In annex 1 contains the nominal coordinates of each point Y and Z and the difference at each point Y and Z in relation to the nominal. | Não |  |  |  |  | Follow TA orientation. Make the repair in CV2-EL1003 e CV2-EL1004 according to the project. | repair See the answer about each product |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 255 Dias | Hugues Bourget | UA |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0393-2021 | 53B | STW | 2021-03-22 18:33 | Nível 2 | COS-SMB-200444 |  | CEDOC Closure | o make CMD evolution of the EV13502P low pressure detector official. According to COSRIDA-07844 we had an evolution from CMD 50DD200D00041 to 50DD200D00042. “Need to update the doc SMB-002989 (catalogue of measuring chains EV) by NG BO with the new values: High pressure detector EV13501P to calibrate at 1.7 bar Low pressure detector EV13502P to calibrate at 0.7 bar It’s also necessary to update the doc SMB-000616 to modify the CMX of the sensor EV13502P. The CMX 50DD200D00041 concerns a sensor with a adjusting range from 1 to 10 bars. For the EV13502P, we need to change the CMX. A sensor 50DD200D00042 will be in the good adjusting range (from 0.5 to 10 bars).” | Não |  |  |  |  | Perform the replacement of CMD 50DD200D00041 to 50DD200D00042. | Regarding the COS RIDA-07844, change the CMD of the sensor EV13502P (CMD 50DD200D00041 to CMD 50DD200D00042). Create a NCR regress to manage the inspection and test to redo. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 251 Dias | Gildas Le Goff | EV | NCR-ICN-REGRESS-12-0052-2021 | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0394-2021 | 53B | ELETRIC | 2021-03-23 11:39 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | The LIP screen CC1 froze. | Não |  |  |  |  | We need to change the screen. | Found loose connection (white connector) on pcb. Picture attached in annex. |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 251 Dias | Etienne Alexandre Sebastien Rene Berot | ME |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0402-2021 | 53B | PIPES | 2021-03-24 11:43 | Nível 2 | COS-SMB-206140, COS-SMB-319486 |  | CEDOC Closure | It is not possible to weld P4502664 to P4170154 and respect the assemble rules for EQ50059Y1. See attached picture. | Não |  |  |  |  | Please advise how to proceed. | AT NG not have a solution for this situation, it is impossible to mount the clamp P4502664 Send to the level 3 for decision . | Based on photos, the same problem exists on SBR1: why has ICN not create a NCR to SBR1? The pitch between the other clamps on the line is sufficient, acceptance as is without mounting the clamp P4502664: same for SBR3 and 4 at ICN to update their job order. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 250 Dias | Franck Rubis | EQ |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0403-2021 | 53B | PIPES | 2021-03-24 12:17 | Nível 2 | COS-SMB-206188 |  | CEDOC Closure | The mounting of equipment FQ00804 is completed with the pipe FQ50803A1 connected but there is no B06 inspection done | Não |  |  |  |  | Redo de mounting using new gasket and washers following the procedure on SMB-200960 Open NCR-REGRESS to invalidate inspections B06, B01, B02 and do new inspections | In accordance with level 1.2 Dismount and remount correctly Raise NCR REGRESS to redo inspections and tests | In accordance with level 2.2 proposal. David BERNEDE | Renato Trabach da Cunha | Renato Trabach da Cunha | 250 Dias | Patrick Daliguet | FQ, EQ | NCR-ICN-REGRESS-12-0036-2021 | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0415-2021 | 53B | PIPES | 2021-03-26 17:35 | Nível 2 | COS-SMB-200561, COS-SMB-200470, COS-SMB-200562 |  | CEDOC Closure | During the final mounting of P4172665 with DV00044 and DV20014 it was impossible to achieve the requirements from SBR-030510. To solve we ask a new manufacture according to the mockup manufacture with the old pipe. Attached a picture of the mockup. | Não |  |  |  |  | ICN Propose a new manufacture according to the mockup manufacture with the old pipe. | NG AT authorizes the manufacture of a new pipe with all the necessary controls for the inspection M01. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 247 Dias | Franck Rubis | DV |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0405-2021 | 53B | ELETRIC | 2021-03-24 15:11 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | During inspection on the CC1 and CC2 converters in the SBR-2, the need to change the clamps of all power plates was identified. Because the angle of the chamfer is not the same used so that it does not damage the bus. | Não |  |  |  |  | During inspection on the CC1 and CC2 converters in the SBR-2, the need to change the clamps of all power plates was identified. Because the angle of the chamfer is not the same used so that it does not damage the bus. | In the beginning the 96 "non-conform" clamps were installed on SBR1 only. Due to the NCR-ICN-ESC-11-1248-2020 and NCR-ICN-ESC-11-1402-2021, all the clamps has been replaced by good ones on SBR1. Now, the non-conform clamps are either on SBR2, either on warehouse. For the non-conform clamps which are on SBR2, replaced them by clamps from Power plates in warehouse. Then collect the 96 non-conform clamps and send them to NVG France for modification. Open a NCR-MAT to follow the repair. No regression on SBR2 (Precom Jeumont not started yet) |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 250 Dias | Yann Jaouen | ME |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0406-2021 | 53B | ELETRIC | 2021-03-24 16:23 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | It'is missing the flow controllers in the CC1 (ME-03101) and CC2 (ME 03102) in the SBR-2. Follow the photo in anexx of the equipament that it's missing. | Não |  |  |  |  | It's missing the both flow controller in the CC1 adn CC2 of the SBR-2. | 1) Take 2 flowmeter panels FC01-U1R2C1 from SBR4 and connect them on SBR2, 2) Open NCR-MAT to supply 2 flowmeter panels FC01-U1R2C1 for SBR4, 3) No regression on SBR2 (Jeumont precom still not done). |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 250 Dias | Etienne Alexandre Sebastien Rene Berot | ME |  | NO | [5 empty] | 2021-04-21 13:53 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-ESC-12-0408-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-25 12:40 | Nível 2 | COS-SMB-206090 |  | CEDOC Closure | NCR raised to treat the disassembly for BH00106 to correct oblonged holes on support as attached photos | Não |  |  |  |  | Remove BH00106 to rework the holes on support P4027395, after done, remounte using procedure on SMB-200960 with new gasket and washers NCR-REGRESS will be raised to invalidate B01, B02, F06 and B06 of BH00106 Inspections F06, B01, B02, B06 and B07 must be redone | In accordance with level 1.2 Dismount and remount correctly Raise NCR REGRESS to redo inspections and tests | In accordance with proposal : correction of the seating and remounting following SMB-002930 inspections and SMB-200960 rules. David BERNEDE | Renato Trabach da Cunha | Renato Trabach da Cunha | 249 Dias | Patrick Daliguet | BH | NCR-ICN-REGRESS-12-0038-2021 | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0416-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-29 14:23 | Nível 2 | COS-SMB-206144, COS-SMB-339470 |  | CEDOC Closure | lt was seen during the first vacuum test on SBR2 lots of metallic pollution inside the FQ00803 valve. This pollution was due to the Jack of protection of the hull sleeve AC32050 during the grinding of the DSRV platform (COR-2021-900344). | Não |  |  |  |  | Send to level 2 to analyze. | Following decision of Diving Safety Engineer: The valve has to be dismounted and replaced by a new one. The polluted one has to be sent to the supplier to be reconditioned properly, the ball and pistons are probably damaged because the valve was maneuvered. Ali inspections previously done have to be cancelled and redone (mounting, pressure tests, traceability...). A NCR regress and NCR MAT will be raise. | In accordance with ICN and Level 2.2 proposal. It is necessary to replace the valve by a new one and to send to the supplier the polluted one. David BERNEDE - ISSP | Renato Trabach da Cunha | Ernanes de Souza | 245 Dias | Patrick Daliguet | FQ, AC | NCR-ICN-REGRESS-12-0069-2021 | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0426-2021 | 53B | PIPES | 2021-03-30 14:45 | Nível 2 | COS-SMB-200728 | CTE00787561 | CEDOC Closure | During visual and dimensional inspection of spool P4161492/DV50064Y1 - Part B (according to NCR-ICN-ESC-12-0350-20 21) some defects were found on the spool and after spool sanding it was found that the thickness (6.6 mm) is below the permitted according to STF33-04-30-C001E_G. See SBH.4C20.ISO.01.P4161492_PART B and attached photos. | Não |  |  |  |  | For analysis by Naval Group. | The pipe P4161492 is not acceptable whith a thickness 6.6mm. Use this pipe for template to manufacture a new pipe ,and scrap the old pipe Realise all the test for the M01 of the new pipe. |  | Joanei Vieira de Sa | Sharles Gomes Silveira | 244 Dias | Franck Rubis | DV | NCR-ICN-ESC-12-0350-2021 | NO |  |  | 2021-04-01 17:54 | Franciellen da Silva Braga |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0424-2021 | 53B | ACOUSTIC DISCRETION | 2021-03-30 12:24 | Nível 1 | COS-SMB-319737 | CTE00943136 | CEDOC Closure | According to SMB-322405_D (PHST), there should be two shock sensors (10G and 15G) glued to DA00002. Only one shock sensor was found glued to DA00002. This sensor has been damaged. See attached photo (annex). Acceptance criteria for inspection A06: SMB-204559_C. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 |  | Luisa Kubrusly | Marcos Aurelio Correa Abrantes | 244 Dias |  | DA |  | NO | [7 empty] | Philippe Falquerho
NCR-ICN-ESC-12-0428-2021 | 53B | ELETRIC | 2021-03-31 11:00 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | During the AIS test it was identified that the DM03101 panel (control card) is not working. | Não |  |  |  |  | The plate must be replaced. Submit for NG specialist review. | Replace the Pcb Control board with RMS stock. NGD:5998145794347 |  | Rafael Thome da Silva | Rafael Thome da Silva | 243 Dias | Etienne Alexandre Sebastien Rene Berot | DM |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0435-2021 | 53B | PAINTING | 2021-04-06 20:09 | Nível 2 | COS-SMB-201451 | CTC00710652 | CEDOC Closure | After inspection of the C121 tank, areas with mechanical damage were observed (breakage of the film at the ends of the flanges). Contamination of the paint film due to hot works carried out internally and externally to the tank. Contamination of the paint film by steel filings. (See photos). | Não | 2021-06-02 19:43 |  |  |  | We suggest repair the tank as follow: 1 - Mapped the bottom and bulkheads areas for the repair. 2 - Opening of the anchoring profile with Vacuum Blasting equipment for the Sa 2 ½ standard; 3 - Cleaning and surface preparation inspection Note: Attention to the surface treatment in the transition areas of the old film with the new application. Isolate with tape and break the edges as instructed by the manufacturer. 4 - Stripe Coat in the regions of the welds and sharp edges as shown in the paint scheme; 5 - Application of the E8 scheme; 6 - Final inspection of the tank; | Rework Repair as per desciption of para.1.2 |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 236 Dias | Hugues Bourget | N/A |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0532-2021 | 53B | ACOUSTIC DISCRETION | 2021-06-10 13:06 | Nível 1 | COS-SMB-200716 |  | CEDOC Closure | According to SMR-204507 the minimum distance between seating (upper part) and electric cables has not been reached. The cables are touching the seating (see attached photo). Minimum distance is 18 mm. The correct positioning of the cables is necessary to carry out the A04 inspection. | Não |  |  |  |  | According to the description the cables must be separated to allow inspection A04. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 172 Dias |  | BK |  | NO
NCR-ICN-ESC-12-0440-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-12 19:52 | Nível 2 | COS-SMB-200228 |  | CEDOC Closure | It was not possible to mount the antenna of the RADAR mast, the antenna did not fit into the mounting housing. Checked the internal diameter and the housing is smaller than the antenna axis. RM00003 | Não |  |  |  |  | During the assembly of the RADAR mast (53C-RM00003 - P0118608 – CMx 09EP000D00014 NAVIGATION RADAR MAST ASSEMBLY) on the SBR2 submarine, the mast antenna 53C-RD02504 - P0123648 CMx 62AB000D00049 RADAR ANTENNA MAST RESET DEVICE did not fit, checking the internal measurements it was identified that the internal diameter does not conform to the design drawing. The mast of the SBR4 was requested for possible assembly, before assembly the measurements were checked, then it was identified that the internal diameter is not in accordance with the design drawing. For this situation, it is suggested that the internal diameters are machined on the mast of SBR3 and SBR4. Machining the mast 53C-RM00003 internal diameter 162.00 mm, mounting area RADAR POD antenna. See annex 1. | The two SBR3 and SBR4 radar antenna support mast 09EP000D00015 (RM00813) must be machined to the correct diameter according to the plan in the appendix (DIAMETER 162/0 + 1 and the depth 487/ 0+5). After machining of the machined part, a coat of gray JOTAMASTIQUE primer must be applied, according to reference documents SMB-002345 and SMB-002083. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 230 Dias | Anthony Jean Marie Georges Gel | RM |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0442-2021 | 53B | PIPES | 2021-04-14 15:36 | Nível 2 | COS-SMB-206095 |  | CEDOC Closure | According to COR-2021-901189 (see attached), due to manufacturing problems, the flanges of spools P4167471/P4167473 need to be discarded. | Não |  |  |  |  | Disassemble the spools, remove and discard the wrong flanges, install the new ones and update M01 inspection. Open an NCR MAT. No tests were performed for this line, so there will be no regression. | In accordance with the COR-2021-901189: The flange with NGD 4730145171318 CMD 18RO110D00077 must to be replace with the CMX 18RO110F00411. On the SBR 2 there are 4 flanges identified with the wrong CMD on the system FQ . The pipes concerned are P4167471 and P4167473 ( annex) Make the change of flanges on templating. Realize all the necessary tests for M01 and send the pipe to the galvanization |  | Franciellen da Silva Braga | Franciellen da Silva Braga | 229 Dias | Franck Rubis | FQ |  | NO |  |  | 2021-04-19 16:53 | Franciellen da Silva Braga |  |  |  | Frederic Pavic
NCR-ICN-ESC-12-0443-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-14 18:30 | Nível 2 | COS-SMB-200512 |  | CEDOC Closure | Equipment without indicator seal rubbers level. The final assembly of the equipment is not possible. | Não |  |  |  |  | It is necessary to install a new level indicator sealing rubber EW10002N - 53B-P0126460 - 50MD500D00015 LEVEL INDICATOR FITTING ED 15MM. | The inferior neoprene gasket of the level indicator EW10002N is missing. Take a new-one in the stock (NGD: 5330143029900) to remount onboard. If no stock canibalize SBR3 or SBR4 and create a NCR-MAT to refund the stock. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 228 Dias | Gildas Le Goff | EW |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0447-2021 | 53B | ELETRIC | 2021-04-20 14:06 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure | Based on the information given in the N2 of the NCR-1573 of the SBR-1, we performed some tests in the SBR-2 and it was found that the Z1 filter in CC2 has an insulation resistance above 250M ohms. | Não |  |  |  |  | Based on the answer given in NCR-1573, we would need to replace the Z1 source. | Replace Z1 component by a new one. Take it on SBR4. Please open NCR-MAT to reorder this part: EMC 3 phase filter SCHAFFNER FN 3258 H-16-44 BDM-00085914 |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 223 Dias | Etienne Alexandre Sebastien Rene Berot | ME |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0463-2021 | 53B | PRESERVATION | 2021-05-03 19:07 | Nível 2 | COS-SMB-330822 |  | CEDOC Closure | "The Preservation team, in agreement with the Quality team, opted to open this NCR (processed by the NCR-CQ system) to replace the NCR-ICN-Preserv-034 (which was being processed physically). Please see the original NCR attached." On March 28, 2019, TAF-TA-2019-0974 was issued requiring a change in the EPMs Preservation routine. Through this document, the Preservation team was instructed to perform the borescope inspection task on EPM bearings in the MT2 phase (equipment installed on board), thus replacing the previously defined shaft rotation activities. This change was consolidated in a new version of PHST (SMB-32221-G), which defines a periodicity of 3 months. Facts occurred in EPM - 02: •On April 9, 2019, after inspection by manufacturer Jeumont in the “Main Hall”, the EPM was filled with lubricating oil and the rotations were performed according to PHST. •On July 11, 2019, a borescope inspection was performed and no sign of oxidation was presented. •On October 4, 2019, a new inspection was carried out according to the periodicity of 3 months and small signs of superficial oxidation were verified, according to report RAP-ME-2019/007. | Não |  |  |  |  | Our suggestion, is to create a flushing system outside of the motors according to the reference document DCNS - BRESIL - NSY - DNA - 8460 Revision-A, putting the lubrication oil on constant movement, thus keeping the engine always lubricated. | Refer to proposed solution by expert Level 1. To be forwarded to level 3 for analysis. (Yann Jaouen) | -Schedule a Jeumont intervention - under the warranty - to bring MEP 2-3-4 back into compliance. Need FO support to prepare the intervention procedure on board MEP 2 (Dismantling of lhe environment for accessibility to the landing on the NDE side); - Update documentary 6EM21228: The documentation must indicate to add preservation grease during reassembly, to give details on the rinsing of the casings and to integrate the descriptive sheet of preservation grease "Shell Ensis engine 30" (End Sept 2020); - ICN need to propose an adequate solution for storage of MEP under optimized conditions (Oct 2020); - A awareness of ICN according to the update of documentation will be done (Dec 2020). (Lepesant M.) | Rafael Tavares do Rego Macedo | Rafael Tavares do Rego Macedo | 209 Dias | Yann Jaouen | ME |  | NO | NO | [6 empty] | Christophe Marret
NCR-ICN-ESC-12-0468-2021 | 53B | PIPES | 2021-05-04 17:35 | Nível 2 | COS-SMB-200426 |  | CEDOC Closure | During a board inspection was identified that the spool DN50242Y1-P4140406, linked to NRV DN00241 (AC33003), was damaged jeopardizing the hull integrity. | Não |  |  |  |  | Raise a new DN50242Y1-P4140406 spool manufacturing. Open NCR-REGRESS to tests already carried out. | -Manufacture a new pipe -Scrap the damaged pipe -Realize the new M01 -Mount the pipe on board -Put a protection to avoid damaging the new pipe on board | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 208 Dias | Franck Rubis | DN | NCR-ICN-REGRESS-12-0055-2021 | NO | NO |  | 2021-05-06 11:31 | Franciellen da Silva Braga |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0477-2021 | 53B | STW | 2021-05-10 13:53 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure | The temperature transmitters DT14141T and DT14142T were not sending 4-20mA to the PLC ACAUX3. | Não |  |  |  |  | Forward to Naval Group. | Modification accepted as it is. Redo calibration at metrology workshop following SMB-002984 and put certificate inside NCR |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 203 Dias | Etienne Alexandre Sebastien Rene Berot | DT |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0492-2021 | 53B | ELETRIC | 2021-05-14 12:44 | Nível 2 | COS-SMB-330822 |  | CEDOC Closure | We need a resolution for another encoder 2 in SBR-2, considering that it was removed to be used in SBR-1 through NCR-ICN-ESC-11-1273-2020. | Não |  |  |  |  | We suggest removing the encoder 2 from the SBR-4 to be used in the SBR-2. | According to NCR-ICN-ESC-11-1165-2020, the encoders were taken from sbr2. Take the 2 encoders of SBR4 and remount them on SBR2. NCR-MAT-001397-2021 had been opened to refund the encoder damaged (encoder 2 of SBR1). No need new NCR MAT (encoder 1 of sbr1 + new encoder will be remounted together on SBR4). |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 199 Dias | Etienne Alexandre Sebastien Rene Berot | ME |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0502-2021 | 53B | SEATING | 2021-05-20 12:20 | Nível 2 | COS-SMB-319592 |  | CEDOC Closure | It’s not possible to pass the seating P4095984 to the final position, due to interference with the equipment DP00282. To put the seating in final position, it’s necessary to cut the seating in two parts. | Não |  |  |  |  | Agree with 1.2. Weld using C27 inspection. | Create a new joint to have a good access. after adjustment weld the butt joint , carry out the inspections 100% VT and 100%MT if it 's correct can continue the fillet welding |  | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 193 Dias | Hugues Bourget | DP |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0511-2021 | 53B | PIPES | 2021-05-26 12:25 | Nível 2 | COS-SMB-319760 |  | CEDOC Closure | During the preparation for test F03_DUZ0001 it was identified an interference between the DU20076 and DU00003 block as presented in attached picture. The position do not allow to connect the filling device for bottle DU00001. | Não |  |  |  |  | ICN waits NVG orientation. | P0125512 > Repair | Considering the situation on board, the mounting has to be let as it is (David Bernede) | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 187 Dias | Gildas Le Goff | DU |  | NO | NO |  | 2021-05-31 12:27 | Felipe Gonçalves Sequeira |  |  |  | Christophe Marret
NCR-ICN-ESC-12-0509-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-25 16:29 | Nível 2 | COS-SMB-319721 |  | CEDOC Closure | The DA00072 tank level indication sensor is damaged, see the attached photo. | Não |  |  |  |  | The sensor must be replaced with a new one. Codigo - 50MD500D00037- INDICADOR DE NIVEL (LIQUIDOMETRO) DE TANQUES 219 MM | make a standard exchange of the DA10002N make ncr mat |  | Rafael Thome da Silva | Rafael Thome da Silva | 188 Dias | Frederic Guevel | DA |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-ESC-12-0517-2021 | 53B | PIPES | 2021-05-28 11:04 | Nível 2 | COS-SMB-200452 |  | CEDOC Closure | The P0122998 piping is assembled according to revision SBH.3B10.TUY.003757_K (EXPEDED). Thus, it is not possible to remove / assemble the EV13500T sensor. (see attached) | Não |  |  |  |  | Assemble piping according to the latest revision. | Agree with the ICN decision. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 185 Dias | Franck Rubis |  | NCR-ICN-REGRESS-12-0061-2021 | NO | [7 empty] | Christophe Marret
NCR-ICN-UFEM-12-0549-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-31 12:41 | Nível 1 | COS-SMB-330725 |  | CEDOC Closure | 1) On the panel (NGD REP0000005310 - MAT424-1054_Ref. 2), a machining was missing on boss of maneuver shaft. See detail in Annex 1 and MAT424-0703 (section A-A); 2) The Recess for Lock of Threaded Ring (NGD REP0000005309 - MAT424-1054_Ref. 1) was not completely machined in the manufacturing phase. See pictures in Annex 2 and MAT424-0704 (section C-C); 3) The Gasket (MAT424-0813_Ref. 6) was delivered mounted in the Vent Valve (CMD 18PA000D00038 - MAT424-1054_Ref. 14) without packaging and traceability. See Annex 3. 4) The Hatch Cover (MAT424-1054_Ref. 2) doesn’t have traceability, not visible on the hatch and nothing on the label delivered. IM: AG00013 MAT: NCR-MAT-001065-2020 and NCR-MAT-001031-2020 | Não | 2021-10-01 18:54 |  |  |  | Rework. 1) The machining missing on boss of maneuver shaft must be machined following MAT424-0703 (section A-A); 2) The recess for lock of Threaded Ring must be redone to achieve the final measurements according MAT424-0704 (section C-C); 3) Replace the gasket by NGD 5330145107997 FLAT GASKET 60 X 79 X 3 FIBER / NBR from batch SMB-RMS-CUR-DB19. NCR-MAT-001065-2020 was opened to supply new gasket; 4) Mark the serial number on cover label according NCR-MAT-001065-2020 answer: SN: AP427130. | NCR LEVEL 1 |  | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 182 Dias |  | AG | NCR-MAT-001065-2020 and NCR-MAT-001031-2020 | NO
NCR-ICN-ESC-12-0531-2021 | 53B | ACOUSTIC DISCRETION | 2021-06-10 12:51 | Nível 1 | COS-SMB-319731 | CTE00946804 | CEDOC Closure | During A06 inspection on FR00001 the lack of one tilt sensor was checked. | Não |  |  |  |  | The equipment has a good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 172 Dias |  | FR |  | NO | [7 empty] | Christophe Marret
NCR-ICN-ESC-12-0539-2021 | 53B | PIPES | 2021-06-15 13:46 | Nível 2 | COS-SMB-206140 |  | CEDOC Closure | After adjust on board on P4168613 it was identified a non-conformity according to weld distance specified by IT33-04-13E_H. We couldn’t find another adjust solution to avoid this scenario. | Não |  |  |  |  | NG, please review the problem found on board. | The distance between welds is not respected (20mm+2 thickness) I request an analysis for decision in level 3. | This case has to be considered as an exception, not as a rule (David Bernerde). | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 167 Dias | Franck Rubis | EQ |  | NO | NO | [6 empty] | Frederic Pavic
NCR-ICN-ESC-12-0545-2021 | 53B | STW | 2021-06-18 17:46 | Nível 2 | COS-SMB-200247 |  | CEDOC Closure | The box of components designed to perform the startup of the high pressure compressors on S-BR 02 cannot be found in ICN. Related product: DY00001 - SET OF TWO HP AIR ELECTRIC COMPRESSOR (SET OF MATERIALS). | Não |  |  |  |  | ICN suggests to use the materials delivered for the HP Electric Compressors from S-BR 04, in order to allow performing the STW of DY subsystem on S-BR 02. The reposition of the material for S-BR 04 should be requested to the supplier (Girodin-Sauer). | Agreed to use the materials delivered for the HP Electric Compressors from S-BR 04, in order to allow performing the STW of DY subsystem on S-BR 02. To create NCR MAT for repositioning of the material for S-BR 04. |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 163 Dias | Gerard Landure | DY |  | NO | [5 empty] | 2021-08-14 17:11 | Franciellen da Silva Braga | Frederic Pavic
NCR-ICN-ESC-12-0550-2021 | 53B | ELETRIC | 2021-06-24 19:29 | Nível 2 | COS-SMB-200501, COS-SMB-CAB-FC-GV |  | CEDOC Closure | The fitted cable GF22504R has a real length of approximately 16m, according to SMB-323607, it has a design length, "L1 min: 24m and L1 max: 25m", so this in actual length does not meet routing. Indicated in the project. | Não |  |  |  |  | PROVIDE A NEW CABLE WITH THE LENGTH ACCORDING TO THE DESIGN. | Use the 25 meter cable stocked at the ESC store under the ESC / E.02.05.D location or the one from the UFEM store under the 18C / H.05.26.A location |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 157 Dias | Stéphane Patrick Philippe Rideau | GF |  | NO | [7 empty] | Frederic Pavic
NCR-ICN-UFEM-12-0525-2019 | 53B | TRACEABILITY | 2019-07-31 17:03 | Nível 2 | COS-SMB-345809 |  | CEDOC Closure/Unfounded | During the inspection it was detected that the traceability (Serial Number) does not correspond to SBR2. | Não |  |  |  |  | Accept as it is. The traceability of the set was delivered mixed (see the report in Annex 02 and documents associated). The Stock and Yoke were received on the mechanical workshop together on the same box from warehouse and the pair was used correctly. Comments: • ICN did not mix the parts in workshop. • All boxes were opened on warehouse and the traceability marked on pieces match with the certificates. | Not accept as it is, the hole stock and yoke are paired on only one submarine. They cannot be mixed. make a traceability report to verify that the part of the steering system belong to the same submarine. When is done, send the NCR in L3 C BOUCHER |  | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 851 Dias | Charles Boucher |  |  | NO |  |  | 2020-04-07 14:34 | Frederic Pavic
NCR-ICN-ESC-12-0058-2020 | 53B | ELETRIC | 2020-05-12 10:26 | Nível 2 | COS-SMB-200501, COS-SMB-CAB-FC-GV |  | CEDOC Closure/Unfounded | “GV22501D, GV22502D and GV22503D” cables (cable fitted) have a length shorter than the length required to service the installation. | Não |  |  |  |  | Supplier delivery | See NCR-ICN-ESC-11-0705-2019 |  | Jair de Barros Sena de Araujo | Claudio Marcelo Guedes da Silva | 566 Dias | Stéphane Patrick Philippe Rideau | GV |  | NO
NCR-ICN-ESC-12-0025-2019 | 53B | PIPES | 2019-11-19 13:22 | Nível 2 | COS-SMB-200430 |  | CEDOC Closure/Unfounded | As discussed with NG GIR, the screws of the clamp (P4168094) did not have 2 threads. | Não |  |  |  |  | the screw should be replaced with one larger than two threads. | follow the decision 2.1 replaced with one longger than two threads. |  | Vladimir Gianotti Lopes | Paulo Jose Lopes Almeida | 741 Dias | Franck Rubis | EW |  | NO |  |  | 2019-11-22 18:49 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0033-2019 | 53B | INTEGRATION EQUIPMENT | 2019-12-10 13:47 | Nível 2 | COS-SMB-200716, COS-SMB-200712, COS-SMB-200569 |  | CEDOC Closure/Unfounded | System HG's HG02511 and HG02512 sockets located in SBR1 compartment C-200 are with positions exchanged respectively with HG02521 and HG02510 sockets on the models, as shown in the annex. In this way, operators of the HG circuit torpedo firing network are in positions exchanged with operators of the internal service network which makes it difficult to drive the SBR. | Não |  |  |  |  | Please change the project for all SBR. Naval Group please check it. |  |  | Glauco Calhau Chicarino | Ana Paula Bernardes de Araujo | 720 Dias | Paul Fosse | HG |  |  |  |  | 2019-12-10 14:48 | Sergio André Telles Soares
NCR-ICN-ESC-12-0040-2020 | 53B | TRACEABILITY | 2020-02-04 12:16 | Nível 2 | COS-SMB-206076 |  | CEDOC Closure/Unfounded | After realization the B07 traceability inspection (CMD-44BO110D00027 - Deck plug over diesel oil general manifold) it was verified that the traceability reference is not unique. The document analysis was realized with the documents received by the Naval Group and the information found in the certificate relates the three equipment that were received by the ICN with the same serial number applied to all. The reference was applied in a SBR1 equipment . ICN requests unique serial numbers for the other two equipment. | Não |  |  |  |  | Wait for NG orientation | Following MAT167-0132, this blind flange is subjected to the traceability procedure. NVG have to supply a unique traceability. | The traceability asked in the document MAT 167-0132 EXP B is not a unique traceability but by lot/batch. It is thus normal and corresponding to have the same traceability number by reception. Naval Group will not give other number of traceability | Emanuela Lucia Justino dos Santos | Sergio André Telles Soares | 664 Dias | Patrick Daliguet | EG |  | NO | NO
NCR-ICN-ESC-12-0051-2020 | 53B | ELETRIC | 2020-04-07 13:16 | Nível 2 | COS-SMB-319323, COS-SMB-200512, COS-SMB-200526, COS-SMB-200551, COS-SMB-319712 |  | CEDOC Closure/Unfounded | An internal inversion was identified in the connections of the transformers of the bigram BE, the internal identifications are exchanged (H1-H2 / X1-X2). For the correct transformation ratio of the transformers, it will be necessary to change the identifications and connections of the interconnection cables of the primary and secondary of the transformer. This change is similar to the changes handled in NCR-ICN-ESC-11-0555-2019 regarding the BT bigram. | Não |  |  |  |  | Send to Naval Group. | Rework according to NCR-ICN-ESC-11-0555-2019. Send in L3 for taking into account this problem for SBR 3 and 4, idnetification must be changed between primary and secondary of the transformer |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 601 Dias | Stéphane Patrick Philippe Rideau | BE |  | NO
NCR-ICN-ESC-12-0057-2020 | 53B | PIPES | 2020-05-11 14:57 | Nível 2 | COS-SMB-206090, COS-SMB-200551 |  | CEDOC Closure/Unfounded | According to TDP-IS files we have an incoherence of connections between the flowmeter BB00040 and the flexible hoses BB21031, BB21032 and BB21033. According to BDM-00075696 the flow meter has a M45x1,5 interface and in the other site all the flexible hoses use a conical thread 24º RBS. | Não |  |  |  |  | ICN suggest to machine a single piece female M45x1,5 and male OD25 RBS 24 from a CuAl Hexagonal bar. | No connection problems found after inspecting the material. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 567 Dias | Franck Rubis | BB |  | NO |  |  | 2020-05-19 13:38 | Frederic Pavic
NCR-ICN-ESC-12-0064-2020 | 53B | STW | 2020-05-20 17:16 | Nível 2 | COS-SMB-319331 |  | CEDOC Closure/Unfounded | According to drawing SMB-000781_M the bottles EF00001, EF00002, EF000017 and EF00018 should have their discharge valve with connection for 2 outlets for piping, as delivered to the SBR1, but all bottles of the SBR2, SBR3 and SBR4 were delivered with the discharge valves with only 1 pipe connection. Attached are photos of the SBR1 valves and the SBR2 / 3/4 valves. | Não | [7 empty] | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 557 Dias | Alain Lamy | [5 empty] | 2020-06-24 16:31 | Frederic Pavic
NCR-ICN-ESC-12-0065-2020 | 53B | STW | 2020-05-21 17:13 | Nível 2 | COS-SMB-200257 |  | CEDOC Closure/Unfounded | The DS2 "Power supply defect" lamp on the EQ03100 panel is burnt out and must be replaced. | Não | [5 empty] | Supply and replace a new lamp |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 556 Dias | Stéphane Patrick Philippe Rideau | EQ |  | NO
NCR-ICN-UFEM-12-0538-2020 | 53B | NON RESISTANT STRUCTURE | 2020-06-24 16:36 | Nível 2 | COS-SMB-345282 | CTE00917217, CTE00917216 | CEDOC Closure/Unfounded | During the dimensional inspection D95-32 (Check the condition and flatness of the attack periscope first stage sun gear) and D95-33 (Check the verticality and centering of the axis with respect to the attack periscope coaming) the following problems were detected: 1) The surface is not flat. (See CTE00917216 and Annex 01) 2) The face plane of the EL340 is not level. (See CTE00917216 and Annex 01) 3) The coaming bottom (EL340 of the tank) is decentralized in relation to the coaming top (AC30060). (See CTE00917217 and Annex 01) | Não |  |  |  |  | Remove the element CI16-EL514 element (with the CI16-EL340-PLATE, CI16-ELAF31028 and CI16-ELAF31019 elements) and remanufacture a new one, respecting the distance rules between welds (50 mm). VT: 100%, RT or UT: 100% and MT or PT 100% (See aneex NCR-ICN-UFEM-12-0538-2020.pdf) |  |  | Silvio Fonseca de Paiva | Rodrigo Altomare de Carvalho | 523 Dias
NCR-ICN-ESC-12-0211-2020 | 53B | ELETRIC | 2020-10-16 14:04 | Nível 2 | COS-SMB-319724 | CTE00934282 | CEDOC Closure/Unfounded | Broken on / off button, as shown in the attached photo. | Não |  |  |  |  | Equipment EM02501 - Change the button |  |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 409 Dias | Etienne Alexandre Sebastien Rene Berot | EM
NCR-ICN-UFEM-12-0540-2020 | 53B | PIPES | 2020-08-05 18:44 | Nível 2 | COS-SMB-200444 |  | CEDOC Closure/Unfounded | The tube P4124839 was manufactured on 02/07/2020 and because of the conformation it will not be possible to install the tube, since the cradle shipped on board section 3 and to several interfaces that cannot be disassembled. | Não |  |  |  |  | disconnect everything and add connections for the junction. Necessary connections. 18RO230D00566 18RO230D00577 44JO312D00002 18RO230D00587 |  |  | Paulo Jose Lopes Almeida | Paulo Jose Lopes Almeida | 480 Dias
NCR-ICN-ESC-12-0159-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-10 16:07 | Nível 2 | COS-SMB-200542 |  | CEDOC Closure/Unfounded | The materials DA01011 has been lost on board. | Não |  |  |  |  | Dismounting the equipment DA01011 from SBR 3 and assembly in SBR 2. Raise a NCR-MAT for SBR 3. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 445 Dias | Frederic Guevel | DA
NCR-ICN-ESC-12-0178-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-24 17:19 | Nível 2 | COS-SMB-319737 |  | CEDOC Closure/Unfounded | The CTE’s: CTE01038535-1, CTE01038536-1 and CTE01038537-1 were not used, as the related equipment already assembled and tested at the shop, according to SMB-360963. | Não |  |  |  |  | The equipments were tested during manufacturing phase. See SMB-360963. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 430 Dias | Patrick Daliguet | FP
NCR-ICN-ESC-12-0217-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-20 14:39 | Nível 2 | COS-SMB-321710 |  | CEDOC Closure/Unfounded | The mounting kit for the AC43064 in the construction process was lost. | Não |  |  |  |  | Send to level 2. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 405 Dias | Patrick Daliguet | AC
NCR-ICN-ESC-12-0229-2020 | 53B | ELETRIC | 2020-10-23 16:46 |  | COS-SMB-200240, COS-SMB-319731, COS-SMB-200160 |  | CEDOC Closure/Unfounded | During the sea trial the converter BF02501 (CMX 11CS400D00016) presented the fault Vdc minimun and stopped to work during the battery charger by Diesel Generator. Beside this both converter (BF02501 and BF02502 CMD 11CS400D00016) show the information "not ready" even when they are working. | Não | [7 empty] | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 402 Dias |  | BF
NCR-ICN-ESC-12-0242-2020 | 53B | PIPES | 2020-10-30 11:15 | Nível 2 | COS-SMB-206065 |  | CEDOC Closure/Unfounded | It was identified what seemed to be a damage in pipe P4116956. Attached you can see the ultra sound thickness test. | Não |  |  |  |  | NG, please analyze the problem encountered on board. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 395 Dias | Franck Rubis | DW |  |  |  |  | 2020-10-30 12:49 | Sergio André Telles Soares
NCR-ICN-ESC-12-0255-2020 | 53B | MECHANICAL | 2020-11-06 14:11 | Nível 2 | COS-SMB-200581, COS-SMB-321709 | CTE01035075 | CEDOC Closure/Unfounded | During the inspection B06_01‐INSP MEASUREMENT “PRESSURE HULL BOLTING MATERIAL"(CTE01035075) of mobile part AC44031, was detected that the criterion "length of stud rods L=116mm" isn't in compliance. Was used the screw M18 X 126 mm. See CTE attached. | Não |  |  |  |  | The 116 mm stud is not appropriate for installing the AC44031, it is necessary to change to 126 mm to be accepted with at least two threads. It is necessary to change the CTE01035075 and DEI-200581-80500-12-001. |  |  | Joanei Vieira de Sa | Franciellen da Silva Braga | 388 Dias | Patrick Daliguet | AC
NCR-ICN-ESC-12-0266-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-12 19:32 | Nível 2 | COS-SMB-200581, COS-SMB-321709, COS-SMB-321710, COS-SMB-319718, COS-SMB-319719, COS-SMB-319149, COS-SMB-200167 |  | CEDOC Closure/Unfounded | For the AFT and FWD Capstan (EX00002 and EX00001), a new lock washer was asked by the NG, an outcome of NCR-ICN-ESC-0212-2020. But the new lock washer was not conform either. A new drawing was sent as annex, but due the lack of time to do redo the work before ceremony and as the watertighness test were already performed and approved, ICN asks to apply the change only after ceremony. | Não |  |  |  |  | Accept as it is for ceremony. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 381 Dias | Patrick Daliguet | EX, AC | NCR-ICN-ESC-12-0212/2020
NCR-ICN-ESC-12-0273-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-13 15:50 | Nível 2 | COS-SMB-319705, COS-SMB-330822, COS-SMB-330822 |  | CEDOC Closure/Unfounded | Due the short time, ICN request accept the NCR’s below as it is for ceremony. • NCR-ICN-ESC-12-0175-2020; • NCR-ICN-ESC-12-0188-2020; • NCR-ICN-ESC-12-0206-2020; • NCR-ICN-ESC-12-0208-2020; • NCR-ICN-ESC-12-0215-2020; • NCR-ICN-ESC-12-0281-2020. | Não |  |  |  |  | Send to level 2. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 381 Dias | Charles Boucher | MB |  |  |  |  | 2020-11-18 18:53 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0279-2020 | 53B | ELETRIC | 2020-11-18 18:22 | Nível 2 | COS-SMB-200444, COS-SMB-206044, COS-SMB-206081, COS-SMB-206085, COS-SMB-206098, COS-SMB-206100, COS-SMB-337143 |  | CEDOC Closure/Unfounded | To make the connection of the valves we need the cable gland whose description is: CABLE GLAND ISO 20 POLYAMIDE IP66, according to the reference document BDM-00076571 the same and supplied with the valve, however, it is not being supplied. | Não |  |  |  |  | The specific document is "BDM-00078234". |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 375 Dias | Stéphane Patrick Philippe Rideau | DJ, DM, EG, EW |  |  |  |  | 2020-12-08 14:42 | Frederic Pavic
NCR-ICN-ESC-12-0305-2021 | 53B | ELETRIC | 2021-01-06 15:02 |  | COS-SMB-319712, COS-SMB-200549, COS-SMB-200145, COS-SMB-200154, COS-SMB-200159, COS-SMB-200160, COS-SMB-200216, COS-SMB-200217, COS-SMB-200434, COS-SMB-200512, COS-SMB-200516, COS-SMB-200526, COS-SMB-200529, COS-SMB-200535, COS-SMB-200538, COS-SMB-200542, COS-SMB-200544, COS-SMB-200546, COS-SMB-200551, COS-SMB-200554, COS-SMB-200563, COS-SMB-200565, COS-SMB-200566, COS-SMB-200569, COS-SMB-200572, COS-SMB-200710, COS-SMB-200712, COS-SMB-200716, COS-SMB-200718, COS-SMB-200730, COS-SMB-200731, COS-SMB-200760, COS-SMB-200762, COS-SMB-200763, COS-SMB-206044, COS-SMB-206070, COS-SMB-206090, COS-SMB-206113, COS-SMB-206140, COS-SMB-206160, COS-SMB-206183, COS-SMB-319693, COS-SMB-319698, COS-SMB-319700, COS-SMB-319717, COS-SMB-319720, COS-SMB-319721, COS-SMB-319725, COS-SMB-319726, COS-SMB-319728, COS-SMB-319730, COS-SMB-319731, COS-SMB-319737, COS-SMB-319738, COS-SMB-319739, COS-SMB-319749, COS-SMB-319750, COS-SMB-319753, COS-SMB-319755, COS-SMB-319757, COS-SMB-319758, COS-SMB-319759, COS-SMB-319760, COS-SMB-319763, COS-SMB-319766, COS-SMB-321696, COS-SMB-321703, COS-SMB-321704, COS-SMB-327470, COS-SMB-327471, COS-SMB-327472, COS-SMB-330663, COS-SMB-331623, COS-SMB-331624, COS-SMB-337143, COS-SMB-338802, COS-SMB-319702, COS-SMB-206071, COS-SMB-206114, COS-SMB-206184, COS-SMB-330822 |  | CEDOC Closure/Unfounded | For the equipment described in annex 1, we found on board the lack of a functional identification plate and (or) voltage and electrical risk label. | Não | [7 empty] | Geraldo Alves Simoes Filho | Franciellen da Silva Braga | 327 Dias |  | EG, HG, KT, GS, HL, UA, RM, FC, OO, DA, EJ, UW, BB, BE, EQ, GN, GV, HE, HJ, HP, HQ, KL, KO, RE, RH, UE, UN, UP, BH, EF, ER, EV, HK, RF, RA, DP, GF, RC, KD, RD, KE, FR, DS, DB, FH, KX, DV, DM, EN, EM, DY, UL, BM, BQ, ES, EL, BC, BF, ME, BS, FP, FQ, FG, FV
NCR-ICN-ESC-12-0297-2020 | 53B | STW | 2020-12-10 11:54 | Nível 2 | COS-SMB-319348 |  | CEDOC Closure/Unfounded | Malfunction of the ES02517 instrument reported in the last sea test | Não |  |  |  |  | Perform a new calibration of the ES02517 instrument |  |  | Sergio Kenji Inoue | Sergio Kenji Inoue | 354 Dias |  | ES | NA
NCR-ICN-ESC-12-0298-2020 | 53B | STW | 2020-12-14 14:48 |  | COS-SMB-200229 |  | CEDOC Closure/Unfounded | Sometimes during automatic lowering, the optronic mast stops before reaching lowered position (right after changing to slow speed). Even after changing to manual mode, it is impossible to lower unless hoisting slightly and then lowering with some speed. It seems that there is too much friction on the lower end, there is an audible metalic noise on the end of lowering. | Não | [7 empty] | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 350 Dias |  | RM
NCR-ICN-ESC-12-0325-2021 | 53B | PIPES | 2021-01-26 12:05 | Nível 2 | COS-SMB-200434 |  | CEDOC Closure/Unfounded | VERIFIED LEAKAGE IN VALVE BODY BODY | Não |  |  |  |  | REPLACE O-RING |  |  | Sergio Kenji Inoue | Sergio Kenji Inoue | 307 Dias | Gildas Le Goff | DY | NA
NCR-ICN-ESC-12-0371-2021 | 53B | GENERAL | 2021-03-12 13:17 | Nível 2 | COS-SMB-319348 |  | CEDOC Closure/Unfounded | RECEIVED AT BATCH 38 (12/18/2020) DOCUMENT SMB-005539 (ASSEMBLY AND INSPECTION SPECIFICATION FOR ES SUBSYSTEM) WITH THE ADDITION OF INSPECTION F07_ESZ0002 (CHECK OF EQUIPMENT ES02100 PRESENCE. DUE TO THE CURRENT COMMISSIONING STAGE OF THE SBR-01, WE REQUEST APPROVAL TO ADD THE REFERRED INSPECTION ONLY TO THE SBR-02/03/04 | Não |  |  |  |  | RECEIVED AT BATCH 38 (12/18/2020) DOCUMENT SMB-005539 (ASSEMBLY AND INSPECTION SPECIFICATION FOR ES SUBSYSTEM) WITH THE ADDITION OF INSPECTION F07_ESZ0002 (CHECK OF EQUIPMENT ES02100 PRESENCE. DUE TO THE CURRENT COMMISSIONING STAGE OF THE SBR-01, WE REQUEST APPROVAL TO ADD THE REFERRED INSPECTION ONLY TO THE SBR-02/03/04 |  |  | Sergio Kenji Inoue | Sergio Kenji Inoue | 262 Dias | Gildas Le Goff | ES | NA |  |  |  | 2021-04-07 18:44 | Gildas Le Goff
NCR-ICN-ESC-12-0376-2021 | 53B | ELETRIC | 2021-03-15 15:11 | Nível 2 | COS-SMB-200569 |  | CEDOC Closure/Unfounded | Due to the incident that occurred with the SBR1 (flooding of the hold in the C200 compartment), it is necessary to replace the following equipment: - DA02604 - DA00004 ELECTRIC PUMP LOCAL CONTROL PANEL - 11CD000D00078 - P0103335 | Não |  |  |  |  | Remove and replace with a new one. |  |  | Rafael Thome da Silva | Rafael Thome da Silva | 259 Dias |  | DA
NCR-ICN-ESC-12-0378-2021 | 53B | STW | 2021-03-15 18:33 | Nível 2 | COS-SMB-200712, COS-SMB-200716 |  | CEDOC Closure/Unfounded | During a routine maneuver to carry out equipment maintenance, Submarino Riachuelo, moored at the Construction Shipyard in Itaguaí, acquired forward hull inclination, causing sea water to be loaded into the hold of the bow compartment. After inspection of the equipment in the bow compartment, salt water was found inside the eletric motor of valve FH00012 and FH00013. | Não |  |  |  |  | ICN suggests to replace the mentioned equipment applying a new one from other submarine. NCR Regress to open. Forward to Naval Group. |  |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 258 Dias |  | FH
NCR-ICN-ESC-12-0380-2021 | 53B | MECHANICAL | 2021-03-16 20:01 |  | COS-SMB-319712 |  | CEDOC Closure/Unfounded | The B06 inspections couldn't be found inside inspection folder for BM00032 and BM00031 The F06 inspection on BM00032 was done before the inspection on BM00031, thus no being possible for the mounting logic | Não | [7 empty] | Renato Trabach da Cunha | Roberto Alves Assunção Medeiros | 257 Dias |  | BM
NCR-ICN-ESC-12-0382-2021 | 53B | NON RESISTANT STRUCTURE | 2021-03-17 14:39 | Nível 2 | COS-SMB-319152 |  | CEDOC Closure/Unfounded | The NAVAL GROUP sent the PR-6114420 overriding the decision of NCR-ICN-ESC-12-0053-2020. Please confirm application of PR-6114420 and consequently PR-6111916 and PR-6111917 for SBR2. | Não |  |  |  |  | Please confirm application of PR-6114420 and consequently PR-6111916 and PR-6111917 for SBR2. |  |  | Bruno Vicente Fernandes | Sharles Gomes Silveira | 257 Dias
NCR-ICN-ESC-12-0417-2021 | 53B | PIPES | 2021-03-29 17:37 | Nível 2 | COS-SMB-206063, COS-SMB-206065 |  | CEDOC Closure/Unfounded | As per item 3.1 of COR-2021-900343, the mounting of equipment and pipes was not finished during the inspection; the grease ER spools and equipment were not connected and not protected properly. | Não |  |  |  |  | ICN suggests, Inject proper grease in the spools, which are in this situation in order to be sure that inside the pipe the grease is clean and dismount the equipment to replace them or clean them in the workshop. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | ER
NCR-ICN-ESC-12-0431-2021 | 53B | PIPES | 2021-03-31 17:30 | Nível 2 | COS-SMB-200424 |  | CEDOC Closure/Unfounded | According NCR-ICN-ESC-12-0334-2021: ​"During the paint inspection in tank B110, an unpainted and rusted valve was identified (EJ00211). ICN requests authorization for sandblasting and painting according to the tank scheme." The valve was sandblasted and painted in the same paint scheme as the tank. However, the steel check valve EJ00210 and EJ00211 in the suction tube of tanks EJ01 and EJ03, CMD: 18CR000D00044 / 18CR000C0197 is not intended to be submerged in a water tank. ICN requests that the Naval Group guide us on what needs to be done and whether it will be sent the valve with the correct material. | Não |  |  |  |  | ICN requests that the Naval Group guide us on what needs to be done and whether it will be sent the valve with the correct material. |  |  | Franciellen da Silva Braga | Franciellen da Silva Braga | 242 Dias | Franck Rubis | EJ | NCR-ICN-ESC-12-0334-2021 - NCR-MAT-001497-2021
NCR-ICN-ESC-12-0449-2021 | 53B | PIPES | 2021-04-26 13:45 | Nível 2 | COS-SMB-321805 |  | CEDOC Closure/Unfounded | During the assembly inboard was identified that the bolts studs of the valve BQ00075-P0136396 and BQ00086-P0137222 are too short without 2 threads. This mounting is concerned the AC32034 and AC32035, respectly, on soft patch. | Não |  |  |  |  | It's needed to change de bolt stud 32VI220D00002 (M16X80) by 32VI220D00003 (M16X85). It's not needed the others fixing elements cause the assembly was just positioned without tight. | In accordance with level 1.2 |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 217 Dias | Patrick Daliguet | BQ |  | NO |  |  | 2021-06-23 14:14 | Christophe Marret
NCR-ICN-ESC-12-0506-2021 | 53B | PAINTING | 2021-05-24 19:38 | Nível 2 | COS-SMB-200273 |  | CEDOC Closure/Unfounded | Scenario: as observed by the TA / NG, see attached pictures, the structure of the KT system present in the forward framework has corrosion spots in an advanced state. Solution: 1) During the RANAE: 1.1) Analyse the KT structure present in the forward framework; 1.2) Clean and paint. | Não |  |  |  |  | Scenario: as observed by the TA / NG, see attached pictures, the structure of the KT system present in the forward framework has corrosion spots in an advanced state. Solution: 1) During the RANAE: 1.1) Analyse the KT structure present in the forward framework; 1.2) Clean and paint. Please, send this NCR to the TA Specialist: Paul Fosse. | This NCR pertaining to SBR 1 It is necessary to: cleaning , degreasing, Change the bolting damaged, brush, to remove the rust, and the dust, after that repaint and greasing, And raise a NCR MAT to re-order the bolting changed |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 188 Dias | Paul Fosse | KT |  | NO |  | Outros | 2021-07-27 14:19 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0507-2021 | 53B | PAINTING | 2021-05-25 11:27 | Nível 2 | COS-SMB-200281 |  | CEDOC Closure/Unfounded | Scenario: as observed by the TA / NG, see attached 5 pictures ("Rouile Msf 0x") of the structure of the Masts (RM) system with presence of corrosion spots in an advanced state. Solution: 1) During the RANAE: 1.1) Analyse the KT structure present in the forward framework; 1.2) Clean and paint. | Não |  |  |  |  | Scenario: as observed by the TA / NG, see attached 5 pictures ("Rouile Msf 0x") of the structure of the Masts (RM) system with presence of corrosion spots in an advanced state. Solution: 1) During the RANAE: 1.1) Analyse the KT structure present in the forward framework; 1.2) Clean and paint. Please, send this NCR to the TA Specialist: Paul Fosse. | It is necessary to: cleaning , degreasing, Change the bolting damaged, brush, to remove the rust, and the dust, after that repaint and greasing |  | Matias Lins Maranhão | Matias Lins Maranhão | 188 Dias | Paul Fosse | RM |  | NO |  |  | 2021-07-22 19:53 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0548-2021 | 53B | ELETRIC | 2021-06-24 17:55 | Nível 2 | COS-SMB-200494, COS-SMB-CAB-DA-DY |  | CEDOC Closure/Unfounded | DM62543I and DM62544R cable connectors belonging to the DM00009 equipment were lost. | Não |  |  |  |  | USE THE SUPPLIED DM62543I AND DM62544R (DM00009) CABLE CONNECTORS FOR THE "SBR4" AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY. | See Deliberação N1 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 157 Dias | Stéphane Patrick Philippe Rideau | DM |  | NO
NCR-ICN-ESC-12-0530-2021 | 53B | STW | 2021-06-08 14:53 | Nível 2 | COS-SMB-200444, COS-SMB-200452 |  | CEDOC Closure/Unfounded | Need to perform calibration of flowmeters EV12151Q – P0123068 – 50MD600D00004 EV12152Q – P0123020 – 50MD600D00005 | Não |  |  |  |  | Replacement with calibrated flowmeters available in stock is required. |  |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 174 Dias
NCR-ICN-ESC-12-0561-2021 | 53B | PIPES | 2021-07-12 13:04 | Nível 2 | COS-SMB-200565, COS-SMB-200562 |  | CEDOC Closure/Unfounded | During assembly check it was identified a lack of two pipes that should connect KE hoses (KE20022 and KE20021) to KE01010. We kindle request authorization to apply the ones from SBR3 (presented at attached pictures). A new pipe must be supplied or manufactured for SBR3. | Não |  |  |  |  | ICN request authorization to apply the ones from SBR3. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 140 Dias | Patrick Daliguet | KE
NCR-ICN-ESC-12-0634-2021 | 53B | ELETRIC | 2021-10-04 14:08 | Nível 2 | COS-SMB-319731 |  | CEDOC Closure/Unfounded | During the Expmáq sea departure, the CC1's IVT-11 presented an incident (PWD-L2) constantly, allowing it to be reset and returning after a few minutes. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | I suggest performing the tests described in document 6EM21458 and after verification, replace the referring card or power plate according to the test result. |  |  | Irlan Nunes da Silva | Luiz Felipe Silva Moreira | 56 Dias |  | ME
NCR-ICN-UFEM-12-0505-2019 | 53B | NON RESISTANT STRUCTURE | 2019-05-17 15:05 |  | COS-SMB-319167 |  | Closed | Drilling mistake on Panel 6A - Oval holes were detected at the recess for installation of hatches AH02B12 and AH02B13. | Não | 2020-01-13 16:53 |  |  |  | Rework according to 1.2 (SMB-326168_C) | Rework |  | Hellen Cristina Vieira Paes | Rodrigo Altomare de Carvalho | 241 Dias |  |  |  | NO | [5 empty] | 2019-09-25 15:18 | Franciellen da Silva Braga
NCR-ICN-UFEM-12-0506-2019 | 53B | SEATING | 2019-05-22 14:49 |  | COS-SMB-200290, COS-SMB-200289 |  | Closed | During analysis and preparation for boarding the AP04000C cradle, ICN production team has verified that it is necessary to remove the seating P4031158 (welded with dimension according to the drawing (SBH.3B10.SAD.003405) and reinstall after AP04000C cradle embarking. | Não | 2020-01-13 18:35 |  |  |  | Remove the seating using Annex 1. Install again using SBH.3B10.SAD.003405_K, C23 and G02 annexed. OBS: NG to check the possibility of not use nittal atack. | Rework as per original |  | Hellen Cristina Vieira Paes | Luiz Felipe Silva Moreira | 236 Dias |  |  |  | NO
NCR-ICN-UFEM-12-0507-2019 | 53B | INTEGRATION EQUIPMENT | 2019-05-23 11:11 |  | COS-SMB-319737 |  | Closed | The FP00200 cylinder was inspected by NG and ICN, and showed corrosion in its internal part (annex01) , being necessary a cleaning. The cylinder is in the bulkhead 58 and is difficult to access (annex02), and its removal is necessary for cleaning. The garbage ejector has already been installed and it is not possible to remove the cylinder without removing several spools. | Não | [5 empty] | As the air bottle is now not accessible, TA suggests to blow, with HP dry air, the internal of the bottle. Decision to be validated by specialist level 3 | Naval Group validate the AT proposal to blow with HP dry air the internal of the bottle | Hellen Cristina Vieira Paes | Osvaldo Luiz de Moura Filho | 921 Dias | Alain Lamy |  |  | NO | NO |  | 2019-07-31 18:38 | Frederic Pavic
NCR-ICN-UFEM-12-0509-2019 | 53B | NON RESISTANT STRUCTURE | 2019-05-28 12:45 |  | COS-SMB-200121 |  | Closed | After dimensional inspection on board it was detected a deviation in the measure between the upper face of the highest step of the floor (without the closing plate) to the top face of the roof of the battery compartment. The values found are in the annex 1. | Não | 2020-01-13 18:54 |  |  |  | Accept as it is. The difference founded just have to be considered in the integration of the battery. | There is a gap of 3mmm between tje measure (1693mm) and the maximum dimension (1690mm) define in TAF-TA-2019-967 page 12/13. In addition to information, tje domension (95mm) define in TAF page 13/13 was 105mm adter checking on board. However, ICN can consider these gaps as accept as it is. There is an adjustement possible on the battery connector of 20mm. This NCR must be validated in level 3. | Naval Group accept to adjust the level of the connectors of the nain swictboard above 20mm. But ICN must protect this 20mm with Rilsan | Leonardo Andrade Gama | Luiz Felipe Silva Moreira | 230 Dias |  |  |  | NO | NO |  | 2019-06-18 14:34 | Frederic Pavic
NCR-ICN-UFEM-12-0513-2019 | 53B | SEATING | 2019-06-04 17:01 |  | COS-SMB-200346, COS-SMB-200345 |  | Closed | The seating P4030791 (EL06, EL07, EL08 and EL09) of AP04000 was welded with dimensions according to the assembly drawing, but during the fixation of the equipment with the fasteners, it has been verified that the manufacture of the seating was in accordance with SBH.PLM.3B22.000617_E. The seating was revised in batch 31.2 and now, the correct is SBH.PLM.3B22.000617_F. See annex 1. | Não | 2019-08-05 13:11 |  |  |  | Rework the seating in accordance with the last revision of the document SBH-PLM-3B22-000617_F (F27 e F35) | Rework Rework using the last TDP version of drawing. |  | Hellen Cristina Vieira Paes | Rodrigo Altomare de Carvalho | 61 Dias |  |  |  | NO
NCR-ICN-UFEM-12-0516-2019 | 53B | SEATING | 2019-06-11 16:54 |  | COS-SMB-319523 |  | Closed | During assembly of equipment on seatings P4172352, P4172360, P4172361, P4172362 and P4172419, ICN production team has verified that the screws paid on part list were smaller than the necessary, as shown in annex 1. CMD: 32VI110D00850 (COATED SCREW H M8X30X22 CL8.8) | Não | 2019-09-19 16:50 |  |  |  | Rework according to item 1.2 | The lengh is correct, please analyse the reason of not corresponding on board and revert to Naval Group. For SBR2, it is acceptable to use 32VI110D00851 (VIS H M8x35x22 CLASSE 8.8). |  | Hellen Cristina Vieira Paes | Rodrigo Altomare de Carvalho | 99 Dias |  |  |  | NO
NCR-ICN-UFEM-12-0517-2019 | 53B | INTEGRATION EQUIPMENT | 2019-06-11 19:30 |  | COS-SMB-200569 |  | Closed | The production team has identified that the screw supplied to the DA00004 equipment is not suitable. See annex 1. CMD: 32VI110D01976. | Não | 2019-09-19 16:44 |  |  |  | Replace the screw CHC M8x45x28 CL 8.8 CMD: 32VI110D01976 by the screw M8x50 CL 8.8 CMD: 32VI110D00792 | Screw lengh are sufficient, please analysis the reason of gap on SBR2 and revert to Naval Group. For SBR2, it is acceptable to use 32VI110D00792, however it is necessary to add washers. |  | Hellen Cristina Vieira Paes | Osvaldo Luiz de Moura Filho | 99 Dias |  | DA00004 |  | NO
NCR-ICN-UFEM-12-0518-2019 | 53B | NON RESISTANT STRUCTURE | 2019-06-14 17:05 |  | COS-SMB-200649 | CTE00917348 | Closed | During the dimensional inspection of the rudder axis marking made by the optical department, it was detected that the theoretical distance of the frame C88 to the rudder axis is not in agreement with the design. It used the axis of AC34027 slleve as a starting reference to mark the rudder axis as directed by the mechanical department. -See attached D45-1_CTE00917348 | Sim | 2019-08-26 15:02 |  |  |  | Accept as it is. Use the axis (x, y) of sleeve AC34027. The reference for positioning of Bow Hydroplane Gear and Rudder Holes (DP00355 and DP00356) will be the center of sleeve AC34027. | Accepted as it is Inform the mechanical team in charge of mounting |  | Silvio Fonseca de Paiva | Joao Paulo Schneider Gonzaga | 72 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0002-2019 | 53B | RESISTANT STRUCTURE | 2019-06-27 11:49 |  | COS-SMB-200768 | CTE00862831, CTE00862808 | Closed | During the assembly inspection of the joint, a gap of between 6,0 and 8,5mm was found, length: 3500mm starting from the radiomark 0 to 315, 875 to TOP PORTSIDE (outside the tolerance). A gap of between 6,5 and 8,5mm was found, length: 8750mm starting from the radiomark 0 to 875 STARBORD (outside the tolerance). WPS: 111 / 3B-3B / 30 / A32 Tolerance from 4 to 6mm CLASS 1/1 – 80 HLES – Thickness 30 mm | Sim |  |  |  |  | After heating the areas with gap out of tolerance should decrease and get into tolerance. For those who still out of tolerance, production have to use a backing rod during welding, according It21-02-10 S-11-14. | For zone where the gap is out of tolerance, NG / TA propose to perform a build up during welding by following the card 4 of the SMB-200049. Open an NCR-RO for the tracability. | agree with the proposal solution, build up during the welding by laying cooper rod traceability must be ensured by NCR RO In term of preventive action ICN must carry onut an analysis on the section abutment to ensure the correct application of the action plan closing junctiun and in particular on the aspect of overlongth of 5mmon the end of the section in order to compensate the withdrawals inherent to the integration operation and thus to ensure a mesh lengh of conformal section | Rodrigo Nunes Freitas | Felipe Trigueiros Silveira | 886 Dias | Hugues Bourget |  |  | NO | NO
NCR-ICN-ESC-12-0003-2019 | 53B | RESISTANT STRUCTURE | 2019-07-01 19:49 |  | COS-SMB-200768 | CTE00862813 | Closed | There is Verticality deviation on forward top of section 2A. Due to the sequence of activities to perform junction, it’s known about this adjustments needs on section’s top. This deviation will be repaired during junction with section 2B. | Sim | 2019-10-04 13:14 |  |  |  | ACCEPT AS IT IS. The deviation is in the foward butt and will be adjusted during junction S2A/S2B. Now for the junction S1/S2A the verticality is OK in aft butt. | Accepted as it is |  | Camila Fagundes de Paula Guedes | Luiz Felipe Silva Moreira | 94 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0520-2019 | 53B | NON RESISTANT STRUCTURE | 2019-07-01 20:08 |  | COS-SMB-319165 |  | Closed | ALLTEC have ran out of the verranne 205 g/m² fabric (NGD 930930013157). (SC2AAH02A05) | Não | 2019-07-31 11:27 |  |  |  | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, and modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  | Hellen Cristina Vieira Paes | Bruno Marcel Lima Ferreira Amancio | 29 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0521-2019 | 53B | NON RESISTANT STRUCTURE | 2019-07-01 20:15 |  | COS-SMB-321679 |  | Closed | ALLTEC have ran out of the verranne 205 g/m² fabric (NGD 930930013157). (AH00308) | Não | 2019-07-31 11:36 |  |  |  | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  | Hellen Cristina Vieira Paes | Bruno Marcel Lima Ferreira Amancio | 29 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0522-2019 | 53B | NON RESISTANT STRUCTURE | 2019-07-01 20:18 |  | COS-SMB-319165 |  | Closed | ALLTEC have ran out of the verranne 205 g/m² fabric (NGD 930930013157). (AH02A01) | Não | 2019-07-31 11:41 |  |  |  | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  | Hellen Cristina Vieira Paes | Bruno Marcel Lima Ferreira Amancio | 29 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0523-2019 | 53B | NON RESISTANT STRUCTURE | 2019-07-01 20:20 |  | COS-SMB-200628 |  | Closed | ALLTEC have ran out of the verranne 205 g/m² fabric (NGD 930930013157). (APGV00514) | Não | 2019-07-31 11:45 |  |  |  | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  | Hellen Cristina Vieira Paes | Bruno Marcel Lima Ferreira Amancio | 29 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0532-2019 | 53B | NON RESISTANT STRUCTURE | 2019-09-16 17:44 | Nível 2 | COS-SMB-325684 |  | Closed | 1.1 GRP panel AV00003 was manufactured with wrong dimension. See annex 1. | Não | 2021-01-15 13:03 |  |  |  | Manufacture a new one according SMB-325993_E | Scrap and Rework a new one |  | Isac Ailton Correia Gomes | Bruno Marcel Lima Ferreira Amancio | 486 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0016-2019 | 53B | RESISTANT STRUCTURE | 2019-09-24 13:20 | Nível 2 | COS-SMB-200157 |  | Closed | During measurements of verticaly of tops the junction of sections 53B-SC2B/SC3, dimensions outside the acceptance criteria were detected. See attached CTE00915085/ CTE00915068. | Não | 2019-10-01 13:59 |  |  |  | Follow to level 2 decision. | The quality department had classified this inspectin as "for information only" while it is a required inspection before joining. The answer that had been made before joining was: Accepted as it is. |  | Neimar Mayrink da Silva | Felipe Trigueiros Silveira | 7 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0533-2019 | 53B | NON RESISTANT STRUCTURE | 2019-10-01 18:49 | Nível 2 | COS-SMB-346222 |  | Closed | Deviations were found on the Upper Rudder Blade trailing edge positioning (inspection C680 - Analysis of the position of the trailing edge – SMB-327598), therefore the blade is not according to the drawing MAT214-1517. See report of the measures found on annex 1 Product: DP00152 - UPPER RUDDER BLADE | Não |  |  |  |  | As agreed with the production team, we proposes to remove the trailing edge, remove all the GRP skin of the blade, produce a new and restart the process from its positioning. | Rework Remove the GRP Skin and the edge . Carry out an inspection form of the premix resin in relation with mechanical part. Correct it if necessary. Rework all the stpes as per original process. |  | Camila Fagundes de Paula Guedes | Bruno Marcel Lima Ferreira Amancio | 789 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0018-2019 | 53B | ACOUSTIC DISCRETION | 2019-10-14 13:02 | Nível 1 | COS-SMB-200526 | CTE00776177 | Closed | It was not found shock and tilt sensors glued on GN02522. | Não | 2021-01-06 14:30 |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 |  | Luisa Kubrusly | Rogerio Milani | 450 Dias |  | GN |  | NO
NCR-ICN-ESC-12-0019-2019 | 53B | RESISTANT STRUCTURE | 2019-10-22 16:07 | Nível 2 | COS-SMB-200769 |  | Closed | During measurements of verticaly of tops the junction of sections 53B-SC2A/SC2B, dimensions outside the acceptance criteria were detected. See attached CTE00862873/ CTE00862867. | Não | 2020-08-06 17:43 |  |  |  | ICN propose to accept as it is. | Accepted as it is The deviation will be corrected during the jonction. |  | Neimar Mayrink da Silva | Felipe Trigueiros Silveira | 289 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0535-2019 | 53B | NON RESISTANT STRUCTURE | 2019-11-05 12:35 | Nível 2 | COS-SMB-200629 |  | Closed | During the manufacturing of the Portside Bow Hydroplane Blade, it was detected that the positioning assembly of Trailing Edge is not in agreement with the design (see CTE00957957). 53B-SC3-APGV00497 – PORTSIDE BOW HYDROPLANE BLADE | Não | 2019-12-13 19:11 |  |  |  | Accept the manufacturing of Portside Bow Hydroplane Blade as it is. During workshop assembly, manufacture two shoulder keys to return the stock cone within Blade Solid Part cone axis following the TAF-TA-2018-0848. The calculations to machining the keys will be done after the both (portside and starboard) blades are mounted in the stock and checked by optical measurement - inpection D52-28 according SMB-208704. After shoulder keys machining, mount and check again the positioning between stock and trailing edge by optical measurement. | Rework, After analysis with mechanical team, NG/TA propose to rework the Blow hydroplane blade as per original. |  | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 38 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0030-2019 | 53B | RESISTANT STRUCTURE | 2019-12-06 15:38 | Nível 2 | COS-SMB-200769 |  | Closed | By divergence of fault mapping inspected by radiographic assay and with the comparison of the masks of repairs emitted, it was found that the place to be repaired (TR8A/TR8B) is divergent from the initial marking. | Não | 2019-12-18 20:06 |  |  |  | Awaiting deliberation of N2. | Rework, After NDTs of junction S2A/S2B 5 HROs were opened to treat the defetcs. The NDT of HRO-ICN-ESC12-019/2109 shown that the repair done in the non affected zone. After analysis , it was approuved that it's due to the wrong localisation during the first riding. Decision : rework using HRO ICN-ESC-12-021/2019 |  | Alexander Vilela Dias | Sergio André Telles Soares | 12 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0205-2018 | 53B | PIPES | 2018-06-15 03:00 |  | COS-SMB-200442 |  | Closed | During cut activity seating on board, the REDUCED TEE P0111242 has been touched by cutting tool, causing a cut in its body of approximately 2 mm of depth. See annex. | Não |  |  |  |  | DECISION: WAITING NAVAL GROUP ORIENTATION, ACCORDING TO ATTACHMENT "1" AND REPAIR ORDER. | DECISION: REPAIR EM ACCORD AVEEL'ISSP (D. BERNIDE). FOLLOW THE DIFFERENT PHASES GIVEN IN ANNEX 2 ( ORDEM DE REPARO ). NAVAL GROUP REQUESTS ICN TO ISSUE AND ENCLOSE TO THIS NCR, ALL PV'S OF CONFORMITY OF THE DIFFERENT PHASES CARRIED OUT DURING THE REPAIR. | N/A | System |  | 598 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0267-2018 | 53B | SEATING | 2018-08-15 03:00 |  | COS-SMB-200294 |  | Closed | for perform tht weilding in the weld reserve area of the frame CO73, it was necessary to remove the following seatings P4048697, P4048698, P404699, P4048700 and P4048701 | Não |  |  |  |  | REINSTALL AFTER WELD. -G02 -100% VT AND 100% MT OR PT. | VERIFY THE DISTANCE TO SEE IF AUSTENITIC WELDING OF THE SEATING CAN STAY BELOW THE WEB/PLANKING WELDING. IF YES REMOVE THE AUSTENITIC. AFTER WEB/PLANKING WELDING RE-INSTALL NEW SEATING. | N/A | System |  | 537 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0333-2018 | 53B | SEATING | 2018-10-16 03:00 |  | COS-SMB-321775 |  | Closed | The seating P4171824 was welded on board according to SMB-TDP-PR-5572871, but now was verified that the seating was manufactured following the DXF that shows the seating plates as S355 steel, not according to SMB-TDP-PR-5572872 with 80HLES plates. | Não |  |  |  |  | CHANGE THE ELEMENTS ACCORDING TO NCR-ICN-CONFIG-12-2625/2018. | AGREES WITH PARAGRAPH 2.1. REWORK | N/A | System |  | 475 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0341-2018 | 53B | NON RESISTANT STRUCTURE | 2018-10-26 03:00 |  | COS-SMB-200111 | CTE00583532 | Closed | During shape inspection of ballast tank 3 and 4 after installation and welding, a deformation was detected in the region between frames C016 to C110 at baseline (OH). | Não |  |  |  |  | ACCEPT AS IT IS. | NG / TA asked to redo the inspections of welding inside the ballast. All be stiffeners betwen 106 bulkhead and III bulkhead in the assected zone. See e mail in annex. | N/A | System |  | 465 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0370-2018 | 53B | MECHANICAL | 2018-12-05 02:00 |  | COS-SMB-200712, COS-SMB-200569 |  | Closed | There is a disagreement in the working instruction of KT01447 and KT01448. For the same equipment CMD (18RT000D00196), lock washer is used in KT01447 and locking nut in KT01448, as shown in the annex. For mechanical assemblies only one type of locking is | Não |  |  |  |  | In order to solve the problem, replace both the lock washer and locking nut by hexagonal nut (32VI310D000060) and Nord-Lock washer (32VI410D000076) on both equipment, as the mentioned nut in working instruction (32VI310D00178) is not in stock. Also use 4 | AGREE WITH LEVEL1: REPLACE FISTENING ELEMENTS FOR KT01448 BY THE SAME OF KT01447. DECISION: UPDATE DOCUMENTATION. TO BE FORWARDED TO EXPERT LEVEL 3. | THE MODIFICATION HAVE BEEN SENT VIA PR ADDENDUM SMB-TDP-PR-6026637, 6026638 & 6026639. | System |  | 425 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0384-2018 | 53B | NON RESISTANT STRUCTURE | 2018-12-20 02:00 |  | COS-SMB-200101 |  | Closed | 1.1 It was detected a twist deformation on the forward part of the upper sail. Situation shown on annex 1. 1.2 Repair as per annex 2. Proposition agreed with TA-NG. | Não |  |  |  |  | FOLLOW ANNEX 2. TO BE FORWARDED TO LEVEL 2. | ACCORDING TO THE ANALYSIS, REPAIR AS PER ANNEX 2 BUT WITH THE COTATIONS MODIFIED ON THE DRAWING. | N/A | System |  | 410 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0406-2019 | 53B | NON RESISTANT STRUCTURE | 2019-01-28 02:00 |  | COS-SMB-343984 |  | Closed | ICN production team received the new revision of "SMB-600537" (B) updating the manufacture of lower rudder blade (metal part). The work on SBR1 is complete and SBR2 is in the finalization phase and ICN production team wants to know if it can be maintained | Não |  |  |  |  | The SBR-2 was done according to the last assue. Production shoukd attach the evidences. | Agree with 2.1 |  | System |  | 372 Dias |  |  |  | NO
NCR-ICN-UFEM-12-0495-2019 | 53B | PIPES | 2019-05-08 03:00 |  | COS-SMB-206090 |  | Closed | The P010575 became smaller 40mm for the closure in the bulb P0104568. | Não |  |  |  |  | adds a 40mm nipple to the P010575 closure in the ampoule P0104568. | FTG-7146. DECISION: AGREE WITH PROPOSAL SOLUTION GIVEN IN 2.1 ABOVE IF THERE IS NO PROBLEM OF ENVIVONNMENT DUE TO THAT MODIFICATIONS. | N/A | System |  | 271 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0496-2019 | 53B | SEATING | 2019-05-08 03:00 |  | COS-SMB-319659 |  | Closed | Items 003 and 007 of seating P4028879 were misplaced on hull. See drawing on annex 1. | Não |  |  |  |  | Remove items 003 and 007 from hull and reinstall in correct position. | REWORK AS PER ORIGINAL. -ICN MUST ANNEX AN INSPECTION REPORT TO CLOSE THIS NCR. -POSITION INSPECTION AND WELDING INSPECTION. DECISION: IF NECESSARY OPEN HRO TO REPAIR THE HULL. | N/A | System |  | 936 Dias |  |  |  | NO | NO |  |  |  |  | 2021-02-08 12:41 | Christophe Marret
NCR-ICN-ESC-12-0070-2020 | 53B | SEATING | 2020-06-04 14:41 | Nível 1 | COS-SMB-200361 |  | Closed | The NCR-ICN-ESC-11-0806-2020 was opened because the EV00100 equipment had a heating problem. The FTG-E626 presents a repair solution proposed to support the valve thermostatic actuator. This solution has been created based on the fixation of ES00024 and proposes a modification on seating P4031069 (item 16) as shown in annex. | Não | 2021-01-13 19:13 |  |  |  | Do the same procedure as NCR-ICN-ESC-11-0806-2020. | NCR LEVEL 1 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 223 Dias |  | ES |  | NO
NCR-ICN-ESC-12-0071-2020 | 53B | SEATING | 2020-06-04 14:42 | Nível 1 | COS-SMB-200257, COS-SMB-319499, COS-SMB-319498 |  | Closed | The NCR-ICN-ESC-11-0887-2020 was opened because all scape suit (MK11) EQ00234 until EQ00243 are installed in the B310 Accommodation alleyway (middle area) obstructing the passage, so, the supports must be modified from places. The FTG-8399 presents the new arrangement in B302, with 3 modified seatings (P4180263, P4180262 and P4180259). | Não | 2021-03-03 20:04 |  |  |  | Do the same procedure as NCR-ICN-ESC-11-0887-2020. | NCR LEVEL 1 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 272 Dias |  | EQ |  | NO
NCR-ICN-ESC-12-0115-2020 | 53B | STW | 2020-08-06 12:55 | Nível 2 | COS-SMB-200281, COS-SMB-345282, COS-SMB-200644, COS-SMB-331623 |  | Closed | Tool RM00317/29OU000D00700 was found to be damaged and thus need to be repaired. | Não |  |  |  |  | As discussed with Anthony Grel, we will fill and machine the damaged part. | folowing the scratch on the tool 29OU000D00700 we recommend repair by welding reloading according to the document SMB-200046 page (25;26/450) with an DP test, A manual recovery will be necessary using a fine file and sandpaper after the weld to garantee the diameter 190g6 as well as the surface finish RA 0,4 according to drawing (SMB-349030) followed by a quality control associate. |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 480 Dias | Paul Fosse | RM |  | NO
NCR-ICN-ESC-12-0148-2020 | 53B | PIPES | 2020-09-02 13:28 | Nível 2 | COS-SMB-321784, COS-SMB-319561 |  | Closed | Interference on board between the connection ruch (P4120621) and the positioning of the clamp (P4109894). Attached picture of solution applied. This NCR suppress RAI-SBR2-02709-319560 and RAI-SBR2-02692-319561. | Não |  |  |  |  | see attached ICN change support and placement for good installation. | repair |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 453 Dias | Franck Rubis | ES |  | NO |  |  | 2020-09-11 16:35 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0505-2021 | 53B | SEATING | 2021-05-24 17:04 | Nível 2 | COS-SMB-200404 |  | Closed | Mounting of the P4149847 seating out of coordinate. During the assembly of the pipes it was verified that the seating P4149847 was 100 mm in X out of coordinate. | Não |  |  |  |  | agree with 1.2. Rework according job order. | REWORK Rework as per original For the area where the old seating was welded ICN must apply the SMB-200043. Open a NCR/RO if it's necessary . |  | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 188 Dias | Hugues Bourget | DV |  | NO
NCR-ICN-ESC-12-0004-2019 | 53B | RESISTANT STRUCTURE | 2019-07-02 11:06 |  | COS-SMB-200768 | CTE00862797 | Closed/Unfounded | There is deviation on distance between frame 32 and aft top of section 2A. This deviation was caused by the adjustments done by grindind to correct the gap for junction. Knowing that the distance between frames are all conform, ICN suggests to accept as it is. | Sim | 2019-07-23 18:12 |  |  |  | Making a projection for the space frame length (inspection D27), we conclude that will be inside the tolerance. ICN propose to accept as it is. |  |  | Camila Fagundes de Paula Guedes | Luiz Felipe Silva Moreira | 21 Dias
NCR-ICN-ESC-12-0006-2019 | 53B | RESISTANT STRUCTURE | 2019-07-19 11:46 |  | COS-SMB-200768 | CTE00862840 | Closed/Unfounded | During VT inspection was detect porosity, defect (type 2011), defect out of the acceptance criteria of IT-26-39-1E C. For repair location and dimensions see sketch in annex. | Sim | 2019-10-03 19:15 | [6 empty] | Rodrigo Nunes Freitas |  | 76 Dias
NCR-ICN-UFEM-12-0530-2019 | 53B | INTEGRATION EQUIPMENT | 2019-09-02 15:57 | Nível 2 | COS-SMB-319719, COS-SMB-339470 |  | Closed/Unfounded | After checking in the maintenance of Scorpene class submarines that mobile parts were not painted, he found that without painting the mobile parts suffered a severe corrosion thus impairing their service life. In this case, some SBR2 mobile parts must be painted to prevent future corrosion. Industrial Markers: AC42001, AC42016, AC42056, AC42081, AC42082, AC42036 and AC42039. | Não | 2019-10-15 12:24 |  |  |  | Remove all mobile parts of S2A and S2B SBR2, check the list in Annex1, discard gasket and washers, check stud bolts and replace if necessary. Send the mobile part for painting. Install new gasket and washers and re-apply the entire torque process per SMB-200960. Redo B06 and B07. |  |  | Osvaldo Luiz de Moura Filho | Osvaldo Luiz de Moura Filho | 42 Dias | Patrick Daliguet | [5 empty] | 2019-10-14 15:26 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0012-2019 | 53B | ACOUSTIC DISCRETION | 2019-09-06 13:58 |  | COS-SMB-200542 |  | Closed/Unfounded | During inspection A07 (traceability) performed on pumps EJ00003 and EJ00007 was checked the following non conformities: a) One of the pumps is missing the nameplate; b) In the position EJ00003 is one pump delivered to SBR3 | Não | 2019-10-10 16:55 | [6 empty] | Marcos Aurelio Correa Abrantes | Rogerio Milani | 34 Dias |  | EJ
NCR-ICN-ESC-12-0246-2020 | 53B | STW | 2020-11-03 18:03 | Nível 2 | COS-SMB-200260 |  | Comissionamento 5.1 | THE AIR FLOW IN THE AFT AND FWD BATTERY COMPARTMENTS INDICATED (MEASURES) IN THE INSTRUMENT FH10106Q DO NOT MEET THE REQUIREMENTS OF ITEM 2.3.3.2 OF DOCUMENT SMB-210250_G (SETTING TO WORK PROCEDURE FOR FH SUB-SYSTEM) | Não |  |  |  |  | NO COMMENTS | send to NG level 3 | - Identify in which scenario unmet requirements are observed (low speed or high speed), forward or aft battery. - In the same way as what is requested in NCR-ICN-ESC-11-1211-2020, check the tightness of the duct if this has not already been done, overpressure 0,5 bar and test using a leak detection spray. | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 390 Dias | Frederic Guevel | FH | NA | NO | YES |  | 2021-09-02 12:31 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0289-2020 | 53B | MECHANICAL | 2020-11-23 22:48 | Nível 2 | COS-SMB-200273, COS-SMB-319693 |  | Comissionamento 5.1 | It was checked on SBR2 that all intenal door electrical connectors (KT0075X, KT01A5X and KT01B5X) were found without the proper "tightening torque". Thus, all "tightening torque" were performed according to their respective B11-19. However, we need to perform that B11-19 in the presence of the Quality Team, record all information in CTEs and perform ("again", if applicable) the B02_KT0025X and B02_KT0055X (where the word "X" is the TLT numbers 1-6). | Sim |  |  |  |  | Thus, all "tightening torque" were performed according to their respective B11-19. However, we need to perform that B11-19 in the presence of the Quality Team, record all information in CTEs and perform ("again", if applicable) the B02_KT0025X and B02_KT0055X (where the word "X" is the TLT numbers 1-6). | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Bruno Correa Ferreira | Bruno Correa Ferreira | 370 Dias | Patrick Daliguet | KT |  | NO | NO |  | 2020-12-01 14:48 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0303-2020 | 53B | PIPES | 2020-12-17 17:26 | Nível 2 | COS-SMB-206081 |  | Comissionamento 5.1 | The torque was done in october, however the latest date for B01/B02 is june. The test must be redone in the EG00202 (NCR-ICN-REGRESS-12-0025/2020). Therefore, the inspections below must be regressed: - B01_EG00202; - B02_EG00202; - B07_EG00202. | Não |  |  |  |  | Regress inspections according to item 2.1 | In accordance with level 1, NCR REGRESS will be raise with: -B07_EG00202 will be redone -B01_EG00202 and B02_EG00202 will be carry out (Pipe EG50202M disassembled). -M05 and S02_EGZ0001 will be carry out for pipe EG50202M -B05 will be updated | In accordance with level 2.2. (David BERNEDE - ISSP) | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 346 Dias | Patrick Daliguet | EG | NCR-ICN-REGRESS-12-0025/2020 | NO | NO |  | 2021-01-13 18:41 | Franck Rubis |  | 2021-04-20 15:29 | Frederic Pavic
NCR-ICN-ESC-12-0329-2021 | 53B | RESISTANT STRUCTURE | 2021-02-01 15:04 | Nível 2 | COS-SMB-200273, COS-SMB-319693 |  | Comissionamento 5.1 | Scenario: During the activities of the KT, it was identified that the KT21A54 / P0153313 / 11CI120D00052 electrical connector present in the internal door of the TLT4 has more than one of the pins broken. Solution: 1) Replace that conector by new one following the procedure "Remove / Replace the wire guidance & remote adjustment crossings - SBR-ETM-000KTM0001_A pages 744-745 - Work Sheet T06", see the attached document; 2) The inspections B02_KT00554 and B02_KT00254 will be carry out again; 3) After a special tool will be available, a pressure test on the internal door at 52,5bar will be carry out (if this tool is only provided for the internal door); 4) Open a NCR MAT; 5) Perform the following protocols: KD13C / K11C / K11; Observation: see the following NCR "NCR-ICN-ESC-12-0289-2020". | Sim |  |  |  |  | Scenario: During the activities of the KT, it was identified that the KT21A54 / P0153313 / 11CI120D00052 electrical connector present in the internal door of the TLT4 has more than one of the pins broken. Solution: 1) Replace that conector by new one following the procedure "Remove / Replace the wire guidance & remote adjustment crossings - SBR-ETM-000KTM0001_A pages 744-745 - Work Sheet T06", see the attached document; 2) The inspections B02_KT00554 and B02_KT00254 will be carry out again; 3) After a special tool will be available, a pressure test on the internal door at 52,5bar will be carry out (if this tool is only provided for the internal door); 4) Open a NCR MAT; 5) Perform the following protocols: KD13C / K11C / K11; Observation: see the following NCR "NCR-ICN-ESC-12-0289-2020". | The correct identification is KT01A54, NGD 1045-14-443-6718. It is necessary to raise a NCR MAT in order to have a new one, ok for B02, but it is not necessary to redo KT13C - KT11C or KT 11. | In accordance with level 2 proposal - the B07, B05 inspections have to be updated after the pressure test done and traceabiltiy folder of the TLT concerned is updated. ICN has to inform NAVAL GROUP about the root causes of the breakage which has never been encountered with this type of equipment. | Bruno Correa Ferreira | Bruno Correa Ferreira | 301 Dias | Patrick Daliguet | KT | NCR-ICN-ESC-12-0289-2020 | NO | NO |  | 2021-02-11 19:44 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0357-2021 | 53B | PIPES | 2021-03-03 12:42 | Nível 2 | COS-SMB-200273 |  | Comissionamento 5.1 | Scenery: Before the launching ceremony of the SBR2, a visual inspection was carried out overhaul installation of the KT system (C200 and Forward Framework). Several points were observed, including: 1) Hydraulic Circuit: 1.1) Hydraulic lines are absent; 1.2) There are no clamps, rubber and screws; 1.3) The hydraulic lines are connected, but without sealing gaskets (seals); 1.4) There are no connections between hydraulic lines and aft hydraulic passage. No sealing gaskets; 1.5) Electrical connections are without protection plugs; 1.6) There are no connections between hydraulic lines and aft hydraulic passage; 1.7) Among other points (see attached documents with all comments / observed points. 2) Electrical Connections: 2.1) Electrical connection are without protection plugs; Solution: about the hydraulic circuit, it is not necessary to regress the inspections B01 / B02 since we still have to perform all tests S01 / M04 / S02. Therefore, ICN propose to reassemble the installation, perform again all inspection related to the Pipe Discipline and perform only the S01 / M04 / S02 since all the valves listed below were still in place. See attached document with the result of visual inspection: "Visual_Verification_KT_Installation_SBR2.pdf". 1) KT03C4X; KT04C4X; KT05C4X; KT06C4X; KT07C4X; KT08C4X; KT01E4X; KT02E4X; KT06E4X (where X letter is about the TLT identification - from 1 to 6). Please send this NCR in reference to Patrick Daliguet / David Bernede. | Não |  |  |  |  | Scenery: Before the launching ceremony of the SBR2, a visual inspection was carried out overhaul installation of the KT system (C200 and Forward Framework). Several points were observed, including: 1) Hydraulic Circuit: 1.1) Hydraulic lines are absent; 1.2) There are no clamps, rubber and screws; 1.3) The hydraulic lines are connected, but without sealing gaskets (seals); 1.4) There are no connections between hydraulic lines and aft hydraulic passage. No sealing gaskets; 1.5) Electrical connections are without protection plugs; 1.6) There are no connections between hydraulic lines and aft hydraulic passage; 1.7) Among other points (see attached documents with all comments / observed points. 2) Electrical Connections: 2.1) Electrical connection are without protection plugs; Solution: about the hydraulic circuit, it is not necessary to regress the inspections B01 / B02 since we still have to perform all tests S01 / M04 / S02. Therefore, ICN propose to reassemble the installation, perform again all inspection related to the Pipe Discipline and perform only the S01 / M04 / S02 since all the valves listed below were still in place. See attached document with the result of visual inspection: "Visual_Verification_KT_Installation_SBR2.pdf". 1) KT03C4X; KT04C4X; KT05C4X; KT06C4X; KT07C4X; KT08C4X; KT01E4X; KT02E4X; KT06E4X (where X letter is about the TLT identification - from 1 to 6). Please send this NCR in reference to Patrick Daliguet / David Bernede. | Agree with the proposition of level 1.2. It' important to mount correctly all lines before pressure tests. In complement, if one of valves listed in 1.2 was dismounted is necessary to redo also B01, B02 and update B05 | All inspections have to be redone : M04, S02, B01, B02, M05 and of course B05 updated. (David BERNEDE - ISSP) | Bruno Correa Ferreira | Bruno Correa Ferreira | 271 Dias | Patrick Daliguet | KT |  | NO | YES
NCR-ICN-ESC-12-0441-2021 | 53B | STW | 2021-04-14 10:59 | Nível 2 | COS-SMB-319321, COS-SMB-200542 |  | Comissionamento 5.1 | BMS_PMU BB02501 is not working. There is a startup problem when trying to connect via the maintenance laptop to the PMU when running the VNC Software (Login: pmu / password: bms), the message "run-time error" 6 ": Overflow" appears. | Não |  |  |  |  | ICN requests NG support to resolve the issue with BMS_SOFT_PMU_SCORPENE \ BMS_PMU_IPMS_V1.17. | On 15-04-2021 the SBR2 PMU was landed by ICN. The 16-04-2021 Naval Group has connected the PMU with external keyboard/ screen/ mouse to check operation. 1) When the PMU started, it froze on the "DISK BOOT FAILURE" error when the BIOS was started => Naval Group has put the BIOS start priorities in order 1 - mini disc "mSATA mini 3ME3" 2 - External Hard Drive "Data" 2) After starting Windows, when launching the application "BMS_PMU_IPMS_1.17.exe", the error "Run time error 6 - Overflow" appeared. => Naval Group saved the following files journal_of_AFT_alarms.log journal_of_alarms_historic.log journal_of_all_alarms.log journal_of_FWD_alarms.log 3) The application "BMS_PMU_IPMS_1.17.exe" has been relaunched without problems and the alarm files have been renewed => Naval Group must take over the PMU maintenance document to add the archiving of the 4 files every year => Naval Group has verified the absence of viruses on the "Black" Laptop of the SBR2: No problem detected On 19-04-2021 the PMU was brought back on board the SBR2 1) The PMU did not communicate with the Laptop or IPMS. => Naval Group "opened" the PMU to directly connect the laptop. Everything was working normally => Naval Group connected the Laptop to the PMU output. Everything was working normally 2) Naval Group found with ICN that the problem was with the BB62871B cable plug => Naval Group asks ICN to redo the connector 3) Naval Group found with ICN that the OO62584B cable plug was missing => Naval Group asks ICN to redo all the connector | There was a communication problem on the BMS system due to a weak communication protocol and a bad connexion of optical fibres. In order to fix this issue, it is necessary to apply two Modification Orders to SBR2: - OM-136780 (SMB-TDP-PR-6862721, applicable SBR1-2, loaded in TDP IS on 05/11/2021) consists in flashing a new firmware on the 360 probes. It will be done in week 46-47 by the supplier DEVELEC. - OM-136776 (SMB-TDP-PR-6862720, applicable SBR1-2-3-4, loaded in TDP IS on 05/11/2021) consists in changing the PMU software. This can be done by ICN. Both OM must be applied at the same time. When re-installing the probes onboard, optical fibers must be carefully cut and tightened. | Marco Aurelio Barbosa | Marco Aurelio Barbosa | 229 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO | YES
NCR-ICN-ESC-12-0484-2021 | 53B | PRESERVATION | 2021-05-11 15:27 | Nível 2 | COS-SMB-321700 |  | Comissionamento 5.1 | ICN Preservation team was not able to do the rotation task of BD00014 (Diesel Generator) of the SBR-2 (Humaitá) after the final installation of the water preheating pump. With the installation of the pump, a support was also installed, but the support prevents the connection of the hose to the manual oil pump, which necessary for the rotation. This issue was not found in any other DG (including SBR-1 DGs) that has a water preheating pump installed. Please see the attached photos. | Não |  |  |  |  | As this Preventive maintenance task could not be performed due to lack of access, we ask NG for a solution to the problem. A "half moon" cut in the support may be a solution. | The connexion can't be done because the lenght of the tool is too long. I suggest you to change the connexion by one with one angle of 90° and the task will be possible. (Jean Christophe Laurent) |  | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 202 Dias | Franck Heidel | BD |  | NO
NCR-ICN-ESC-12-0485-2021 | 53B | PIPES | 2021-05-11 19:31 | Nível 2 | COS-SMB-200273, COS-SMB-200727 |  | Comissionamento 5.1 | Scenario: during the flushing activity, it was verified that the lines KT51382RB / P0115900 and KT51042R / P0116185 are inverted. Solution: ICN proposes in the closest position, and most accessible point, cut/increase the length and invert the lines/and weld them. | Não |  |  |  |  | Scenario: during the flushing activity, it was verified that the lines KT51382RB / P0115900 and KT51042R / P0116185 are inverted. Solution: ICN proposes in the closest position, and most accessible point, cut/increase the length and invert the lines/and weld them. Please, send this NCR to the NG spetialist: Alain Lamy. | Reverse the pipes to restore functional conformity -purge the circuit -cut the pipes -reverse the pipes -welding -carry out the associated checks |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 201 Dias | Franck Rubis | KT | NCR-ICN-REGRESS-12-0057-2021 | NO
NCR-ICN-ESC-12-0495-2021 | 53B | PRESERVATION | 2021-05-17 12:05 | Nível 2 | COS-SMB-200710, COS-SMB-319731 |  | Comissionamento 5.1 | The Preservation Team detected that the torque of some screws in the BS fwd and aft battery box cells (BS02508 and BS02507) were above the requirement. In the Fwd battery box, 4 cells had screws damaged during the removal, possibly due to the high torque. In the Aft battery box, due to what happened to Fwd battery and following TA instructions, the torques were verified without removing the screws to avoid damaging the equipment. Please see the attached photos. | Não |  |  |  |  | ICN Preservation team asks NG for orientation on how to proceed. | Update of the NCR: NG confirms the damage of 4 batteries, instead of 2. From the photos and videos provided by ICN, the torque applied for the tightening to the batteries seems too high( more than 15 Nm) for some batteries, damaging the thread of the screw of two batteries. These batteries, according to ICN, were not untightened since the acceptance from the manufacturer. Naval Group Front Office suggests to take 4 batteries from SBR and equalize with the 16 other batteries. This NCR is being sent for Level 3(Back Office BS system specialist) in order to decide what to do with the manufacturer. | Additional information to be transmitted to level 3: - Communicate to NG on the presence of oxidation / deposits on the pole threads, take pictures if there are any. - Check the presence of oxidation / deposits on the threads of the SBR3 and SBR4 battery poles. Temporary action: - Take 4 accumulators from SBR3 or SBR4 batteries which have a no-load voltage greater than 1.2V, and perform an equalization: discharge all the accumulators from the SBR2 battery and the 4 accumulators up to 1.0V per cell, then charge forced from 8h at 0.2C. Definitive action: - Do NOT create NCR-MAT for replenishment => A full set of BS batteries is already being restocked for the SBR2. Delivery expected Q2-2022. The BS batteries currently in Brazil and identified as defective wil be able to be scrapped by ICN following the delivery of the new accumulators. | Rafael Tavares do Rego Macedo | Rafael Tavares do Rego Macedo | 196 Dias | Thomas Le Corre | BS |  | NO | YES |  | 2021-07-22 17:46 | Christophe Marret
NCR-ICN-ESC-12-0551-2021 | 53B | STW | 2021-06-28 19:17 | Nível 2 | COS-SMB-206184 |  | Comissionamento 5.1 | As per deliberation N2 at NCR-ICN-ESC-11-1687-2021, HE Valves HE00162, HE00180 and HE00181 have to have their internal surface soften , by production team. This procedure will be applied in all 4 submarines . This NCR is intended to implement these changes in SBR 2. NCR Regress will be created to adress tests Regresion. | Não |  |  |  |  | Valves arealdy removed, work from mechanical team in progress. | The soften of the internal surface of the valves HE00162, HE00180, HE00181 can be extend on the SBR2, SBR3 and SBR4. |  | Matias Lins Maranhão | Matias Lins Maranhão | 153 Dias | Gildas Le Goff | HE | NCR-ICN-REGRESS-12-0071-2021 | YES
NCR-ICN-ESC-12-0571-2021 | 53B | STW | 2021-07-22 19:29 | Nível 2 | COS-SMB-200551 |  | Comissionamento 5.1 | The computer started to have problems as soon as it was available, even without long use. As it will be delivered to the customer in the future, I suggest replacing it. | Não |  |  |  |  | The computer started to have problems as soon as it was available, even without long use. As it will be delivered to the customer in the future, I suggest replacing it. | The computer shall be repaired. Also, this computer will be removed from the use of SBR, because it is very fragile. ICN can continue to use this computer as a tool, removing its name of BB02505 A new computer has been delivered for SBR2 which be name BB02505. ICN to open an NCR MAT to follow the process. |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 129 Dias | Etienne Alexandre Sebastien Rene Berot | BB |  | YES
NCR-ICN-ESC-12-0629-2021 | 53B | MECHANICAL | 2021-09-30 11:29 | Nível 1 | COS-SMB-200731, COS-SMB-200145 |  | Comissionamento 5.1 | KT - FILLING AND DRAINING TANK PRES. REGULAT / AIR INLET SAFETY VALVE During a calibration attempt of pressure regulat. valves (KT02517/P0110250/18DP000D00007; KT02518/P0116321/18DP000D00007) it was identified that it is impossible to calibrate the valve due to internal leakage. During a calibration attempt of safety valves (KT02217/P0130346/18SA000D00017; KT02218/P0116312/18SA000D00017) it was identified that it is impossible to calibrate the valve due to the fact that the safety valve does not close after a pressure drop, closing near 0 bar. | Não |  | Mecânico | Anomalia de Integração | Defeito de estanqueidade | About the pressure regulat. valve (KT02517/KT02518) and pressure safety valve (KT02217/KT02218) it is necessary to change by new one from SBR3 or SBR4 and raise a NCR MAT. | NCR LEVEL 1 |  | Matheus Fernandes da Silva | Matheus Fernandes da Silva | 60 Dias |  | KT |  | NO
NCR-ICN-ESC-12-0666-2021 | 53B | STW | 2021-10-25 13:36 | Nível 2 | COS-SMB-319220, COS-SMB-200255, COS-SMB-321696 |  | Comissionamento 5.1 | Conector of DP24180D (CABLE RUDDER STEERING INDICATIONS SENSOR 3) damaged according to the attached picture. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Forward to Naval Group. | Reconnect the cable DP24180D of the sensor DP14113 according to SMB-EQUIPMENT-P0131513 (wire white on pin1and wire pink on pin6). |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 35 Dias | Etienne Alexandre Sebastien Rene Berot | DP |  | NO
NCR-ICN-ESC-12-0007-2019 | 53B | INTEGRATION EQUIPMENT | 2019-07-26 17:08 |  | COS-SMB-200565 | CTE00954000, CTE00954002 | Comissionamento 6.1 | During inspection D97-02 and D97-05 after tightening the dampers it was found that some dimensions are in disagreement with the design tolerance. See Annex 01 and 02 to D97-02_CTE00954002 and Annex 01 to D97-05_CTE00954000. | Não |  |  |  |  | ICN aligned the rack with the intermediate brackets of TLT 1 and 2, following NG recommendations described in NCR-ICN-UFEM-12-457 / 2019. Comparing the CTE D97-01 and D97-05, it is possible to verify that the intermediate rack brackets is conform. In addition, the remaining racks (TLT 3, 4, 5 and 6) are not aligned with the middle brackets of TLT 1 and 2, showing downward tilting. NG must align the TLT 1 and 2 rack brackets and propose a solution for TLT 3, 4, 5 and 6 racks. Send This NCR to Paul Fosse | Rances will be adjusted during the starting of installation and the setting to works. |  | Silvio Fonseca de Paiva | Osvaldo Luiz de Moura Filho | 856 Dias | Patrick Daliguet |  |  | NO
NCR-ICN-ESC-12-0017-2019 | 53B | ACOUSTIC DISCRETION | 2019-10-14 12:58 | Nível 2 | COS-SMB-200716 | CTE00806561, CTE00806556 | Comissionamento 6.1 | It was not found shock and tilt sensors glued on KD07010 and KD07020. | Não |  |  |  |  | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. Please, Herve DE BACKER "herve.debacker@naval-group.com" and Paul FOSSE "paul.fosse@naval-group.com". | Both equipment were installed and tested onboard (AIS/STW) without any issue. To close. |  | Luisa Kubrusly | Rogerio Milani | 777 Dias | Herve Gerard de Backer | KD |  | NO
NCR-ICN-ESC-12-0119-2020 | 53B | ELETRIC | 2020-08-12 11:57 | Nível 2 | COS-SMB-200551, COS-SMB-200763, COS-SMB-321704, COS-SMB-200549, COS-SMB-200542, COS-SMB-206100, COS-SMB-200716, COS-SMB-200712, COS-SMB-200544, COS-SMB-319755, COS-SMB-319698, COS-SMB-327470, COS-SMB-319721, COS-SMB-319720, COS-SMB-319730, COS-SMB-200526, COS-SMB-200569, COS-SMB-200512, COS-SMB-319750, COS-SMB-206085, COS-SMB-206081, COS-SMB-200426, COS-SMB-319760, COS-SMB-200546, COS-SMB-319693, COS-SMB-319712, COS-SMB-321700, COS-SMB-200511, COS-SMB-319731, COS-SMB-200516, COS-SMB-206140, COS-SMB-200760, COS-SMB-319739, COS-SMB-330822, COS-SMB-206044, COS-SMB-200762, COS-SMB-200538, COS-SMB-319738, COS-SMB-327472, COS-SMB-319724, COS-SMB-321703, COS-SMB-206218, COS-SMB-200160, COS-SMB-200566, COS-SMB-200731, COS-SMB-331623, COS-SMB-319763, COS-SMB-319753, COS-SMB-319711, COS-SMB-206202, COS-SMB-319737, COS-SMB-200710, COS-SMB-330663, COS-SMB-200452, COS-SMB-321696, COS-SMB-319725, COS-SMB-200535, COS-SMB-319700, COS-SMB-319757, COS-SMB-319749, COS-SMB-206096, COS-SMB-200216, COS-SMB-200159, COS-SMB-319759, COS-SMB-206098, COS-SMB-200145, COS-SMB-319726, COS-SMB-337143, COS-SMB-319758, COS-SMB-319734, COS-SMB-206160, COS-SMB-200434, COS-SMB-200718, COS-SMB-200560, COS-SMB-200562, COS-SMB-206210, COS-SMB-319766, COS-SMB-200563, COS-SMB-200217, COS-SMB-200554, COS-SMB-200154, COS-SMB-331624, COS-SMB-200444, COS-SMB-206114, COS-SMB-200565 |  | Comissionamento 6.1 | For the equipment described in "list of products impacted" attached, we found on board the lack of a functional identification plate and (or) voltage and electrical risk label. | Não |  |  |  |  | Send to level 2. | Check and apply if necessary SMB-002443 and SMB-051148 in reference All equipment is delivered with its labels to be put in place by the production. The equipments have a self-adhesive label, replace them with dilophane labels as specified in the BDM. Implement the voltage presence labels. Lights in battery rooms do not need "voltage" labels, because they are ATEX equipment. |  | Geraldo Alves Simoes Filho | Geraldo Alves Simoes Filho | 474 Dias | Stéphane Patrick Philippe Rideau | EG, HG, KT, GS, HL, UA, RM, FC, OO, DA, EJ, UW, BB, BE, EQ, GN, GV, HE, HJ, HP, HQ, KL, KO, RE, RH, UE, UN, UP, BH, EF, ER, EV, HK, RF, RA, DP, GF, RC, KD, RD, KE, FR, DS, DB, FH, KX, DV, DM, EN, EM, DY, UL, BM, BQ, ES, EL, BC, BF, ME, BS, FP, FQ, FG, FV |  | YES |  |  | 2021-06-30 19:57 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0190-2020 | 53B | STW | 2020-10-05 16:56 | Nível 2 | COS-SMB-319760, COS-SMB-206090 |  | Comissionamento 6.1 | During a calibration attempt of RM00116/18DP000D00005 it was identified that it is impossible to calibrate the valve due to internal leakage | Não | [5 empty] | If the pressure reductor RM00116 has an internal leakage is certainly due to some dust. So unmount and inspect it at your workshop, and redo a calibration, if is alway bad, replace it by a new, and do a NCR Mat to order a new one. |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 420 Dias | Paul Fosse | RM |  | NO
NCR-ICN-ESC-12-0196-2020 | 53B | STW | 2020-10-06 18:07 | Nível 2 | COS-SMB-319362 |  | Comissionamento 6.1 | The following HP loudspeakers in SBR2 need to be replaced: HP02522 - SN 120112-12031 HP02525 -SN 120112-12034 CMD 62AE000D00002 | Não |  |  |  |  | replace the equipment | Naval Group suggests to replace both HP lounspeakers and edit a NCR MAT (Note all serial numbers of new and old equipment) |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 418 Dias | Herve Gerard de Backer | HP |  | NO
NCR-ICN-ESC-12-0267-2020 | 53B | STW | 2020-11-12 19:51 | Nível 2 | COS-SMB-200239, COS-SMB-200240, COS-SMB-319326, COS-SMB-319731, COS-SMB-319730, COS-SMB-200560, COS-SMB-200160, COS-SMB-200710 |  | Comissionamento 6.1 | I am sending the attached list of backlogs found on the SBR2 panels. | Não |  |  |  |  | Replace items | All recommendations have been made in the "Produtos" tab |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 381 Dias | Etienne Alexandre Sebastien Rene Berot | BC, BF, BS |  | NO
NCR-ICN-ESC-12-0293-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-26 18:52 | Nível 2 | COS-SMB-319750, COS-SMB-339470 |  | Comissionamento 6.1 | In order to perform the inspections B01 and B02 from UL SBR2, the hull passage (AC32010) was withdrew, as per inspection procedure. In this task, some of the 20 washers DN10 LOCK TAB (35SA000D00008_3002) were damage. A new pack with 20 washers is needed in order to reinstall the Hull Passage for the J6 Cerimony. | Não |  |  |  |  | A new pack with 20 washers (DN10 LOCK TAB 35SA000D00008_3002) is needed in order to reinstall the Hull Passage (AC32010) for the J6 Cerimony. Please proceed with the requesition. | Item dismounted is not AC32010 (welded on hull) but UL00114. To fix UL00114 on AC32010, 20 Tab washers (32VI420D00028) were used as explain PR-5707023. NCR MAT will be raise to launch a new purchase of 20 tab washers 32VI420D00028. |  | Matias Lins Maranhão | Matias Lins Maranhão | 367 Dias | Patrick Daliguet | AC, UL |  | NO |  |  | 2020-12-10 17:47 | Frederic Pavic
NCR-ICN-ESC-12-0384-2021 | 53B | PIPES | 2021-03-18 11:13 | Nível 2 | COS-SMB-206081 |  | Comissionamento 6.1 | According do SMB-002930 latest version "I", BM00175 now requires B01 and B02 inspection but the PTRH was not updated with the new version and there is no inspection file for the B01 and B02 | Não |  |  |  |  | The IM BM00175 is inside the B01 and B02 circuit of valve BM00042 and BM00040. Since the B01_BM00042, B02_BM00042, B02_BM00040 was done on 28/07/2020, 03/08/2020 respectively and there is no PTRH yet, accept as it is for SBR2. For SBR3 and SBR4 the latest revision from PTRH should be updated and the inspections must be done | B02 for BM00175 was asking in the last version of SMB-002930. -Duplicate the B02 of BM00040 with provisory number. action ICN -Update PTRH SMB-005544 to add B02 of NRVs. action NG | The SMB-005544-F will be delivred with COS-SMB-319324-H on batch 39. The corresponding inspections will be added with the update of - COS-SMB-206080 / COS-SMB-206081 for BM00176 and BM00175 - COS-SMB-206082 / COS-SMB-206083 for BM00202 and BM00201. | Renato Trabach da Cunha | Renato Trabach da Cunha | 256 Dias | Patrick Daliguet | BM |  | NO | NO
NCR-ICN-ESC-12-0454-2021 | 53B | STW | 2021-04-29 16:55 | Nível 2 | COS-SMB-200239, COS-SMB-319731 |  | Comissionamento 6.1 | A problem has been identified in the serial coupling of the BC02500 panel, as reported in SBR1's NCR-ICN-ESC-11-1297-2021. The auxiliary power supply U2 for the RXDC Dm1, Dm2 and Dt1 circuit breakers is not correctly wired: - according to Schneider's plans, it must be connected to a 500V bus, during inspection of the panel cabling, it was verified that it is connected to a 1000V bus. This problem extends to the BC02500 panel of the SBR1, SBR2, SBR3 and SBR4. | Não |  |  |  |  | A new cable must be supplied, and installed on the BC02500 panel according to the Scheneider plans. Make adequacy. | As for SBR1, the cabling and connection done by the manufacturer Schneider is wrong, for the supply U2 of DM1, DM2, DT1, leading to a burning of the card if serial coupling is activated. At this time, the cards are OK. Schneider will come to correct the problem of connection. This NCR is being sent to level 3(Back Office specialist) It is mandatory that ICN blocks the serial coupling, in order to prevent another burning of card, until the manufacturer has corrected the problem. | Prohibit the serial coupling of the BC02500 cabinet. The mufacturer (Schneider) will come to correct the wiring of the BC02500. | Paulo Roberto de Souza | Paulo Roberto de Souza | 214 Dias | Thomas Le Corre | BC |  | NO | NO
NCR-ICN-ESC-12-0466-2021 | 53B | MECHANICAL | 2021-05-03 20:31 | Nível 2 | COS-SMB-200273 |  | Comissionamento 6.1 | Scenario: during the construction process (S01, M04, S02, and application in SBR1), several screws and washers of the solenoid valves (of the port hydraulic blocks) were lost: KT00942 / 18BA200D00046; KT00944 / 18BA200D00046; and KT00946 / 18BA200D00046. Solution: please NG, send to us three sets of screws and washers according attached information. | Não |  |  |  |  | Scenario: during the construction process (S01, M04, S02, and application in SBR1), several screws and washers of the solenoid valves (of the port hydraulic blocks) were lost: KT00942 / 18BA200D00046; KT00944 / 18BA200D00046; and KT00946 / 18BA200D00046. Solution: please NG, send to us four sets of screws and washers according attached information. | Please find in the attached file (Reference.pdf), specifications of screws. |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 209 Dias | Herve Gerard de Backer | KT |  | NO
NCR-ICN-ESC-12-0522-2021 | 53B | STW | 2021-06-01 14:29 | Nível 2 | COS-SMB-319737, COS-SMB-200260 |  | Comissionamento 6.1 | Due to the request for additional graphic card tests in the battery plazas made by the Naval Group through the attached e-mails, the REAGENT TUBES FUMIGENE DRAGER CH25301 BOX OF 10 was used. We need this amount to be replenished as soon as possible. NGD: 6660121893182 DESCRIPTION: REAGENT TUBES FUMIGENE DRAGER CH25301 BOX OF 10 | Não |  |  |  |  | Repor material utilizado | Open NCR MAT to buy asap: NGD: 6660121893182 DESCRIPTION: REAGENT TUBES FUMIGENE DRAGER CH25301 BOX OF 10 |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 181 Dias | Etienne Alexandre Sebastien Rene Berot | FH |  | NO
NCR-ICN-ESC-12-0523-2021 | 53B | STW | 2021-06-01 16:50 | Nível 2 | COS-SMB-200239, COS-SMB-319731 |  | Comissionamento 6.1 | This NCR is being created according to the request made by TA NG in the response of RD-08410. During the execution of the inspection test F01_BCZ0082 of SMB-051162_J, measurement errors were found, the values measured during the test are attached. | Não |  |  |  |  | According to the response of RD-08410: Use the pcb UM of the rack DM1: MIQ02013/15-02 (NCR-ICN-ESC-11-1297-2021) to make some test. Send to NG specialist. | Use the pcb UM of the rack DM1: MIQ02013/15-02 (NCR 1297) to make some test and report the result to TA Naval Group. Update 29/09/2021: Put back the original UM pcb and adjust the zero scale and full scale in order to obtain values inside tolerance. Report the new values of adjustment to NG TA. |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 181 Dias | Etienne Alexandre Sebastien Rene Berot | BC |  | NO
NCR-ICN-ESC-12-0554-2021 | 53B | STW | 2021-06-30 16:08 | Nível 1 | COS-SMB-200712 |  | Comissionamento 6.1 | During the leak test (S02 PTRH) on the pneumatic lines, some leakage was identified. Some connections were opened to check the presence of o'rings and rush seal. On the air distribution panel (KT00528/P0129485/10AC000D00006) it was verified the absence of o'rings and rush seal on some connections. Solution: Put the rush seal on the connections and the o'rings on the niples: 1) 03 units of ruch seals: 44JO312D00002; 2) 09 units of o-rings: 44JO110D00009. | Não |  |  |  |  | During the leak test (S02 PTRH) on the pneumatic lines, some leakage was identified. Some connections were opened to check the presence of o'rings and rush seal. On the air distribution panel (KT00528/P0129485/10AC000D00006) it was verified the absence of o'rings and rush seal on some connections. Solution: Put the rush seal on the connections and the o'rings on the niples: 1) 03 units of ruch seals: 44JO312D00002; 2) 09 units of o-rings: 44JO110D00009. | NCR LEVEL 1 |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 152 Dias |  | KT |  | NO
NCR-ICN-ESC-12-0556-2021 | 53B | PIPES | 2021-07-02 15:38 | Nível 2 | COS-SMB-206184 |  | Comissionamento 6.1 | Valves HE00180 and HE00181 were installed a bord Inverted, flow direction was inverted. Since we had to remove the valves to be machined, the valves are now in the correct direction, but the holes for the support screws are in a wrong position We have already faced a similar problem in SBR 1 whith valve HE00162, as per NCR-ICN-ESC-11-0473-2019. | Não |  |  |  |  | Repair Valve Support, in order to be able to fix the valve in its support. | Decision made in FTG-9491 |  | Matias Lins Maranhão | Matias Lins Maranhão | 150 Dias |  | HE |  | NO
NCR-ICN-ESC-12-0564-2021 | 53B | STW | 2021-07-14 13:23 | Nível 2 | COS-SMB-319724, COS-SMB-319334 |  | Comissionamento 6.1 | Filter EL00012 (18FL200D00001) ​missing pressure differential device, see the attached picture. | Não |  |  |  |  | Check the possibility of installing another pressure differential device from other SBR and open a NCR-MAT to request a new device. | To canibalize on SBR4 a clugging indicator (Rep 6 on SBR-ETM-00000M0011 rev.C page 236/636) for fillter EL00012 (18FL200D00001) To create a NCR MAT to provide a new item. |  | Rodrigo Lino Castro | Rodrigo Lino Castro | 138 Dias | Gerard Landure | EL |  | NO
NCR-ICN-ESC-12-0587-2021 | 53B | STW | 2021-08-20 18:55 | Nível 1 | COS-SMB-200273, COS-SMB-200731, COS-SMB-200145 |  | Comissionamento 6.1 | KT - material absence To perform pressure tests on the KT system air lines, some line adjustments need to be performed such as: installing rush seals, screws, o-rings. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Putting sealing gasket and fixing the equipments. | NCR LEVEL 1 |  | Bruno Correa Ferreira | Matheus Fernandes da Silva | 100 Dias |  | KT |  | NO
NCR-ICN-ESC-12-0639-2021 | 53B | STW | 2021-10-05 12:54 | Nível 1 | COS-SMB-200145 |  | Comissionamento 6.1 | KT - pressure gauge During the pre-test on the KT system, it was verified that the pressure gauges KT11048P / P0115743 / 50MD200D00034 and KT11148P / P0115745 / 50MD200D00037 were lost. | Não |  | Tubulação | Anomalia de Aprovisionamento Logístico | Entrega perdida, mau assinada | It is necessary to put another one. | NCR LEVEL 1 |  | Matheus Fernandes da Silva | Matheus Fernandes da Silva | 55 Dias |  | KT |  | NO
NCR-ICN-ESC-12-0646-2021 | 53B | PRESERVATION | 2021-10-08 14:49 | Nível 2 | COS-SMB-200546 |  | Comissionamento 6.1 | The acrilic visor of CESM cabinet on SBR2 - 62ER000D00184 - RA00011 - P0119505 - was broken during the constructive process. See the photo attached. It is necessary to replace this visor | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | need new acrilic visor to repair | -Take a glass from SBR 3 or 4 -Issue a NCR MAT for replenishment -Apply TAF-2015-0582 and TAF-2017-0827 for material and equipment protection. |  | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 52 Dias | Franck Heidel | RA |  | YES
NCR-ICN-ESC-12-0657-2021 | 53B | GENERAL | 2021-10-15 14:34 | Nível 2 | COS-SMB-319352, COS-SMB-206058 |  | Comissionamento 6.1 | Follow the same did at NCR-ICN-ESC-11-1264-2020: "As discussed with Frédéric Guevel, it would be interesting and necessary to intervention in the drains FA22004, FA22005, FA22006, FA22007, which receive oily water from the DAR, due to the accumulation of dirt in the FA50097A junction line. One idea would be to place a protective drain screen type. | Não |  | Tubulação | Anomalia de Aplicação | Modo operatório errado | Proceed as the same in SBR1. | performed the FTG-9312. It's the same thing of SBR1 (NCR-ICN-ESC-11-1264-2020) |  | Luiz Felipe Silva Moreira | Luiz Felipe Silva Moreira | 45 Dias | Frederic Guevel | FA | NCR-ICN-ESC-11-1264/2020 | YES
NCR-ICN-ESC-12-0665-2021 | 53B | STW | 2021-10-25 11:58 | Nível 2 | COS-SMB-321784, COS-SMB-206056 |  | Comissionamento 6.1 | Valve opening indication is damaged. See attached ES00020 ES00041 ES00042 ES00043 ES00044 | Não |  | Tubulação | Outras Anomalias | Vários defeitos | Replace the Handwheel. | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 35 Dias | Gildas Le Goff | ES |  | NO
NCR-ICN-ESC-12-0013-2019 | 53B | INTEGRATION EQUIPMENT | 2019-09-11 12:07 | Nível 2 | COS-SMB-319356 |  | CQ 7.1 | The instrument FV11710T of SBR2 was reproved in calibration. Apresented values out criteriou acceptable. | Não |  |  |  |  | Send next step. | check availability on another SBR if available, do an NCR-MAT to take-it or, send in level 3 for supply |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 810 Dias | Stéphane Patrick Philippe Rideau | FV |  | NO |  |  | 2020-03-20 12:03 | Frederic Pavic
NCR-ICN-UFEM-12-0456-2019 | 53B | MECHANICAL | 2019-08-06 03:00 |  | COS-SMB-200511 |  | CQ 7.1 | Lacking the supply of shim's rolled for adjustment of the angle of the Fhari tank connection with the pipe. items 11 and 12; | Não |  |  |  |  | FOR ALIGNMENTNT BETWEEN ADAPTER P4146263 (18RO230D00149) AND DT50199R LINE USE CMD 32FI301D00003 BRASS LAMINATED PEELABLE OD41.5-PS100 54X65X ADJUSTEMENT. | Agree with FTG-7670. Decision: Apply FTG-7670. | N/A | System |  | 846 Dias |  |  |  | NO | NO
NCR-ICN-ESC-12-0087-2020 | 53B | PIPES | 2020-06-25 16:51 | Nível 2 | COS-SMB-206190, COS-SMB-321793, COS-SMB-206188 |  | CQ 7.1 | During the manufacturing of blason for P4168509 it was identified an incoherence between the isometric drawing and the real condition of pipe P4168509. ICN resquest NG for repair orientation. | Não |  |  |  |  | ICN resquest NG for repair orientation. | Manufacture a dummy (in steel) of the pipe P4168509 according to requirement on board SBR2. Then, achieve in the work shop a "blason" following the steel dummy of P4168509. Fit the inconel pipe delivered by Naval-Group, on this "blason" and then modify, ajust the inconel pipe according to the dimensions of the "blason". Record in a follow up file all the modifications carried out on the pipe as cut, bevelling, welding, addition of a new straight part in inco (tracability)..... in order to complete the compliant file of this modified pipe. | A Naval Group Pipefitter and welder have reworked the pipe P4168509 / BQ50016E5. Please update the traceability file of this pipe. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 522 Dias | Alain Lamy | BQ |  | NO | YES
NCR-ICN-ESC-12-0145-2020 | 53B | ELETRIC | 2020-08-31 17:59 | Nível 2 | COS-SMB-319731 |  | CQ 7.1 | The base of circuit breaker DA01 from equipment BF02505 was damaged. | Não |  |  |  |  | Exchange the broken item. NG inform the CMx | FO decided temporary to glue 2 blind rivet nuts (tubtara) diameter 4. We machined the 2 screws in order to tight the circuit breaker on the base See the attached photos of the job The base should be replaced by OEM or ICN during the RANAE Open NCR MAT to buy 2 new screws and a new base breaker: SCHNEIDER ELECTRIC BASE NS630 3P Manufacturer Ref: 2988502 §6.4 | The following items are Ordered and will be sent to the ICN for repair: - 1x NSX630 LV432516 circuit breaker base (NGD 5925930231348) - 2x M5x85 screws | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 454 Dias | Etienne Alexandre Sebastien Rene Berot | BF |  | NO | NO
NCR-ICN-ESC-12-0254-2020 | 53B | MECHANICAL | 2020-11-04 16:31 | Nível 2 | COS-SMB-330663 |  | CQ 7.1 | Due the damage of the Hatch EQ00043 (P0120353) o’ring, ICN asks the NG authorization to use the o’ring belonging of the CMD 44JO312D00010 (RUCH SEAL PLAIN OD57) joint, in replacement of the CMD 44JO110D00540 (O-RING 56,52X5,33-20A8-GN), which we do not have in the warehouse, since the shelflife has expired. | Não |  |  |  |  | The o’ring CMD 44JO110D00540 (O-RING 56,52X5,33-20A8-GN), belonging of the CMD 44JO312D00010 (RUCH SEAL PLAIN OD57) was used in the mounting of the Hatch EQ00043. The Hatch was already tested in the hyperbaric chamber and the tests were approved. Raise a NCR MAT to supply new item. | A item for mounting EQ00043 is a O-RING 56,52X5,33-20A8-GN CMD:44JO110D00540 -A item of RUCH gasket OD57 is the same O-ring 56,52X5,33-20A8-GN NNO:5331143135502 -If the the validity date of the gasket is not expired it's possible to use the O-ring of RUCH gasket insted of CMD:44JO110D00540. (Patrcik Daliguet) | The traceability reference of the panel is missing in accordance to use O Ring NN0 5331143135502 This information have to be indicated in the traceability folder of the panel D BERNEDE | Rodrigo Moraes Pereira | Osvaldo Luiz de Moura Filho | 389 Dias | Patrick Daliguet | EQ |  | NO | NO
NCR-ICN-ESC-12-0249-2020 | 53B | PIPES | 2020-11-04 12:08 | Nível 2 | COS-SMB-206065 |  | CQ 7.1 | After manufacturing inspection of some spools, it was not possible to check the batch and serial number of the products. | Não |  |  |  |  | Remanufactured. As aligned with Vladimir Gianotti and Robson Andrade the tubes will be remanufactured. | Do not re-manufacture a new pipe but keep the same pipe. This pipe diameter is only used on the DB system. -So just retrieve the batch number -Fill in the N01 -Fill in the M03 -Engrave the corresponding mark on the pipe |  | Emanuela Lucia Justino dos Santos | Franciellen da Silva Braga | 390 Dias | Franck Rubis | DB |  | NO
NCR-ICN-ESC-12-0210-2020 | 53B | MECHANICAL | 2020-10-16 11:36 | Nível 2 | COS-SMB-319093 |  | CQ 7.1 | According NCR-ICN-UFEM-12-292/2018, the upper platform is out of the tolerance specified in drawing SMB-600513_A, It was not possible to perform the assembly and welding according to the inspection performed. | Não |  |  |  |  | Agree with 1.2. Replace the Upper Platform of DSRV from SBR 2 to be installed on SBR 3. A new analisys will be done to verify the possibility of use the platform of SBR 2 in another SBR. | Repair, Use the DSRV plateform of SBR3 on SBR2. Change the tracability documents Open the same NCR for SBR3. a new analysis must be done to correct the plateform. |  | Renato da Silva Goncalves | Joao Paulo Schneider Gonzaga | 409 Dias | Hugues Bourget |  | NCR-ICN-UFEM-12-292/2018 | NO
NCR-ICN-ESC-12-0264-2020 | 53B | ELETRIC | 2020-11-11 17:44 | Nível 2 | COS-SMB-319737 |  | CQ 7.1 | Equipment damaged in the production process. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Take an NGD 49AU100D00074 on SBR4, if available Open an NCR-MAT to supply a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 382 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO |  |  | 2020-12-16 19:05 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0282-2020 | 53B | ELETRIC | 2020-11-19 14:31 | Nível 2 | COS-SMB-200226 |  | CQ 7.1 | Equipment damaged in the production process. | Não |  |  |  |  | USE THE SBR4 GF02504 LUMINAIRE, IF APPROVED BY THE NAVAL GROUP. | Take on sbr 4 the light GF02504 (cmx 48ES300D00098) Open the the defective light at workshop for investigation and put the report in the NCR Open NCR MAT for the defective part after investigation. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 375 Dias | Etienne Alexandre Sebastien Rene Berot | GF |  | NO
NCR-ICN-ESC-12-0323-2021 | 53B | INTEGRATION EQUIPMENT | 2021-01-22 12:12 | Nível 2 | COS-SMB-319718, COS-SMB-319719, COS-SMB-206056, COS-SMB-319604 |  | CQ 7.1 | ICN production cannot alignment the hydraulic motor pump in the aft capstan shaft. The misalignment could be in the sleeve. In annex Impacted products. | Não |  |  |  |  | Repair according to soluction 1. See coments annex 1. | After analysis, The cabestan will be deslocalized about 32mm, ( see annex CROQUIS), Naval-group/TA purpose to re-install a new AC32042. Must be send to level 3 for decision | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Vinicius Siqueira dos Santos | Ernanes de Souza | 311 Dias | Hugues Bourget | EX |  | NO | NO
NCR-ICN-ESC-12-0373-2021 | 53B | PIPES | 2021-03-12 13:30 | Nível 2 | COS-SMB-321803 |  | CQ 7.1 | According to COR-2021-900343 item 3.12 there is a misalignment in BM21031 higher than 2mm. | Não |  |  |  |  | NG, please advise us how to proceed. | 1/Assembly BM21031 in accordance compliance with assembly rules for the compensating sleeve double wave ND100----> SMB-030510 E 2/Screw mounting of the valves BM : P0134229 P0154923 P0134228 P0136127 P0154920 P0154922 P0136088 in accordance with the part-list : threaded rod 16x160 cl 8.8 CMD 32VI210D00231 REWORK |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 262 Dias | Franck Rubis | BM |  | NO
NCR-ICN-UFEM-12-0544-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-30 13:57 | Nível 2 | COS-SMB-330724, COS-SMB-330662 |  | CQ 7.1 | During assembly of the Hatch AG00017 in workshop some deviations were found: 1. After adjustment of the recess for lock of Threaded Ring (MAT424-1051_Ref. 1) according NCR-MAT-001395-2021, the dimensions are out of tolerance of the drawing MAT424-0896. See report in ANNEX 1; 2. The thread length of the pin (MAT424-1051_Ref. 84) is short. The nut does not attend the acceptance criteria with a minimum of 2 threads protruding. See dimensional report in ANNEX 2 and photos in ANNEX 3; 3. The machining overlength of the Stopper (MAT424-1052_Ref. 45) is not enough with the Hatch in unlocked position. See ANNEX 4. | Não |  |  |  |  | Rework. See comments and solution in attachment "2.1 ICN SOLUTION". Send to TA Patrick Daliguet to analysis. | Agree with proposal in annex: 2.1 ICN SOLUTION - NCR-ICN-UFEM-12-0544-2021 | In accordance with level 2.2 : 1- Recess for lock (Rep.1) --> ACCEPT AS IS under conditions. Potential bad working / blocking of safety lock (Rep.23). Proposition of Accept as is of Rep.1 with adding a checking phase of complete safety latch adjustment --> If the gap between the 2 parts is consistent with the initial gap, Accept as is also for Rep.23 --> If not, re-manufacturing of Rep.23 with engraving the NCR number on this specific part and picture + dimensional report and certificate of conformity of the part to be joined to the NCR. 2- Gear shaft (pin) and 3- Stopper --> REWORK Re-manufacture the parts according to ICN proposal in annex. Engrave the NCR number on a non-functional area. Dimensional report and certificate of conformity of the part to be joined to the NCR. | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 244 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0524-2021 | 53B | ELETRIC | 2021-06-01 17:11 | Nível 2 | COS-SMB-206100, COS-SMB-206081 |  | CQ 7.1 | During routine verification on board, the EG00236 and EG01165 equipment was found, with its broken connection bases. | Não |  |  |  |  | To replace | Due of no protection, the connectors on both were damaged. Change the 2 electric actuators. Take on SBR4 and protect the pins of connectors. Open NCR MAT to refund the actuators. |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 180 Dias | Etienne Alexandre Sebastien Rene Berot | EG |  | NO
NCR-ICN-ESC-12-0557-2021 | 53B | ELETRIC | 2021-07-06 14:15 | Nível 2 | COS-SMB-338802 |  | CQ 7.1 | After performing the C121 trim tank calibration test, it was identified that the DJ12513N sensor does not satisfactorily stabilize to maintain the tank volume shown on the DSC. | Não |  |  |  |  | It is necessary to remove the sensor to perform a new calibration. Replace it with one already calibrated. | In accord with ICN for replace sensor SBR1 with a new sensor (warehouse) Do a Recalibration sensor SBR1 If the sensor sbr1 after recalibration is not satisfaction replace the sensor Open NCR regress |  | Rafael Thome da Silva | Rafael Thome da Silva | 146 Dias | Frederic Guevel | DJ |  | NO
NCR-ICN-ESC-12-0563-2021 | 53B | STW | 2021-07-12 17:53 | Nível 2 | COS-SMB-200241, COS-SMB-206090 |  | CQ 7.1 | During a calibration attempt of DY00304/18DP000D00007 it was identified that it is impossible to calibrate the valve due to internal leakage | Não |  |  |  |  | Change with a new one fro storage or SBR4 | The leak rate is about 2bar/minute To canibalize a 250-45 bar air pressure reducing valve 18DP000D00007 on SBR4 To initiate a NCR MAT |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 139 Dias | Gerard Landure | DY |  | NO
NCR-ICN-ESC-12-0620-2021 | 53B | ELETRIC | 2021-09-21 19:00 | Nível 2 | COS-SMB-200496, COS-SMB-CAB-HD-KD |  | CQ 7.1 | HJ62532R cable connector belonging to the HJ 02506 equipment was lost during the construction process. | Não |  |  |  |  | The requested information is in the attachment TRATATIVA_NCR-ICN-ESC-12-0620-2021. | Use connector from SBR4 if available Open a NCR-MAT to supply a new one connector D38999 / 26 FB 35 SN |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 68 Dias | Stéphane Patrick Philippe Rideau | HJ |  | NO |  | Informações incorretas ou imprecisas | 2021-09-28 17:26 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0635-2021 | 53B | PRESERVATION | 2021-10-04 14:32 | Nível 2 | COS-SMB-319711 |  | CQ 7.1 | "The Preservation team, in agreement with the Quality team, opted to open this NCR (processed by the NCR-CQ system) to replace the NCR-ICN-Preserv-083/2020 (which was being processed physically). Please see the original NCR attached." Regarding MT02 task described in PHST SMB-322714, when oil is pumped inside the Diesel Generator Rectifier it leaks though the connection showed on the photos attached. The pipe was bended and the joint unplugged | Não |  | Mecânico | Anomalia de Integração | Defeito de estanqueidade | ICN Preservation Team requests NG orientation on how to proceed to fix the issue. | To repair this part I suggest one intervention of MTU (Laurent J. C. - 23/09/2020) | MTU GERMANY will be consulted first, because the engine is still under warranty until 04/15/2021. Kindly make a more precise photos report on the degraded area to optimize MTU's future intervention. (EUSTACHE.J - 18/12/2020 LST TEAM MEMBER) | Rafael Tavares do Rego Macedo | Luiz Felipe Silva Moreira | 56 Dias | Jean Christophe Laurent | BD |  | NO | NO
NCR-ICN-ESC-12-0678-2021 | 53B | ELETRIC | 2021-11-03 19:25 | Nível 2 | COS-SMB-200542 |  | CQ 7.1 | During the DJ system transfer test, it was identified that the DJ10007 equipment does not mark the transferred water flow correctly. The value indicated on the panel is much higher than the real one. All settings were made as per procedure SMB-005853_D and the problem was not remedied. A new panel was tested and it worked correctly. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | O equipamento deve ser substituído por outro novo. | Standard exchange of the panel DJ10007 is required Open NCR MAT to purchase a new one. |  | Rafael Thome da Silva | Rafael Thome da Silva | 25 Dias | Etienne Alexandre Sebastien Rene Berot | DJ |  | NO
NCR-ICN-ESC-12-0122-2020 | 53B | ELETRIC | 2020-08-12 19:16 | Nível 2 | COS-SMB-319731, COS-SMB-319750, COS-SMB-200544, COS-SMB-200526, COS-SMB-200716 |  | DA 3.2 | The fiber optic connector provided on the equipment’s OO02530, OO02531, OO02532, OO02533, OO02534, OO02536, OO02500, BD02527, BD02528 is not compatible for cables CMD 11LS215D00012 that are provided on project. | Não |  |  |  |  | NG should define the correct conector (NGD) | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 473 Dias | Serge Meyer | OO |  | NO |  |  | 2020-10-08 13:08 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0194-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-06 17:04 | Nível 2 | COS-SMB-330725, COS-SMB-330663 |  | DA 3.2 | The length (35mm) of the pin axis (rep:13) is not in accordance with the width of hatch cover part (36mm). A lenth of 50mm will be adapted: 36mm + thickness of washer + hole of pin Ø3,2mm | Não |  |  |  |  | Send to NG. | Manufacture 2 new pins with length below head 50mm from material bar delivered by NG. The conformity file of the panel will be updated The design will be updated by NG. GIR comments 24/03/2021: The part list of BDM-00026679 should be updated in order to put the dimension of the axis (item 13) at 50 mm. Send to the back office to take the modification into account in AG00013 concernant documents. | Agree with the modification in paragraph 2.2, rework. | Vinicius Siqueira dos Santos | Osvaldo Luiz de Moura Filho | 418 Dias | Patrick Daliguet | AG |  | NO | NO
NCR-ICN-ESC-12-0204-2020 | 53B | MACHINING | 2020-10-13 16:46 | Nível 2 | COS-SMB-207763 | CTE00964995 | DA 3.2 | During the inspection D59-06 (CHECK THE THICKNESSES OF THE BUTT STRAP FLAT STRIPS AFTER ADJUSTMENT). Was detected two points of measures below the acceptance criteria. See CTE attached. | Não |  |  |  |  | Accept as it is. Send to Level 2 and DA to validate. | ACCEPT AS IT IS Accept as it is . use a machining shim on the longitudinal flat bar to correct the deviation.( see photo in annex). to be confirmed by L3 | The thicknesses noted at the level of the holes in the edge plate do not affect the structural strength at this stage, however particular attention must be paid to monitoring the thicknesses of the edge plate during the life of SBR2. BUT - standardize the material used for the shims - take a clearance record after placing the shims. - if the shims cannot be of unique geometry, they must be marked to ensure the geographical traceability of these shims. The marking must be proposed to the BO. Repair actions are the responsibility of ICN (through the NCR) but also assigned to the Front Office to guarantee their completion and return to the Back Office. Attention: Following decision L3, a follow-up, checks and documents will be sent to the BO at the end of the work. | Joanei Vieira de Sa | Ernanes de Souza | 412 Dias | Hugues Bourget |  |  | NO | NO |  | 2020-12-17 14:53 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0228-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-23 13:35 | Nível 2 | COS-SMB-330663, COS-SMB-330662 |  | DA 3.2 | During the assembly of AG00016 and AG00013 it was discover the same problem: axes too short. | Não |  |  |  |  | Manufacture new pin axis with Ø12x50 mm in CuAL10Ni5Fe4 according porposed by TA Patrick Daliguet. | -In accordance with level 2.1: Manufacture new pin axis with Ø12 lenght below head:50 mm (Total lenght:53mm) in CuAL10Ni5Fe4 -The disign will be updated by NG ( Patrick Daliguet) GIR comments 24/03/2021: Update part list BDM-00021867 of door AG00016 to put the axis marked 13 at 50mm. Sending to the BO for taking into account this modification of BDM-00021867. | Agree with the modification in paragraph 2.2, rework. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 402 Dias | Patrick Daliguet | AG |  | NO | NO
NCR-ICN-ESC-12-0429-2021 | 53B | TRACEABILITY | 2021-03-31 13:02 | Nível 2 | COS-SMB-319719, COS-SMB-339470, COS-SMB-200763, COS-SMB-321710, COS-SMB-CAB-UA-UW, COS-SMB-330663, COS-SMB-331842, COS-SMB-200712, COS-SMB-200569, COS-SMB-321709, COS-SMB-206184 |  | DA 3.2 | It was identified problems related to Certificate of Conformity requested for the inspection B05 (discribed in the SMB-002930). Each problem found is indicated in the file annexed. | Não |  |  |  |  | ICN request the modification on the Certificate of Conformity documents informed in the Annex, as well as the dispatch for those that were not received before. | update and provide the missing informations To be treat by NG BO |  | Rodolfo Alves de Abreu | Rodolfo Alves de Abreu | 243 Dias |  | AC |  | NO |  |  | 2021-04-07 18:01 | Frederic Pavic
NCR-ICN-ESC-12-0450-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-28 16:29 | Nível 2 | COS-SMB-319718 |  | DA 3.2 | During installation of BQ00006 the fixing screw (stuck) locking inside the thread, being necessary to destroy it for its removal. During the assembly and disassembly of the 53B-BQ00006 valve, the hole and the guide pins for fixing it were damaged. | Não |  |  |  |  | Remove the damaged screw, clean and treat the internal thread of the valve. reassemble install a new screw CMx 32VI110D00167 - SCREW H M39X100X100 CL12.9 FLZN. Repair the drilling, remove the valve and shims for the workshop, machine the valve and shims together to a new diameter and fabricate new guide pins. See annex 1 - damaged materials. | 'Physical on board: -The mounting is conform to the COS-SMB-319718 rev C (Screws X05T / nuts A4-80 / washers NL stainless steel) instead of COS-SMB-319718 rev D (srews CL12.9 / nuts CL12 / washers NL steel). -Due to the lack of stock of screw X05T it was mounted one srew CL12.9 -Due to the modification of the positioning of the valves, holes of pins are not in line and it's necessary to increase the diameter (initially Ø16). Inconsistencies: - The COS-SMB-319718 rev D specify the using of Nord Lock washers in steel (32VI410D00138 STEEL WASHER N-L ND39 DELTA-PROTEKT) but the mounting drawing SBH.2D30.SAD.005739_L F15 specify stainless steel plain washers. - The COS to manufacture seating COS-SMB-319547 rev C / drawing SBH.2D30.SMD.005740_I F22 specify the manufacturing of centering pins Ø16 (items 27-28-29-30 des carlingages BQ00005C / P4165388 et BQ00006C / P4165387) in steel S355 (01BA110D00142 S355J2 STEEL GRADE CIRCULAR BAR DIA 18MM) but the mounting drawing SBH.2D30.SAD.005739_L F15 specify centering pins Ø16 in stainless steel. Action NG: - Inform which material it's necessary to use (bolting and pin) and confirm torque value on SMB-327319 B - Inform the possibility to increase diameter of centering pins (Ø18 maximum). - Update document to remove inconsistencies Action ICN: -The mounting of SBR1 have to be verified to identify the material of bolting. - Manufacture one screw with X05T to change the screw in 12.9 (with Nord-Lock washers) - ICN have to provide positionning before and after machining holes of pins of BQ valve with dimensions of pins already manufactured and material. - Raise NCR for BQ00005 to follow the same physical mounting and inconsistencies |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 215 Dias | Patrick Daliguet | BQ |  | NO |  |  | 2021-05-31 11:40 | Patrick Daliguet
NCR-ICN-ESC-12-0455-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-29 18:02 | Nível 2 | COS-SMB-319719 |  | DA 3.2 | After the NCR-ICN-ESC-12-0015-2019 that asked severals mobile parts disassembled that AC41016 was mounted but the B11 was lost, so it's necessary completely dismount the mobile and mount again with the properly inspections CTE filled. However the ICN warehouse doesn't have the nut retainer that is used in the assembly, because is supplied together the mobile wich was already used. So now it's needed manufacture the new nut retainer in ICN workshop cause the AC41016 is so important to do the DY test that is critical path for the submarine construction and now is the only thing pending. Before mounting ICN team will presente the fabrication to NG-TA, and the process of fabrication will follow the MAT425-0513_N last version currently, respecting, even, the material especifications . And new gasket it's also necessery. | Não |  |  |  |  | P0151172- AC41016-17/001 - The nut retainer need to be manufacturing in ICN workshop cause there's not in warehouse, using the MAT425-0513_N, even, with the same material. And a new gasket also need to be used in the AC41016 remounting. Ensure that the inspections CTEs will be correctly filled and the B01/B02 retest has be carry out again. The materials certificates were attached. | Agree with proposal. NCR REGRESS should be raise to carry out inspections and pressure tests. B05 should be updated. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 213 Dias | Patrick Daliguet | AC |  | NO |  | Informações incorretas ou imprecisas | 2021-09-13 11:50 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0488-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-13 12:28 | Nível 2 | COS-SMB-319712 |  | DA 3.2 | During the 12-PTRH-BM-B01_BM00042 test happen a leak between the flanges of the valve BM00040 and the BM00042. After dismounting we believed that would be needed just remounting using new fiber gasket and lock washers as in NCR-ICN-ESC-12-0469-2021, but we also discovered, during the new F06, that the HALAR coating is damaged. This matter is related to hull integrity in AC32005. | Não |  |  |  |  | The BM00042 valve that was mounted in SBR2 was 18SC011D00141-SN.016(ISSARTEL) but because of this coating problem it was dismounted and returned to the warehouse. And, to solve the problem, it will be used the BM00032-SN.021(MICROMASSA) of the SBR3 that will be mounted in SBR2-BM00042 place. It will already be applicated the OM-118711/SMB-TDP-PR-6650723 to use the new hydraulic actuator CMD: 14VE200D00034 and 2 new units of the O-ring 16.90x2.70 20A8 CMD: 44JO110D00009. The procedure is SMB-371504 and it's needed doing a workshop test M09 and after new F06, B06, B07,B01 and B02. | Agree with proposal. A NCR MAT will be raise to follow the repairing of the valve A NCR REGRESS will be raise to carry out inspections and tests |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 200 Dias | Patrick Daliguet | BM |  | NO
NCR-ICN-UFEM-12-0547-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-25 18:59 | Nível 2 | COS-SMB-330724 |  | DA 3.2 | The dimensions of BORFLEX Lip Seal (NGD 5330930186238 / CMD 44JO320D00002) are out tolerances. See report attached as requested by TA-NG. IM: AG00017. | Não |  |  |  |  | 1. The BORFLEX lips seal is out of tolerance and manufactured according MAT424-1296_A. See ANNEX 1; 2. The BORFLEX cannot be installed in the hatch as per ANNEX 2; 3. Continue the hatch assembly with non-conform SMAC lip seal; 4. Check the good assembly of the seal and perform the Resistance Test at PEH (70 bar) in the Hyperbaric Chamber; 5. Open a NCR-MAT to supply new parts; 6. During onboard integration phase replace the SMAC lip seal by a new seal manufactured according MAT424-1296_B. Check the dimensions before mounting; 7. The Leak Test (PEE) will be validate after vacuum test of the submarine; 8. The non-conform seals must be scrapped. | The lip seal is out of tolerance on the external diameter not conform to MAT424-1296 B |  | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 187 Dias | Patrick Daliguet | AG |  | NO |  | Informações incorretas ou imprecisas | 2021-09-02 12:58 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0515-2021 | 53B | TRACEABILITY | 2021-05-27 13:15 | Nível 2 | COS-SMB-331842, COS-SMB-321710, COS-SMB-CAB-DA-DY, COS-SMB-331842, COS-SMB-CAB-EF-EZ, COS-SMB-CAB-OO-RM, COS-SMB-339470, COS-SMB-321710, COS-SMB-CAB-BE-BH, COS-SMB-CAB-HD-KD, COS-SMB-CAB-UA-UW, COS-SMB-CAB-FC-GV, COS-SMB-200469 |  | DA 3.2 | It was identified problems related to Certificate of Conformity requested for the inspection B05 (discribed in the SMB-002930). Each problem found is indicated in the file annexed. This NCR add other items not previously mentioned in the NCR-ICN-ESC-12-0429-2021. However, the problem is the same mentioned in that NCR. | Não |  |  |  |  | ICN request the modification on the Certificate of Conformity documents informed in the Annex, as well as the dispatch for those that were not received before. | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  | Rodolfo Alves de Abreu | Rodolfo Alves de Abreu | 186 Dias | Patrick Daliguet | AC | NCR-ICN-ESC-12-0429-2021 | NO
NCR-ICN-ESC-12-0527-2021 | 53B | INTEGRATION EQUIPMENT | 2021-06-02 20:22 | Nível 2 | COS-SMB-330725, COS-SMB-330663 |  | DA 3.2 | Items 5, 8, 70 and 71 were removed from the hatch from SBR2 to SBR1 as per NCR-ICN-ESC-11-1400-2021. Request to change the items mentioned for SBR2 is required. | Não |  |  |  |  | For 53B-AG00013 hatch - P0145898 - CMD 01PE200D00049, carry out supply new materials as annex 1. Open NCR MAT. | Agree with proposal. A NCR MAT will be raise to order new parts The traceability folder of the panel will be updated |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 179 Dias | Patrick Daliguet | AG | NCR-ICN-ESC-11-1400-2021 | NO
NCR-ICN-ESC-12-0535-2021 | 53B | PIPES | 2021-06-11 18:58 | Nível 2 | COS-SMB-200470 |  | DA 3.2 | The valve DV00063-P0107802 (01PM300D00007-SN.17/012-ISSARTEL) was difinitely mounted following the SBR-ETM-00000M0007 and the finals tests S02_DVZ0004/B02_DV00063 was carried out. But the inspection B11.27 (CTE01040298) was not filled. This matter is related to hull integrity in AC34005. | Não |  |  |  |  | Dismount the valve DV00063-P0107802 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040298/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0004/B02_DV00063 tests and a NCR-MAT to replace the material (o-ring). | Agree with proposal. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 170 Dias | Patrick Daliguet | DV | NCR-ICN-REGRESS-12-0066-2021 | NO
NCR-ICN-ESC-12-0536-2021 | 53B | PIPES | 2021-06-11 19:02 | Nível 2 | COS-SMB-200470 |  | DA 3.2 | The valve DV00044-P0107805 (01PM300D00007-SN.17/014-ISSARTEL) was difinitely mounted following the SBR-ETM-00000M0007 and the finals tests S02_DVZ0005/B02_DV00044 was carried out. But the inspection B11.27 (CTE01040297) was not filled. This matter is related to hull integrity in AC34006. | Não |  |  |  |  | Dismount the valve DV00044-P0107805 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040297/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0005/B02_DV00044 tests and a NCR-MAT to replace the material (o-ring). | Agree with proposal. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 170 Dias | Patrick Daliguet | DV | NCR-ICN-REGRESS-12-0067-2021 | NO
NCR-ICN-ESC-12-0537-2021 | 53B | PIPES | 2021-06-11 19:05 | Nível 2 | COS-SMB-200470 |  | DA 3.2 | The valve DV00054-P0107804 (01PM300D00007-SN.17/013-ISSARTEL) was difinitely mounted following the SBR-ETM-00000M0007 and the finals tests S02_DVZ0005/B02_DV00054 was carried out. But the inspection B11.27 (CTE01040295) was not filled. This matter is related to hull integrity in AC34007. | Não |  |  |  |  | Dismount the valve DV00054-P0107804 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040295/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0005/B02_DV00054 tests and a NCR-MAT to replace the material (o-ring). | Agree with proposal. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 170 Dias | Patrick Daliguet | DV | NCR-ICN-REGRESS-12-0068-2021 | NO
NCR-ICN-ESC-12-0552-2021 | 53B | INTEGRATION EQUIPMENT | 2021-06-29 13:50 | Nível 2 | COS-SMB-331842 |  | DA 3.2 | The correct orientation of the mobile AC41019-P0151127 (01PM100D00052-6227186-2015-01) was done as asked in the NCR-ICN-ESC-12-0269-2020 and used the version B of the construction book DEI-331842-80500-12-001 and SBH.1D10.IMZ.006927 (sheet F04) that guide numbers 07 and 01 in top and numbers 05 and 03 in low, to hull out side. However, there is a divergence found in spool mounting process that occurred cause the mobile came with the internal RUCHs as descriminated in the MAT425-0609 (folio 42) where the number 02 should be DN10 is 14 and the number 06 which should be 14 is 10. Finally, the RUCHs dismounted were 02, 06 and 08 (internals). This matter is related to hull integrity in AC31019. | Não |  |  |  |  | Remount the internal RUCHs following the references of the table in SBH.1D10.IMZ.006927 (sheet F04): the number 02 is couple with number 01 (DN10) , the 06 is with 05 (DN14) and 08 is with 07 (DN14); and SEFC33-04-21-I794E_B which ask a tightening torque of the 410 Nm -0%/+10%, that using the ICN wrench TOQ-006 (Range: 140-760 Nm, Unit Division: 10 Nm and Tolerance: + -4%) it will be 430 N.m. Before remounting the RUCHs it's important annealing the copper flat gaskets (CMD: 44JO303DD00017) and make a test to grant the maximum hardness is 50 HB or 50 HV. The hardness report should be attached on B07 which will be updated together the gaskets declaration of conformity. It's needed doing a dedicated test process that's specified in MAT425-0633_EXP: Internal pressure strength and leak test for each mobile hole where the RUCH was disassembled and filling the results on a M09. During these tests the orifices will be pluged with CMD: 44BO230D00183 and 44BO230D00184. The B01/B02 don't need to be regressed cause for these tests the spools already have being disconected, so the union spool thightness can be verified in the S02 test. The MAT425-0609 (folio 42) need being updated for the AC41019. | Agree with proposal. -The drawing MAT425-0609 folio:42 have to be updated. -But B01 and B02 for the internal pipes were regressed a NCR REGRESS have to be raise. -It's possible to indicate that S02 will be replace B01 and B02 for the ruch connection because valves were not dismounted. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 153 Dias | Patrick Daliguet | AC |  | NO |  |  | 2021-06-29 15:00 | Patrick Daliguet
NCR-ICN-ESC-12-0569-2021 | 53B | PIPES | 2021-07-20 13:36 | Nível 2 | COS-SMB-206043 |  | DA 3.2 | During S02 test for DU system it was identified an inversion on closing lines for EM00013. To treat this it was inverted the connection of P4148861 and P4148846 at the lower part of the spool (taking z coordinate into account). P4148861 – From 18RO220F00308 (female) to 18RO220F00311 (male) P4148846 – From 18RO220F00311 (male) to 18RO220F00308 (female) | Não |  |  |  |  | NG, please review the problem found on board. | -Reverse the piping on board to regain the functionality of the DU system on EM00013 -Realize the associated controle with the modification of pipes P4148861 and P4148846 -Check the origin of the error: -->inversion during assembly on board -->error in the 3D model -->atlas diagram Requires analysis at level 3 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 132 Dias | Franck Rubis | EM, DU |  | NO
NCR-ICN-ESC-12-0585-2021 | 53B | ELETRIC | 2021-08-17 18:15 | Nível 2 | COS-SMB-200542 | CTE00758526 | DA 3.2 | Panel EJ 02501 with damaged paintwork, damaged shock sensor and air outlet without fins and filter. As per the attached photo. | Não |  |  |  |  | 1 - The circumstances of triggering the shock sensor could not be effectively ascertained. It should be noted that this equipment, despite having a "shock sensor", is not part of the equipment that must comply with the acoustic discretion rules according to SMB-204559_C and SEFC 17-50-07, so we believe that the completed self-inspection form is enough for the constructive step. 2 - If you consider the presentation of the "information sheet" pertinent, it must be attached by the person who effectively fixed the equipment on board. Attached are: NCR-ICN-ESC-12-0585-2021 and CP1-NCR-ESC-12-0585-2021 paint deal email. To replace the filter, it is necessary that the TA indicate where to use, another SBR or spare. | The CTE00758526 is a E01 inspection, it's not a control of shock sensor 1 - in what circumstance, did the shock sensor trigger? 2 - Has the follow-up form been completed? please put it as an attachment Wait for level 3 instruction |  | Fabio Brito da Silva | Geraldo Alves Simoes Filho | 103 Dias | Stéphane Patrick Philippe Rideau | EJ |  | NO |  | Informações incorretas ou imprecisas | 2021-08-31 17:36 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0575-2021 | 53B | ACOUSTIC DISCRETION | 2021-07-27 12:44 | Nível 2 | COS-SMB-321700, COS-SMB-319713, COS-SMB-321797, COS-SMB-321795, COS-SMB-321794 | CTE00963339 | DA 3.2 | During MS01 inspection on AM00003 was checked that minimum distances were not achieved according to SMB-204507_C: Diesel generator BD00013: P0133574 and P4151297; P0133574 and P4151886; Diesel generator BD00014: P0133575 and P4151881. See annex. | Não |  |  |  |  | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. ICN request the Naval Group to inform the minimum distance to be met for the vertical direction. | Non-respect of minimum distances according to SMB-204507_C : - Apply answer to NCR-ICN-ESC-11-0444-2019 for: BD00013 and clamp P4151297 / DY70082Y1A (pipe P4133971 / DY50082Y1) - Request level 3 analysis for : BD00013 and pipe P4151886 / EL50030L2 BD00014 and pipe P4151881 / EL50038L2 Nota 1 : same situation observed on SBR1. Nota 2 : in 3D mock-up, 3D model of diesel engine is not in accordance with the real engine, appendices at the bottom are missing on the 3D model. Nota 3 : Diesel engines may have particular rules related to acoustic requirememts. See also NCR-ICN-ESC-12-0574-2021 on same topic for BD00015 and BD00016. (Fabien RENVOISE) |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 125 Dias | Patrick Daliguet | AM, BD |  | NO
NCR-ICN-ESC-12-0574-2021 | 53B | ACOUSTIC DISCRETION | 2021-07-27 12:40 | Nível 2 | COS-SMB-319713, COS-SMB-319711, COS-SMB-206079 | CTE00963760 | DA 3.2 | During MS01 inspection on AM00005 was checked that minimum distances were not achieved according to SMB-204507_C: Diesel generator BD00015: P0133571 and P4151875; Diesel generator BD00016: P0133568 and P4129588. See annex. | Não |  |  |  |  | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. ICN request the Naval Group to inform the minimum distance to be met for the vertical direction. | - Request level 3 analysis for : BD00015 and P4151875 / EL50105L2 BD00016 and P4129588 / EL50103L2 Nota 1 : same situation observed on SBR1. Nota 2 : in 3D mock-up, 3D model of diesel engine is not in accordance with the real engine, appendices at the bottom are missing on the 3D model. Nota 3 : Diesel engines may have particular rules related to acoustic requirememts. See also NCR-ICN-ESC-12-0575-2021 on same topic for BD00013 and BD00014. (Fabien RENVOISE) |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 125 Dias | Patrick Daliguet | AM, BD |  | NO
NCR-ICN-ESC-12-0580-2021 | 53B | PIPES | 2021-08-10 18:04 | Nível 2 | COS-SMB-200443, COS-SMB-200444 |  | DA 3.2 | As discussed with NVG GIR, there are missing plugs for EV20304, EV22019, EV22020, EV22025 and EV22102. ICN waits NVG orientation. | Não |  |  |  |  | ICN request application of Plugs as defined by TA in NCR-ICN-ESC-11-0523-2019. | This NCR should be submitted for lvl 3 validation for future necessary updates. See FTG-9510 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 110 Dias |  | EV |  | NO
NCR-ICN-ESC-12-0592-2021 | 53B | STW | 2021-08-31 16:38 | Nível 2 | COS-SMB-200532 |  | DA 3.2 | Ball valve RF00008 was dismounted during alignment of RF00001. Needs to be remounted and tested. | Não |  |  |  |  | Remount and re-test | NCR REGRESS have to be raise NCR MAT have to be raise to order new spare parts changed during dismounting (gasket, lock washers..) |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 90 Dias | Patrick Daliguet | RF |  | NO
NCR-ICN-ESC-12-0615-2021 | 53B | INTEGRATION EQUIPMENT | 2021-09-17 11:49 | Nível 2 | COS-SMB-200716 |  | DA 3.2 | During the system assembly process according to MAT424-0892, the NGD 5975142425989 - CA TYPE HOSE (POLYCHLOROPRENE Rubber) referring to MAT131-0018 and MAT131-0019, a damaged rubber (the equipment 53B-AG00066). | Não |  | Mecânico | Anomalia de Aplicação | Defeito no fluxo, rastreabilidade, revestimento, usinagem, moldagem | For the assembly process of equipment 53B-AG00066 - P0146676 CMD 14VM000D00011 - NAV.BRIDGE LOWER TRUNK QUICK SHUT hatch, according to MAT424-0892. Supply a new part NGD 5975142425989 - SLEEVE TYPE CA (material -POLYCHLORPENE TYPE 31B6), Ref. MAT131-0018 and MAT131-0019. Open NCR MAT. | Change the rubber by new ones from store. Raise NCR MAT to purchase a new ones. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 73 Dias | Patrick Daliguet | AG |  | NO |  |  | 2021-10-26 15:16 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0613-2021 | 53B | INTEGRATION EQUIPMENT | 2021-09-16 13:34 | Nível 2 | COS-SMB-330663 |  | DA 3.2 | Referent: 53B-AG00013 / 53B-AG00033 1) During the AG00013 assembly process, the pins items 10 and 13 referring to MAT424-1054 / MAT424-1056_EXP_B, were identified that the length is small, making final assembly impossible. It is necessary to manufacture in a larger size than specified. 2) For items 8, 9, 11 and 12 items were not found, being lost during the assembly process of the SBR2 hatch. It is necessary to provide new items cited for SBR2. | Não |  | Mecânico | Anomalia de Aplicação | Defeito de nivelamento, defeito dimensional, ... | For the AG00013 assembly process, the items 10 and 13 referring to MAT424-1054 / MAT424-1056_EXP_B, perform manufacture the pins in the larger size than specified and assemble in order. See the length annex 1 in the list. For items 8, 9, 11 and 12 items, supply a new items for SBR2. Open NCR MAT. | Take from store new ones Raise NCR MAT to purchase new spare parts |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 74 Dias | Patrick Daliguet | AG |  | NO |  | Descrição Incompleta | 2021-09-24 12:58 | Patrick Daliguet
NCR-ICN-ESC-12-0612-2021 | 53B | INTEGRATION EQUIPMENT | 2021-09-15 18:17 | Nível 2 | COS-SMB-200221 |  | DA 3.2 | The equipment Item 92: 53B-KT00010 - 53B-KT00155 - P0130899 CMD 14CD000D00069 - TUBE TOP STD CTRL CONNECTION OF STEM OPERATIONS, ref. DEI-200221-80500-12-001 - Task 20.800. Rework, adjustment of link arm of bow shutters TLT 5. During the assembly and adjustment of link arm of bow shutters TLT 5. 53B-KT00155 - P0130899 CMD 14CD000D00069, the bow shutters 53B-KT00055 did not close total, was identified that the length of the link arm it is necessary to adjust. | Não |  | Mecânico | Anomalia de Aplicação | Defeito de nivelamento, defeito dimensional, ... | For the assembly and adjustment of link arm of bow shutters TLT 5. The link arm 53B-KT00155 - P0130899 CMD 14CD000D00069 - According MAT321-0072 and MAT321-0073, perform to adjust the length total to 1816,00 mm. For the adjustment of link arm, use the machining and to cut 10mm from the extrem and open the thread in 13mm. See annex 2. | Agree with proposal to machine the connecting rod to allow the correct adjustment. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 74 Dias | Patrick Daliguet | KT |  | NO
NCR-ICN-ESC-12-0617-2021 | 53B | INTEGRATION EQUIPMENT | 2021-09-21 13:48 | Nível 2 | COS-SMB-319737 |  | DA 3.2 | The equipment FQ10400P / FQ10500P, were lost during the construction process. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Install new pressure gauges for the SBR2. 1) New pressure gauge in ref. 53B-FQ10400P - P0137393 - CMD 50MD200D00030 - PRESSURE MANOMETER CONCERNING 0 TO 4BAR M20 STAINLESS TYPE. 2) New pressure gauge ref. 53B-FQ10500P - P0137386 - CMD 50MD200D00034 - RELATIVE PRESSURE MANOMETER 0 TO 60 BAR M20 STAINLESS STEEL TYPE A. Open NCR MAT. | Agree with proposal. |  | Vinicius Siqueira dos Santos | Luiz Felipe Silva Moreira | 69 Dias | Patrick Daliguet | FQ |  | NO
NCR-ICN-ESC-12-0625-2021 | 53B | STW | 2021-09-23 12:47 | Nível 2 | COS-SMB-319760, COS-SMB-200255 |  | DA 3.2 | The DP00204 (Hand Distributor 4W/3P For Stern Hydroplane Gear) remote control support is not aligned with the fork joint, according to the image on ANNEX 1 file. | Não |  | Mecânico | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | ICN added the ANNEX 2 file with corrective suggestions for Naval Group verification, which consists on: (1) Reduce the length of the remote control support or/and (2) Reduce the length of the screw thread of the slide valve shaft. Forward to Naval Group to verify and authorize ICN to apply the suggestions or propose other corrective action. | 1) Concerning the axis of DP00204, we can cut a part of the threaded rod of the distributor necessary to keep 11,5 mm in engagement (10 mm of threads + 1.5 mm of bevel) + the lenght to instal the lock nut. ICN must write the real value of the threaded in engagement in the NCR level 3 and the lenght of the threaded cutting. 2) if necessary, we can also reduce the length of the remote control support => maximum 3mm. Send the NCR in level 3 |  | Marcelo Fonseca Arantes | Luiz Felipe Silva Moreira | 67 Dias | Frederic Guevel | DP |  | YES
NCR-ICN-ESC-12-0637-2021 | 53B | PAINTING | 2021-10-04 17:29 | Nível 2 | COS-SMB-319315, COS-SMB-339470, COS-SMB-319737 |  | DA 3.2 | As noted by the TA of NG, please check the applicable paint scheme on AC30005, as according to the attached photos, the connection face with the waste ejector is not painted and/or if painting in the region is not necessary, please inform. | Não |  | Isolamento, pintura, revestimento | Outras Anomalias | Vários defeitos | 1.The sleeve of passage AC30005 should be painted according to SMB-002525. As this work was not done in properly time sequence. Today is needed to move away the panels FH02621 and FH02623, without disconnecting them, dismounting the STUD RODS of the garbage ejector FP00100, paint the structure sleeve, without affecting the seal (O-ring). Remounting the stud rods and return the panels for theirs place. 2. Raise a NCR-REGRESS for redo the B06 inspection, updated the B07 and retest the B01/B02 following IT34-00-01E_B orientations. Redo, also, the E01 of electrical panels. | Rework rework as per croquis ( conform with SMB-002525). To paint the zone between the coaming and the equipment, it will necessary to remove the screws , clean, and take care to paint till the maximum of the possibility without touch the joint. On the seating and the equipment paint the machined not fonctional area Open a NCR regress. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 55 Dias | Hugues Bourget | AC |  | YES |  | Informações incorretas ou imprecisas | 2021-11-22 16:48 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0640-2021 | 53B | WELDING / BRAZING | 2021-10-06 10:29 | Nível 2 | COS-SMB-206179, COS-SMB-206180 |  | DA 3.2 | What is proposed in the SMB-TDP-PR-6748406 and SMB-TDP-PR-6748407 was not used for spools P4166955 and P4184016 as per the attachments (highlighted in red). Item #007 of P4166955 has been deleted, current weld is #009 with #005 and before it was #007 with #009 and #007 with #005, it is necessary to review welding documents. In P4184016, however, a curve was excluded and a welded curve was added, the documents must also be updated. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | ICN requests that NG accept the modifications, so that the modifications can be updated via NCR or update the project again, as without one of these options we cannot reissue the CTE's of unofficial documents. see attached. | AT accepts the pipe isometry modification because technically the PR is difficult to apply in the Y axis. Only the Y will not be respected, the X and Z axes will conform to the PR. The 2 important dimensions Z =5,785 and Z=5,741 are respected. Send to the level 3 for aprobation. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 54 Dias | Franck Rubis | EQ |  | NO
NCR-ICN-ESC-12-0648-2021 | 53B | RESISTANT STRUCTURE | 2021-10-14 19:21 | Nível 2 | COS-SMB-200710 |  | DA 3.2 | The hatch HL40080-29OU000D00166-SN:C0001-NG-LOT:19CH1246151-ORDER:DCS00782, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items to be remounted: lock plate, stud rods and seal. | Não |  | Mecânico | Anomalia de Preparação | Modo operatório errado (guia Profissões, procedimento, ...) | 1.Remount the hatch HL40080 on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B06 and B07 for hatch HL40080. | Agree with proposal. Manufacture new tab washers with the material dedicated and material certificate. For parts not manufactured it's necessary to raise NCR MAT to purchase new ones. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO |  | Fluxo indevido | 2021-10-15 16:40 | Marcia de Souza Sales
NCR-ICN-ESC-12-0649-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:23 | Nível 2 | COS-SMB-200710, COS-SMB-CAB-HD-KD |  | DA 3.2 | The cable HL22100D-11LS572D00112-DCNS-SN:N/A-LOT:18CH1012467-ORDER:CFE-1704073, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items that were damaged or lost in the dismounting cable process. Some others items should also be manufactured to finish the hatch HL40080 and mobile AB36010. The SN. was not informed on DOC-2018-901048. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1. Remount the cable HL22100D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB36010; B25, B13 and B07 for cable HL22100D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0650-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:27 | Nível 2 | COS-SMB-200710, COS-SMB-319718, COS-SMB-CAB-HD-KD |  | DA 3.2 | The cable HL22102D-11LS572D00113-DCNS-SN:N/A-LOT:17CH1104440-ORDER:CFE-1704072, which was dismounted from SBR1-RANAE to be mounted on SBR2, had the BESCOND cone damaged and should be completely changed by a new cable. Some others items should also be manufactured to finish the hatch HL40053-29OU000D00129-NG-SN:C0001-LOT:19CH1245672-ORDER:DCS00782 and HL40080. The SN. was not informed on DOC-2017-910404 for cable. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount a new cable HL22102D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B06 and B07 for hatch HL40053; B25, B13 and B07 for cable HL22102D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. 2. Open a NCR-MAT to send the damaged cable to repair. It’s important always having a new spare cable of hull leak to be used on demand. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise or the spare parts added with NCR MAT of cable. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0651-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:28 | Nível 2 | COS-SMB-200710, COS-SMB-200581, COS-SMB-CAB-HD-KD |  | DA 3.2 | The cable HL22103D-11LS572D00116-DCNS-SN:N/A-LOT:17CH1104438-ORDER:CFE-1704070, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items that were damaged or lost in the dismounting cable process. Some others items should also be manufactured to finish the hatch HL40080 and mobile HL44030-11TE142D00009-MINERVAISSARTEL-SN:N/A-LOT:18CH1196012-LOTNº:000001-ORDER:6497441. The SN. was not informed on DOC-2017-910404 for cable and DOC-2019-903426 for mobile. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount the cable HL22103D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL44030; B25, B13 and B07 for cable HL22103D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0652-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:29 | Nível 2 | COS-SMB-200710, COS-SMB-CAB-HD-KD |  | DA 3.2 | The cable HL22104D-11LS572D00117-ADS-SN:N/A-LOT:18CH1016301-ORDER:CFE-1704067, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items that were damaged or lost in the dismounting cable process. Some others items should also be manufactured to finish the hatch HL40080 and mobile AB32501. The SN. was not informed on DOC-2018-903821. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount the cable HL22104D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB32501; B25, B13 and B07 for cable HL22104D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0654-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:34 | Nível 2 | COS-SMB-200710, COS-SMB-CAB-HD-KD |  | DA 3.2 | The cable HL22124D-11LS572D00115-DCNS-SN:N/A-LOT:17CH1104437-ORDER:CFE-1704071, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items that were damaged in the dismounting cable process. The SN. was not informed on DOC-2017-910404. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount the cable HL22124D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B25, B13 and B07 for cable HL22124D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0655-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:36 | Nível 2 | COS-SMB-200710, COS-SMB-CAB-HD-KD, COS-SMB-200554 |  | DA 3.2 | The cable HL22101D-11LS572D00114-DCNS-SN:N/A-LOT:17CH1104439-ORDER:CFE-1704068, which was dismounted from SBR1-RANAE to be mounted on SBR2, needs news items that were damaged or lost in the dismounting cable process. Some others items should also be manufactured to finish the mobile HL42087-11TE142D00008-MINERVAISSARTEL-SN:N/A-LOT:18CH1196008-LOTNº:000002-ORDER:6497441 that also came out of SBR1-RANAE. The SN. was not informed on DOC-2017-910404 for cable and DOC-2019-903426 for mobile. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount the cable HL22101D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL42087; B25, B13 and B07 for cable HL22101D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Patrick Daliguet | HL |  | NO
NCR-ICN-ESC-12-0659-2021 | 53B | PIPES | 2021-10-15 16:42 | Nível 2 | COS-SMB-321798 |  | DA 3.2 | Lack of material for connection between accessories of spool P4160281 was identified; Adapter 18RO000D00439 (010) and tube 18LT100D00149 (003) | Não |  | Tubulação | TDPIS | Documento errado | ICN suggested changing CMD 18RO000D00439 to 18RO230D00566 between the tube and adapter 18RO000D00439 and that it is also possible to update the CTEs and document SBH.2A21.ISO.01.P4160281 as well. | See FTG-9614. |  | Bruno Vicente Fernandes | Sharles Gomes Silveira | 45 Dias | Franck Rubis | BX |  | YES |  |  | 2021-11-09 18:59 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0662-2021 | 53B | ELETRIC | 2021-10-22 11:52 | Nível 2 | COS-SMB-319329, COS-SMB-206085 |  | DA 3.2 | During testing it was identified that the control board of the new SGM 07.1 AUMA electric actuator did not work correctly. The same 7.1 actuator board delivered to the SBR1 had the same problem. See NCR-ICN-ESC-11-1045-2020. During testing it was identified that the control board of the new SGM 07.1 AUMA electric actuator . | Não |  | Eletricidade | Anomalia de Teste | Comissionamento da instalação imperfeita | Substituir a placa de controle do atuador AUMA 07.1 por outra nova. | ICN in accordance with NG FO used the pcb control of the previous motor 05.1 to repair the new motor 07.1 who is not working in remote mode. Open NCR MAT to refund the pcb taken. Report attached in annex. |  | Rafael Thome da Silva | Rafael Thome da Silva | 38 Dias | Etienne Alexandre Sebastien Rene Berot | DJ |  | NO
NCR-ICN-ESC-12-0663-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-22 11:56 | Nível 2 | COS-SMB-200229, COS-SMB-200224 |  | DA 3.2 | During the assembly of the guide rails of the Multicom mast, the ICN team of mechanics noticed that the fixing brackets touch or are very close to the structure, so there is not enough space to put the resin "shockfast" (minimum use thickness is 8mm). | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Perform an upward offset of 20 mm in the Grounding Supports (BDM-00031571_Ref. 8 and Ref. 11) from the origin in order to increase the thickness of the resin chocking; Note: The resin thickness will be between 15mm to 20mm with the new positioning of supports. Counter mark the holes and drill the new threaded holes M16; Manufacture slotted set screws M16 CL 8.8 and fix with Loctite 270; Suggestion: Apply a layer of epoxy resin (for example: DEVCON) and grind to good profile; Apply painting according specific plan for the equipment. | Agree with proposal already applied for SBR1. Documentation will be updated. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 38 Dias | Patrick Daliguet | RM |  | NO
NCR-ICN-ESC-12-0676-2021 | 53B | MECHANICAL | 2021-11-03 14:58 | Nível 2 | COS-SMB-319718 |  | DA 3.2 | During the dimensional inspection performed after reworking in accordance with NCR-ICN-ESC-12-0438/2021, deviations in the positioning of the BQ00005 equipment were detected in disagreement with the design tolerance. | Não |  | Mecânico | Anomalia de Integração | Defeito de posicionamento, interferência, ... | Accept as it is. The current position of the valve has been adjusted to suit assembly of the pipe P4164088. | Agree with proposal. A checking of the good shutting of BQ00005 will be carry out during the B02BQZ0011 and S02BQZ0004 |  | Silvio Fonseca de Paiva | Ernanes de Souza | 26 Dias | Patrick Daliguet | BQ |  | NO
NCR-ICN-ESC-12-0677-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-03 14:59 | Nível 2 | COS-SMB-319718 |  | DA 3.2 | During the dimensional inspection carried out after reworking in accordance with NCR-ICN-ESC-12-0438/2021, deviations in the positioning of the BQ00006 equipment in disagreement with the design tolerance were detected. | Não |  | Mecânico | Anomalia de Integração | Defeito de posicionamento, interferência, ... | Accept as it is. The current position of the valve has been adjusted to suit assembly of the pipe P4164085. | Agree with proposal. A check of the good closing of BQ00006 will be carry out during the B02BQZ0009 and S02BQZ0003 |  | Silvio Fonseca de Paiva | Ernanes de Souza | 26 Dias | Patrick Daliguet | BQ |  | NO
NCR-ICN-ESC-12-0682-2021 | 53B | SEATING | 2021-11-08 11:30 | Nível 2 | COS-SMB-200755, COS-SMB-319542, COS-SMB-319541 |  | DA 3.2 | Interference was detected in the assembly of the ampoule of the DW00102 with seating P4121692. Adjustment of the lower stop of the ampoule of the DW00102. | Não |  | Chapa, suporte, antepara leve | Outras Anomalias | Vários defeitos | ICN propose to adjust the lower support according to the DW ampoule. | REPAIR Cut the lower stopper Ajust and reweld after adjustment. Carry out 100% VT, 20% RT and 100% MT |  | Renato da Silva Goncalves | Sharles Gomes Silveira | 21 Dias | Hugues Bourget | KT |  | YES |  | Informações incorretas ou imprecisas | 2021-11-08 17:53 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0692-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-16 18:57 | Nível 2 | COS-SMB-330665 |  | DA 3.2 | During the assembly process of AG00014, the pins item 13 ref. SMB-361762_23 / 51 (MAT424-0715 /MAT424-0717) , it was identified that the length is small, making final assembly impossible. It is necessary to manufacture in a larger size than specified. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | For the assembly process of AG00014 and AG00034 SBR2, carry out supply of materials for the fabrication of new pins ref. position 13 of SMB-361762_23 / 51 (MAT424-0715 / MAT424-0717). Perform manufacturing of pins larger in PIN size AXIS 12x45 - Qty: 02 units and assemble in order. | NCR-ICN-ESC-12-0194-2020 treat of the similar problem. All nomenclatures of panel involved will be updated. Pin axis 12x45 NGD: 9980000005612 material: CuAl10Ni5Fe4 can be used if it's in stock or manufacture with the good material with material certificate and traceability folder updated. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 12 Dias | Patrick Daliguet | AG |  | NO
NCR-ICN-ESC-12-0111-2020 | 53B | PIPES | 2020-07-31 13:53 | Nível 2 | COS-SMB-206041, COS-SMB-206042 |  | DA 3.2 Qualité Validation | During metalwork campaign inspection, NG informed a non-conformity on the nut of MB00307 with line MB50302M. It was verified on board and there is no solution to this case other than use the nut already applied. It was applied the nut foreseen in STF33-02-VE001E but on the final result was that we didn't get 2 threads. Was used nut of the 12mm height for screw (M14). | Não |  |  |  |  | Send to level 2. | Send to level 3 for decision Proposal solution level 2.2 : a) accept as it is b) reduce 2 mm the high of the nut ( by machining ) Precision sur les ecrous montes a bord deux types diametre 14 - BC et 7C Hauteur 7C = 13,95 cm BC=13,61 cm | Please apply following modifications : - PR Addendum SMB-TDP-PR-6782896 and SMB-TDP-PR-6782897 loaded in TDP IS on 10/03/2021 - 32VI310D00299 / 9980000039624 NUT H M14 42CRMO4 to be delivered in batch SMB-US07A-DB90-SAH | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 486 Dias |  | MB |  | NO | NO |  | 2020-09-21 13:10 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0265-2020 | 53B | STW | 2020-11-11 19:12 | Nível 2 | COS-SMB-319326, COS-SMB-200710, COS-SMB-319731 |  | DA 3.2 Qualité Validation | The unbalanced battery light is on for 3 elements (5, 6 and 9) on the FWD BCA BS battery. We are having problems with the autonomy of the FWD BCA (BS02500 - CMD - 05SE100D00088) and AFT BCA (BS02501 - 05SE100D00091). The forecast is that the emergency system will have a 30-minute autonomy, but this is not happening, as we can see in the attached report. | Não | [5 empty] | Need a reforming of batteries fwd and aft as sbr1 ICN doesn't have the specific charger to it. Need Adelco do perform it Send to level 3 | Replace defective batteries with new ones. Electrical measurements to be carried out on the charger according to the written protocol. Electrical monitoring of the batteries to be carried out every 1 to 3 months. Expertise of defective batteries to be carried out according to a written procedure. Return to France of 3 SPH 115 batteries and 3 SPH190 batteries for expertise according to RTE-2021-08-117. (Packaging procedure before return transport attached to the RTE) | Paulo Roberto de Souza | Paulo Roberto de Souza | 382 Dias | Etienne Alexandre Sebastien Rene Berot | BS | NCR-ICN-REGRESS-12-0044-2021 | NO | YES
NCR-ICN-ESC-12-0689-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-12 14:50 | Nível 2 | COS-SMB-206081 |  | DA 3.2 Qualité Validation | Discrepancy between commissioning test B02_BM00031 (DT-319712-25600-12-012-rev.0) and the orientation of the PTRH, item 4.13 of SMB-005544_F about the leak test on NVR BM00176. This matter is related to hull integrity in AC32007. | Não |  | Mecânico | Anomalia de Preparação | Documento errado (pasta, caderno de fabricação, especificação, desenho, planejamento de teste/inspeção) | 1. Retest the inspection B02_BM00031. Fit the test device over the hull passage AC32007. Dismount the pipe BM50103Y1-P4147627 and be sure that valve BM00073-P0134117 is OPEN. Apply the leak pressure considering +2% according to IT34-00-01E_B, 53.5 bar during 5 min. The leak inspection between the BM00178 and BM00032 flanges will be ensured through the pressure drop in test manometer. 2. The ICN DT should be updated for others SBRs. 3. After retest, the pipe BM50103Y1-P4147627 should be remounted and M05 and S02 redone and updated. | Agree with proposal. In complement NCR REGRESS will be raise and B05 will be updated. | In accordance with proposal | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 17 Dias | Patrick Daliguet | BM |  | NO | YES
NCR-ICN-ESC-12-0179-2020 | 53B | PIPES | 2020-09-29 14:25 | Nível 2 | COS-SMB-206057, COS-SMB-206095, COS-SMB-200451, COS-SMB-206089, COS-SMB-200425, COS-SMB-327471, COS-SMB-321794, COS-SMB-337142, COS-SMB-200443, COS-SMB-206043, COS-SMB-206084, COS-SMB-206099 |  | Especialista ICN | Some spools were installed onboard without painting, because at the time of their installation it was not intended for painting for them, there is a change the paint scheme and due to the difficulty of access, it is not possible to paint these products from the current revision of SMB-002345 (see attachment). | Não |  |  |  |  | Take actions in accordance with Annex 1 of this NCR. For other products with the same problem, we suggest the same actions defined in this NCR. (This NCR is specific to SBR2. For the analysis of these problems, please check the NCR-ICN-ESC-11-0728-2019). |  |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 426 Dias | Hugues Bourget | N/A |  |  |  |  | 2021-01-19 13:42 | Hugues Bourget
NCR-ICN-ESC-12-0369-2021 | 53B | ELETRIC | 2021-03-10 18:42 | Nível 2 | COS-SMB-319693 |  | Especialista ICN | KT21A54 torpedo 4 connector input damaged during construction. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | 2 cases possible: 1)-it's possible to repair: repair the connector and check the good functionality 2)-not possible to repair and it will be necessary to change: NCR regress will be raise to redo all inspections and test (B11,B07, B02 ...) and NCR MAT to purchase a new one. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 263 Dias | Patrick Daliguet | KT |  | NO |  | Descrição Incompleta | 2021-09-13 13:43 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0479-2021 | 53B | ELETRIC | 2021-05-10 18:44 | Nível 2 | COS-SMB-200546 |  | Especialista ICN | The RH62603D, RH62583D, RH62588D cable connectors were not located close to the equipment. Please open NCR-MAT. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 202 Dias | Stéphane Patrick Philippe Rideau | RH |  |  |  |  | 2021-05-11 14:50 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0472-2021 | 53B | MECHANICAL | 2021-05-06 13:33 | Nível 2 | COS-SMB-200273, COS-SMB-319693 |  | Especialista ICN | Scenario: During a pre-test (52.5 bar) on TLT1 (SBR2), to verify all flanges and finalize the Flooding and Draining Circuit TLT 1-3-5 installation, it was observed a leak on the body of the filling/draining valve "KT01011 / P0113704 / 18RT010D00566" of the TLT1. Solution: 1) Replace this hull valve "KT01011 / P0113704 / 18RT010D00566" by new one from SBR3 / SBR4; 2) Redo the B02 / B01 (B01_ KT03611 / B02_ KT03611 - adapted with the special tool inside the TLT1). | Não |  |  |  |  | Scenario: During a pre-test (52.5 bar) on TLT1 (SBR2), to verify all flanges and finalize the Flooding and Draining Circuit TLT 1-3-5 installation, it was observed a leak on the body of the filling/draining valve "KT01011 / P0113704 / 18RT010D00566" of the TLT1. Solution: 1) Replace this hull valve "KT01011 / P0113704 / 18RT010D00566" by new one from SBR3 / SBR4; 2) Redo the B02 / B01 (B01_ KT03611 / B02_ KT03611 - adapted with the special tool inside the TLT1). Please, send this NCR to NG specialist Patrick Daliguet / Herve de Backer / Bertrand Belle. |  |  | Bruno Correa Ferreira | Gustavo Magarao Sambaquy | 207 Dias |  | KT |  |  |  |  | 2021-06-18 15:43 | Patrick Daliguet
NCR-ICN-ESC-12-0601-2021 | 53B | ELETRIC | 2021-09-03 17:47 | Nível 2 | COS-SMB-200716, COS-SMB-319760 |  | Especialista ICN | Connectors applied only to the connection part. | Não |  |  |  |  | Provide new complete connectors. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 86 Dias |  | DB, BH
NCR-ICN-ESC-12-0578-2021 | 53B | PIPES | 2021-07-28 15:24 | Nível 2 | COS-SMB-200273 |  | Especialista ICN | Scenario: After the multiple attempts to fill and drain the TLT's, there are some problems encountered, after doing some research and visual inspection on TLTs, we found one bad thing: 1) The gap between the edges of the drain pipes in the upper part of the TLTs and the tube body must be between 1 and 5 millimeter (see attached picturies): Solution: ICN proposes to perform: - Remove/Adjust/Assembly the drain piping tube (bad adjustment - see appendix); - Check the water flow detectors (settings...); - KT3C: Elementary test N°1: One tube complete flooding. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | Scenario: After the multiple attempts to fill and drain the TLT's, there are some problems encountered, after doing some research and visual inspection on TLTs, we found one bad thing: 1) The gap between the edges of the drain pipes in the upper part of the TLTs and the tube body must be between 1 and 5 millimeter (see attached picturies): Solution: ICN proposes to perform: - Remove/Adjust/Assembly the drain piping tube (bad adjustment - see appendix); - Check the water flow detectors (settings...); - KT3C: Elementary test N°1: One tube complete flooding. Please, send this NCR to the NG experts: Paul Fosse / Anthony Grel. |  |  | Bruno Correa Ferreira | Matheus Fernandes da Silva | 124 Dias |  | KT
NCR-ICN-ESC-12-0579-2021 | 53B | PIPES | 2021-07-29 17:24 | Nível 2 | COS-SMB-200271 |  | Especialista ICN | Scenario: During a visual check onboard, it was verified that some metallic collars lost on KE pipes (see attached pictures). Solution: replace by new one from SBR3 and manufacture new to put instead of SBR3. | Não |  |  |  |  | Scenario: During a visual check onboard, it was verified that some metallic collars lost on KE pipes (see attached pictures). Solution: replace by new one from SBR3 and manufacture new to put instead of SBR3. Please, send this NCR to the NG specialists: Paul Fosse. |  |  | Bruno Correa Ferreira | Matheus Fernandes da Silva | 122 Dias |  | KE |  |  |  | Outros | 2021-08-11 16:03 | Paul Fosse
NCR-ICN-ESC-12-0598-2021 | 53B | ELETRIC | 2021-09-01 17:28 | Nível 2 | COS-SMB-339062, COS-SMB-200496, COS-SMB-CAB-OO-RM |  | Especialista ICN | The RC60021D/RC60012D/RC60011D/RH62621D cable connectors, belonging to the RC20010 equipment, were not supplied with the equipment as mentioned in DEI-200551-30700-12-005 | Não |  |  |  |  | Use the supplied connectors for the "SBR4" an "NCR-MAT" the same supply for the "SBR2" and a new supply for the "SBR4". |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 88 Dias | Stéphane Patrick Philippe Rideau | RC, RH |  |  |  | Informações incorretas ou imprecisas | 2021-09-16 16:27 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0599-2021 | 53B | ELETRIC | 2021-09-01 17:47 | Nível 2 | COS-SMB-319757 |  | Especialista ICN | The BT0650BD/BE0400CR/BE0300AE equipment was lost during the construction process. | Não |  |  |  |  | Use the equipment provided for the "SBR4" available in the warehouse referring to the same "CMD's" and open an "NCR-MAT" for a new supply. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 88 Dias | Stéphane Patrick Philippe Rideau | BT |  |  |  | Informações incorretas ou imprecisas | 2021-09-20 17:57 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0607-2021 | 53B | ELETRIC | 2021-09-09 18:11 | Nível 2 | COS-SMB-339062, COS-SMB-CAB-KE-KO, COS-SMB-CAB-UA-UW |  | Especialista ICN | KO60513B, UW64554D and KO60514B cable connectors belonging to UW04000 equipment were applied incomplete. | Não |  | Eletricidade | Anomalia de Aplicação | Mau uso dos documentos de aplicação | Use the supplied complete connectors on the "SBR2" for another Submarine and open an "NCR-MAT" for a new supply. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 80 Dias | Stéphane Patrick Philippe Rideau | UW, KO |  |  |  | Informações incorretas ou imprecisas | 2021-09-16 16:33 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0611-2021 | 53B | PAINTING | 2021-09-15 13:08 | Nível 2 | COS-SMB-206084, COS-SMB-200451 |  | Especialista ICN | Hot work was carried out near Products P4152783, P4153056, P4133152, P4153066 in the B240 SBR2 compartment, causing localized damage to the external coating (galvanizing) of the spools. | Não |  | Tubulação | Anomalia de Aplicação | Defeito no fluxo, rastreabilidade, revestimento, usinagem, moldagem | ICN suggest perform LP and US tests. And if there are no contaminations, apply zinc-rich (not on the list of paints listed on SMB-002083) in areas with low thickness (see annex). | REPAIR A painting isn´t a subsitute of galvanisation, In this case it can be o poutside protection of the pipe. |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 75 Dias |  |  |  | NO |  | Informações incorretas ou imprecisas | 2021-10-05 17:12 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0623-2021 | 53B | ELETRIC | 2021-09-22 13:35 | Nível 2 | COS-SMB-319698 |  | Especialista ICN | When receiving the material referring to DP04200 from RM 123591, 1 item of cmd 11CI000D00011_2002 came missing from the connection part as shown in the attachment. | Não |  | Eletricidade | Anomalia de Aplicação | Defeito no fluxo, rastreabilidade, revestimento, usinagem, moldagem | Provide the missing item or a new set to continue the construction process. |  |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 68 Dias | Stéphane Patrick Philippe Rideau | DP |  |  |  | Descrição Incompleta | 2021-11-09 18:43 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0624-2021 | 53B | STW | 2021-09-22 15:19 | Nível 2 | COS-SMB-200281, COS-SMB-200644 |  | Especialista ICN | Attack Periscope ram RM00207 is leaking through the valve RM00017. It's necessary to change lipseals and scrapper rings from the lower part of the ram. | Não |  | Mecânico | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | Change seals. Send 2 sets to be able to change for both rams if necessary. |  |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 68 Dias |  | RM |  |  |  | Informações incorretas ou imprecisas | 2021-09-22 19:30 | Bertrand Belle
NCR-ICN-ESC-12-0633-2021 | 53B | ELETRIC | 2021-10-04 13:18 | Nível 2 | COS-SMB-200526, COS-SMB-319731 |  | Especialista ICN | When going from local command to remote command, the defect appears as attached, sometimes even with the defect we have the remote command and other times we must repeat the operation until it normalizes or we alternate between NRCM and BRCM for it to work. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | Expert assessment level 2 will be required. |  |  | Irlan Nunes da Silva | Jair de Barros Sena de Araujo | 56 Dias |  | ME |  |  |  | Outros | 2021-10-06 11:31 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0641-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-06 13:45 | Nível 2 | COS-SMB-330662 |  | Especialista ICN | After dimensional inspection requested in NCR-ICN-ESC-12-0399-2021, a deviation was detected in disagreement with the project. See attached dimensional report | Não |  | Mecânico | Anomalia de Integração | Defeito de nivelamento, defeito, dimensional, ... | According email historic and alignment report of balancing system AG00036 (NCR-ICN-ESC-12-0399-2021): REWORK. 1. On the Hinge Support (Rep. 26): Check the the flatness of the seating bearing surface e fix it using a hydraulic press. Perform a NDT 100% VT and 100% PT; 2. Measure again the coaxiality and procced according below if it is not conform: a) Machining the bearings according tolerances: • Side A: Ø50 the 2 sets of bearings at Ø50 0/+0,039; • Side B and C: Ø64 the 2 sets of bearings at Ø64 0/+0,046. b) Mark the positions of bearings to avoid mixing; c) Assembly the Bearing Caps (Rep. 06, 08 and 09) and tight the screws manually; Note: The ¼ of turning is impossible to apply. d) Check the clearance of 0,5 mm after tightening the bearing caps; e) Reaming the inner diameters Ø50H8 and Ø64H8 in the same axis. Coaxiality of 0,02 mm between 3 positions; f) Assembly the Hinge Axis (Rep.01) and Hinge Arm (Rep. 07) in the Hinge Support (Rep. 26) and control the arm movement. The movement should be without hard point and fluid. Send report final machining and coaxiality. 3. Seating onboard: rework the blue matching at 80% of the bearing surface (D55-02), reinstall the balancing system AG00036, take the measurements and machine a new shim (SBH.PLM.3D30.000166-F sheet F03) as required; 4. Check again the movement of complete set of Hatch AG00016 and Balancing System AG00036. |  |  | Silvio Fonseca de Paiva | Ernanes de Souza | 54 Dias | Patrick Daliguet | AG | NCR-ICN-ESC-12-0399-2021 |  |  | Descrição Incompleta | 2021-11-01 14:43 | Patrick Daliguet
NCR-ICN-ESC-12-0642-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-06 13:45 | Nível 2 | COS-SMB-330663 |  | Especialista ICN | After dimensional inspection requested in NCR-ICN-ESC-12-0397-2021, deviation was detected in disagreement with the project. See attached dimensional report | Não |  | Mecânico | Anomalia de Integração | Defeito de nivelamento, defeito, dimensional, ... | According email historic and attached the alignment report of balancing system AG00033 before machining (NCR-ICN-ESC-12-0397-2021). Rework, carry out machining bearings according tolerances: o Side Ø55 the 2 sets of bearings at Ø55 0/+0,046 o Side Ø48 the 2 sets of bearings at Ø48 +0,07/+0,10 To be reassembly, follow instruction: o Mark the positions of bearings to avoid mixing; o Assembly the Bearing Caps (Rep. 09 and 59) and tight the screws manually; o Note: The ¼ of turning is impossible to apply. o Check the clearance of 0,5 mm after tightening the bearing caps; o Reaming the inner diameters Ø55H8 and Ø44H8 in the same axis. Coaxiality of 0,02 mm between 3 positions; o Assembly the Hinge Axis (Rep. 56) and Hinge Arm (Rep. 07) in the Hinge Support (Rep. 01) and control the arm movement. The movement should be without hard point and fluid. Send report final machining and coaxiality. |  |  | Silvio Fonseca de Paiva | Ernanes de Souza | 54 Dias | Patrick Daliguet | AG | NCR-ICN-ESC-12-0397-2021 |  |  | Descrição Incompleta | 2021-11-01 14:45 | Patrick Daliguet
NCR-ICN-ESC-12-0672-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-28 16:20 | Nível 2 | COS-SMB-330664, COS-SMB-200470 |  | Especialista ICN | During the opening and closing test of the hatch 53B-AG00019, the hatch touches the tube DB-50013M1 - P4119254, which makes it impossible to fully open the hatch AG00019. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Repair. For attend the assembly of the hatch 53B-AG00019, Perform new adjust in the pipe 53B- P4119245, must be allowing full opening and closing of hatch on board. |  |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 32 Dias |  | AG |  |  |  | Descrição Incompleta | 2021-11-08 16:58 | Franck Rubis
NCR-ICN-ESC-12-0674-2021 | 53B | ELETRIC | 2021-10-29 16:45 | Nível 2 | COS-SMB-200569, COS-SMB-200710, COS-SMB-319760, COS-SMB-200546, COS-SMB-200549, COS-SMB-200551, COS-SMB-200542, COS-SMB-200566 |  | Especialista ICN | BE0900AE, BE0800AE, BE0B00AC, BE0B00AA, BE0610CC, BE0610BC, BE0B00AF, BE0B00AB, BE0B00AA, BE0500AE, BE0500AD and BE0B00AE luminaires damaged during the construction process. Attached is an image as an example of the damaged part. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 31 Dias | Stéphane Patrick Philippe Rideau | BE |  |  |  | Descrição Incompleta | 2021-11-04 17:19 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0699-2021 | 53B | ELETRIC | 2021-11-22 14:08 | Nível 2 | COS-SMB-200529, COS-SMB-331623, COS-SMB-319760 |  | Especialista ICN | Valve actuation device BH00003 is conflicting in BE0710DB. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | This interference has to be verify In the project by Level 2.2. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 7 Dias |  | BE, BH
NCR-ICN-ESC-12-0700-2021 | 53B | STW | 2021-11-22 15:12 |  | COS-SMB-200532 |  | Especialista ICN | The equalizing valve lever which resides inside RF00008 Ball valve has a pin which is very rusted and needs to be replaced. | Não |  | Mecânico | Anomalia de Teste | Defeito de configuração da instalação |  |  |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 7 Dias |  | RM
NCR-ICN-ESC-12-0703-2021 | 53B | PRESERVATION | 2021-11-23 16:21 | Nível 2 | COS-SMB-319725 |  | Especialista ICN | During the work on the aft battery Develec sensors, the pipe connection of the battery refrigeration system was damaged by a tool and broke. Check photo attached. The problem has been already fixed, check evidence attached. An NCR-Regress will be opened to redo the tests as indicated. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | The pipe needs to be fixed. NCR-Regress must be opened to retest the circuit. |  |  | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 5 Dias |  | BB
NCR-ICN-ESC-12-0709-2021 | 53B | NON RESISTANT STRUCTURE | 2021-11-29 13:26 | Nível 2 | COS-SMB-319698, COS-SMB-200581 |  | Especialista ICN | Rework in according with TAF-TA-2021-1378 for DY bottles. Some non-conformities identified and there are several inconsistencies in the documents for fixing the bottles on D230 (forward) and A210 (aft). | Não |  | Chapa, suporte, antepara leve | Anomalia de Integração | Documentação inapropriada (referência errada, indicio errado, ...) | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 3 Dias | Hugues Bourget | DY
NCR-ICN-ESC-12-0291-2020 | 53B | PIPES | 2020-11-25 12:54 | Nível 2 | COS-SMB-206116, COS-SMB-327464 |  | ICN 1.1/1.2 | “During adjust of pipe P4123636 a new solution was presented to solve the issue of NCR-ICN-ESC-12-0248-2020. Instead of lose (scrap) the pipe material a new connection was added in the middle of the old pipe, allowing the adjust of the correct pipe length. Please close NCR-ICN-ESC-12-0248-2020, and consider this one as solution.” | Não |  | Tubulação | Outras Anomalias | Vários defeitos | NG, please validate the solution found by ICN; |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 369 Dias | Franck Rubis | KT | NCR-ICN-ESC-12-0248-2020 |  |  | Descrição Incompleta | 2021-10-14 19:27 | Franck Rubis
NCR-ICN-ESC-12-0388-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-18 18:40 | Nível 2 | COS-SMB-321681 |  | ICN 1.1/1.2 | The SMB-TDP-PR-6115397 (OM-115734) arrived late so the solution cannot apply onboard. ICN propose to change the bolt class (12,9) and keep the diameter 8. | Não |  |  |  |  | Send to level 2. |  |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 255 Dias | Franck Rubis | AF |  |  |  |  | 2021-03-26 16:22 | Hugues Bourget
NCR-ICN-ESC-12-0628-2021 | 53B | PIPES | 2021-09-28 14:23 | Nível 2 | COS-SMB-200452 |  | ICN 1.1/1.2 | During construction it was identified a double loose flange on P4125767 (EV51042J1 - SBH.3B10.ISO.01.P4125767_G.), same condition found on NCR-ESC-11-1784-2021. ICN production team changed from 10RO120D00008 to 18RO120D00033 and have a different configuration. The proposed solution is to accept as it is, that means, with the flange 18RO120D00033. | Não |  | Tubulação | Anomalia de Aplicação | Defeito no fluxo, rastreabilidade, revestimento, usinagem, moldagem | ICN suggests accepting it as is, ie changing the flange to 18RO120D00033. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 62 Dias | Franck Rubis | EV | NCR-ESC-11-1784-2021 |  |  | Descrição Incompleta | 2021-10-14 19:32 | Franck Rubis
NCR-ICN-ESC-12-0683-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-08 13:17 | Nível 2 | COS-SMB-206144 |  | ICN 1.1/1.2 | The valve FQ00803-P0140161 , traceability reference 18RT010D00814-6216726-007-MCROMAZZA was mounted incorrectly. The harmonization of the stud rods did not respect the 2 threads protruding. But before remouting, during F06 inscpection, was noticed that HALAR coating is damaged. This matter is related to hull integrity in AC32050. | Não |  | Mecânico | Anomalia de Aplicação | Modo operatório errado | 1. Dismount the spool P4176456 and valve FQ00803. 2. Remount the valve FQ00803 using new fiber gasket and lock washers and following the B06 inspection orientations, remembering of doing the F06 before. 3. Raise a NCR-REGRESS to redo the F06, B06, B07, M05 and the PTRH/2 already carried out, as the S02. | Agree with proposal. In complement NCR MAT will be raise to purchase new gasket and lock washers. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 21 Dias | Patrick Daliguet | FQ |  | NO |  | Outros | 2021-11-12 14:34 | Carmelo Alves Batista
NCR-ICN-ESC-12-0345-2021 | 53B | STW | 2021-02-12 18:38 | Nível 2 | COS-SMB-200433, COS-SMB-200434 |  | PCP 6.1 | Piping spool RM50027R does not reach the actuator adaptor and thus cannot be properly connected. | Não |  |  |  |  | Add a section to the pipe and update the project with the correct line length. | The same issue was reported on SBR1 the solution will be the same On SBR1 NCR-ICN-ESC-11-0703-2019 the project should not been update but Job Order information should be read carefully by the production team Decision: REPAIR As per Job Order information, ICN designated this spool with adjustable length in its extremeties. Naval Group suggests to manufacture a new spool with more length of adjustment in its extremities. |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 289 Dias | Bertrand Belle | RM |  | NO |  |  | 2021-03-29 19:10 | Frederic Pavic
NCR-ICN-ESC-12-0349-2021 | 53B | INTEGRATION EQUIPMENT | 2021-02-22 16:13 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | PCP 6.1 | NCR-ICN-UFEM-12-299/2018 describe the problems in the depth of the thread. NCR-299 reworked, accepted as it is and closed. NCR-ICN-ESC-12-0206-2020 describe the missing problem of 2 minimum stud rod threads. This NCR could be the consequence of NCR-299. NCR-ICN-ESC-12-0330-2021 described the internal manufacture problem in the stern gland that informed by NG thought email. Current problem: After some investigations with NG, we concluded that: • Some depths of the thread in the coamming are out of tolerance (bigger in the length). See annex; • All studs rod (CMD: 5306930200878) are in the maximum tolerance. The union of both problems described above, are the reason of the lack of 2 minimum threads. | Não |  |  |  |  | Send to level 2. | The length (a=36) of the stud are too big and don't allow one good assembly. The time to receive new conform stud is a minimum of 6 months. After discuss about the situation with NG BO the solution is to assembly the stud with Loctite and a distance, between the end of the stud and the face of the coaming, of 82mm (0+0,5) . When it will be supply new stud, the easier solution to remove and replace the non-conform stud without disassembly the PELA can be to change 2 stud per 2 stud in opposite side and re-do the resistance and leak test at the end. With this solution we don't need to remove the SKF coopling. Use loctite 270 because after test the process with loctite 243 we saw that was not enough strong and the stud were turning during torque tight. | in accordnace with level2 proposal , the position of all studs has to be mesured and indicated in the B11 inspection file A work has to be made between the studs , the nuts and the body of sterngland to be sure that the studs will be not umthightered during sea trial. The solution is acceptable until RANAE if there is no problems The decision for a new solution on this particular mounting will be decided at the RANAE. D BERNEDE | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 280 Dias | Jean Christophe Laurent | MB | NCR-ICN-ESC-12-0330-2021; NCR-ICN-ESC-12-0206-2021; NCR-ICN-UFEM-12-299/2018 | NO | NO |  |  |  | Informações incorretas ou imprecisas | 2021-11-16 18:04 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0444-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-16 16:41 | Nível 2 | COS-SMB-206044, COS-SMB-206043 | CTE01003918 | PCP 6.1 | The inspection F06 of the valve EM00013-18SC011D00163-008-ISSARTEL was performed 2 years before the mounting of the equipment B06. This matter is related to hull integrity in AC32013. | Não |  | Mecânico | Anomalia de Preparação | Modo operatório errado (guia Profissões, procedimento, ...) | 1. Retest the inspections B01/B02_EM00013 to validate the resistance and watertightness of the EM00013-P0120399 valve flanges. Dismount the pipe EM50100Y1-P4129081. Fit the test device over the valve EM00018 and let the valve EM00012-P0120301 OPEN. Fit a block flange over hull passage AC32013. Apply the pressure for resistance test (B01) +1% according to IT34-00-01E_B, 71 bar during 30 minutes, if no external leaks, return the pressure to 0 (zero) and performing the watertightness test (B02) feeding 53,5 bar during 30 minutes too. The internal leak inspection between the EM00013-P0120399 flanges will be ensured through the pressure drop in test manometer. External leaks is not acceptable. 2. After retests, the pipe EM50100Y1-P4129081 should be remounted and M05 and S02 updated. | In accordance with proposal. The pressure test was done without leak. B05 will be updated with new B01 and B02. | In accordance with proposal Raise NCR REGRESS and redo all inspections concerning this equipment. (David BERNEDE - ISSP) | Rodolfo Alves de Abreu | Roberto Alves Assunção Medeiros | 227 Dias |  | EM |  | NO | YES | Outros | 2021-11-16 19:01 | Carmelo Alves Batista
NCR-ICN-ESC-12-0475-2021 | 53B | ELETRIC | 2021-05-07 14:32 | Nível 2 | COS-SMB-319731 |  | PCP 6.1 | During the replacement of the clamps in order to adapt the model with the smallest chamfer, it was identified the lack of a pin that locks one of the connections on the power plate 1/4 in the CC2 of the SBR-2 as attached. | Não |  |  |  |  | A small pin is missing to lock the connection plate, we must provide a new pin. | Forward to level 3 | Take the same Power Plate 1-4 on CC2 SBR4 and install it on SBR2. Create a NCR MAT for the damaged Power Plate (NGD = 0930930253995 and 9980000002849) . As recalled in sheet C1 of the maintenance manual, the handling, removal and insertion of Power Plates must be the subject of special attention. An exhaustive check must be planned to be carried out on the other SBR2 Power Plates during the STW of the supplier Jeumont to come. | Irlan Nunes da Silva | Irlan Nunes da Silva | 206 Dias | Etienne Alexandre Sebastien Rene Berot | ME |  | NO | YES
NCR-ICN-UFEM-12-0545-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-07 15:54 | Nível 2 | COS-SMB-330724 |  | PCP 6.1 | The dimensions of SMAC Lip Seal (NGD 5330930186238 / CMD 44JO320D00002) are out tolerances. See report attached as requested by TA-NG. | Não |  |  |  |  | ICN request to use BORFLEX Lip Seal delivered in Batches SMB-RMS-CUR-DB34 or SMB-RMS-CUR-DB35 to continue the inspections and tests. The NCR-MAT-001652-2021 was opened to supply new part. | Agree with proposal. | The supplied lip seal is compliant to MAT424-1296_A applicable at the time of procurement, but however non-compliant to MAT424-1296_B now applicable. It was detected that lip seals procured according to MAT424-1296_A (large diameter and extended tolerance) could sometimes create waves in the hatch groove, but not at the level observed on the photo received for another hatch "Pb montage joint SMAC_AG00017_SBR2.jpg", so the lip seal has been stretched. Please scrap (even if it conforms to its specification) the lip seal according to MAT424-1296_A and replace it with a lip seal in stock according to MAT424-1296_B. A new lip seal will be supplied for replenishment. In addition, it is almost impossible to obtain such a wave if the seal is fitted correctly: - in view of the assembly, it was stretched from a single point A on the perimeter of the hatch towards the diametrically opposite point; - it can appear waves at 1/4 or 1/8 turn but not such a shape. Please contact the AT Naval Group so that it reminds the ICN fitters on the method of fitting the lip seal in the hatches grooves. | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 206 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0567-2021 | 53B | PIPES | 2021-07-15 17:45 | Nível 2 | COS-SMB-330822 |  | PCP 6.1 | During the turn of shaft line a pipe integrated to ME00001 was damaged. It is possible to identified it in the 3D view, that is from aft to forward with starboard to the right side of the view. | Não |  |  |  |  | NG, please review the problem found on board. | Open NCR MAT to supply the pipes 1/2 ep 2.11 mat: 316L necessary for the realization of the OM-109280 Remanufacture the pipe in accordance with the OM-109280 there are 2 pipes concerned: oil draining and oil filling of the MEP. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 136 Dias | Franck Rubis | ME |  | YES
NCR-ICN-ESC-12-0593-2021 | 53B | INTEGRATION EQUIPMENT | 2021-08-31 17:27 | Nível 2 | COS-SMB-319698 |  | PCP 6.1 | According to the attached image, the shim provided for the equipment (14SE300D00084 - SHOCK CABLE TYPE 20-15-10_2) is not suitable, not supporting the weight of the equipment. | Não |  |  |  |  | Rework. Perform the assemble of the 53B-DB02501 equipment with the new item 53B-DB02501S - 53B-P4124785 - CMD 14SE300D00084 - CABLE SHOCK ABSORBERS HELICAL-TYPE 20-15 as specified. NG Please check the project specifications if it changes. | Assembly with the material with the CMD:14SE300D00006 like SBR1 |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 89 Dias | Jean Christophe Laurent | DB |  | YES
NCR-ICN-ESC-12-0627-2021 | 53B | STW | 2021-09-28 11:45 | Nível 2 | COS-SMB-200716 |  | PCP 6.1 | The valve DB00114 presented external leaks through the ports P1 and U1 with the valve in standby position (closed). | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Need to replace valve by a new one from another submarine. In case of no stock available, Naval Group must provide the delivery as soon as possible. | The distributor DB00114-18SC173D00001 (serial number: 15/002, pilot stage: 15/007) presents leakage at the ports P1 and U1 in standby position. In standby position, normally, the air cannot pass from A1 cannot pass to U1 and P1. This wrong passage of air can be explain by o-ring damaged (items 3, 4, 7, 8, 17, 18 ? on the drawing added in the NCR). Proceed to a standard exchange of the distributor. Create a NCR MAT to manage the expertise and the reparation. Create a NCR REGRESS to manage the inspections and tests to redo. |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 62 Dias | Gildas Le Goff | DB |  | YES
NCR-ICN-ESC-12-0645-2021 | 53B | ELETRIC | 2021-10-08 13:36 | Nível 2 | COS-SMB-206085 |  | PCP 6.1 | The electrical connection bases of the EW00010 valve were damaged. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Use the electrical connection base of these same equipment supplied for the “SBR4” and open an “NCR-MAT” for a new supply. | Replace the motor of the DJ00004 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 52 Dias | Stéphane Patrick Philippe Rideau | EW |  | YES
NCR-ICN-ESC-12-0658-2021 | 53B | PIPES | 2021-10-15 16:30 | Nível 2 | COS-SMB-321783 |  | PCP 6.1 | THE LACK OF CONNECTION TO SPOOL P4122496 WAS IDENTIFIED TO CONNECT WITH P0147630 (CAP). ACCORDING TO THE ATTACHED GIR EMAIL, ICN REQUESTS A SOLUTION TO THE PROBLEM AND THE PROJECT UPDATE FOR THE OTHER SBR'S | Não |  | Tubulação | Outras Anomalias | Vários defeitos | ICN proposes to discard spool P4122496 and clamp P4116375 to connect CAP P0147630 directly to the valve as well as the example of P0133276. | See FTG-9613. | Temporarily: agreement to put a cap (CMD 44BO230D00259) directly on the valve P0104826. The pipe plan P4122496 will be updated to include CMD 18RO230D00632. However, ICN needs to open an NCR for SBR1 as it appears from the photo attached to the FTG that the valve, P0133272, which should be mounted uncoupled, is not. As per drawing SBH-PLM-3B10-000453 folio 1. Furthermore, this rigid mounting is not correct, the Ø19 holes should have been filled in before drilling the holes for the screws. | Bruno Vicente Fernandes | Sharles Gomes Silveira | 45 Dias |  | MB |  | YES | NO
NCR-ICN-ESC-12-0684-2021 | 53B | PIPES | 2021-11-08 18:01 | Nível 1 | COS-SMB-206089 |  | PCP 6.1 | The pipe P4126613 was found damaged on board. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Remanufacture the spool according to the document issued by CEDOC. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 20 Dias |  | DW |  | NO
NCR-ICN-ESC-12-0685-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-09 19:17 | Nível 2 | COS-SMB-200154 |  | PCP 6.1 | For equipment 53B-GS02502 - P0125244 - CMD 55PP000D00001 - OCULAR BOX. The right handle was removed from to meet the NCR-ICN-ESC-11-1252-2020 / SBR01. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Rework. For 53B-GS02502 - P0125244 - OCULAR BOX equipment . Carry out the supply of a new right handle for the Ocular box - CMD 55PP000D00001. See ref. SBR-ETM-000GSM0001_page 62 and 63/1450, item 9 - A right handle. Take this one from SBR 3 or SBR 4. According to NCR-MAT-001373-2021 to supply a new one. This NCR is to treat of a new one delivery of new item for SBR2, the right handle part must be supplied for SBR3 or SBR4. | Agree with proposal. Take care of the ocular box protection. A checking after mounting of all functionality will be done. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 19 Dias | Patrick Daliguet | GS |  | NO |  | Descrição Incompleta | 2021-11-10 12:17 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0686-2021 | 53B | ELETRIC | 2021-11-10 11:19 | Nível 2 | COS-SMB-206085 |  | PCP 6.1 | During AIS test of the DM system, it was identified that the DM00006 valve did not present an open signal. It was verified that the actuator control board 5.1 - DM00006L is damaged as shown in the attached photo. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | The problem must be evaluated by the NG specialist. ICN suggests testing with valve actuator board DM00008 which is with NCR-12-0541 (power board damaged). | Agree with deliberacao N1 Add picture of serial number of the AUMA where the pcb was taken |  | Rafael Thome da Silva | Rafael Thome da Silva | 19 Dias | Etienne Alexandre Sebastien Rene Berot | DM |  | NO
NCR-ICN-ESC-12-0687-2021 | 53B | STW | 2021-11-10 20:10 | Nível 2 | COS-SMB-319724, COS-SMB-206071 |  | PCP 6.1 | The DEW POINT INDICATOR DY11905 of the HP Air Dryer DY01906 presented an alarm of error instead of the temperature measurement. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Need to replace the sensor by a new one. The Air Dryer from SBR3 is segregated at Warehouse due to NCR-MAT-001006-2020. ICN proposes to use the sensor from that same Air Dryer and request a new one to refund SBR3. | Agree to canibalize the dew point sensor DY11905 CMX: 50AM800A00002, item 2 of the drawing (PARKER, product code: EA2-ZHM-100, Art.-no: ZHM-100/450, Range: -100/+20) on the air dryer of the SBR3. Need to create a new NCR-MAT to refund the SBR3, (scrap the old sensor). |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 18 Dias | Gildas Le Goff | DY |  | NO
NCR-ICN-ESC-12-0696-2021 | 53B | STW | 2021-11-19 14:40 | Nível 2 | COS-SMB-319724, COS-SMB-200247 |  | PCP 6.1 | The Air Electric Compressor Starter Unit DY02512 presented a failure preventing the start and stop of the panel by the buttons. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | A test was performed by using the pcp control from SBR3 with satisfactory results. Need to perform the exchange. | After further investigation, it was found that the thyristor of the pre-charge doesnt close. After change the control card, the pre-charge is working well and no more incident variator with the start stop button. Change the control card on sbr3 DY02512. Open NCR MAT to purchase a new one. |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 10 Dias | Etienne Alexandre Sebastien Rene Berot | DY |  | YES
NCR-ICN-ESC-12-0697-2021 | 53B | STW | 2021-11-19 16:43 | Nível 2 | COS-SMB-319333, COS-SMB-200542 |  | PCP 6.1 | Damaged MODULAR ANALYSIS CHAMBER see attachment | Não |  | Mecânico | Outras Anomalias | Vários defeitos | to replace EJ00017 | Replace the modular analysis chamber damaged (EJ00017, CMX: 50AM906D00026, NGD; 0930930263891) by a new one from the stock or SBR4. Create a NCR MAT to provide a new modular and refound the stock. Scrap the modular analysis chamber damaged. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 9 Dias | Frederic Guevel | EJ |  | NO
NCR-ICN-ESC-12-0001-2021 | 53B | NON RESISTANT STRUCTURE | 2021-11-29 13:26 | Nível 2 | COS-SMB-319698, COS-SMB-200581 |  | PCP 6.1 | Rework in according with TAF-TA-2021-1378 for DY bottles. Some non-conformities identified and there are several inconsistencies in the documents for fixing the bottles on D230 (forward) and A210 (aft). | Não |  | Chapa, suporte, antepara leve | Anomalia de Integração | Documentação inapropriada (referência errada, indicio errado, ...) | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 3 Dias | Hugues Bourget | DY
NCR-ICN-ESC-12-0130-2020 | 53B | ELETRIC | 2020-08-18 13:03 | Nível 2 | COS-SMB-319724 |  | PCP 6.1 PEND MATERIAL | Broken button on the doors of the panels DY02511 and DY02512. | Não |  |  |  |  | Change the button. NG should should inform the NGD. | Replace the BIPOLAR REVERSER 2 POSITIONS LOCKING LEVER by a new one. Open a NCR-MAT to supply NGD 0930930255198 => see the BDM-00063900 COMPRESSOR STARTER UNIT-PARTS LIST |  | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 468 Dias | Stéphane Patrick Philippe Rideau | DY |  | NO
NCR-ICN-ESC-12-0171-2020 | 53B | INTEGRATION EQUIPMENT | 2020-09-21 10:27 | Nível 2 | COS-SMB-349603, COS-SMB-STW-TOOLS |  | PCP 6.1 PEND MATERIAL | During the shipment of the SBR2 batteries, items 6.10 and 11 of the IM BB01012 broke and were repaired to continue the shipment (Annex 1). During the shipment of the batteries of the SBR2 or 13.5mm recess of the IM BB01013 it was machined to 14 mm, since the pins, item 7, did not lock as batteries (Annex 2). | Não |  |  |  |  | NCR level 1 | BB01012 (CMD 19AS000D00006): - Ask Level 3 to create NGD for items 6.10 and 11. - Open an NCR-MAT to supply 2 items of each in RMS BB01012 (CMD 19AS000D00006): - Update drawing from 13.5mm to 14mm (see drawing in Appendix 2) |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 434 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO |  |  | 2020-12-09 23:14 | Benoit Guillaume Pierre Cuquemelle
NCR-ICN-ESC-12-0176-2020 | 53B | ELETRIC | 2020-09-23 11:13 | Nível 2 | COS-SMB-200563, COS-SMB-321702, COS-SMB-200564 |  | PCP 6.1 PEND MATERIAL | The pole positions of the "J1" busbars are not compatible with the pole positions in the battery cells in the front and rear squares, in the "AFT / FWD" compartments. | Não |  |  |  |  | Use the 1.5m cell bypass cables temporarily until NAVAL GROUP presents the definitive solution to the busbar problem. | The copper bar J1 received are not compliant with the required design, see annex. Could not be fixed on board. Solution given by ICN 2,1 is not avalaible Tempory mounting solution given by TA : use 3 cables CEI 1x150 mm² per pole, meaning 9 cables per battery, 18 per boat HOW EVER THIS SOLUTION NOT ALLOW TO USE FULL POWER MAXIMUM ALLOW IS 1250A PER BATTERY | See corrective maintenance sheet C13 of the technical manual (page 99/109) "Only use three bridging connectors of the same length to bridge a cell" So use of one cable per pole. Or 3 cables of the same length to replace a J1 connector. Total need 6 cables for SBR2 (same length) Where does the power limitation requirement come from? No contraindication to use cables under 2500A. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 432 Dias | Stéphane Patrick Philippe Rideau | BB |  | NO | NO
NCR-ICN-ESC-12-0191-2020 | 53B | ELETRIC | 2020-10-06 11:48 | Nível 2 | COS-SMB-321702, COS-SMB-319730 |  | PCP 6.1 PEND MATERIAL | The connection bars of the after battery pack are incompatible with the BC02501 panel. | Não |  |  |  |  | FOLLOW LEVEL 2.2 ORIENTATION. | The copper bar E4 (pole +) received are not compliant with the required design, see annex. Could not be fixed on board on the Forward Direct Current Main Switchboard BC02501(pole +) Tempory mounting solution given by TA : use 2 cables CEI 1x120 mm² per pole of battery, meaning 6 cables per BC02501 (pole +), use the same tempory solution like SBR1 HOW EVER THIS SOLUTION NOT ALLOW TO USE FULL POWER MAXIMUM ALLOW IS 1250A PER BATTERY (Stephane Rideau) | Scrap- Destruction of non-conforming material. Naval group will replenishment the material conform. According to paragraph 2.2, for the temporary solution : installation of 6 120mm² cables per pole. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 419 Dias | Stéphane Patrick Philippe Rideau | BB |  | NO | NO |  | 2020-10-21 18:05 | Christophe Marret
NCR-ICN-ESC-12-0203-2020 | 53B | ELETRIC | 2020-10-13 14:49 | Nível 2 | COS-SMB-200716 |  | PCP 6.1 PEND MATERIAL | KE65202D cable connector lost for the construction process. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Naval Group suggests to use the same connector from SBR4 if available. If not, from SBR3, then edit a NCR MAT |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 412 Dias | Paul Fosse | KE |  | NO
NCR-ICN-ESC-12-0285-2020 | 53B | STW | 2020-11-19 18:57 | Nível 2 | COS-SMB-200258 |  | PCP 6.1 PEND MATERIAL | Damaged local / remote switch on EV02501 / EV03501 / EV02500 starter units. EV02500 - CMX 11CD300D00009 EV02501 - CMX 11CD300D00009 EV03500 - CMX 11CD300D00009 | Não |  |  |  |  | According to the similar problem addressed by NCR-ICN-ESC-11-0071 / 2018, we need to replace the accessory “Code 5930930151289 INVERTER DIAM6 UNIPOLAR YELLOW LATCH LEVER”. 3 units required for replacement. | For EV02501, in accordance with decision N1, replace the "local / remote" inverter, make an NCR-MAT to supply a new 5930930151289 "INVERTER DIAM6 UNIPOLAR YELLOW LATCH LEVER" For EV02500 and EV03500, open the cabinet door and put the inverter in place, see photo in appendix. As a reminder: some small fragile equipment is deliberately kept (pre-equipped) inside the cabinet to avoid being broken during transport. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 374 Dias | Stéphane Patrick Philippe Rideau | EV |  | NO
NCR-ICN-ESC-12-0326-2021 | 53B | ELETRIC | 2021-01-29 12:20 | Nível 2 | COS-SMB-327470 |  | PCP 6.1 PEND MATERIAL | Conector belongig to the torpedo 6 (KT05286), making impossible to connect. | Não |  |  |  |  | Use the "socket" referring to the same tube as the "SBR4" and open an "NCR-MAT" for a new supply. | The socket has been damage due to a poor protection, it is for that it is not possible to connect it. So now it is necessary to raise a NCR MAT in order to replace this device by the same device to take on SBR 4 or 3, and to order a new socket to repare this one damaged. Record all the serial number between the Damaged valve and the new. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 304 Dias | Paul Fosse | KT |  | NO |  |  | 2021-03-09 17:19 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0352-2021 | 53B | ELETRIC | 2021-02-23 15:38 | Nível 2 | COS-SMB-206081 |  | PCP 6.1 PEND MATERIAL | Fixing the damaged connection base, making it impossible to connect the connector. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Check if 18SC013D00036 available at the store. Replace and open an NCR-MAT to provision a new one. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 279 Dias | Stéphane Patrick Philippe Rideau | EG |  | NO
NCR-ICN-ESC-12-0395-2021 | 53B | SEATING | 2021-03-23 17:47 | Nível 2 | COS-SMB-207732 |  | PCP 6.1 PEND MATERIAL | Change in seating fixing elements P4026010. For the seating P4026010 to be level with the structure of the candle, the shim’s painted red in the annex, had to increase the thickness and with that the M16x50x50 (32VI120D00275) screws do not give enough thread. | Não |  |  |  |  | Follow 1.1 request and the orientation to change the material, use 80 - 32VI110D00898 (COATED SCREW H M16X80X38 CL8.8), 80 - 32VI310D00166 (COATED HFR NUT M16 CL8 DAX2) and 160 - 32VI410D00004 (COATED PLAIN WASHER M ND16 40CRMOV4-6). | Repair, Agrees with paragraph 2.1: lenght of the screw adjusted and bolting assembly in steel material. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 250 Dias | Hugues Bourget | EQ |  | NO |  |  | 2021-05-06 13:57 | Frederic Pavic
NCR-ICN-ESC-12-0421-2021 | 53B | PIPES | 2021-03-29 18:17 | Nível 2 | COS-SMB-325846, COS-SMB-325847, COS-SMB-206065 |  | PCP 6.1 PEND MATERIAL | Ballast tank passage AB35055 was not protected, some stripes were seen, and some corrosion could be seen on ballast tank passage AB35013. The paint cover the main part of the passage, the painting was done without any surface preparation. Besides that the ballast passages are not completely painted (COR-2021-900343). | Não |  | Tubulação | Anomalia de Integração | Montagem incompleta, desordenada, degradada | NG, please review the suggestion given by ICN. | Rework as per ICN proposal. Open a NCR/Regress |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Hugues Bourget | AB |  | YES |  | Outros | 2021-10-14 19:29 | Franck Rubis
NCR-ICN-ESC-12-0437-2021 | 53B | ELETRIC | 2021-04-08 15:00 | Nível 2 | COS-SMB-319738 |  | PCP 6.1 PEND MATERIAL | Identification terminal with provisional identification, from the manufacturer. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | The FC00522 was received with the wago terminals marked with the felt. Kindly provide printed plastic labels suitable for wago terminals, please. Wait for BO orientation. | Refer to NCR-ICN-ESC-12-0106-2020-Answer. Multiple marking systems horizontal printing NGD 9905930185410, have been sent. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 235 Dias | Stéphane Patrick Philippe Rideau | FC |  | NO | NO
NCR-ICN-ESC-12-0474-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-07 14:15 | Nível 2 | COS-SMB-200716 |  | PCP 6.1 PEND MATERIAL | During stage 5.2 to perform the maximum operating depth test (MOD) the MGC N ° 1 (HL12661)(Serial number 172.16.1.101) presented problems and needed to be replaced by the reserve equipment (this NCR replaces NCR-ICN-ESC-11-1531-2021). | Não |  |  |  |  | Proceed as 1.2 | It's necessary to repair before using on SBR2. Please open a NCR MAT for NVG to organize this repair |  | Marcos Messias da Cunha | Marcos Messias da Cunha | 206 Dias | Yann Jaouen | HL |  | NO
NCR-ICN-UFEM-12-0546-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-12 10:38 | Nível 2 | COS-SMB-330724 |  | PCP 6.1 PEND MATERIAL | According NCR-ICN-ESC-12-0400-2021, the dimensions of Balancing System AG00037 are out tolerances. See report attached as requested by TA-NG. | Não |  | Mecânico | Anomalia de Integração | Defeito de nivelamento, defeito, dimensional, ... | Rework. See comments and solution in attachment "2.1 ICN SOLUTION". Send to TA Patrick Daliguet to analysis. | AG00037 CMD: 01PE200D00035 Production order cronos: OS1306 Agree with level 2.1, the work was done following annex enclosed. | In accordance with rework done at the shipyard to allow right maneuver of the hatch AG00017 / balancing AG00037. Please proceed to a dimensional report of the parts and join it to the traceability file of the hatch and balancing. | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 201 Dias | Patrick Daliguet | AG |  | NO | YES | Descrição Incompleta | 2021-10-01 16:32 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0501-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-19 19:59 | Nível 2 | COS-SMB-200581, COS-SMB-321709 |  | PCP 6.1 PEND MATERIAL | During the assembly of the task equipment 50,300 of the DEI-200581-80500-12-001, the nuts (item n ° 6 and 8) were damaged during the assembly process. See attached. | Não |  |  |  |  | For the assembly of the AC44031 equipment. Necessary replace new nuts and rod threads, according to (items 6 and 8) referring to MAT427-0026 and MAT427-0027. Open NCR MAT. | Raise NCR MAT to launch the purchase of new nuts and stud rods | In accordance with level 2.2 proposal (David Bernerde) | Vinicius Siqueira dos Santos | Ernanes de Souza | 193 Dias | Patrick Daliguet | AC |  | NO | NO
NCR-ICN-ESC-12-0510-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-25 17:03 | Nível 2 | COS-SMB-319721 |  | PCP 6.1 PEND MATERIAL | The DA02500 panel selector button (Bilge water sparateur control panel) MANUAL / AUTO was lost during the installation process. See attached photo. | Não |  |  |  |  | A new selector button for the panel must be provided. NG must outline the button for a new supply. | Take the commutator S1 (AUTO/MAN) of the panel DA02500 of SBR4 Open NCR MAT to refund it |  | Rafael Thome da Silva | Rafael Thome da Silva | 187 Dias | Etienne Alexandre Sebastien Rene Berot | DA |  | NO
NCR-ICN-ESC-12-0520-2021 | 53B | STW | 2021-05-28 14:46 | Nível 2 | COS-SMB-319725, COS-SMB-200563 |  | PCP 6.1 PEND MATERIAL | Some of the Develec Sensors (SBR1 and SBR2) has its labels unreadable due its use. Request for supply of blank label and printing software ICN proposes to manufacture the label and exchange the unreadable ones. | Não |  |  |  |  | ICN requests NG to check comments. | The SBR1 / SBR2 / OAB RSU sensor identification labels are partially damaged due to contact with the electrolyte. => Naval Group reminds that clean gloves must be used for all sensor disassembly and reassembly operations => Naval Group requests to open an NCR-MAT to supply the following labels: - 14S0xxx to 14S0400 - 15S0xxx to 15S0400 - 18S20xxx to 18S20XXX or provide 1200 blank labels and the print file |  | Luiza de Oliveira Pereira | Marco Aurelio Barbosa | 185 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO
NCR-ICN-ESC-12-0558-2021 | 53B | ELETRIC | 2021-07-06 14:16 | Nível 2 | COS-SMB-206098, COS-SMB-206100, COS-SMB-337143, COS-SMB-206081, COS-SMB-206100, COS-SMB-206044 |  | PCP 6.1 PEND MATERIAL | During the verification of the EG00130, EG00140, EG00234, EG01110, EG01130, EG01140, EG00110 and EG00205 equipment, to carry out the NCR-ICN-ESC-12-0498-2021, some items that are no longer found in the valves were found. Attached is an example of the items we need. | Não |  |  |  |  | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 146 Dias | Stéphane Patrick Philippe Rideau | EG | NCR-ICN-ESC-12-0498-2021 | NO
NCR-ICN-ESC-12-0538-2021 | 53B | ELETRIC | 2021-06-14 18:54 | Nível 2 | COS-SMB-200542 |  | PCP 6.1 PEND MATERIAL | FR00002 equipment connection terminal screw missing, it was found like this. Below are images attached. | Não |  |  |  |  | USE FIXING ELEMENTS SUPPLIED FOR "SBR4" AND OPEN "NCR-MAT" FOR NEW SUPPLY. | Take the power terminals from SBR4 if available. Open an NCR-MAT to supply new terminals |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 167 Dias | Stéphane Patrick Philippe Rideau | FR |  | NO
NCR-ICN-ESC-12-0541-2021 | 53B | ELETRIC | 2021-06-15 18:36 | Nível 2 | COS-SMB-200444 |  | PCP 6.1 PEND MATERIAL | It was identified during the preparation of the DM00008 valve adjustment that the energizing (supply) board of the 5.1 AUMA actuator has the varistor burnt. | Não |  |  |  |  | The actuator must be repaired or replaced with a new one. | Due of a supply issue of the actuator DM0008 during trials at workshop, found that the PCB SUPPLY is burned (varistance) picture attached Take a new actuator on SBR4 Open NCR MAT to buy a new PCB SUPPLY for AUMA 05.1 |  | Rafael Thome da Silva | Rafael Thome da Silva | 166 Dias | Etienne Alexandre Sebastien Rene Berot | DM |  | NO
NCR-ICN-ESC-12-0544-2021 | 53B | ELETRIC | 2021-06-17 13:34 | Nível 2 | COS-SMB-200569, COS-SMB-200712 |  | PCP 6.1 PEND MATERIAL | The equipment KD05020 / KD05030 / KD03010 / KD03020 / KD06020 / KD06030 / KD06040 / KD06050 / KD06060, had their connectors used in SBR1, the need for the incident, we currently need these same connectors for application in SBR2. There is an NCR-MAT to supply a new supply of connectors for the SBR2”. | Não |  |  |  |  | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 165 Dias | Herve Gerard de Backer | KD |  | NO
NCR-ICN-ESC-12-0584-2021 | 53B | ELETRIC | 2021-08-17 16:57 | Nível 2 | COS-SMB-200551, COS-SMB-331623 |  | PCP 6.1 PEND MATERIAL | The RM62559D / RM62571D / RM62558D/ RM62555D/ RM62570D/RM62554D cable connectors belonging to the RM00087/RM00058 equipment were not supplied with the equipment as described in DEI-331623-80500-12-007/DEI-200551-80500-12-014. | Não |  |  |  |  | As described in 1.2, in the annex "RM00058_RM00087", the request for supplying the connectors with the equipment follows. | DEI-331623-80500-12-007 / DEI-200551-80500-12-014 are ICN job orders, they are not material definition documents. Look for missing connectors at the store. |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 104 Dias | Stéphane Patrick Philippe Rideau | RM |  | NO
NCR-ICN-ESC-12-0602-2021 | 53B | PIPES | 2021-09-08 19:54 | Nível 1 | COS-SMB-327472 |  | PCP 6.1 PEND MATERIAL | The equipment KT02211 was lost in the construction process. | Não |  | Tubulação | Anomalia de Aplicação | Modo operatório errado | Prepare an NCR-MAT to request the material for NG. | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 81 Dias |  | KT |  | NO
NCR-ICN-UFEM-12-0519-2019 | 53B | SEATING | 2019-07-01 19:53 |  | COS-SMB-200386 |  | PROD 6.1 | The seating P4020367 was not welded with dimensions according to the drawing SBH.4C20.SAD.004162_C. See annex 1. | Não |  |  |  |  | Remove the seating using Annex1. Reinstall again using SBH.4C20.SAD.004162_D and CTE´s annexed. | Rework as per original. Use annex 1 for removing. |  | Hellen Cristina Vieira Paes | Luiz Felipe Silva Moreira | 881 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0524-2019 | 53B | INTEGRATION EQUIPMENT | 2019-07-29 12:11 |  | COS-SMB-200551 |  | PROD 6.1 | It was identified during the pre-installation that the joystick of the KO02550 and KO02560 equipments are damaged because when the keyboard is closed the joystick button is pressed. Damage identified by ICN production team (UFEM) - CMD 62ER000D00181. | Não |  |  |  |  | Replace the joystick. | Please send this NCR to level 3 (Patrick Renavot),for analyse and purshase NG will analyse if the damage is due to a design defect or bad treatment of the material The protection team must protect the joystick. | Naval Group will send replenishment material batch number SMB1234-CMS1-DB1 | Hellen Cristina Vieira Paes | Osvaldo Luiz de Moura Filho | 854 Dias | Philippe Falquerho | KO02550, KO02560 |  | NO | NO |  | 2020-03-09 17:49 | Philippe Falquerho
NCR-ICN-UFEM-12-0536-2019 | 53B | NON RESISTANT STRUCTURE | 2019-11-13 15:39 | Nível 2 | COS-SMB-321680 |  | PCP 6.1 PEND MATERIAL | The panel was trimmed at the theoretical contour at one of the sides where it should be trimmed with overlength. See Annex 1. AH00411 - CASING PANEL NUMBER 11 | Não |  |  |  |  | ICN suggests adjustment during installation onboard the cut face on the theoretical contour. | Accepted as it is. After presentation on board new analysis will be done. |  | Adriano Ribeiro Pinheiro Chamadoira | Bruno Marcel Lima Ferreira Amancio | 747 Dias | Hugues Bourget |  |  | NO
NCR-ICN-UFEM-12-0537-2019 | 53B | INTEGRATION EQUIPMENT | 2019-12-04 17:40 | Nível 2 | COS-SMB-321700, COS-SMB-319711 |  | PROD 6.1 | In the disassembly of the diesel engines by the MTU team, rust was detected in the exhaust elbows (Part nº 5561401609). See item 1 of drawing BDM-00132709_FL605 and ANNEX01. | Não |  |  |  |  | See DA 3.2 comments and attachments. The products were added according PROD 6.1 request. | Repair To wait the Naval-group design authority answer | Replace the defective elbows, Naval Group will send new ones - Check the entire SBR 1/2/3/4 series to check if the problem is present on the other SMs. | Osvaldo Luiz de Moura Filho | Ernanes de Souza | 725 Dias |  | BD |  | NO | NO |  | 2020-11-17 17:24 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0044-2020 | 53B | SEATING | 2020-02-13 18:19 | Nível 2 | COS-SMB-319718 |  | PCP 6.1 PEND MATERIAL | During dimensional inspection, it was verified that the seating P4165381 is not conform. It is necessary adjust the seating to install the equipment EQ00511. (See NCR-ICN-ESC-11-0726-2019, DECISION L3 DAVID BERNEDE - ANNEX) | Não |  |  |  |  | Wait Naval Group solution to change the seating P4165381 as mentioned in NCR-ICN-ESC-11-0726-2019. | After inspection the seating hight is not in acordance with the drawing . rework as per original. |  | Charles Douglas de Oliveira | Luiz Felipe Silva Moreira | 654 Dias | Patrick Daliguet | EQ |  | NO
NCR-ICN-UFEM-12-0363-2018 | 53B | INTEGRATION EQUIPMENT | 2018-11-26 02:00 |  | COS-SMB-200581 |  | PROD 6.1 | The motor housing has been broken during the test of the hydraulic motor capstan, as soon as the test pressure reached 200 bar. Fluid: FHARI oil. PEE: 246 bar - according MAT527-0167_A, ITEM 6.4. | Não |  |  |  |  | TAKE THE HYDRAULIC MOTOR CAPSTAN FROM SBR3 WITHOUT PERFORMING ANY TEST; INSTALL ON BOARD AND MAKE THE TEST DURING COMISSIONING. DECISION: SEND THE HYDRAULIC MOTOR CAPSTAN FROM SBR2 TO TECHNICAL ANALYSIS BY MANUFACTURER AND CHECK FOR POSSIBLE REPAIR/REP | Send to level 3. Decision: Send to level 3. | The broken dydraulic motor have to be scrapped. ICN have to send to Naval Group the proof of scrapped. | System |  | 1099 Dias |  |  |  | NO | NO
NCR-ICN-UFEM-12-0478-2019 | 53B | GRP | 2019-04-24 03:00 | Nível 2 | COS-SMB-319167 |  | PCP 6.1 PEND MATERIAL | The recess designed to fit the GRP covers AH02B16 and AH02B17 was laminated considering a 6mm shim, which resulted in a 16mm depth recess, instead of 10mm. | Não |  |  |  |  | ICN proposes to repair as suggested by TA-Naval Group, laminating 6 layers of VS830g/m² over the recess in order to correct the mistake. The suggested procedure/scheme can be seen on annex 1. DECISION: TO BE FORWARDED TO EXPERT LEVEL 2. | REWORK AS PER T.A. ORIENTATION. SUGGESTED DECISION: REWORK. | N/A | System |  | 950 Dias | Hugues Bourget |  |  | NO | NO
NCR-ICN-ESC-12-0078-2020 | 53B | NON RESISTANT STRUCTURE | 2020-06-10 11:00 | Nível 2 | COS-SMB-339463, COS-SMB-339462 |  | PROD 6.1 | Modification in the positioning of the seating’s P4169957, P4169967 e P4169971 according to drawing review SBH.2D31.SAD.006298_B. During the assembly oh the BQ’s pipes, there was interference in the positioning of the seating’s. | Não |  |  |  |  | The job order CC-339463-18111-12-001_D already considered the SMB-TDP-PR-6026603 that made this change in the document. Use the C23 and G02 annexed to make the inspections. | Rework Rework as per original. during the remotion if the thickness is below that the minimum requered, open an NCR/RO to build up. Carry out the welding inspections requered. |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 537 Dias | Hugues Bourget | BQ |  | NO
NCR-ICN-ESC-12-0086-2020 | 53B | INTEGRATION EQUIPMENT | 2020-06-23 12:51 | Nível 2 | COS-SMB-200565 |  | PROD 6.1 | Measure found in KE structure is out of tolerance. Due to the problem found on measures in SBR1, an inspection was made in SBR2 , and the measure found is out of tolerance. According the measure report, the KY system was assembly out of tolerance, following the SMB-204491. | Não |  |  |  |  | Waiting for NG orientation. | It's necessary to redo the alignment following the email in annex. |  | Renato da Silva Goncalves | Osvaldo Luiz de Moura Filho | 524 Dias | Patrick Daliguet |  |  | NO
NCR-ICN-ESC-12-0100-2020 | 53B | STW | 2020-07-14 16:03 | Nível 2 | COS-SMB-200260, COS-SMB-319737, COS-SMB-319738 |  | PROD 6.1 | The Elastomer monting (14SE100D00006) for the FH system fan panels and motors have not yet been installed, as they have not been delivered in Brazil. I would like to know if I can perform the STW tests and the HCT (FH2C) tests without Elastomer monting? | Não | [5 empty] | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 503 Dias | Sebastien Jacquin | FH |  | NO
NCR-ICN-ESC-12-0102-2020 | 53B | ELETRIC | 2020-07-15 15:50 | Nível 2 | COS-SMB-319730 |  | PROD 6.1 | The BC22501 junction box (CMD 11BJ000D00078) of the SBR2 is totally different from the one in the SBR1 does not conform to document BDM-00073604. | Não |  |  |  |  | Wait for NG orientation | In accordance with the declaration, the bj does not correspond to the BDM. Please clarify. Please note this bj is a prerequisite for J1 and J3 (battery boarding) | kits must be provided to the front office for October 2020 for final modification of the SBR2 junction box see annex Seen with TA : SMD-TDP-PR-6783312 . OM 127188 . | Jair de Barros Sena de Araujo | Sergio André Telles Soares | 502 Dias | Stéphane Patrick Philippe Rideau | BC |  | NO | NO
NCR-ICN-ESC-12-0103-2020 | 53B | ACOUSTIC DISCRETION | 2020-07-20 18:46 | Nível 1 | COS-SMB-200542 | CTE00756885, CTE00758560, CTE00758561, CTE00758562, CTE01054115, CTE00756875, CTE01054127, CTE00758940, CTE00758941 | PROD 6.1 | Due to the BSMI boarding of the SBR3, the mounts of the DM00001 and DM00002 pumps were removed from the SBR2 to be placed in the SBR3. | Não |  |  |  |  | After reassembling the mount, redo the inspections according to the especific CTE list. DM00001: Inspections A03, MS02_1 and MS02_2 must be redone. DM00002: Inspections A03, MS02_1 and MS02_2 must be redone. | NCR LEVEL 1 |  | Franciellen da Silva Braga | Rogerio Milani | 496 Dias |  | DM |  | NO
NCR-ICN-ESC-12-0106-2020 | 53B | ELETRIC | 2020-07-27 12:34 | Nível 2 | COS-SMB-200542 | CTE00931543 | PROD 6.1 | Terminal strip identified provisionally with adhesive. See attached photo. | Não |  |  |  |  | Wait for NG orientation | Provided standardized terminal strip (to replace adhesif labelling) | Naval Group will send WMB multiple marking system Horizontal printing 9905930185410 | Fabricio Duarte Ramos | Sergio André Telles Soares | 490 Dias | Stéphane Patrick Philippe Rideau | FC |  | NO | NO
NCR-ICN-ESC-12-0120-2020 | 53B | NON RESISTANT STRUCTURE | 2020-08-12 13:33 | Nível 2 | COS-SMB-339463 |  | PROD 6.1 | Modification in the positioning of the seating’s P4169961, P4169959 e P4169069 according to drawing review SBH.2D31.SAD.006298_B. During the assembly oh the BQ’s pipes, there was interference in the positioning of the seating’s. | Não |  |  |  |  | The job order CC-339463-18111-12-001_D already considered the SMB-TDP-PR-6026603 that made this change in the document. Use the C23 annexed to make the inspections. | carry out of inspections |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 474 Dias | Hugues Bourget | BQ |  | NO |  |  | 2020-08-12 18:25 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0136-2020 | 53B | PIPES | 2020-08-21 14:29 | Nível 2 | COS-SMB-206115, COS-SMB-327464, COS-SMB-206080, COS-SMB-200728, COS-SMB-206095, COS-SMB-206057, COS-SMB-337142, COS-SMB-206055, COS-SMB-206065, COS-SMB-206084, COS-SMB-206089, COS-SMB-200730, COS-SMB-200443, COS-SMB-206070, COS-SMB-200457, COS-SMB-206173, COS-SMB-327471, COS-SMB-200469, COS-SMB-200445 |  | PROD 6.1 | It was observed during the closing of M01 inspections that some spools had inconsistencies related to galvanizing. | Não |  |  |  |  | We suggest corrective actions according to Annex 1. For other products with the same problem, we suggest the same actions defined in this NCR. | ICN must clarified the situatiopn - identified the date of galvanisation - compare with the welding date - if discrepancy check if a new CTE had been issue after welding Situation not acceptable as it is |  | Elaine Maria Ignacio da Silva | Bruno Marcel Lima Ferreira Amancio | 465 Dias | Franck Rubis | N/A |  | NO
NCR-ICN-ESC-12-0164-2020 | 53B | PIPES | 2020-09-16 11:11 | Nível 2 | COS-SMB-200469 |  | PROD 6.1 | Two welds were reproved on x-ray and we must do a repair. | Não |  |  |  |  | NG, please analyze the problem. | To repair and access to the welds on tubes DB50014M1 and DB50004M1: - it is necessary to disassemble the tube P4147761 -cut the support P4147774 REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 439 Dias | Franck Rubis | DB |  | NO
NCR-ICN-ESC-12-0170-2020 | 53B | ELETRIC | 2020-09-18 11:18 | Nível 2 | COS-SMB-319731 |  | PROD 6.1 | The solution for the need to ground the equipment “BD02527 and BD02528” was provided in “NCR-ICN-ESC-11-0513-2019” with the application of FTG-7158, in alignment with “TA” Stephane Rideau, the same instructed to open an “NCR” to register that the problem was solved with the application of FTG-7158 on a date prior to the date of “OM110635”. | Não |  |  |  |  | ACCEPT AS IT IS | The grounding of the cabinet was forgotten during the design The problem has been solved with the FTG-7158 before to receive the OM110635 Awaiting BO decision to confirm : 1 - acceptance as is 2 - rework now, with all the regressions that implies 3 - rework at RANAE | Carry out a ground continuity check to be carried out in order to validate the provisional assembly. OM-110635 to be carried out during the RANAE on SBR2. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 437 Dias | Stéphane Patrick Philippe Rideau | BD |  | NO | NO
NCR-ICN-ESC-12-0180-2020 | 53B | ACOUSTIC DISCRETION | 2020-09-29 19:39 | Nível 1 | COS-SMB-319760 | CTE00933863, CTE00933860 | PROD 6.1 | During MS02 inspection on DP20204 and DP20206 the lack of shims it was checked. These shims are used to complement the seating thickness in the contact area of the resilient mounts. These shims are found in the drawing SBH.3B22.SMD.004549 F10 and F12 (items 144, 163 and 164 for DP20206 and items 155, 156, 157 and 158 for DP20204) | Não |  |  |  |  | Rework according to SBH.3B22.SMD.004549 Do the assembly including the shim according to the drawing. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 425 Dias |  | DP |  | NO
NCR-ICN-ESC-12-0199-2020 | 53B | ELETRIC | 2020-10-07 16:42 | Nível 2 | COS-SMB-319760 | CTE00929628 | PROD 6.1 | Interference with the piping, preventing the opening of the equipment door, as shown in the attached photo. | Não |  |  |  |  | Wait for NG orientation | 1/ check the position of the electrical box GN22701 on board 2/check the iso of the pipe P4127322 after disassembly 3/adjust the pipe P4127322 to eliminate the interference when opening the electrical box GN22701 4/do the same checks for SBR 3 and SBR 4 REPAIR |  | Geraldo Alves Simoes Filho | Sergio André Telles Soares | 418 Dias | Franck Rubis | GN |  | NO
NCR-ICN-ESC-12-0186-2020 | 53B | STW | 2020-10-02 11:16 | Nível 2 | COS-SMB-319362, COS-SMB-206090 |  | PROD 6.1 | The o'ring kit inside HP00002 valve (18RT010D000816 C002, s/n 002) is not ok, since the vedation is not good. ICN requests NG a new o´ring kit to replace them of this valve. ICN requests NG the list of tests that must be performed in this valve to certify its functionality. | Não |  |  |  |  | ICN requests NG a new o'ring kit to replace and test the valve. | This valve has be damaged due to bad alignment, to have a new O-ring kit it is necessary to raise an NCR MAT. | A NCR MAT has to be raised and sentto level 3 to analyze if only new o'ring is sufficient and if all the valves needs to be checked by a specialist. It is necessary before changing the o'ring to inspect completely the valve including a dimensional check/measurement of all parts of the valve ICN has all the informations to find the O'ring | Luiz Carlos do Carmo Junior | Luiz Carlos do Carmo Junior | 423 Dias | Paul Fosse | HP |  | NO | NO |  | 2020-11-05 13:11 | Frederic Guevel
NCR-ICN-ESC-12-0226-2020 | 53B | MECHANICAL | 2020-10-22 19:50 | Nível 2 | COS-SMB-200228 | CTE00937278 | PROD 6.1 | During the inspection D95-21 - CHECK THE HEIGHT OF THE RADAR ANTENNA MAST EXTENSION (CTEPROV20022801) it was detected that the measurement is not in compliance. See CTE attached. | Não |  |  |  |  | Accept as it is. This assembly was authorized by TA Naval Group. | That is important and necessary to respect it is the height of radar beam in order to have the Radar Pod at the good height. For that following the thickness of the shim s hydraulic jack we adjust the heights of the beam with the adjustable Radar mast extension. So your CTE must take into account this value, like that we are be able to know if Thickness Shim + adjustable Radar mast extension + Radar mast Beam are correct to put in place the Radar POD. |  | Neimar Mayrink da Silva | Joao Paulo Schneider Gonzaga | 402 Dias | Paul Fosse | RM |  | NO
NCR-ICN-ESC-12-0231-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-24 12:00 | Nível 2 | COS-SMB-319712 |  | PROD 6.1 | On two valves inside boxes in workshop for SBR2 it was found problems: The first: CMX:18SC000D00157 P/N:D1240111 S/N:004 The second: CMX:18SC000D00156 P/N:D1240110 S/N:003 | Não |  |  |  |  | Repair. 1) Clean/degrease the surface using WD 40 or equivalent; 2) Smooth grinding with Carborundum Stone 400/1000 and sandpaper 320/500 in order to reduce/remove the scratches and achieve a good shape. 3) Carry out flatness inspection on the tightness face. 4) Until to assembly step, keep the surface cleaned and protected to avoid new damages. | -In accordance with level 2.1 ( Patrick Daliguet) | Agree with paragraph 2.1: And redo tightness tests before assembly. If ICN does not have the capacity to conduct them, then tests B01 and B02 to be done on board in the presence of Naval Group. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 401 Dias | Patrick Daliguet | BQ |  | NO | YES
NCR-ICN-ESC-12-0299-2020 | 53B | ELETRIC | 2020-12-16 18:20 | Nível 2 | COS-SMB-319228, COS-SMB-CAB-OO-RM |  | PROD 6.1 | Damaged cable OO64027B on board during the construction process. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | Replace the damage cable by a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 347 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO
NCR-ICN-ESC-12-0253-2020 | 53B | MECHANICAL | 2020-11-04 14:42 | Nível 2 | COS-SMB-200542 |  | PROD 6.1 | MN03-260 wedges, purchased in Brazil by the nationalization contract, are showing breakage after the application of 923Nm torque. We believe there is a manufacturing error in the shoes. | Não |  |  |  |  | Send to NG analysis. | -Elastic mount (MN03-260) of DM00001S and DM00002S were tightened by normal value following SMB-200949: 923Nm -bumpers were destroyed. -Check the number of lot and isolate all in store, change all elastic mount by new ones with a different lot. -Ask to the manufacturer to supply new elastic mount conform and follow this by NCR MAT (Patrick Daliguet) 07/01/2021: The solution is not wrong. It is clear. Change for new ones from a different lot. If you don't have a differente lot, a NCR MAT should be opened for purchase new elastic mounting. 19/03/2021: After analyse the back office the damage of the rubber was due to didn't use of special tool to immobilize buffer ring during the tightening. see the document in annex (extract of SMB-200949). | The damage of the rubber is not due to a manufacturing problem on the elastic mount, but is due to the fact that the mount "head" was not handle in place with the associate tool during the mounting of the mount. Damage of the rubber is due to the twisting of the mount as it can be seen by the "lines" at the surface of the damaged material. Not acceptable as it is. Mounts are to be replaced by new ones that are going to be orderd (costs will be charged to ICN), and are to be mounted according to SMB-200949. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 390 Dias | Patrick Daliguet | DM |  | NO | NO
NCR-ICN-ESC-12-0250-2020 | 53B | TRACEABILITY | 2020-11-04 12:09 | Nível 2 | COS-SMB-200716 |  | PROD 6.1 | After performing the traceability inspection it was found that the traceability reference it was not found on the AG00066 equipment (CMD: 14VM000D00011). | Não |  |  |  |  | Rework. We request to Naval Group the serial number to be engraved on the equipment and the delivery of the Certificate and Declaration of Conformity to validate the B07. | -In accordance with level 2.1 -Traceability will be provide by NG and engraved by ICN. ( Patrcick Daliguet) | Traceability of the quick release must be ensured in accordance with SMB-2000052 as follows: CMD / Unique manufacturer serial number / Body supplier contract number For the naked body: As it is not possible to differentiate the parts which were machined in sets of 3, ICN must engrave the following information on the body: 01PM000C0922 (CMD Bare body) / number to follow 001 to 003/6418493 (supplier contract no. ) For the mobile part: Once assembled, ICN will have to engrave at the place deemed most suitable: 14VM000D00011 (CMD PM complete) / same serial number as the body (001, 002, 003) / ICN (to identify that ICN made the assembly ) After test: ICN must engrave at least PEH and the value of the test. Note: ICN must verify that the instructions relating to the tests of the mobile part (see MAT424-0800_K §9,1,5) have been respected. | Emanuela Lucia Justino dos Santos | Franciellen da Silva Braga | 390 Dias | Patrick Daliguet | AG |  | NO | NO
NCR-ICN-ESC-12-0247-2020 | 53B | ELETRIC | 2020-11-03 18:10 | Nível 2 | COS-SMB-200542, COS-SMB-200710, COS-SMB-319731 |  | PROD 6.1 | The “53B-OO22906, 53B-OO22604, 53B-OO22900” equipments is not supplied with the internal connections of the “53B-OO22904, 53B-OO24230 53B-OO24308” connected to the internal terminals. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | For UPS internal modules integrated in junction boxes according to document SMB-201629 (DEFINITIONS OF UPS MODULES) Call the wiring kit 49AU100D00072. For P0101461, apply the wiring described in BDM-00073923 For P0101439, apply the wiring described in BDM-00073670 For P0101458, apply the wiring described in BDM-00073674 Open a NCR-MAT to supply cables as following Cable NGD 0930930277886 => quantity 4 Cable NGD 9980000062323 => quantity 7 | 07/07/2021 : Please apply repair order OR-282037 delivered in answer to NCR-MAT-001336-2021 (Fabien RENVOISE) | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 390 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO | NO |  | 2020-12-01 11:02 | Frederic Pavic
NCR-ICN-ESC-12-0308-2021 | 53B | INTEGRATION EQUIPMENT | 2021-01-15 11:24 | Nível 2 | COS-SMB-319712 |  | PROD 6.1 | On the 2 blocs BQ00017 and BQ00018 to fit the ruch adapter, a shim is mounting between the bloc and the adapter to fix the orientation. Inside nominal dimensions of shim (OD 25) are: external Ø:46mm internal Ø:34,5mm not compatible with rush adapter. The good size is OD 20 NNO: 5365143084793. | Não |  |  |  |  | Replace the shim by OD 20 NGD: 5365143084793. Update the nomenclature. | A temporary shim in CuAl10Ni5Fe4 will be define in replacement of the definitive ones to allow the manufacture of pipes. NCR MAT will be raise to update nomenclature and provided the good shims |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 318 Dias | Patrick Daliguet | BQ |  | NO
NCR-ICN-ESC-12-0328-2021 | 53B | PIPES | 2021-02-01 11:33 | Nível 2 | COS-SMB-327471 |  | PROD 6.1 | During the correction proposed on NCR-ICN-ESC-12-0276-2020 the pipe P4161842 was damaged and set into a scrap condition. | Não |  |  |  |  | Manufacture a new pipe and replace. | REWORK Manufacture a new pipe . -Inspection M01 category A -Inspection M10 -Pressure test |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 301 Dias | Franck Rubis | KT | NCR-ICN-ESC-12-0276/2020 | NO
NCR-ICN-ESC-12-0365-2021 | 53B | NON RESISTANT STRUCTURE | 2021-03-08 12:57 | Nível 2 | COS-SMB-319088, COS-SMB-339470 | CTE00851422 | PROD 6.1 | During inspection D94_14 CTE00851422-1 dimensions were detected for dimensional tolerance. See attachment. | Não |  |  |  |  | Deviation will be corrected during machining onboard. Accept as it is | accept as it is will be correct during machining on board The mounting sequence of DSRV plateform is diferrent than the original. This inspection was done after platform welding and before machining . A new inspection will be done after the machining |  | Neimar Mayrink da Silva | Felipe Trigueiros Silveira | 266 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0339-2021 | 53B | PIPES | 2021-02-10 11:59 | Nível 2 | COS-SMB-206144, COS-SMB-319170 |  | PROD 6.1 | It was identified an impossibility of assembly order onboard due to a mistake in the assembly sequence. To solve that we must disassemble the EV pipes (EV51215J4 and EV51238J4) in order to make possible to assembly the DG02280. | Não |  |  |  |  | NG, please analyze the problem found on board. | Agree to dismount the pipes EV51215J4, EV51238J4, remount them and create a NCR REGRESS to report the remounting inspections M05, the pipes coupling (straub) mounting inspections and to manage the tests to redo on the EV circuit. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 292 Dias | Gildas Le Goff | EV, DG |  | NO
NCR-ICN-ESC-12-0351-2021 | 53B | ELETRIC | 2021-02-23 15:33 | Nível 2 | COS-SMB-200492, COS-SMB-200494, COS-SMB-CAB-UA-UW |  | PROD 6.1 | The cables UA63332D, UA63331D, UA66640D.UA67500D were found on board with their respective terminals ready in contact with water as shown in the attached images. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | TA NGV would to know, why there were some water in this area. Where came this water? So it is necessary to check the cables: 1- visually check if there are some oxidation. Make a picture for each cable (where we see the wires and their terminaison). 2- Check the insulation (under 500 V cc) between each wire and the others, and the earthing too, record the results. 3 Check the continuity. Following the results we will decide if it is necessary to change these cables or not. See, the complement in annexure, and raise a NCR MAT to re-order the part changed |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 279 Dias | Paul Fosse | UA |  | NO
NCR-ICN-UFEM-12-0543-2021 | 53B | RESISTANT STRUCTURE | 2021-02-25 12:59 | Nível 2 | COS-SMB-319093, COS-SMB-339470 |  | PROD 6.1 | According to step 2.2 of NCR-ICN-ESC-12-0341-2021, ICN proposes to surfacing 6mm on the 100x100x80 HL plate and then, machining in order to obtain the thickness described in MAT 425-1611 to manufacture the AC32065 DSRV sleeve (CMD 01ME000D0006). | Não |  |  |  |  | Waiting for TA analysis | REWORK build up by TIG process with W69. WPS 141/3B-3B/30/RCA3 . take care of temperature, always < 120 degree. Carry out 100% VT , 100% US and 100% MT |  | Cláudio Branquinho da Costa | Felipe Trigueiros Silveira | 277 Dias | Hugues Bourget | AC |  | NO
NCR-ICN-ESC-12-0355-2021 | 53B | PIPES | 2021-03-01 14:38 | Nível 2 | COS-SMB-319093, COS-SMB-339470, COS-SMB-339468 |  | PROD 6.1 | For the proposed solution on NCR-ICN-ESC-12-0341-2021 a new updated must be done regarding the pipes connected to the sleeves. ICN request the updated pipe data. | Não |  |  |  |  | ICN requests update of spools that link with the sleeves. see attached file. | -Follow the piping modification in the annex . -Ajust the news pipes with the new position of the sleeves -REPAIR |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 273 Dias | Franck Rubis | AC | NCR-ICN-ESC-12-0341-2021 | NO |  |  | 2021-03-08 12:29 | Franck Rubis
NCR-ICN-ESC-12-0366-2021 | 53B | PIPES | 2021-03-08 14:13 | Nível 2 | COS-SMB-200452 |  | PROD 6.1 | It is identified a lack of clamp (DM50051M2 – P4133168) on DM circuit. Due to the construction phase we don’t have access to perform the weld, below main cradle in B240. | Não |  |  |  |  | ICN requests update of spools that link with the sleeves. see attached file. | To allow the craddle loading (BSMI) in the local B240 : - The pipe P4133167 must be removed - The clamp P4133168 must be cuted Today ,there are not access to weld the clamp P4133168 .For information on the sbr 2 , the conection "STRAUB" has been replaced by two flanges . ( in annex NCR-UFEM-12-314-2018) So because of this new configuration, the TA could accept the situation. Send to Level 3 for decision. | Rework according to SMB-TDP-PR-6817922, SMB-TDP-PR-6817923 and SMB-TDP-PR-6817917. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 266 Dias | Franck Rubis | DM |  | NO | YES
NCR-ICN-ESC-12-0367-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-09 15:50 | Nível 2 | COS-SMB-321699, COS-SMB-200575, COS-SMB-200464 |  | PROD 6.1 | During the diving safe inspection performed by David Bernede, a lot of problems on DW system were found, see COR-2021-900344. | Não |  |  |  |  | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | In accordancce with level 2 proposal. rework | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 265 Dias | Patrick Daliguet | DW |  | NO | NO
NCR-ICN-ESC-12-0370-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-12 13:07 | Nível 2 | COS-SMB-319738 |  | PROD 6.1 | A set of flexible shim that was deformed during the construction and assembly process. | Não |  |  |  |  | Rework. Replace the DECOUPLING WASHER - ELASTOMER - TYPE MN03- 40 (CMD 14SE200D00005) by new one; All works must be done according procedure SMB-200949; Scrap the damaged pieces (send back to warehouse); Raise a NCR-MAT to supply new parts. | In accordance with level 1.2 |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 262 Dias | Patrick Daliguet | FC |  | NO
NCR-ICN-ESC-12-0379-2021 | 53B | PIPES | 2021-03-16 17:35 | Nível 2 | COS-SMB-206063 |  | PROD 6.1 | As per item 3.1 of COR-2021-900343, the mounting of equipment and pipes was not finished during the inspection; the grease ER/DP spools and equipment were not connected and not protected properly. | Não |  |  |  |  | ICN suggests injecting suitable grease into the spools, which are in this situation, to make sure that the grease is clean inside the tube. | -Agree with the ICN solution proposed (1.2) - dismount the materials for cleaning in the workshop -fill the piping with clean grease to evacuate the dirty grease |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 257 Dias | Franck Rubis | DP |  | NO
NCR-ICN-ESC-12-0389-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-19 13:16 | Nível 2 | COS-SMB-200228 |  | PROD 6.1 | The Radar Antenna support RAM mounted on SBR2 (SMB2-MA19-DB2 and serial number 1609117) was disassembled and mounted on SBR1. All the inspections sheets must be redone. | Não |  |  |  |  | Send to level 2. | No as well SBR 1 than SBR 2, it is just necessary to redo orperform a CTE pertaining to: The tightening and bending the lock washer, for the beam on the jack, For the Zero mechanical device, For the deplumer For the POD. The verification of good working (Hoisting/Lowering time and indication limit switch, Radar POD) will be done by commissionning Team. In order to replace the Radar beam took on SBR 2, take this one of SBR 3, befor to put in place the new Radar beam (this one of SBR 3) check the inner diameter (162 . 0/+1). |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 255 Dias | Paul Fosse | RM |  | NO
NCR-ICN-ESC-12-0392-2021 | 53B | PIPES | 2021-03-22 12:49 | Nível 2 | COS-SMB-331842, COS-SMB-200470 |  | PROD 6.1 | Due to the NG report, annex, we should do an internal inspection in the whole valves. | Não |  |  |  |  | Send to level 2. | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | In accordance with level 2.2. (David BERNEDE - ISSP) | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 252 Dias | Patrick Daliguet | DV |  | NO | NO
NCR-ICN-ESC-12-0407-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-25 11:06 | Nível 2 | COS-SMB-321699 |  | PROD 6.1 | The bottles are mounted on board and there position is fixed in the SM so there is no reason when the bottles are integrated on board not to perform the complete mounting o Lock washers are missing when the seating is mounted. Besides, Some HP air bottles were not protected from pollution and some metallic dust could be seen (COR-2021-900343). | Não |  |  |  |  | Agree with 1.2. Rework according COR-2021-900343. | Applied all the actions recommandations given in COR-2021-900343 dated January, 05th 2020 regarding the Air HP cylinders DW outside pressure hull and DY inside SBR2. | In accordance with level 2.2 proposal. David BERNEDE | Vinicius Siqueira dos Santos | Ernanes de Souza | 249 Dias | Alain Lamy | DW |  | NO | NO
NCR-ICN-ESC-12-0409-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-26 10:40 | Nível 2 | COS-SMB-321699 |  | PROD 6.1 | The length of the rods used is ER grease dosing connection blocks were not long enough (COR-2021-900344). | Não |  |  |  |  | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 248 Dias | Jean Christophe Laurent | ER |  | NO
NCR-ICN-ESC-12-0411-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-26 10:52 | Nível 2 | COS-SMB-319698, COS-SMB-321699 |  | PROD 6.1 | Deviations of the mounting of the DY00011 HP air cylinder: - The orientation of the internal bleed tube was not conform. The mark on the housing at the bottom of the cylinder had to be on the top; - The DY00011 HP air cylinder junctions were protected by tap and not with proper cap; - The bolting of the seating of DY00011 was not locked. The tab washers were not bend or were missing; Deviations of the mounting of the DY00021 HP air cylinder: - The label indicated the product number P0109137. The product number P0109137 refers to the HP cylinder DW00106 (which is outside the pressure hull); - The orientation of the internal bleed tube was not conform. The mark on the housing at the bottom of the cylinder had to be on the top; - The DY00021 HP air cylinder junctions were protected by tap and not with proper cap; Deviations of the mounting of the DY00022 HP air cylinder: - The DY00022 HP air cylinder junctions were protected by tap and not with proper cap; - The bolting of the seating of DY00022 was not locked or not mounted (see COR-2021-900343). | Não |  |  |  |  | Follow 1.2. | Following the recommendations given by Naval-Group within inspection report COR-2021-900343, carry out on SBR1: - Endoscopic inspection of all the air bottles outside pressure hull. Clean if necessary and protect the adaptators (head and bottom) with adequate plastic capes or connect them with their pipes. Regarding the air bottles DY00011 / DY00012 / DY00021 / DY00022 inside submarine: - also an endoscopic inspection has to be done on these bottles. Clean if necessary and protect the adaptators (head and bottom) with adequate plastic capes or connect them with their pipes. In addition to that, for DY00011 and DY00021 these two bottles must be re-orientated in order to put the internal dip tube in vertical position. For that, the mark "T" graved on the hexagonal part of the bottom´s adaptor must be on top. - For DY00011 and DY00022, finalyse the bolting of their seating because some bolting are not locked or not mounted. - For DY00021, confirm that the traceability number graved on the head of the bottle matches with the CMD of the bottle DY00021. If yes, removed the label (P0109137) from DY00021 and put it on DW00106 bottle in D132. Naval-Group reminds ICN that a particular attention has to be paid to the internal cleanliness of the type of equipment. For this reason, plastic protections must be put in place on the fittings when the connecting pipes are not in place. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 248 Dias | Alain Lamy | DY, DW |  | NO
NCR-ICN-ESC-12-0422-2021 | 53B | PIPES | 2021-03-29 18:23 | Nível 2 | COS-SMB-319606, COS-SMB-319730 |  | PROD 6.1 | The copper alloy adapters of CO2 EF00018 and EF00017 bottles were mounted with Teflon. The tightness is only done by the use of a cooper gasket (COR-2021-900343). | Não |  |  |  |  | Justify the use of TEFLON. It is necessary to dismount the adapters of CO2 EF00018 and EF00017 bottles, to check if there are copper gaskets. | Mounting of the valves EF00017/EF00018/EF00001 in accordance with the applicables rules. Check the preservation cycle and if it's soon ,optimise the control time by doing the work. Removing the teflon and replace with: -for the conical conection----> loctite 577 ( NGD:8040144255346) -for the adapters 18RO000D00503 and 18RO000D00504---->copper gasket (HV<50) Perform new pressure tests. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | EF |  | NO
NCR-ICN-ESC-12-0432-2021 | 53B | PIPES | 2021-03-31 18:52 | Nível 2 | COS-SMB-206079, COS-SMB-321795 |  | PROD 6.1 | During assembly of valves 18SC013D00114 it was identified a interference between the position of the valve hand wheel and diesel engine, in fact we should receive a valve with a different assembly. To solve the issue the screw from the upper part of picture “Problem 2” was unscrewed and the valve actuator twisted 180 degree. To guarantee the good work a M09 was performed with 3 Bar according to SMB-005545_F and approved. For traceability matters pictures attached presents the code for valve body and actuator (see Valve in annex). | Não |  |  |  |  | NG, please analyze the problem found on board. | This valves must be mounted respecting the direction of the fluid indicated by the arrow on the body's valve. And the threads to fix the seating are only on one side of the valve. So we can use only the CMD :18SC013D00115 for the valves P0136440 and P0136161 starboard forward and portside aft engines without modification. But for the CMD:18SC013D00114 to use the valves P0135831 and P0136708: 1/Make the missing holes and threads in acccordance with the BDM- 00075908. 2/Rotate the actuator with 180°. 3/Realize the test PEH/PEE in accordance with the SMB-328961. 4/Realize the functional tests in accordance with the SMB-328961. Consult the view in the appendix to analyze the configuration described. ICN must to open a NCR MAT to regularize this situation at the back-office. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 242 Dias | Franck Rubis | BQ |  | YES
NCR-ICN-ESC-12-0436-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-08 11:19 | Nível 2 | COS-SMB-200224 |  | PROD 6.1 | Equipment can be installed pending component 09EP000D00035_2012, according to NCR-ICN-CONFIG-11-3027-2018 and replacement through NCR-MAT (awaiting issuance). Replacement installation can be performed on board | Não |  |  |  |  | Agree with item 1.2, the quipment will be installed pending component 09EP000D00035_2012, according to NCR-ICN-CONFIG-11-3027-2018 and replacement through NCR-MAT (awaiting issuance). Replacement of the missing componete can be carried out on board. | Please apply the SMB-TDP-PR-5635148 (OM-96298) on SBR1, as written in the Modification Order, it is already done on SBR2 |  | Charles Douglas de Oliveira | Ernanes de Souza | 235 Dias | Bertrand Belle | RM |  | NO
NCR-ICN-ESC-12-0458-2021 | 53B | PIPES | 2021-04-30 21:55 | Nível 2 | COS-SMB-206095 |  | PROD 6.1 | It was identified that the pipe is shorter than the project request, so it will increase the dead volume in the compartment. | Não |  |  |  |  | NG, Favor analisar a solicitação o problema encontrado abordo. | Readjust the pipe to maintain a distance of 40 mm between the strainer and the bilge Modify the pipe to lengthen it and send it to galvanizing |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 212 Dias | Franck Rubis | DA |  | NO
NCR-ICN-ESC-12-0456-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-29 19:39 | Nível 2 | COS-SMB-200224 |  | PROD 6.1 | The screws for fixing the RAM equipment refering to DEI-200224-80500-12-001 - material list item 18 (53B-RM00001 - CMx 09EP000D00026_2016 - quantity 11 SCREW H M16X140X44 unit), the screws are not long enough for assembly. It is necessary to request new screws with the correct length for mounting the equipment. | Não |  |  |  |  | The supplied screw does not meet the RM00001 equipment assembly process. To assemble the equipment, it is necessary to use a 15mm larger screw in length. It is suggested the screw that meets the correct length: 1. SCREW H M16X160X44 A4L-80 – CMD 32VI120D00318 – total: 11 unit. 2. SCREW H M16X180X44 A4L-80 – CMD 32VI120D00319 – total: 5 unit. References SMB-002465 and SMB-000500. | A NG propose to replace these screw by the following screws so: - SCREW HM16x160x44- A4L80 - CMD 32VI120D00318 - NGD 0930930261849. Available in the Batch: RM-SMB1-US07A-DB6/01_PARTE2 - SCREW HM16x180x44-A4L80 - CMD 32VI120D00319 - NGD 5305145376820. There are available in the Batch: RM-SMB1-US07A-DB2/01_PARTE2 Raise a NCR MAT to re-order and re completed the batches. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 213 Dias | Patrick Daliguet | RM |  | NO |  |  | 2021-05-13 14:08 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0464-2021 | 53B | MECHANICAL | 2021-05-03 19:32 | Nível 2 | COS-SMB-207763, COS-SMB-319079 |  | PROD 6.1 | During the final assembly of the male soft-patch a small gap was identified in relation to the holes of the male with female soft patch. New inspection was done, and We can see that the male soft patch is at the same position than june 2020 , the blu maching gone and we have some contact point in the forward angle ( so without gap) . see annex. | Não |  |  |  |  | After checking the male and female soft-patch, dimensional checks were carried out requested by the Technical Assistance of Grupo Naval (TA). Analyze the current situation of mounting the male soft-patch on the female soft-patch, for correction of small misalignment the ICN suggests: 1. Clean the contact areas of the soft-patch, reposition the male soft-patch on the female soft-patch without the fixing screws, perform a tapping process with a sledgehammer to ensure positioning with maximum contact between the faces. 2. For the misalignment of the fixing holes between the male and female soft-patch, perform a new machining of the fixing holes according to SMB-314163 in order to guarantee the concentricity of the holes and the current positioning of the male soft-patch in the female soft-patch. 3. Manufacture new adjustable pins according to SMB-104061 for the new diameters of the drilled holes. 4. Closing plate (flat bar), readjusting plate by grinding the upper face until the flatness between the plates of the soft male and female is obtained, seen in a report that the lag will not compromise the thickness tolerance, however it is necessary to adjust the plate carefully. | After all the verifications, the position neutral fiber give a possilibity to restart the adjust of soft patch. Wait a level 3 decision. Send to level 3 for validation | Agreement for grinding the rounded edges of the male soft patch in contact with the female soft patch as proposed by the FO Naval Group, then BOFO stop point after checking the adjustment and measuring the neutral fiber alignment before any subsequent operation. Rework by ICN under permanent control of the FO Naval Group. Point of vigilance: careful approach in order not to remove more metal than necessary. | Vinicius Siqueira dos Santos | Ernanes de Souza | 209 Dias | Hugues Bourget | N/A |  | NO | NO |  | 2021-06-07 13:41 | Frederic Pavic
NCR-ICN-ESC-12-0486-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-12 11:42 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | PROD 6.1 | During the assembly of the bolts, the nut groove did not match the bolt's bore hole. After checking the template, he found that it deformed during the torquing of the screws in the workshop, consequently decreasing the pre-defined length, influencing the torque and final positioning of the nut. MB00002 - P0104796 | Não |  |  |  |  | To correct the position of the bolts lock hole, consequence of the jig deformation. The ICN suggests. See annex 1. 1. Perform the assembly and torque of 680 N.m. of the bolts on board. 2. Mark the position of the nut stop hole at 120 ° on two sides. 3. Remove the bolts for the workshop and drill the Ø6.3mm diameter bolts in the marked area. Remove two bolts at a time. 4. Reinstall the bolts, tighten the nut until the hole is in position and install the locking pin. | Agree with the proposition L1. It's important to confirm the torque on board before mark the new position of the pin. The number of the nut need to correspond with the bolt, if not do a new one in order to don't mix the material. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 201 Dias | Jean Christophe Laurent | MB |  | NO
NCR-ICN-ESC-12-0494-2021 | 53B | ELETRIC | 2021-05-14 18:01 | Nível 2 | COS-SMB-200542, COS-SMB-200569, COS-SMB-200712 |  | PROD 6.1 | Adapters with the descriptions below, were not supplied correctly according to the attached images. 18RO000D00479_2003 - ADAPTER FOR FLEX CONNECTOR, SHORT 18RO000D00479_2004 - ADAPTER FOR FLEX CONNECTOR, SHORT 18RO000D00478_2003 - ADAPTER FOR FLEX CONNECTOR, SHORT 18RO000D00478_2004 - ADAPTER FOR FLEX CONNECTOR, SHORT | Não |  |  |  |  | It is necessary to supply new short adapters with holes that correspond to the holes of the long adapters. | Send to level 3 Waiting for BO orientation | - Make the holes of a plate oblong to allow the insertion of the screws. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 198 Dias | Stéphane Patrick Philippe Rideau | N/A |  | NO | YES
NCR-ICN-ESC-12-0490-2021 | 53B | STW | 2021-05-14 11:07 | Nível 2 | COS-SMB-200452 |  | PROD 6.1 | As described in NCR-ICN-ESC-11-0998-2020, CMD evolution of the EV00100 valve. Revised SMB-000615_X / EV00100 to CMD-18SC000D00198. | Não |  |  |  |  | Perform replacement on board | The CMD of the valve EV00100 changed regarding the modification order OM-108713 (SMB-TDP-PR-6650629). 18SC000D00104 replaced by 18SC000D00198 (NGD 9980000066618). Need to apply this modification on board of the SBR2. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 199 Dias | Jean Christophe Laurent | EV |  | NO
NCR-ICN-ESC-12-0491-2021 | 53B | STW | 2021-05-14 11:17 | Nível 2 | COS-SMB-319720 |  | PROD 6.1 | As described in NCR-ICN-ESC-11-0774-2019, CMD evolution of the ES00024 valve. Revised SMB-000806_W / ES00024 to CMD-18SC000D00197. | Não |  |  |  |  | Perform replacement on board | The CMD of the valve ES00024 changed regarding the modification order OM-108713 (SMB-TDP-PR-6650629). 18SC000D00105 replaced by 18SC000D00197 (NGD 9980000066615). Need to apply this modification on board of the SBR2. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 199 Dias | Jean Christophe Laurent | ES |  | NO
NCR-ICN-ESC-12-0497-2021 | 53B | TRACEABILITY | 2021-05-17 20:00 | Nível 2 | COS-SMB-319712 |  | PROD 6.1 | After analyzing the evidence of the BMs valves (BM00001 - P0136019, BM00002 - P0136019, BM00007 - P0136065, BM00008 - P0136066, BM00010 - P0135969, BM00011 - P0135944, BM00012 - P0135970, BM00016 - P0135945, BM00031 - P0134355, BM00032 - P0134354, BM00037 - P0134350, BM00038 - P0134352, BM00040 - P0134346, BM00041 - P0134351, BM00042 - P0134348 and BM00046 - P0134353) it was observed that some components (CMD: 14RD000D00003, CMD: 50DD000D00007 and CMD: 14VE200D00002) have the same serial number and the same traceability reference of some SBR1 valves (6989396 contract number). See the Annex 1. | Não |  |  |  |  | ICN proposes to NG the creation of identification tags .This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Emanuela Lucia Justino dos Santos | Emanuela Lucia Justino dos Santos | 195 Dias | Patrick Daliguet | BM |  | NO | NO
NCR-ICN-ESC-12-0496-2021 | 53B | STW | 2021-05-17 19:36 | Nível 2 | COS-SMB-206071, COS-SMB-200247, COS-SMB-206042 |  | PROD 6.1 | The hose DY20104, DY20110 and DY20210 installed onboard has a different CMD than the one specified on updated SMB-000598_R. | Não |  |  |  |  | ICN suggests to replace the hose. Apply CMD 18FG205D00042 (according to SMB-000598_R). | Need to respect the SMB-000598 at the last version (R currently). In this case, several flexibles' CMD changed since the version N (DY20103, DY20104, DY20100, DY20110, DY20111, DY20100 and DY20210). Please check the conformity of the flexibles onboard with the SMB-000598_R. |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 195 Dias | Gildas Le Goff | DY |  | NO |  |  | 2021-05-19 16:51 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0498-2021 | 53B | ELETRIC | 2021-05-18 12:54 | Nível 2 | COS-SMB-206085, COS-SMB-206044, COS-SMB-206098, COS-SMB-206100, COS-SMB-337143, COS-SMB-206081, COS-SMB-200444 |  | PROD 6.1 | To make the connection of the valves we need the cable gland whose description is: CABLE GLAND ISO 20 POLYAMIDE IP66, according to the reference document BDM-00076571 the same and supplied with the valve, however, it is not being supplie. | Não |  |  |  |  | USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 195 Dias | Stéphane Patrick Philippe Rideau | EW, EG, DJ, DM |  | NO
NCR-ICN-ESC-12-0503-2021 | 53B | PIPES | 2021-05-20 14:22 | Nível 2 | COS-SMB-206089 |  | PROD 6.1 | The pipe P4127403 (RM50048M3) was remanufactured and installed onboard. With this, the test B01 RM00078 and B02 RM00078 that were performed before, are now invalidated. | Não |  |  |  |  | Pipe already manufactured. Redo test B01 RM00078 and B02 RM00078. | Raise NCR REGRESS to redo inspections and pressure tests. B05 should be updated | In accordance with level 2.2 proposal (David Bernerde). | Rodolfo Alves de Abreu | Rodolfo Alves de Abreu | 193 Dias | Patrick Daliguet | RM |  | NO | NO
NCR-ICN-ESC-12-0512-2021 | 53B | PIPES | 2021-05-26 12:31 | Nível 2 | COS-SMB-331842, COS-SMB-321782 |  | PROD 6.1 | The valves DW01116 and DW01215 were mounted on their seating but pressure test labels were put on pipes DW50113Y1 and DW50220Y1. The pressure test can only be performed if the circuits, equipment are completely mounted on their seating and clamps (COR-2021-900343). | Não |  |  |  |  | ICN waits NVG orientation. | Regarding the defects found on the SAR of the SBR1 regarding the cleaness of the circuits DW, ICN has to take all precautions possible to keep the circuits clean. All outs must absolutely be plugged. Before to peform the pressure test, need to blow the lines with air and connect them to the valves. No need to perform a new pickling operation. | Wrong Product Marks given in this NCR : are quoted the marks of operating restrictions and weldings : P0109281 -> DW01116V / OPERATING RESTRICTION VALVE DW01116 P0109296 -> DW01215V / OPERATING RESTRICTION VALVE DW01215 SP0024018 -> SOUDURE_DW50113Y1_003_023 SP0024014 -> SOUDURE_DW50220Y1_003_023 But the concerned marks are valves and NRV : P0109110 / DW01116 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109126 / DW01215 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109146 / DW50113Y / DW01110 VALVE DISCHARGE NRV LEAK INDICATOR P0109167 / DW50220Y / DW01210 VALVE DISCHARGE NRV LEAK INDICATOR In any case disagree, if dirt found it is necessary to redo a pickling. David BERNEDE - ISSP | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 187 Dias | Gildas Le Goff | DW |  | NO | NO
NCR-ICN-ESC-12-0508-2021 | 53B | MECHANICAL | 2021-05-25 14:17 | Nível 2 | COS-SMB-206090 | CTE00950775 | PROD 6.1 | During inspection F06 of BH00106 was detected 2 grooves in the coatings according to attached photos. There was no visualization of the steel of the damaged region, however the SMB-205602_C does not specify the criterion to accept this discontinuity in the coating. We request NG analysis. | Não |  |  |  |  | ICN proposes to accept as it is and requests analysis of NG. | The coating is present on all of the surface. The water tightness is not compromised by the defect. | In accordance with level 2.2 proposal, The reference of the NCR has to be added to traceability folder of the valve. Alert : there is no reference of the Traceability of the valve concerned. Update the NCR to indicate the Traceability Reference. David BERNEDE - ISSP | Alexander Vilela Dias | Franciellen da Silva Braga | 188 Dias | Patrick Daliguet | BH |  | NO | NO
NCR-ICN-ESC-12-0514-2021 | 53B | MECHANICAL | 2021-05-26 16:21 | Nível 2 | COS-SMB-200572 |  | PROD 6.1 | During the alignment inspection of the DP00399 equipment, the following deviations were detected: 1) The procedure used for the alignment is not the one described in DEI-200572-80500-12-0001_ Task 70.400. 2) The dummy ram was not used, the alignment was performed with definitive equipment. 3) The alignment was not in accordance with the tolerance specified in MAT214-1717. | Não |  |  |  |  | Agree with deliberation 1.2. Send to naval group analyze. | Agree with level 1. The alignment was done with the definitive material and according to the quality control the alignment is OK. |  | Silvio Fonseca de Paiva | Ernanes de Souza | 187 Dias | Jean Christophe Laurent |  |  | NO
NCR-ICN-UFEM-12-0550-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-31 16:58 | Nível 2 | COS-SMB-330724 |  | PROD 6.1 | - The Gasket (MAT424-0813_REP 6) was delivered installed in the Vent Valve (CMD 18PA000D00038) without packaging and traceability; - The material described in the part list is the "Latty Gold" brand is not used anymore by NG; - ICN request to use NGD 5330145107997 - FLAT GASKET 60 X 79 X 3 FIBER / NBR received in Batch SMB-RMS-CUR-DB19. IM: AG00017. | Não |  |  |  |  | Replace the non-conform gasket by NGD 5330145107997 - FLAT GASKET 60 X 79 X 3 FIBER / NBR delivered in Batch SMB-RMS-CUR-DB19. See attached the NG authorization to use the spare part. Raise a NCR-MAT to supply new parts (minimum 2 units), update the nomenclature and part list. | In accordance with proposal: raise NCR MAT to supply new gaskets | In accordance with proposal - change the gasket, identify the operation in the traceability folder of the panel | Joao Paulo Schneider Gonzaga | Joao Paulo Schneider Gonzaga | 182 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0525-2021 | 53B | STW | 2021-06-01 18:38 | Nível 2 | COS-SMB-319702, COS-SMB-200716, COS-SMB-200245 |  | PROD 6.1 | As already pointed in NCR-ICN-ESC-11-0617-2019, when the solenoid valves are operated in the opening position, rotates over the limit switch with the solenoid stroke, avoiding the shaft to return to the idle position. | Não |  |  |  |  | Proceed as defined on NCR-ICN-ESC-11-0617-2019. Extend solution from OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to SBR2, SBR3 and SBR4. | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Lucas Abrantes Conde | Lucas Abrantes Conde | 180 Dias | Gildas Le Goff | DV |  | NO | YES
NCR-ICN-ESC-12-0543-2021 | 53B | ELETRIC | 2021-06-17 13:30 | Nível 2 | COS-SMB-319693, COS-SMB-319693 |  | PROD 6.1 | The equipment KT03612/KT03611, had their connectors used in SBR1, the need for the incident, we currently need these same connectors for application in SBR2. There is an NCR-MAT to supply a new supply of connectors for the SBR2”. | Não |  |  |  |  | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | Take those on of SBR 4 or 3, and the news will replace those take on SBR 3 or 4 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 165 Dias | Paul Fosse | KT |  | NO
NCR-ICN-ESC-12-0572-2021 | 53B | SEATING | 2021-07-23 13:24 | Nível 2 | COS-SMB-200387 |  | PROD 6.1 | Interference in the assembly of seating P4019157. During the assembly of seating P4019157, an interference with seating P4018956 was observed, where it is installed with overlength. In annex, it was detached in 3D how this assembly is with the interference of the overlength and its measurements. | Não |  |  |  |  | Send to NG to adapt the seating. | We propose to send the NCR in level 3 for BO considerations about the differences between definition plan and the 3D model. | The decision taken to modify the seating according to the 3D mockup to avoid any interference is the right one. For SBR3 and SBR4 do the same. | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 129 Dias | Hugues Bourget | DP |  | NO | YES | Outros | 2021-07-28 16:36 | Christophe Marret
NCR-ICN-ESC-12-0583-2021 | 53B | INTEGRATION EQUIPMENT | 2021-08-13 12:50 | Nível 2 | COS-SMB-330822 |  | PROD 6.1 | According decision Level 3 of NCR-ICN-ESC-12-0391-2021, the PELA – traceability AP402618 (SBR 3) was installed in SBR 2 and showed leaks during the test; Naval Group proposed to make a new watertightness test using parts of PELA - AP402618 (SBR 2) with PELA - AP435534 (SBR 4) and assembly it on SBR 3. See part list in ANNEX A. | Não |  |  |  |  | Agree with action 1.2. Disassemble the PELA - AP435534 and remove its parts according to annex A, install it in the AP402618 SBR 2. Replace all the items per new listed in ANNEX B. Perform a new hydrostatic test to validate the assembly. | Install items (REF: MAT422-0109): REP 2 TIGHTNESS PIECE, REP 28 POLISHED SURFACE-CARBON FRICTION SUB-ASSEMBLY of PELA 2 with the PELA 3 on SBR2. Use new O-ring (REP 46/9/34/11/13/29/35) for assembly and perform test (70 bar and 52,5 bar) to validate the new assembly. Record all the numbers of each item for traceability. Send in level 3 for validation | Agreement for the use of the polished surface-carbon assembly of PELA 2 with PELA 3 mounted on SBR2. ICN has to ensure a follow-up of the traceability files of each PELA. NG will replenish item 13 NGD 5331145330432 O-RING 493,00X7,00 20A8-AN in quantity 2 (for use on SBR3 and SBR4). Other components of ANNEX B will be replenished through NCR-MAT-001859-2021. | Vinicius Siqueira dos Santos | Ernanes de Souza | 108 Dias | Jean Christophe Laurent | MB |  | NO | NO
NCR-ICN-ESC-12-0589-2021 | 53B | INTEGRATION EQUIPMENT | 2021-08-27 18:34 | Nível 2 | COS-SMB-200526 |  | PROD 6.1 | Equipment will be installed with component pending, according to NCR-ICN-ESC-11-1034-2020 and replacement through NCR-MAT-001120-2020. Component replacement installation can be performed on board. | Não |  |  |  |  | Rework, perform the installation of equipment with pending component according to NCR-ICN-ESC-11-1034-2020. From of the NCR-MAT-001120-2020, take the components and complete the installation on board. | Agree with Deliberaçao N1 |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 93 Dias | Etienne Alexandre Sebastien Rene Berot | FR |  | NO
NCR-ICN-ESC-12-0603-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-09 17:30 | Nível 1 | COS-SMB-200160 | CTE00973676 | PROD 6.1 | Mount MN45-60 is in wrong position. This resilient mount was mounted port aft and the correct position is starboard forward. | Não |  | Mecânico | Anomalia de Integração | Mau uso dos documentos de aplicação | Rework the assembly and positioning of the MN45-60 see DEI-000000-80500-12-181 page 5. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | FC |  | NO
NCR-ICN-ESC-12-0604-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-09 17:37 | Nível 1 | COS-SMB-319721 |  | PROD 6.1 | During MS02 inspection on DA02000 it was checked that the compression of the resilient mount was out of tolerance. See attached CTE. | Não |  | Mecânico | Anomalia de Integração | Defeito de nivelamento, defeito, dimensional, ... | Rework compression of damper disks to specified tolerance. (9.1mm to 11.5mm). | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | DA |  | NO
NCR-ICN-ESC-12-0605-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-09 17:44 | Nível 1 | COS-SMB-200542 | CTE00978503 | PROD 6.1 | During MS02 it was checked that the EJ02003 pump was mounted without resilient mounts. See attached CTEs MS02-1 and MS02-2. | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | Equipment mounted without resilient mount - Rework | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | EJ |  | NO
NCR-ICN-ESC-12-0606-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-09 17:51 | Nível 1 | COS-SMB-200542 | CTE00759196 | PROD 6.1 | During MS02 it was checked that the EJ00007 pump was mounted without resilient mounts. See attached CTEs MS02-1 and MS02-2. | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | Equipment mounted without resilient mount - Rework | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | EJ |  | NO
NCR-ICN-ESC-12-0608-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-10 12:57 | Nível 1 | COS-SMB-208703 | CTE00895103 | PROD 6.1 | During MS02 inspection on DP00319S it was checked that resilient mounts of type MN01-08 were mounted instead of MN03-14 in disagreement with LMA-04C200-S04FM06-BB-12-003_B. | Não |  | Mecânico | Anomalia de Integração | Mau uso dos documentos de aplicação | According to field description, incorrect material applied. See LMA-04C200-S04FM06-BB-12-003_B. Remove and Rework. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | DP |  | NO
NCR-ICN-ESC-12-0609-2021 | 53B | ACOUSTIC DISCRETION | 2021-09-10 13:18 | Nível 1 | COS-SMB-200444 | CTE01069520 | PROD 6.1 | During MS02 inspection on DM00051S it was checked that the compression of the resilient mounts was out of tolerance. See attached CTE. | Não |  | Mecânico | Anomalia de Integração | Defeito de nivelamento, defeito, dimensional, ... | Rework in accordance with SMB-200949 and see tolerances for mount MN03_14 (8.4mm to 10.7mm). | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 80 Dias |  | DM |  | NO
NCR-ICN-ESC-12-0616-2021 | 53B | PIPES | 2021-09-17 13:22 | Nível 2 | COS-SMB-319638 |  | PROD 6.1 | During the rework forecasted on NCR-ICN-ESC-12-0588-2021 it was necessary to cut the bottle seating P4029629, we ask authorization to do that. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | NG, please validate the solution found by ICN; | Repair Cut as per annex 10 Install the new pipe build up the removed part of the seating Ajust on board check with the bottle Weld 100% VT and 100% LP Weld |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 73 Dias | Hugues Bourget | RM | NCR-ICN-ESC-12-0588-2021 | YES
NCR-ICN-ESC-12-0622-2021 | 53B | ELETRIC | 2021-09-21 19:07 | Nível 2 | COS-SMB-200716, COS-SMB-319750, COS-SMB-200544, COS-SMB-319731, COS-SMB-200551 |  | PROD 6.1 | During the tests and inspections of the optical fiber cables of the OO02536 / OO02532 / OO02531 / OO02533 / DP02500 equipment, it was found that the connectors are damaged, since it is a very sensitive connector in need of new connectors. Equipment: OO02536 Cables: OO62504B / OO62505B Equipment: OO02532 Cables: OO62507B / OO62510B Equipment: OO02531 Cables: OO62508B / OO62509B Equipment: OO02533 Cables: OO62509B / OO62510B Equipment: DP02500 Cables: OO62511B / OO62504B Equipment: OO02536 Cables: OO62504B/OO62505B Equipment: OO02532 Cables: OO62507B / OO62510B Equipment: OO02531 Cables: OO62508B / OO62509B Equipment: OO02533 Cables: OO62509B / OO62510B Equipment: DP02500 Cables: OO62511B / OO62504B | Não |  | Eletricidade | Anomalia de Aplicação | Modo operatório errado | The damage caused to the connector is internal and cannot be seen visually. This damage occurs at the time of connector preparation and is evidenced when the fiber is tested as can be seen in the "connector photo attachment". | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 68 Dias | Stéphane Patrick Philippe Rideau | OO |  | YES |  | Falta de registro fotográfico do produto danificado | 2021-09-24 16:40 | Thomas Le Corre
NCR-ICN-ESC-12-0638-2021 | 53B | INSULATION | 2021-10-04 17:43 | Nível 2 | COS-SMB-200617, COS-SMB-202499, COS-SMB-333222 | CTE00999475, CTE00999535, CTE01000218 | PROD 6.1 | During the visit of NG's light materials specialist, severe cracks were observed between the glue and the cork fixed to the hull. | Não |  | Isolamento, pintura, revestimento | Outras Anomalias | Vários defeitos | Probable retraction of mastic CLR. We suggest don't use of manual CLR. | REWORK Remove the mastic with dommage, re-do a new joint with CLR mastic |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 55 Dias | Hugues Bourget |  |  | YES
NCR-ICN-ESC-12-0643-2021 | 53B | ELETRIC | 2021-10-07 13:42 | Nível 2 | COS-SMB-206081, COS-SMB-206044, COS-SMB-337143, COS-SMB-206085, COS-SMB-206098 |  | PROD 6.1 | The electrical connection bases of the EG01140, EG1120, EG00110, EG00234 and EG00130 valves were damaged. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | Replace all the motor of the EG valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 53 Dias | Stéphane Patrick Philippe Rideau | EG |  | YES
NCR-ICN-ESC-12-0644-2021 | 53B | ELETRIC | 2021-10-08 13:22 | Nível 2 | COS-SMB-206085 |  | PROD 6.1 | The electrical connection bases of the DJ00004 valve were damaged. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | Replace the motor of the DJ00004 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 52 Dias | Stéphane Patrick Philippe Rideau | DJ |  | YES |  | Outros | 2021-10-18 18:49 | Frederic Guevel
NCR-ICN-ESC-12-0660-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-15 18:58 | Nível 2 | COS-SMB-321699 |  | PROD 6.1 | Regarding equipment 53B-ER00052, 53B-ER00053, 53B-ER00054, 53B-ER00055 and 53B-ER00210. The length of the screws provided does not suit the assembly process, it is short. See annex 1 of assembly on board. Doc. DEI-000000-80500-13-038. The screws suppled - SCREW H M 14X80X80 A4-80. it is short. But the replacement by a longer length was verified and there is no balance. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  | Vinicius Siqueira dos Santos | Luiz Felipe Silva Moreira | 44 Dias | Jean Christophe Laurent | ER |  | NO
NCR-ICN-ESC-12-0664-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-22 11:56 | Nível 2 | COS-SMB-321697 |  | PROD 6.1 | During the assembly of the 53B-DP00159 SBR2, ref. DEI-321696-80500-12-001 assambly part item 22 - 53B-DP00159 - CMD 21AG000D00016_2029 -CONNECTION PIECE, after welded the piece the alignment was not good. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Rework. The steering rudder axiometric alignment must be redone. For adjustment, take the piece MAT214-1418_Ref. 29 (CMD 21AG000D00016 - CONNECTION PIECE) from SBR 3 or SBR 4. 1) Remove the connecting piece. 2) Align the rudder steering gear with the optical team support. 3) Perform a dimensional alignment inspection before installing the connecting piece part. 4) Carry out the machining of the connecting piece in the workshop; 5) Make the fitting and install the connecting piece. 6) Carry out the dimensional alignment inspection after installing the connecting piece before locking with the weld. 7) Once the alignment is approved, carry out the welding of the connection piece. 8) Perform the final dimensional inspection of the alignment of the Rudder Blades. Open NCR MAT to supply new part or material 80HLES to manufacture a new one. | Agree with level 1. Use the TAF-TA-2019-1013 for ensure the process. Open one NCR-MAT for supply the material. ICN can confirm the alignment in the middle of the adjusting process (blue matching)to verify the good alignment of the rudder. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 38 Dias | Jean Christophe Laurent | DP |  | YES
NCR-ICN-ESC-12-0669-2021 | 53B | PIPES | 2021-10-26 18:15 | Nível 1 | COS-SMB-200469 |  | PROD 6.1 | During NG on board inspection, some damaged pipes was identified. This NCR is to trace the material and start the remanufacture of the items. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | Remanufacture the spools according to the project | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 33 Dias |  | DW, DY |  | NO
NCR-ICN-ESC-12-0670-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-26 18:27 | Nível 2 | COS-SMB-330664 |  | PROD 6.1 | Following the adjustment of the position of the panels AG00019 SBR2, the holes provided for fitting the 12mm diameter pins of the balancing bearings AG00039 no longer correspond to the holes in the brackets. This happened because the 12mm diameter holes of the supports P4128742 (drawing: SBH.4D30.SAD.003126) should only be drilled after mounting the panel and adjusting its position. Here the P4128742 brackets arrived already drilled (12mm holes), so it will be important to follow the manufacture of these brackets for SBR3. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | For assembly of the hatch AG00019 with the balancing bearings AG00039 SBR2. Perform a new adjustment of the holes in the seating P4128742 provided for fitting the 12mm for 13mm diameter pins. The supports P4128742 (Drawing SBH.4D30.SAD.003126). Agree should only be drilled after mounting the panel and adjusting its position. Necessary the supply of four pins 13mm diameter new. Carry out the assembly the new pins in order. | Agree with proposal. On the SBH.4D30.SMD.003124 the 4 holes Ø12 0/+0,2 for pins are present, it's necessary to update this drawing to remove these 4 holes to allow the good positioning and drill after the mounting validated. | Agreement with the solution proposed by LVL1 and validated by LVL2 for mounting on SBR2. Drawing SBH.4D30.SMD.003124 of seating P4128742 will be updated in BO to indicate that the holes for the positioning pins are to be counter-drilled on board during assembly. | Vinicius Siqueira dos Santos | Ernanes de Souza | 33 Dias | Patrick Daliguet | AG |  | NO | NO
NCR-ICN-ESC-12-0673-2021 | 53B | ELETRIC | 2021-10-29 13:23 | Nível 2 | COS-SMB-200542 |  | PROD 6.1 | Part of the EJ00017 equipment that consists of the description MEASURE CONVERTER 4..20 MA, with the CMD 50TA000D00157, was lost during the construction process. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Use the required component from the one supplied for the equipment "EJ00017" referring to the "SBR4" and open an "NCR-MAT" for a new supply. | Agree with decision N1 Used an 50TA000D00157 available Open a NCR-MAT to supply a new one |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 31 Dias | Stéphane Patrick Philippe Rideau | EJ |  | NO
NCR-ICN-ESC-12-0675-2021 | 53B | ELETRIC | 2021-10-29 17:08 | Nível 2 | COS-SMB-200716 |  | PROD 6.1 | Performing a routine inspection on board, it was verified that the internal parts of the BE0900BA equipment had been removed. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Exchange the complete equipment supplied to the SBR4 and open an "NCR-MAT" for a new supply. | NCR-ICN-ESC-11-1465-2021 is treating the issue. It was asking to dismount the switch BE0900BA on sbr3or sbr4 but ICN dismount on sbr2. ICN commissioning should replace the switch with the one of sbr4 to solve this NCR. NCR-MAT-001542-2021is already open to refund the item. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 30 Dias | Etienne Alexandre Sebastien Rene Berot | BE |  | NO
NCR-ICN-ESC-12-0693-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-16 19:31 | Nível 2 | COS-SMB-200387 |  | PROD 6.1 | During the assembly of the AG00037 balancing in the AG00037C - P4019056 seating, it was not possible to carry out the assembly, there is a difference of 5mm between the holes. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Agree with 1.2. As per SMB-200387, the seating AG00017C (P4019056) - All holes will be counter-drilled when mounting with the equipment. For seat P4019057, it is rework. Close the holes with welding and make the holes according to the procedure. | Change de Element 001 and 006 of the seating AG00037C Weld following SMB-200856 Carry out 100% VT 100% DP No defect on the seating AG00017C |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 12 Dias | Hugues Bourget | AG |  | NO
NCR-ICN-ESC-12-0698-2021 | 53B | PIPES | 2021-11-19 18:10 | Nível 1 | COS-SMB-321700, COS-SMB-319711 |  | PROD 6.1 | This NCR is a requirement to open a NCR mat and request new material. The material listed above was lost in the shipyard. We need a new supply. CMD Descrição Quantidade 32VI110D00904 M16x150x44 4 UNIDADES 32VI110D00831 M16x70x70 12 UNIDADES 32VI410D00077 Arruela DN16 32 UNIDADES 44JO230D00019 Junta 92x49x2 2 UNIDADES 44JO230D00037 Junta 82x40x2 3 UNIDADES I kindly request to supply more than the strictly necessary. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | PCP, please provide material for production as attached; | NCR LEVEL 1 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 9 Dias |  | BD |  | NO
NCR-ICN-ESC-12-0701-2021 | 53B | ACOUSTIC DISCRETION | 2021-11-22 15:15 | Nível 1 | COS-SMB-200452 | CTE00884251 | PROD 6.1 | During MS02 inspection on DM00016S it was checked that the resilient mounts screws were not torqued. | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | According to the description, the screws must be mounted correctly. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 7 Dias |  | DM |  | NO
NCR-ICN-ESC-12-0702-2021 | 53B | ACOUSTIC DISCRETION | 2021-11-23 14:20 | Nível 1 | COS-SMB-200452 | CTE00888637 | PROD 6.1 | During MS02 inspection on DM00026S it was checked that the resilient mounts were painted and the torque was not applied to the screws. | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | According to SMB-200949 there can be no paint on the resilient pads. Rework on the torque of the fastening screws. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 6 Dias |  | DM |  | NO
NCR-ICN-ESC-12-0706-2021 | 53B | ACOUSTIC DISCRETION | 2021-11-25 11:56 | Nível 1 | COS-SMB-321784 | CTE00801976 | PROD 6.1 | During MS02 inspection on MB00303S it was checked paint residue on resilient mount elastomer. See attached photos. | Não |  | Mecânico | Anomalia de Aplicação | Defeito no fluxo, rastreabilidade, revestimento, usinagem, moldagem | Remove residual ink from the shims. According to SMB-200949 decoupling disks should not have paint marks or damage. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 4 Dias |  | MB |  | NO
NCR-ICN-ESC-12-0581-2021 | 53B | ELETRIC | 2021-08-12 12:32 | Nível 2 | COS-SMB-200712 |  | TA 2.2 GIR | It is not possible to make the connection of the ER00011/ER00012 equipment, because the interference of a pipe as shown in the attached image. | Não |  |  |  |  | To connect the cable ER62514R in the forward part of the ER00011 it's needed dismounting temporary the spool ER50068X2-P4160794 and ER50067X2-P4160797, just. To connect the cable ER62515R in the forward part of the ER00012 it’s needed dismounting temporary the spool ER50070X3-P4160800, just. This problem happened because these spools were mounted before connecting these cables, so it's important to keep this matter to avoid rewords on SBR3 and 4 too. |  |  | Jair de Barros Sena de Araujo | Roberto Alves Assunção Medeiros | 109 Dias | Stéphane Patrick Philippe Rideau | ER |  |  |  | Outros | 2021-09-01 17:48 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0632-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-01 11:49 | Nível 2 | COS-SMB-206140 |  | TA 2.2 GIR | According to NCR-ICN-UFEM-10-0017-2019 where the equipment P0131553 - 18AB000D00110 was supplied with REF: 0312001 being this 1/8 male connection, the adapter provided for connection with the P4176628 tube and 3/4 male (18RO000D00417) being not compatible. Note: The TA level 2 Yann Gloanec informs in your deliberation in the NCR cited above that to SBR2 (ICN must manufacture adapter 18RO230D00694 defined in STF33-04-21-C716 p29/80.) | Não |  | Mecânico | Anomalia de Integração | Defeito de posicionamento, interferência, ... | We want to proceed the solution as SBR1 in NCR-ICN-UFEM-10-0017-2019. |  |  | Carmelo Alves Batista | Luiz Felipe Silva Moreira | 59 Dias | Patrick Daliguet | UL |  |  |  | Outros | 2021-11-04 19:33 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0152-2020 | 53B | TRACEABILITY | 2020-09-03 18:48 | Nível 2 | COS-SMB-319693 |  | TA 2.2 Specialist | During the analysis of the B07 inspections, some divergences (repeated serial number) were found for the following equipment: CMD: 01PM100D00120 - KT40001 - P0114145 (serial number 11RS1075687); CMD: 01PM100D00120 - KT40002 - P0115842 (serial number 11RS1075687); CMD: 01PM100D00120 - KT40003 - P0115418 (serial number 11RS1075687); CMD: 01PM100D00120 - KT40004 - P0114831 (serial number 11RS1075687); CMD: 01PM100D00120 - KT40005 - P0114628 (serial number 11RS1075687); CMD: 01PM100D00120 - KT40006 - P0133721 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41001 - P0114147 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41002 - P0115843 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41003 - P0115419 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41004 - P0114830 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41005 - P0114629 (serial number 11RS1075687); CMD: 01PM100D00120 - KT41006 - P0133712 (serial number 11RS1075687); CMD: 01PM100D00121 - KT42001 - P0114148 (serial number 11RS1075688); CMD: 01PM100D00121 - KT42002 - P0115844 (serial number 11RS1075688); CMD: 01PM100D00121 - KT42003 - P0115420 (serial number 11RS1075688); CMD: 01PM100D00121 - KT42004 - P0114833 (serial number 11RS1075688); CMD: 01PM100D00121 - KT42005 - P0114630 (serial number 11RS1075688); CMD: 01PM100D00121 - KT42006 - P0115632 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43001 -P0114150 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43002 -P0115846 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43003 -P0115422 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43004 -P0114835 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43005 -P0114632 (serial number 11RS1075688); CMD: 01PM100D00121 - KT43006 -P0115634 (serial number 11RS1075688); CMD: 01PM100D00121 - KT44001 -P0114149 (serial number 11RS1075688); CMD: 01PM100D00121 - KT44002 -P0115845 (serial number 11RS1075688); CMD: 01PM100D00121 - KT44003 -P0115421 (serial number 11RS1075688); CMD: 01PM100D00121 - KT44004 -P0114834 (serial number 11RS1075688); CMD: 01PM100D00121 - KT44005 -P0114631 (serial number 11RS1075688); CMD: 01PM100D00120 - KT45001 -P0114151 (serial number 11RS1075687); CMD: 01PM100D00120 - KT45002 -P0115847 (serial number 11RS1075687); CMD: 01PM100D00120 - KT45003 -P0115423 (serial number 11RS1075687); CMD: 01PM100D00120 - KT45004 -P0114836 (serial number 11RS1075687); CMD: 01PM100D00120 - KT45005 -P0114633 (serial number 11RS1075687); CMD: 01PM100D00120 - KT45006 -P0115638 (serial number 11RS1075687); In the documents received by NG -2017-905033 -17-SBR-290A / B (DBA and Declaration of Conformity) the CMD was not found for the equipment listed above. ICN requests the certificates and Declaration of Conformity for all listed equipment and the sending of unique serial numbers or the release for ICN to create the serial numbers. | Não |  |  |  |  | ICN requests the certificates and Declaration of Conformity for all listed equipment and the sending of unique serial numbers or the release for ICN to create the serial numbers. | To be treated in Level 3. | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Emanuela Lucia Justino dos Santos | Sergio André Telles Soares | 451 Dias | Patrick Daliguet | KT |  | NO | NO
NCR-ICN-ESC-12-0200-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-07 17:49 | Nível 2 | COS-SMB-319321 |  | TA 2.2 Specialist | In the calibration process of develec sensors 50AM901D00001 and in the update of the new O ring we have 11 develec sensor with the following problems: SÉRIE FALHA APRESENTADA Box 15S0268 TENSION OUT OF CALIBRATION 8/10 15S0255 TENSION OUT OF CALIBRATION 8/10 15S0264 TENSION OUT OF CALIBRATION 8/10 15S0288 TENSION OUT OF CALIBRATION 8/10 15S0271 TENSION OUT OF CALIBRATION 8/10 15S0259 TENSION OUT OF CALIBRATION 8/10 15S0326 NO COMUNICATION WITH THE SYSTEM 2/6 15S0310 NO COMUNICATION WITH THE SYSTEM 9/10 15S0319 NOT POSSIBLE TO CALIBRATE 9/10 15S0342 NOT POSSIBLE TO CALIBRATE 2/10 15S0151 NOT POSSIBLE TO CALIBRATE 5/10 | Não |  |  |  |  | 1- ICN confirm the sensor 15S0268; 15S0255; 15S0264; 15S0288; 15S0271 and 15S0259 are recalibrated and available for submarine 2. 2-Regarding the three sensor missing: 15S0319 recalibrated by metrology and applied in element num 16 15S0342 recalibrated by metrology and applied in element nem 108 15S0151 is missing; 3- Please see the table attached "sensores danificados na metrologia". There are 21 damaged sensors damaged no possible to recalibrated. ICN kindly request reposition. | ICN must open these 11 probes in presence of Naval Group to determine the origin of the problem. Naval Group will perform a new test with a dedicaded box of calibration. Return the NCR to ICN |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 417 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO |  |  | 2020-12-15 23:27 | Benoit Guillaume Pierre Cuquemelle
NCR-ICN-ESC-12-0288-2020 | 53B | ELETRIC | 2020-11-23 18:02 | Nível 2 | COS-SMB-200563, COS-SMB-319725 |  | TA 2.2 Specialist | Some of the density battery measurements is out of tolerance regarding the document SMB-337002_B (Density: 1.3 g/ml at 30°C ± 0.005 g/ml). ICN kindly request Naval Group In adition ICN would like to confirme if the formulas used (based in the battery manual BDMAT-BDM-00080876-B2) in the table attached are correct. This is a Navy question. Corrected density at 30°C (g/ml) - dt: density measured + 0,0007 * ( temperature measured - 30) Corrected level at 30°C (mm) - ∆Level: level measured + 0,8* (30- temperature measured) Final corrected density (g.ml) - d: If (Corrected level at 30°C (mm) - ∆Level) > 0 ; (Corrected density at 30°C (g/ml) - dt) - (0,00034*Corrected level at 30°C (mm) - ∆Level); Else (Corrected density at 30°C (g/ml) - dt) + (0,00034*Corrected level at 30°C (mm) - ∆Level); | Não | [5 empty] | In agreement with EXIDE, Naval Group confirms that the density corrections (to have 1,300g/l at 30°C) will be made between 6 and 12 months after the activation of the SBR2 batteries knowing that they will not enter in "Operational mode" before 1 year. Naval Group confirms that the BDMAT-BDM-00080876-B2 formulas have been confirmed in the V1.9 release to be transmitted in the next Documents Batch |  | Luiza de Oliveira Pereira | Luiza de Oliveira Pereira | 370 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO
NCR-ICN-ESC-12-0462-2021 | 53B | PRESERVATION | 2021-05-03 18:05 | Nível 2 | COS-SMB-319725, COS-SMB-200563 |  | TA 2.2 Specialist | The ICN preservation team has performed all battery charges since they were activated by the commissioning team. In the past few months, we have noticed an abnormal failure rate. 38 sensors in failure in SBR2, since last February. This problem has caused a lot of investigation and reinstallation work to keep the battery sensor in good working condition. | Não |  |  |  |  | We ask the Naval Group to present a line of action to improve the resistance of DEVELEC sensors and also to provide a set of spare sensors to avoid keeping the ship in port due to the bad information sent by the loops through the BMS. Update: On July 2nd we received an updated list of SBR-2 defective develecs from the metrology team. There are 38 units. Please see the attached file. |  |  | Rafael Tavares do Rego Macedo | Rafael Tavares do Rego Macedo | 209 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  |  |  |  | 2021-05-18 11:27 | Thomas Le Corre
NCR-ICN-ESC-12-0568-2021 | 53B | PRESERVATION | 2021-07-19 19:42 | Nível 2 | COS-SMB-200452, COS-SMB-206085 |  | TA 2.2 Specialist | Swivel Hoses EN20005 and DM20002 were installed with the storage deadline exceeded. | Não |  |  |  |  | Wait for NG orientation. |  |  | Franciellen da Silva Braga | Franciellen da Silva Braga | 132 Dias | Franck Heidel | EN, DN
NCR-ICN-ESC-12-0636-2021 | 53B | PIPES | 2021-10-04 16:56 | Nível 2 | COS-SMB-206090 |  | TA 2.2 Specialist | 1.It was noticed that the valve HP00001-18RT010D00815-SN020-MICROMAZZA is incorrectly mounted with hexagonal screws, washer NORD-LOCK and some roles without fixation. 2. After the disassembly it was noticed the coating HALAR was damaged too. 3. This valve will be sent to be used on SBR1 after evaluation of specialist NG. 4. This matter is related to hull integrity in AC33043. | Não |  | Tubulação | Anomalia de Aplicação | Modo operatório errado | 1. Dismount the valve and located it at workshop for investigation in order to validate by specialist NG if we can use it for SBR1. 2. Raise a NCR-REGRESS to B06/B07/B01/B02 and a NCR-MAT to replenish a new one for SBR2. | Agree with the ICN decision . Redo the inspections and test if they have already been validated. Send to the level 3 . | In accordance with the proposal Don´t forget to redo F06 inspections also. Take care also of the length of the stud rods for the mounting to have the 2 threads on each side of the flange | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 56 Dias | Patrick Daliguet | HP |  | NO | YES | Outros | 2021-11-22 19:50 | Carmelo Alves Batista
NCR-ICN-ESC-12-0647-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 18:04 | Nível 2 | COS-SMB-200542 |  | TA 2.2 Specialist | The equipment (EJ00006) – CMD 22RE000D00100 was lost during the construction process. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Carry out instalation of a new one equipment EJ00006 – CMD 22RE000D00100. Open NCRMAT of material supply to SBR2. |  |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 45 Dias | Franck Rubis | EJ
NCR-ICN-ESC-12-0656-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-15 12:38 | Nível 2 | COS-SMB-200516 |  | TA 2.2 Specialist | Equipment without indicator seal rubbers level. The final assembly of the equipment is not possible. The same happened with NCR-ICN-ESC-12-0443-2021. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | For the level indicator equipment 53B-BH10007N - 53B-P0104562 - CMD 50MD500D00015 - LEVEL INDIC. TAP ED 15MM. The sealing rubber that damaged, perform change a new one sealing rubber NGD: 5330143029900. same solution to NCR-ICN-ESC-12-0443-2021. Take a new-one in the stock (NGD: 5330143029900) to remount onboard. If no stock canibalize SBR3 or SBR4 and create a NCR-MAT to refund the stock. |  |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 45 Dias | Franck Rubis | BH
NCR-ICN-ESC-12-0668-2021 | 53B | ELETRIC | 2021-10-25 17:21 | Nível 2 | COS-SMB-200495, COS-SMB-CAB-OO-RM |  | TA 2.2 Specialist | RF60040D cable connection not in accordance with the instructions described in SMB-205665, its connection was not performed by ICN. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Rework to fit the reference SMB. |  |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 34 Dias | Stéphane Patrick Philippe Rideau | RF |  |  |  | Descrição Incompleta | 2021-11-04 18:55 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0688-2021 | 53B | ELETRIC | 2021-11-11 20:20 | Nível 2 | COS-SMB-200542 |  | TA 2.2 Specialist | The PMU does not communicate with the IPMS and does not allow access to the software through the maintenance console. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | We should evaluate driver v1.20 as it appeared in the message when trying to access the PMU. It will be necessary to remove the on-board PMU BB02501 for bench evaluation, as the space on board does not allow for a better analysis. The front led is also not on. |  |  | Irlan Nunes da Silva | Irlan Nunes da Silva | 17 Dias | Benoit Guillaume Pierre Cuquemelle | BB
NCR-ICN-ESC-12-0690-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-15 14:21 | Nível 2 | COS-SMB-206184, COS-SMB-321710 |  | TA 2.2 Specialist | It was not done the inspection B11.28 for the 12 NRVs of the book B05_AC33059 (01PM000D00069-6359238-MEGA-P/004) and for the 12 NVRs of the book B05_AC33065 (01PM000D00069-6359238-MEGA-P/001), according is demanded on SMB_002930_I. | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | 1. Retest the leakage circuit PTRH-S02. To be sure that the O-ring inspected on B11.28 is good for each valve, redo the tests S02_HEZ0004/5/6/7, feeding the pressure during 30 minutes and following the IT34-00-01E_B orientations. External leaks is not acceptable. Moreover, the external pipes, after NRVs, should be properly purged at the tests end. 2. Even though the retests approved, do every B11.28 mentioning this NCR and attach them to B05 books. And attach over there the S02_HEZ0004/5 for AC33065 and S02_HEZ0006/7 for AC33059. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 14 Dias | Patrick Daliguet | AC, HE
NCR-ICN-ESC-12-0691-2021 | 53B | PIPES | 2021-11-16 14:05 | Nível 2 | COS-SMB-200516 |  | TA 2.2 Specialist | During assembly of BH10007N it was identified an mistake in the assembly position. The pipe touch the level valve. We request authorization to rework the pipe according to conditions on board, and if necessary add non forecast weld. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | ICN request authorization to rework the pipe according to conditions on board, and if necessary add non forecast weld. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 13 Dias | Franck Rubis | BH
NCR-ICN-ESC-12-0695-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-18 19:56 | Nível 2 | COS-SMB-319693 |  | TA 2.2 Specialist | The smallest flanges of the pneumatic ram KT03721-14VE100D00011-1550259-F3018 (TLT1) and KT03722-14VE100D00011-1458182-F3018 (TLT2) are mounted with stud rods too long and the B06 for this case was not registered. See the reprises forms attached. This matter is related to hull integrity in AC30101 and AC30102. | Não |  | Mecânico | Anomalia de Aplicação | Modo operatório errado | 1. Dismount the longest stud rods and use M14x90 CMD: 32VI220D00152, use a new O-ring for each pneumatic ram too CMD: 44JO110D00455. 2. Redo the B06 correctly and update the B07. 3. Raise a NCR-MAT for material replacing. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 10 Dias | Patrick Daliguet
NCR-ICN-ESC-12-0705-2021 | 53B | WELDING / BRAZING | 2021-11-25 11:33 | Nível 2 | COS-SMB-206065, COS-SMB-206064, COS-SMB-200463, COS-SMB-200466 |  | TA 2.2 Specialist | Due to the lack of material for the brazing requalification of the 41.5mm diameter, we ask to the Naval Group to extend the authorization for brazing of the member Wagner Henrique de Souza (BR-581). Thus, we will be able to handle the brazing activities to J06 of SBR2. • Attached list of tubes to be brazed (Pipes in yellow forbidden to be brazed due to lack of qualification); • Attached Latest Inspection Reports (Brazing CTE) • Materials available for requalification in diameters 14mm, 20mm and 36mm; • Unavailable materials for requalification in diameters 8mm and 41.5mm | Não |  | Tubulação | Outras Anomalias | Vários defeitos | Waiting NG answer. |  |  | Charles Douglas de Oliveira | Luiz Antonio da Silva | 4 Dias | Franck Rubis | DW
NCR-ICN-ESC-12-0707-2021 | 53B | INTEGRATION EQUIPMENT | 2021-11-25 16:50 | Nível 2 | COS-SMB-200387, COS-SMB-200395, COS-SMB-339462 |  | TA 2.2 Specialist | Items referring to the hatch system spring were supplied unpainted. Necessary to carry out the painting of the springs. | Não |  | Isolamento, pintura, revestimento | Outras Anomalias | Vários defeitos | PERFORM THE SPECIFIC PAINT TREATMENT FOR EACH SPRING, AS PER SMB-002345. REFERENCES: 1) 53B-AG00037 - P0145870 - CMD 01PE200D00035 - EQUALISING SYSTEM OF 01PE200D00040 HATCH. Item 41 - Compression Spring Ø18xØ196x930 - ref. MAT424-1437 / MAT424-0845. 2) 53B-AG00034 - P0145868 CMD 01PE200D00034 - HULL HATCHES - BALANC. OF MID. ACC. HATC. Item 28 - Compression Spring Ø18xØ121x652 - ref. MAT424-0860 / MAT424-0857. 3) 53B-AG00039 - P0145871 - CMD 01PE200D00036 - EQUALISING SYSTEM OF 01PV000C0106 HATCH Item 8 - Compression Spring Ø14xØ120x531 - 0 0000 ref. MAT424-1480 / MAT424-0859. 4) 53B-AG00036 - P0145876 CMD 01PE200D00032 - EQUALISING SYSTEM OF 01PE200D00028 HATCH. Item 14 - Compression Spring Ø15xØ120x532 - ref. MAT424-1365 / MAT424-0802 |  |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 3 Dias | Hugues Bourget | AG
NCR-ICN-ESC-12-0708-2021 | 53B | ELETRIC | 2021-11-25 19:11 | Nível 2 | COS-SMB-319211, COS-SMB-CAB-UA-UW |  | TA 2.2 Specialist | Cable supplied with a diameter greater than that of the AB36001 through piece. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | A check on the problem by level 2.2 is required. |  |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 3 Dias | Stéphane Patrick Philippe Rideau | UW
NCR-ICN-ESC-12-0709-2021 | 53B | NON RESISTANT STRUCTURE | 2021-11-26 13:26 | Nível 2 | COS-SMB-319698, COS-SMB-200581 |  | TA 2.2 Specialist | Rework in according with TAF-TA-2021-1378 for DY bottles. Some non-conformities identified and there are several inconsistencies in the documents for fixing the bottles on D230 (forward) and A210 (aft). | Não |  | Chapa, suporte, antepara leve | Anomalia de Integração | Documentação inapropriada (referência errada, indicio errado, ...) | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 3 Dias | Hugues Bourget | DY
NCR-ICN-UFEM-12-0528-2019 | 53B | PIPES | 2019-08-08 13:52 | Nível 2 | COS-SMB-319152 |  | TA 7.2 | The ventilation tubing is not in the top of the tank. This creates an air bag in the top of the tank preventing the DA12510N sensor from working and filling the tank completely. | Não |  |  |  |  | Change CMD 01PM300D00125 (STF 33-04-30 / TS003E F) to CMD 01PM300D00117 (STF 33-04-30 / TS003E F) and one flange 18RO110D00066 and connect a pipe as per the attached drawing. Note that the weld of the through piece in tank B100 should be 25mm apart from the other welds. It should be applied to both SBR3 and SBR4. | Decision: REPAIR NVG accepts ICN level 1 proposition. |  | Paulo Jose Lopes Almeida | Paulo Jose Lopes Almeida | 844 Dias |  |  |  | NO
NCR-ICN-ESC-12-0021-2019 | 53B | PIPES | 2019-10-28 20:14 | Nível 2 | COS-SMB-206139, COS-SMB-206140 | CTE00912276 | TA 7.2 | The passage P015610 (UL20012), which is composed of a half-flange in steel and another half-flange in stainless steel, has been galvanized. | Não |  |  |  |  | We suggest that the inner area of the stainless steel part be sanded for removal of the zinc. The steel part must maintain the galvanization. (See N2 analysis in NCR-ICN-UFEM-11-0913-2019). | refere to the NCR-ICN-UFEM-11-0913-2019 concording with the STF-33-04-21-A622E |  | Nelson Moreira de Oliveira | Bruno Marcel Lima Ferreira Amancio | 762 Dias | Franck Rubis |  |  | NO
NCR-ICN-UFEM-12-0425-2019 | 53B | PIPES | 2019-02-19 03:00 | Nível 2 | COS-SMB-200255, COS-SMB-206096 |  | PROD 6.1 | P4167453 tube due to interference with the structure can not be mounted on board. | Não |  |  |  |  | Inclusion of Straub in the spool P4167453 to facilitate assembly of the FQ circuit. Clamp exclusion P4167454. Exclusion of Seating P4169460. Inclusion of 2 new clamps as shown below: | REFERE TO THE FTG-5285 ( see SMB-PR5663653_NCR-ICN-ESC-11-0232-2019.pdf) DECISION: APPLY SAME SOLUTION OF THE SBR-1 | N/A | System |  | 1014 Dias | Franck Rubis |  |  | NO | NO
NCR-ICN-UFEM-12-0447-2019 | 53B | PIPES | 2019-03-13 03:00 |  |  |  | TA 7.2 | It has been verified by NG , after a conform tightening of the connection, a loose on the DRAIN pipes connected to the HP Air bottles listed on the file attached. | Não |  |  |  |  | Naval Group analyze the problem of item 2.1. | Apply the ncr answer in the appendix. Respecting the different steps of the inspection and repair on the 34 bottles chesterfield (table in appendix) | N/A | System |  | 992 Dias |  |  |  | NO | NO
NCR-ICN-ESC-12-0048-2020 | 53B | PIPES | 2020-03-10 15:11 | Nível 2 | COS-SMB-206112, COS-SMB-206111, COS-SMB-206185 |  | TA 7.2 | “During the assembly it was impossible to fit the pipe P4503093, that was already welded to pipe P4148895 (in accordance to project), in place because an interference with the accommodation cradle in S2B. In agreement with TA, the weld and straub union position was modified and applied to issue B of the spool.” | Não |  |  |  |  | Wait for NG orientation. | For the assembly of pipes P4503093 - P4148895 modify the position of straub as per sketch shown in anexo. For that, replace the old position of the straub by a welding and move the straub on the spool P4148895. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 629 Dias | Franck Rubis | EW |  | NO
NCR-ICN-ESC-12-0053-2020 | 53B | NON RESISTANT STRUCTURE | 2020-04-29 12:26 | Nível 2 | COS-SMB-319152 |  | PROD 6.1 | The passage AF35092 was deleted from Project, however in ICN control for SBR2 the piece is a 100% installed (welded and inspected). ICN request NG a repair procedure to correct the deviation. | Não |  |  |  |  | We propose to: -Hot cut to remove the AF35092 -Create an insert plate according to IT-21-02-10E (C-6-23) - Use C24 annexed to inspect the weld the insert element in the plate. Do 100% VT and 100% PT or MT. | Repair, Close with an circular insert plate. with REP2 bevel. Weld it using SMB-200853. Carry out welding inspections requered. Take care of the cut. to respect the para C-6-23 of IT21-02-10-E the center of the repair will be different that the center of the passage. Carry out leak test inséction S05 |  | Bruno Vicente Fernandes | Luiz Felipe Silva Moreira | 579 Dias | Hugues Bourget | AF |  | NO
NCR-ICN-ESC-12-0055-2020 | 53B | ACOUSTIC DISCRETION | 2020-05-07 16:06 | Nível 2 | COS-SMB-319733 |  | TA 7.2 | During MS01 inspection (previous measurement performed in november 2019) on Electric Cradle AM00002 it was checked that the compression of the resilient mounts was out of tolerance in disagreement with SMB-200965_D. See measurement results in annex. | Não |  |  |  |  | For deliberation of TA Level 2. Decision item 2.1 on 07/05/2020. => Rework the compression of the resilient mounts using shims according to SMB-200965. See annex data. | As NCR on SBR1 NCR-ICN-ESC-11-282/2019 with same problem, it can be accept as it is. A analyze should be done by NG specialist level 3 | Accepted as it is. | Marcos Aurelio Correa Abrantes | Rogerio Milani | 571 Dias | Patrick Daliguet | AM |  | NO | NO
NCR-ICN-ESC-12-0068-2020 | 53B | PIPES | 2020-06-01 15:24 | Nível 2 | COS-SMB-206071 |  | TA 7.2 | During flexible hose MB20300 final assembly it was identified a mistake in the adjust of pipes, making the hose length too short. | Não |  |  |  |  | NG. please inform how to proceed. | Adjust the length of the pipe P4129698 (add a straight part ) in order to get a correct mounting of the flexible hose MB20300. Carry out all new inspection required. After completion and before final mounting on board, this modified pipe must undergo again a passivation Redo all ncessary CTE Insert the straight part between the 3 way and the flange on P0105314. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 546 Dias | Alain Lamy | MB |  | NO
NCR-ICN-ESC-12-0076-2020 | 53B | INTEGRATION EQUIPMENT | 2020-06-09 13:00 | Nível 2 | COS-SMB-200226 |  | TA 7.2 | During the assembling between BH00001 and BH00002, was verified some scratches bewteen on the tightness face, see images attached. | Não |  |  |  |  | • Clean/degrease the surface using WD 40 or equivalent; • Smooth grinding with Carborumdum Stone 1000/3000 and JIG (ring with sandpaper 600/1000) to achieve a good shape. • Carry out flatness inspection on the tightness face. • Until to assembly step, keep the surface cleaned and protected to avoid new damages. | Find hereafter the solution to repair the bearing of the snorkel mast (seating of the Head valve), 1- Hoist the snorkel and secure it on its stopper. 2- Put some blue on the bearing and check with a marble, take some pictures, 3 - Polish everywhere (sand paper 320/500 see 1000) in order to reduce/remove the scratches and to keep the same plan, put again some blue and check with a marble, do that up to remove the scratch. It's necessary to keep a roughness among 3.2 and 12.5 on the surface. Take some pictures. Clean all. Think to take care to protect an close the inner pipe to avoid, that there are nothing and dust fall down inside, and the same for the external part. | Make the repair according to the method proposed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 538 Dias | Patrick Daliguet | BH |  | YES | NO |  | 2021-06-14 16:34 | Franciellen da Silva Braga |  | 2020-11-17 18:31 | Philippe Falquerho
NCR-ICN-ESC-12-0085-2020 | 53B | INTEGRATION EQUIPMENT | 2020-06-22 19:50 | Nível 2 | COS-SMB-200426 |  | TA 7.2 | ICN doesn’t have all the material to install the NRV’s. According to NCR-MAT-000935-2020, the NRV’s were received without item 6 (BDM-00024963_B). | Não |  |  |  |  | Manufacture the nuts according BDM-00024963_B - FL7. Fill a CTE with CQ inspection to register the dimensions and attach the certificate to be sure that the material is correct. | The quantity of NRV for the batch of SBR2 is 13 items: the needing is for the total batch. Nut (rep:6 MAT177-0297) and seal (rep:7 MAT177-0297) should be supplied with the complete set. NVG have to provide nuts and seals, in case of the arrival time is too far it's possible to manufacture localy in respect of material, and provide material certificate for each item. | - Agreement for making item 6 by ICN without deviation from plan BMD-00024963 F07. - Analysis of the cause of the absence of the rep. 6 during procurement and the resulting actions are dealt with by NCR-MAT-000935-2020. - ICN must provide the material report and the dimensional control of all the manufactured parts. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 524 Dias | Patrick Daliguet |  |  | NO | NO
NCR-ICN-ESC-12-0143-2020 | 53B | NON RESISTANT STRUCTURE | 2020-08-27 18:14 | Nível 2 | COS-SMB-319581 |  | TA 7.2 | Interference between battery element and floor plate (P4119096 - corresponds to porsidet and starboard, see photo in annex). During the trolley loading test, contact between the battery element and the floor plate was observed. According to the TA Hugues alignment, the repair was carried out as follows: - 14/08/2020 -Remove the welding around elements 648 and 649 to prevent deterioration of support and cut a new element and bend it. - 15/08/2020 - Tack weld new element and verify if the interference is desappeared - 15/08/2020 and 16/08/2020 - Weld and carry out inspection required in IT21-02-10E - 17/08/2020 - Carry out leak test of lower floor (S05) and 18/08/2020 was performed the test (S02). | Não |  |  |  |  | Follow 1.2 for repair the seating. Use CTE´s annexed to weld the seating on board and inspect the test S05 again. | REPAIR - Remove the welding around elements 648 and 649 to prevent deterioration of suport base. - Carry out 100%VT - Cut a new element and bend it. - Tack weld new element and verify if the interference is desappeared - Weld and carry out inspection required in IT21-02-10E - Carry out leak test of lower floor. | .Please apply PR Addendum loaded in TDP IS on 03/02/2021 : Seating : SMB-TDP-PR-6779506 SMB-TDP-PR-6779507 SMB-TDP-PR-6779488 | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 458 Dias | Hugues Bourget |  |  | NO | YES |  | 2020-09-02 19:11 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0227-2020 | 53B | ELETRIC | 2020-10-22 20:10 | Nível 2 | COS-SMB-200496, COS-SMB-CAB-OO-RM |  | TA 7.2 | Damaged cable RH62597 and RH62600D on board during the construction process. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | coaxial cable damaged, risk of insulation failure replace cables |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 402 Dias | Stéphane Patrick Philippe Rideau | RH |  | NO
NCR-ICN-ESC-12-0165-2020 | 53B | PIPES | 2020-09-16 12:33 | Nível 2 | COS-SMB-206140, COS-SMB-339470 |  | TA 7.2 | It was detected a misalignment between the valve EQ00003 and the AC32084. To solve we must twist the valve in the pipe axis. | Não |  |  |  |  | NG please analyze this problem. | proposition of the FO: - install the valve EQ00003 with the manoeuvre into AC32084 -adjust the new position of the flanges on the pipes EQ50001M2 and EQ50001M3 request to the BO: -for information: COS text and isometrics of the spools EQ50001M2 and EQ50001M3 will be updated by adding an observation that the orientation of the flanges have to be adjust on board according to the position of the seating of the valve EQ00003 and the position of the escape trunk | According to paragraph 2.2 the COS Text SMB-206140 will be updated : 1- Mechanical assembly of the EQ00003 valve with its control through the AC32084 passage 2- Presentation of pipes EQ50001M2 and EQ50001M3 without their connection flange to EQ00003 3- adjustment / positioning of the flanges and pointing thereof with the pipes on board 4- Removal of the pipes and final welding of the flanges in the workshop 5- Reassembly of the pipes on board and final connection to the valve | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 439 Dias | Franck Rubis | EQ, AC |  | NO | NO
NCR-ICN-ESC-12-0198-2020 | 53B | ELETRIC | 2020-10-07 14:25 | Nível 2 | COS-SMB-200542, COS-SMB-200569, COS-SMB-200712 |  | TA 7.2 | The bypass cables of the SBR2 battery cells after being connected to them and the torque of them are applied, did not guarantee the necessary fixation to maintain electrical contact. | Não |  |  |  |  | The measurement found in the contact area of the bypass cable is approximately 21mm. | The measurements were made by ICN using a calibrated caliper (PAQ-191). The deviations (between 0 and + 1mm) are higher than the tolerance mentioned in EXIDE Plan 292448.3.1. NG BO asks Level 3 what needs to be done to ensure that these makeshift cables (9902924480 and 9902924520) don´t "hole" after a torque tightening of 80N.m. | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 418 Dias | Benoit Guillaume Pierre Cuquemelle | BB |  | NO | NO |  | 2020-12-09 23:02 | Benoit Guillaume Pierre Cuquemelle
NCR-ICN-ESC-12-0213-2020 | 53B | MECHANICAL | 2020-10-16 18:30 | Nível 2 | COS-SMB-200763 | CTE00891598 | TA 7.2 | During the inspection of B06 on valve DN-00212 CTE00891598 it was verified that the screw supplied to attend SMB-TDP-PR-6027761 does not attend the acceptance criteria SMB-002930_I and SMB-200960_H with a minimum of 2 threads according to the photo in attachment 01, to attend the acceptance criterion, a screw of 90 mm in length was used, as shown in the photo in attachment02. | Não |  |  |  |  | Accept as it is. | The length 85mm is not sufficient to respect 2 minimum threads visible. The upper size is 90mm, this size will be used on board. It's necessary to modify the nomenclature. | Change the 2 screws interfacing with the seating to change to 90mm length, in accordance with the paragraph 2.2. (type 1 bolts). Seen with TA : the code of material is CMD : 32VI220D00004 (M16 lenght 90 mm) | Carmelo Alves Batista | Joao Paulo Schneider Gonzaga | 408 Dias | Patrick Daliguet | DN |  | NO | NO
NCR-ICN-ESC-12-0220-2020 | 53B | MECHANICAL | 2020-10-21 18:52 | Nível 2 | COS-SMB-347362 | CTE00956968 | TA 7.2 | During the inspection G06 -DIMENSIONAL CONTROL IN WORKSHOP was detected that the cotes marked in CTE00956968.7 was found outside allowed tolerance. See CTE attached. | Não |  |  |  |  | Accept as it is. The lower surface was not machined to avoid impact in the welded structure (see annex 1). This overlength will not affect the mounting of the gudgeon. | Accept as it is only with this over dimension not impact on the installation of the CVR protection cover. ICN must make a analysis before to accept as it is and please send the analysis to Naval Group. If not re-machine to be in the tolerance (Charles Boucher) |  | Neimar Mayrink da Silva | Joao Paulo Schneider Gonzaga | 403 Dias | Charles Boucher | N/A |  | NO
NCR-ICN-ESC-12-0230-2020 | 53B | INTEGRATION EQUIPMENT | 2020-10-24 11:35 | Nível 2 | COS-SMB-321710 |  | TA 7.2 | As discussed with NVG GIR, the nut of the hull passage AC33031 has not been duly locked as predicted in de design. Since the locking of this nut would trigger a huge impact and regression. For this reason, ICN asks NVG orientation in order to propose another solution. | Não |  |  |  |  | Follow the temporary solution that was proposed for SBR 1 in NCR-ICN-ESC-11-0554-2019. See attachments. Wait for NAVAL GROUP orientation. | Naval Group is in accordance with ICN. Deliberation N1 can be applied. Use FTG-7268 - AC33031 already attached within NCR. Regarding following boats SBR3 and SBR4, ICN has to properly add the Nut retainer defined in folios 7 and 26 of MAT425-0513, during mounting of Mobile part, in order to avoid this problem to occur again. GIR proposal However this problem was already found on SBR1 with a temporary acceptation till RANAE, ICN should have to manage properly the conform mounting as required by the TDP. D BERNEDE | Solution applied for SBR1 is a temporary solution till RANAE. For present NCR-ICN-ESC-12-0230-2020 related to SBR2, rework must be performed: mounting has to be conform to the initial and standard prescription before floating. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 401 Dias |  | AC |  | NO | NO
NCR-ICN-ESC-12-0234-2020 | 53B | MECHANICAL | 2020-10-24 12:31 | Nível 2 | COS-SMB-200538 |  | TA 7.2 | The movement of the base "SUPPORT FOR WATERPROOF PRESSURE RESISTANT BEARING REPEATER" (GN02560) is very heavy and can cause damage due to the weight in the "WATERPROOF PRESSURE RESISTANT BEARING REPEATER" (GN02545). ICN request some mechanical modification in GN02560. | Não |  |  |  |  | Proceed as per drawings attached. The porposed solution is the same according NCR-ESC-11-0945-2020. | The mechanical modification of GN02560 will be done regarding the OM 118496, as soon as the modification kit will be received. |  | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 401 Dias | Herve Gerard de Backer | GN | NCR-ICN-ESC-11-0945-2020 | NO
NCR-ICN-ESC-12-0240-2020 | 53B | RESISTANT STRUCTURE | 2020-10-28 17:49 | Nível 2 | COS-SMB-319088 |  | TA 7.2 | During the assembly of the DSRV, there was a change in elevation - annex 1. Because of that, it will be necessary to make a weld recomposition on the DSRV, weld recomposition on the items detached in red to increase the elevation of the platform (Height). | Não |  |  |  |  | Rework by surfacing. Recompose the good profile according IT21-02-10 11.2. Use C15 file inspection. | Rework Due to the gap betweenthe uper and lower part of DSRV plateform, it ´s necessarry to build up the lower part and ajust by grinding to avoid any gap. |  | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 396 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0286-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-23 13:33 | Nível 2 | COS-SMB-200569, COS-SMB-200712 |  | TA 7.2 | Problems occurred in the valves (KT03517 and KT03518): - Orientation of switch box not correct (both sides); - Fixing on the support with holes oblong and support not correctly positioning (both sides). | Não |  |  |  |  | Problems occurred in the valves (KT03517 and KT03518): - Orientation of switch box not correct (both sides); - Fixing on the support with holes oblong and support not correctly positioning (both sides). Solution of this issue: - Remove the valves KT03517 / KT03518, put the switch box in correct orientation and redo all inspection about these valves. | -In accordance with level 2.1 -NCR-ICN-ESC-12-0244-2020 for valves KT01417 and KT01418 is in link with this NCR. -A NCR REGRESS will be raise to follow new inspections and tests. ( Patrick Daliguet) | --> Remove valves KT03517 / KT03518 and put the switch box in correct orientation. --> Check well manoeuvre of the valves in both positions open and close. --> Redo all inspections about these valves, raise a NCR REGRESS. This operation must be mentionned in the valves tracability file. Nota : actions above mentionned do not impact tightness nor strength --> new pressure tests are not required. | Vinicius Siqueira dos Santos | Bruno Correa Ferreira | 371 Dias | Patrick Daliguet | KT | NCR-ICN-ESC-12-0160-2020 | NO | NO |  | 2020-12-08 15:45 | Frederic Pavic
NCR-ICN-ESC-12-0287-2020 | 53B | TRACEABILITY | 2020-11-23 17:49 | Nível 2 | COS-SMB-319693 |  | TA 7.2 | After the inspection of B07 on board it was found that some products are divergent. The CMD 01PE000D00063 (KT01451-P0153287, KT01452-P0153280, KT01453-P0153285, KT01454-P0127042, KT01455-P0153282 and KT01456-P0153289) and 01PE000D00062 (KT01461-P0153286, KT01462-P0153281, KT01463-P0153284, KT01464-P0153279, KT01465-P0153283 and KT01466-P0153290) are in inverted positions in all the TLTs the accordance with SMB-000676-H, page 05 (see the attachment). | Não |  |  |  |  | For analysis by Naval Group. | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Emanuela Lucia Justino dos Santos | Sergio André Telles Soares | 370 Dias | Patrick Daliguet | KT |  | NO | YES |  | 2020-12-10 18:38 | Patrick Daliguet
NCR-ICN-ESC-12-0292-2020 | 53B | INTEGRATION EQUIPMENT | 2020-11-26 13:00 | Nível 2 | COS-SMB-206096 |  | TA 7.2 | The handwheel of the valve FQ00101 was disassembled, so ICN production ask to redo B01 and B02 in order to be certainty the handwheel is correct assembled and the valve is completely close. | Não |  |  |  |  | Rework. Open a NCR Regress and redo the inspections B01 and B02. | Rework. Make a NCR regress and performed the necessary tests | The topic is not only the handweel but the whole reducer (gearbox). Inspections B01 and B02 have to be perfomed again but not only : according to MAT171-2727E, the closed position of the valve is setting by the "stop" of the reducer, so, after assembly on the valve it's necessary to perform §5.2, §5.3, §5.4 of MAT171-2727_EXP (BDM-00035068). Nota : §5.4 include the test of leaktight integrity of the valve. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 368 Dias | Frederic Guevel | FQ |  | NO | NO
NCR-ICN-ESC-12-0313-2021 | 53B | ELETRIC | 2021-01-15 18:05 | Nível 2 | COS-SMB-339062, COS-SMB-CAB-UA-UW |  | TA 7.2 | Damaged the cables UE63704D and UE63705D on board during the construction process. | Não |  |  |  |  | Provide two new cables (UE63704D and UE63705D). | If the armour of these cable are not damaged you can repair with a heat shrinkable see protocol SMB-325107. If not change them |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 317 Dias | Paul Fosse | UE |  | NO |  |  |  |  | Informações incorretas ou imprecisas | 2021-08-17 18:42 | Frederic Pavic
NCR-ICN-ESC-12-0430-2021 | 53B | ELETRIC | 2021-03-31 14:57 | Nível 2 | COS-SMB-319227, COS-SMB-200502, COS-SMB-CAB-BK-BZ |  | TA 7.2 | For the connection of BT22613 and BT22614 equipment to be carried out, it will be necessary to carry out the route changes of the following cables: BT62578I and BT64210I. The origin route of the same as the documentation is not compatible with the location of the equipment. | Não |  |  |  |  | FOLLOW LEVEL 2.2 GUIDELINES. | The BT sockets are mounted on the GN02522C, cables BT62578I and BT64210I routing needs to be redefined. Waiting orientation BO, please transmit the new route and the new lengths | No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-500189 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-500189 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. 07/07/2021: ANSWER V2: No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-330521 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 243 Dias | Stéphane Patrick Philippe Rideau | BT |  | NO | NO
NCR-ICN-ESC-12-0320-2021 | 53B | NON RESISTANT STRUCTURE | 2021-01-20 18:33 | Nível 2 | COS-SMB-200138 |  | TA 7.2 | Mounting the panel cover 18, AH00418. To assemble the cover of panel 18, a different strap from the project was paid, according to annex 1. | Não |  |  |  |  | Wait NG to check the CMD or description of the material to use the correct Straps. | Remove the bukles ajust at the good length these two elements stick it. To re-inforce the junction cut two plates of stainless steel 1 or 1,5 mm drill for holes and block on each side with blind rivet in stainless steel |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 312 Dias | Hugues Bourget |  |  | NO | [5 empty] | 2021-09-22 20:12 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0322-2021 | 53B | PIPES | 2021-01-21 19:35 | Nível 2 | COS-SMB-200262, COS-SMB-206096 |  | TA 7.2 | As discussed with Frédéric Guevel, the valve FQ00102 (P0137364), CMD: 18CR000D00022 of SBR2 leaked when performing the 70 bar resistance test. | Não | [5 empty] | During the test of SBR1, with found a leak on FQ00102 SBR1. i proposed to make a standard exchange with the FQ00102 of SBR2. Before remonted the FQ00102 SBR2 on the SBR1, i asked to icn to follow the procedure in annex to test it. During the pressure test, we found a leak on the seal superior of the hat. we didn't have a new seal in stock, we proposed (NG FO/BO) to manufacture a new one with the same material. After that, we tested the FQ00102 in the workshop = test OK at 52bar and 70bar. Make a NCR mat Make a NCR Regress Make the CTE of FQ00102 SBR2 (repaired in workshop) and CTE of FQ00102 of SBR1 | According to specialist : Rework -As soon as the boat's availability allows it (RANAE) the retrofit of the valve described in OM 127497 is to be applied. Kits were sent to the site in SAH for repair and modernization of SBR1 and SBR2 equipment. SAH: Ref UR: UR-SBR-2021.02-00105 Batch: SMB-MU18B-DB50-SAH | Marcelo Ricardo Alves Silva | Marcelo Ricardo Alves Silva | 311 Dias | Frederic Guevel | FQ |  | NO | NO
NCR-ICN-ESC-12-0332-2021 | 53B | SEATING | 2021-02-04 20:23 | Nível 2 | COS-SMB-200410 |  | TA 7.2 | During the assembly of the CYLINDRICAL ARRAY, there was interference in the holes of the seating P4022827. It was noticed during the assembly of the CYLINDRICAL ARRAY, that the lower seating’s P4022827, highlighted in yellow in annex 1, have the holes displaced 6mm with the equipment CYLINDRICAL ARRAY. | Não |  |  |  |  | Fill the holes in the itens mentioned, inspect 100% VT and 100% MT using CTE annexed. Do the holes again using drawning SBH.4D10.SMD.003283_C annexed. | To correct the position of CA elements , and respect the alignment with lubber line, it´s necessary to build up all the holes. -Use a copper back support After welding carry out 100 VT, and 100% MT or DP. -Carry out a new drilling. in respect of the reference alignment and hight. in parallele due the dismount of the part of equipment P0117844, it will necessary to blast and paint the half ring (see SMB-002723) following the painting document BDMAT-BDM-00053491-A1 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 297 Dias | Hugues Bourget | UA |  | NO |  |  | 2021-02-05 16:29 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0343-2021 | 53B | INTEGRATION EQUIPMENT | 2021-02-12 13:04 | Nível 2 | COS-SMB-319152 |  | TA 7.2 | According to PR-6114420, there is a new mobile part AF36510 that will be mounted on the B235 tank. The AF36510 was pre-assembled, it was soon realized that it was assembled out of coordinate. In annex 1, it shows the sketch of the mobile part assembled with the wrong coordinates and in the place where it should be assembled according to the project. PR-6114420. In addition, we inform the need to remanufacture the AF36510 element due to loss in the construction process. | Não |  |  |  |  | It was proposed by ICN to insert a plate with a Ø60 diameter to cover the hole that was made at the wrong coordinates and rework the new hole. ICN inform the need to remanufacture the AF36510 element due to loss in the construction process. | Repair insert a round element , diameter 60 thickness of 25mm in S355 steel Weld with E42 fillet weiding Carry out 100% VT, and 100%MT Drill a new drilling with the good coordonates It's possible to manufacture locally with integrality followed STF 33-04-30-TS017E. The construction folder will be done since the beginning (material certificate, qualification,...) Welding following SMB-030501 Inspections of welding following IT33-04-13E. Tests as explained in STF 33-04-30-TS017E The complete construction folder with all elements will be supplied for the closure of NCR |  | Renato da Silva Goncalves | Sharles Gomes Silveira | 290 Dias | Hugues Bourget | AF |  | NO |  |  | 2021-08-25 18:41 | Hugues Bourget
NCR-ICN-ESC-12-0346-2021 | 53B | PRESERVATION | 2021-02-18 12:33 | Nível 2 | COS-SMB-319725 |  | TA 7.2 | Concerning the aft battery of SBR-2: During the last Refresh charge, the H2 (Hydrogen) level surpassed 1,5%, lasting approximately 1 minute. This is a non-recurring fact, although the H2 level during the past charges has been slightly above the expected by the charging team. ICN Preservation Team believes this has to do with faulty calibration on the ventilation system. A Full charge is expected to take place on March 1st, so this is a urgent matter to be analysed and fixed. | Não |  |  |  |  | ICN Preservation Team wishes to inform NG that during the last refresh charge the H2 level reached and surpassed 1.5%. We believe the problem is faulty calibration of the ventilation system. Nevertheless, we would like orientation on how to proceed in case this is not the present issue. | Make an inspection in aft battery: * Control the air flow of grids => use the anemometer with parameter 2 and the cone. * Write the result of flow in the excel file to check the correct balance of the system => send the result to the back office naval group. * Redo the ventilation Chart *After received the comments from the back office => maybe necessary to modify the flow air of the grids. * the Pitot Aft battery system need also be checked ( the value of the pitot in low speed is not nominal) => need to check the lines of the pitot system with soap and water at 0,5bar. if you modify the grid, necessary to make a NCR regress. | The latest H2 rate results from the last AR battery charge are much lower (around 0.5%). Continuation of the subject to be piloted directly via the ITRs by updating the PPE FH2C and creation of a new high and low speed wind map (to be carried out by ICN with AT support and communication to the BO at each stage) . | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 284 Dias | Frederic Guevel | BB |  | NO | NO
NCR-ICN-ESC-12-0383-2021 | 53B | PIPES | 2021-03-17 17:06 | Nível 2 | COS-SMB-200433 |  | TA 7.2 | The assembly of the pipe P4127359 was not finished (brazed), and to perform the activity at this moment we created a new connection (reducing the size and making possible the disassembly) and now a new manufacture according to template. | Não |  |  |  |  | For pipe assembly P4127359, ICN created a new connection, reducing the size and allowing disassembly. NG, please guide us how to proceed. | REPAIR Autorize to add a new conection on the pipe P4127359 to finish the spool (brazed) Use this CMD : -18RO230D00595 (1) -18RO230D00573 (1) -18RO230D00574 (1) |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 256 Dias | Franck Rubis | RM |  | NO
NCR-ICN-ESC-12-0374-2021 | 53B | PIPES | 2021-03-15 11:33 | Nível 2 | COS-SMB-206044 |  | TA 7.2 | Was noticed on board the IM DN00112 had one stud in contact with the hull | Não |  |  |  |  | Remove DN00112, remount according SMB-200960 using new gasket and new tab washers, redo new inspections B06, B01, B02 and update B07 NCR-REGRESS will be open to invalidate old inspections B06, B01 and B02 of DN00112 | Agree with level 1.2. Dismount and remount conform, take new gasket and new lock washers. Raise NCR regress to redo inspections and tests | In accordance with level 2.2. (David BERNEDE - ISSP) | Renato Trabach da Cunha | Renato Trabach da Cunha | 259 Dias |  | DN | NCR-ICN-REGRESS-12-0033-2021 | NO | NO |  | 2021-03-23 13:38 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0375-2021 | 53B | PIPES | 2021-03-15 11:56 | Nível 2 | COS-SMB-206096 |  | TA 7.2 | Was notice on baord one stud of FQ00101 was in touch with the pressure hull | Não |  |  |  |  | Remove FQ00101, remount according SMB-200960 using new gasket and new tab washers, redo new inspections B06, B02 and update B07 NCR-REGRESS will be open to invalidate old inspections B06 and B02 of FQ00101 | Agree with level 1.2. Dismount and remount conform, take new gasket and new lock washers. Raise NCR regress to redo inspections and tests | - The bolts in contact with the hull can damage. Dismounting and remounting with new bolts. - In accordance with level 2 proposal - dismount the valve, change the gasket, redo all integrity inspections for this hull passage | Renato Trabach da Cunha | Renato Trabach da Cunha | 259 Dias | Patrick Daliguet | FQ | NCR-ICN-REGRESS-12-0034-2021 | NO | NO
NCR-ICN-ESC-12-0386-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-18 12:28 | Nível 2 | COS-SMB-319712 |  | TA 7.2 | The F06 and B06 documents for BM00031 and BM00032 doesn't fit the timeline for the logic mounting B01 and B02 was done 1 year after the mounting the nut tracebility of BM00032 B06 is Not Compliant, with differents Batchs and no mapping for the nuts disposal on the sleeve | Não |  |  |  |  | Open NCR-REGRESS to invalidate inspections F06, B06, B01 and B02 of BM00031 and BM00032 Remove BM00031 and BM00032, remount according SMB-200960 using new gasket and new tab washers, redo inspection F06, B06, B01, B02 and update B07 | Agree with level 1.2: -Dismount and remount conform -Raise NCR Regress to redo inspections and tests | In accordance with level 2.2 proposal. David BERNEDE | Renato Trabach da Cunha | Renato Trabach da Cunha | 256 Dias | Patrick Daliguet | BM | NCR-ICN-REGRESS-12-0035-2021 | NO | NO
NCR-ICN-ESC-12-0391-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-19 13:40 | Nível 2 | COS-SMB-319705, COS-SMB-330822 |  | TA 7.2 | The shaft stern gland (MB00003) was presented leak during the production test. See images annex. Traceability: AP435534. | Não |  |  |  |  | Send to level 2 to analyze. | After verify the good assembly of the PELA and all the O-ring ICN/NGFO try to do a new leak test: PELA was good assembly and the leak continu. Remove PELA with traceability AP435534 (SBR4) and use PELA with traceability AP419848 (SBR3) to assembly on board. Change all the O-ring and perform a new test. Open one NCR-MAT in order to supply new O-ring. To be forwarded in level 3 for traceability and to receive information about PELA SBR4 | Agreement on LVL2 decision to replace with the PELA initially planned for SBR3. The DTR of the PELA SBR4 does not show any non-conformity that could induce these leaks, which did not exist during the FAT of the PELA in the presence of the Brazilian Navy before its expedition. Actions to be carried out and results to be reported to BO Naval Group: - use an endoscope on the spreaders for seeing the potential spacing between the 2 rings - realize a spring dimensional control and compare the values with the DTR values | Vinicius Siqueira dos Santos | Ernanes de Souza | 255 Dias | Jean Christophe Laurent | MB |  | NO | NO
NCR-ICN-ESC-12-0397-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-23 18:55 | Nível 2 | COS-SMB-330725, COS-SMB-330663 |  | TA 7.2 | Due to the experience return from SBR1, we should do a dimensional inspection in the whole components. | Não |  |  |  |  | Send to level 2. | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0398-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-23 18:56 | Nível 2 | COS-SMB-330663, COS-SMB-330665 |  | TA 7.2 | Due to the experience return from SBR1, we should do a dimensional inspection in the whole components. | Não |  |  |  |  | Send to level 2. | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0399-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-23 18:56 | Nível 2 | COS-SMB-330662 |  | TA 7.2 | Due to the experience return from SBR1, we should do a dimensional inspection in the whole components. | Não |  |  |  |  | Send to level 2. | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0400-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-23 18:56 | Nível 2 | COS-SMB-330662 |  | TA 7.2 | Due to the experience return from SBR1, we should do a dimensional inspection in the whole components. | Não |  |  |  |  | Send to level 2. | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Patrick Daliguet | AG |  | NO | YES |  |  |  | Outros | 2021-10-01 19:03 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0401-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-23 18:56 | Nível 2 | COS-SMB-330664 |  | TA 7.2 | Due to the experience return from SBR1, we should do a dimensional inspection in the whole components. | Não |  |  |  |  | Send to level 2. | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Vinicius Siqueira dos Santos | Joao Paulo Schneider Gonzaga | 250 Dias | Patrick Daliguet | AG |  | NO | YES
NCR-ICN-ESC-12-0404-2021 | 53B | SEATING | 2021-03-24 14:07 | Nível 2 | COS-SMB-319548, COS-SMB-319719 |  | TA 7.2 | To remove the Mobile Part AC32042, it will be necessary to remove the seating P4171847. To meet NCR-ICN-ESC-12-0323-2021 in removing the Mobile Part AC32042. | Não |  |  |  |  | Remove seating P4171847, manufacture and install it again. Use CTE´s annexed. | rework rework a new seating and replace after the end of NCR 12-323 |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 250 Dias | Hugues Bourget | AC, EX | NCR-ICN-ESC-12-0323-2021 | NO
NCR-ICN-ESC-12-0418-2021 | 53B | PIPES | 2021-03-29 17:46 | Nível 2 | COS-SMB-206065, COS-SMB-331842, COS-SMB-206066 |  | TA 7.2 | As in ballast tank 1, some spools were not protected when they were not connected to the equipement (COR-2021-900343). | Não |  |  |  |  | NG, it is necessary to dismantle the tubes to check the cleanliness by blowing at least clean air. | Refere e apply the decison 1.2 |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | DW |  | NO
NCR-ICN-ESC-12-0419-2021 | 53B | PIPES | 2021-03-29 17:55 | Nível 2 | COS-SMB-321788, COS-SMB-319701, COS-SMB-321782 |  | TA 7.2 | The spool DB50131Y1 was not connected to valve DB00111 and not protected by cap (COR-2021-900343). | Não |  |  |  |  | NG, please analyze the problem found on board. | It is necessary to dismount the pipe P4119159 and to check the cleanness by at minimum blowing clean air but it is better to send the spools to a new pickling operation. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | DB |  | YES |  |  | 2021-04-01 11:23 | Franck Rubis | Falta de Anexo14 | 2021-11-09 18:13 | Erica de Lima Alves Silva
NCR-ICN-ESC-12-0420-2021 | 53B | PIPES | 2021-03-29 18:00 | Nível 2 | COS-SMB-321786, COS-SMB-321785 |  | TA 7.2 | The spools DP50145R3 and DP50144R3 were not protected by caps. These pipes supply the steering gear and pollution inside theses circuits can damage the circuit especially the servovalve DP00101 (COR-2021-900343). | Não |  |  |  |  | NG, It is necessary to proceed to a flushing of these pipes DP50145R3 and DP50144R3. It can be done on board connected the external flushing station or in workshop after dismounting the pipes. | Close the valves : -DP00110 -DP00108 Dismounting of the pipes: -DP50145R3 -DP50144R3 Flushing of this pipes at the workshop |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | DP |  | NO
NCR-ICN-ESC-12-0414-2021 | 53B | SEATING | 2021-03-26 12:54 | Nível 2 | COS-SMB-321781, COS-SMB-319593 |  | TA 7.2 | The seating of the NRV DY00906 was welded on the hull lately, the NRV is mounted and connected to its pipes. The weld joint was not cleaned and it is not painted (COR-2021-900343). | Não |  |  |  |  | (Seating): Communicate the process of welding used and the inspections realized (filer metal, welding documentation) to the seating P4095704 (DY00906C). See C23 53B-CTE00827182 annexed. (Painting): If the welding followed the NG requirement on hull welding, Brush properly and protected by painting and filling the inspections related. See COR-2021-900343 annexed. | Accepted as it is Apply the painting protection |  | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 248 Dias | Hugues Bourget | DY |  | NO |  |  | 2021-06-02 13:13 | Hugues Bourget
NCR-ICN-ESC-12-0410-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-26 10:48 | Nível 2 | COS-SMB-206071 |  | TA 7.2 | The hull valve EL00007 is mounting but the tab washers were not bent. The tightening of the valve could be considered as done from several (days because the pipe EL50002Ll was in presentation. As it is required in the SMB-200960 concerning hull integrity mounting, if the strength test cannot be done immediately after mounting, a paint mark has to be done on the bolting on each rod and nut to ensure there is no loosening of the bolting (COR-2021-900344). | Não |  |  |  |  | Proceed according 1.2. | Following instruction gave by ISP: Check the torque, if during the checking none nut turn, proceed to the strength test B01 even if the pipes outside the pressure hull are not mounted and then bend the tab washers. lt is necessary to complete the B06 inspection file to indicate all operations done. lf any nuts turn, the valve should be dismounted and NCR regress will be raise | In accordance with level 2.2. (David BERNEDE - ISSP) | Renato Trabach da Cunha | Joao Paulo Schneider Gonzaga | 248 Dias | Patrick Daliguet | EL | NCR-ICN-REGRESS-12-0053-2021 | NO | NO
NCR-ICN-ESC-12-0412-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-26 11:01 | Nível 2 | COS-SMB-319719 |  | TA 7.2 | The lock washer of the Mobile Part AC41016 was not bent so the mobile part was not locked but the pipe is connected. lt is important to finish completely the mounting of mobile parts before connecting the spools. | Não |  |  |  |  | Follow 1.2. | According decision of Diving Safety Engineer: Check of the torque of the mobile part nut: -lf the nut doesn't turn, bend the lock washer and indicate all the operations done in the B11-19 inspection file of the hull passage AC31016. -lf the nut of the mobile part turns, it is necessary to dismount the mobile part. | In accordance with level 2.2. (David BERNEDE - ISSP) | Renato Trabach da Cunha | Joao Paulo Schneider Gonzaga | 248 Dias | Patrick Daliguet | AC |  | NO | NO
NCR-ICN-ESC-12-0413-2021 | 53B | PIPES | 2021-03-26 11:57 | Nível 2 | COS-SMB-321786, COS-SMB-321790 |  | TA 7.2 | Two main deviations were seen for the DP valves DP00208, DP00216, DP00210, DPDD215, DPO0207, DP00211 and DP00209: A lack of protection of the valve DP00216, no cap was used to protect the valve against pollution. The position of the pipes, DP valves and their seatings are not compatible. The decoupling washers MN01-08 could not be mounted properly (COR-2021-900343). | Não |  |  |  |  | Send to level 2.2 to analyze. It is necessary to modify the seating’s of the OP valves DP00208, DP00216, DP00210, DP00215, DPD0207, DP00211 and DP00209 in order to have an acceptable mounting. For DP00216 it is necessary to perform an endoscopic inspection. lf some dust is found inside, it is necessary to change the valve. The polluted one will be cleaned in the workshop by flushing. | Agree with the ICN décision . AS a reminder : DP is a FHARI circuit and requires cleaning work in order not to pollute the system. | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Vinicius Siqueira dos Santos | Ernanes de Souza | 248 Dias | Franck Rubis | DP |  | NO | NO
NCR-ICN-ESC-12-0427-2021 | 53B | PIPES | 2021-03-30 14:51 | Nível 2 | COS-SMB-206044, COS-SMB-206071 |  | TA 7.2 | During inspection over EM21002 and EM21004 knuckle hoses it was identified a damage over the drain screw NGD 530514685691. Also it will be necessary a new 5330142097081 (BS gasket). Annex 1 shows a damage and a good screw and BDM-00032881_D present the items. | Não |  |  |  |  | NG, please analyze the problem found on board. | -Remove the broken screw -Manufacture a new screw, folowing drawing (repere / item : 22 (NGD : 5305143685691) ,23, 31): -MAT 166-0732 -MAT 166-0733 -Mounting of the new screw in accordance with applicables rules | - Remove the screws concerned. - Inspect the tapping in holes of the screws concerned: if tapping OK continue with the following steps, if tapping NOK write a new NCR. - Machine screws NGD 5305145376477 CMD 32VI120D00246 according to drawing FTG-9418. - Refit the machined screws with a new ring BS A8 PC851 NGD 5330142349929 CMD 44JO311D00034. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | EM |  | NO | YES
NCR-ICN-ESC-12-0434-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-06 12:01 | Nível 2 | COS-SMB-330822 |  | TA 7.2 | During the hydrostatic test, the equipment leaked during the test between 0-5 bar rising and 0-8 bar lowering the pressure. | Não |  |  |  |  | Regarding the shaft line stern gland (MB00003, CMD 15PE000D00001) delivered for SBR3 (AP419848) and assembled in SBR2. During the hydrostatic resistance test (70 bar) and the water tightness test (52,5 bar) a leakage was detected between 0 – 5 bar. To reach the test, It was necessary to open and close the cam holder (MAT422-0109, position 30), when the pressure overtaken 5 bar, the pressure remains constant without any leakage, the pressure was increased step by step until the maximum pressures requested in each test. Decreasing pressure, around 8 bar the leakage appear again, the leakage was quantified around one liter per hour. This phenomenal does not happen in the SBR1 tests. | If we consider the leak of 1L/H, the PELA is inside the tolerance of test during the last test done after some try before . The problem is during the first test it was impossible to rise the pressure until 5 bar due to a leak to important out of tolerance. ICN and NGFO are asking NGBO if it's acceptable as is or not. To be forwarded in level 3 to analyze | Regarding the photo added to the NCR, the pressure test can't be validated because of the orientation of the tab washers which can't be bend in this position. To re-orientate the tab washers it is necessary to untight the nuts, so put the tab washers in the good position to be bend properly and reperform the pressure test 70 bar, bend the tab wahers and perform the B02 pressure test (52,5 bar). Regarding a leakage, it is acceptable if in the tolerance. Factory Acceptance Tests were performed successfully with Brazilian Navy and DGA for this stern gland, so there is no manufacturing reason for a leakage over the tolerance. | Vinicius Siqueira dos Santos | Ernanes de Souza | 237 Dias | Jean Christophe Laurent | MB |  | NO | NO
NCR-ICN-ESC-12-0438-2021 | 53B | MECHANICAL | 2021-04-09 14:13 | Nível 2 | COS-SMB-319718 |  | TA 7.2 | VALVES BQ00005 AND BQ00006 SBR2 - Dimensional checked does not conform to design measures. (P0136477; P0136946) | Não |  |  |  |  | The STARBOARD EXTERNAL GAS EXHAUST VALVE BQ00005 53B-P0136477 - CMx 18SC000D00158 manufacturing drawing BDM-00024118 and PORTSIDE EXTERNAL GAS EXHAUST VALVE BQ00006 53B-P0136946 - CMx 18SC000D00159 manufacturing drawing BDM-00016755. Were checked the dimensions of positioning of the valves BQ00005 and BQ00006 in the submarine SBR2 on board. The measurements found are not in accordance with the manufacturing drawing BDM-00024118 and BDM-00016755. NG, please analyze the problem found. See annex 1. | Following drawing BDM-00016754 of BQ00005 and dimensions taken in annex 1: -The positionning of BQ00005 is not correct on 2 axis (X and Z). -For axis X: it's necessarry to update thickness ofshims to respect the dimension 205 +ou- 0,5mm. -For axis Z: a adjustment is possible on the actuator; can be accept as it is. Following drawing BDM-00016755 of BQ00006 and dimensions taken in annex 1: -The positionning of BQ00006 is not correct on 3 axis -For axis X: it's necessarry to update thickness ofshims to respect the dimension 205 +ou- 0,5mm. -For axis Y: a gap exist on both side between clevis and pushrod (0,5 and 2mm); can be accept as it is. -For axis Z: a adjustment is possible on the actuator; can be accept as it is. For both BQ valves a production document and inspection from quality are required: D85 To avoid this problem the D85 should be updated with a report of dimensions listed in annex 1 and the thickness of shims. -After BQ00005 and BQ00006 will be remounted a new inspection will be done and the production file (D85) will be updated with new thickness of shims and new dimensions in X, Y and Z. | For BQ00005 : - for axis X : adjust the position in accordance with level 2.2 proposal - for axis Y : acceptable - for axis Z : it is necessary to adjust the position of the actuator For BQ00006 : - for axis X : adjust the position in accordance with level 2.2 proposal - for axis Y : adjust the position of the valve - for axis Z : it is necessary to adjust the position of the actuator The "caderno" of mounting have to be updated to modified inspection files. First the inspection files have to be completed by quality so it is necessary to have D85-2 inspection and not seff inspection D85-1. The D85-2 inspection files have to present the interface documentation BDM-00016754 and BDM-00016755 for BQ00005 and BQ00006 and as required by level 2.2, it is necessary to have a table indicating the values expected in X, Y and Z axes and the results found by qualitiy specialists in this kind of measurement. David BERNEDE - ISSP | Ernanes de Souza | Ernanes de Souza | 234 Dias | Patrick Daliguet | BQ |  | NO | NO
NCR-ICN-ESC-12-0439-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-09 15:21 | Nível 2 | COS-SMB-206202 |  | TA 7.2 | The valve is stuck and does not allow the equipment to function (opening and closing). FH00010 - P0132369 | Não |  |  |  |  | REMOVE VALVE, CORRECT, APPLY TAF-TA-2020-0999 AND MOUNT ON BOARD | Make a inspection in FH00010 in workshop. You will find below the work done by ICN: Regarding the FH00010 valve was repaired according to the steps below: 1) Disassembled and removed the on-board valve FH00010 for the workshop; 2) The disassembly of the valve was carried out; 3) Shaft polishing performed; 4) Positioned the sealing gasket; 5) Test carried out in the workshop; 6) Reinstalled on board. Make a NCR regress |  | Ernanes de Souza | Ernanes de Souza | 234 Dias | Frederic Guevel | FH | NCR-ICN-REGRESS-12-0042-2021 | NO |  |  | 2021-05-04 12:28 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0445-2021 | 53B | PIPES | 2021-04-16 16:57 | Nível 2 | COS-SMB-200426, COS-SMB-206081, COS-SMB-206044, COS-SMB-206092, COS-SMB-200436 |  | TA 7.2 | 9 NRVs disassembled to check the good condition and correct alignment the lock washer that comes from factory with the valves. This action was started after production team cut the little tab bended of new valve that came misaligned how can be seen in the annex and they didn’t know if this incorrect action had been taken for others that was already mounted and some inspected too. It was verified that all disassembled NRVs are good, so ICN will paint and assemble them again and it’s necessary return all inspections related like B01, B02 and B11, opening a NCR-REGRESS. Valves-Parts: DM00032-AC33000 / DN00341-AC33002 / DN00241-AC33003 / EQ00014-AC32052 / DN00141-AC32012 / BM00175-AC32005 / KT00718-AC34024 / KT00717-AC34025 / BM00176-AC32007 | Não |  |  |  |  | It's necessary painting and remounting the valves. And after carry out the inspections. | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | In accordance with level 2.2. (David BERNEDE - ISSP) | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 227 Dias | Patrick Daliguet | DM, KT, BM, DN, EQ | NCR-ICN-REGRESS-12-0050-2021 | NO | NO
NCR-ICN-ESC-12-0448-2021 | 53B | PIPES | 2021-04-20 15:07 | Nível 2 | COS-SMB-206083 |  | TA 7.2 | ICN need to use 2 units of the CMD 18CR000D00002 (STRAINER BLOW NON-RETURN VALVE WITH RUCH UNION), that was delivered for spare-parts (SMB-RMS-CUR-DB35/01), in place of BM00201-P0136081 and BM00202-P0135968 in the SBR2. This action is necessary cause we received 2 units by SAH to solve the SBR1 questions that would be delivered for SBR2. The 2 RMS material came without gasket informations, thus just the gaskets will be discarted and it'll be necessary get the SBR3 new ones. It's needed opening a NCR-MAT to replace the 2 gasket units for SB3. And ask NG why did not come the information of the gasket supplied and why the color valve came beige in RMS. | Não |  |  |  |  | Using the RMS material in SBR2 and open the NCR-MAT like was described in the cover page. | In accordance with level 1.2 2 years ago 2 NRV on SBR1 were lost and replace by 2 of lot SBR2. Now we have to use RMS to replace on this 2 on SBR2. The both RMS were supply with gasket without packaging and information ( validity date, provenance..). NCR MAT should be raise to follow the purchase of 2 new fiber gasket and inform of the strange color (salmon) of both NRV. | The traceability of the seals is well in the technical acceptance file of the material. The salmon colour is not a problem. | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 223 Dias | Patrick Daliguet | BM |  | NO | YES
NCR-ICN-ESC-12-0451-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-28 17:32 | Nível 2 | COS-SMB-321697 |  | TA 7.2 | During the assembly of the DPs of the SBR2, the items below were not found (lost). It is necessary to request new correction items for the assembly of the DPs of the SBR2 (see attached the necessary items). | Não |  |  |  |  | Request assembly items for the DP00159, DP00160 and DP00259 of the SBR4 indicated in Annex (kit - DP00259 - DP00160 - DP00159 SBR02) to complete the assembly of the DPs of the SBR2. Open NCR MAT SBR4 to supply new materials. | ICN need to use the all the material necessary from SBR 3. Raise one NCR MAT with all the good information necessary in order to replace the material in the stock. | In accordance with level 2.2 proposal. (David BERNEDE) The NCR MAT has to quote the NGD and quantities of requested items. | Vinicius Siqueira dos Santos | Ernanes de Souza | 214 Dias | Jean Christophe Laurent | DP |  | NO | NO |  | 2021-06-02 13:52 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0452-2021 | 53B | PIPES | 2021-04-28 18:14 | Nível 2 | COS-SMB-200452, COS-SMB-206160 |  | TA 7.2 | The project requirements doesn’t meet the quality criteria requested in SMB-030510, so it was proposed the attached solution (FTG-8264). Please consider the design evolution for SBR2. | Não |  |  |  |  | Modify the Spool as defined in the attached FTG-8264-SBR2. It will be necessary to create CTEPROD to carry out the inspections and attach the NCR. Any modification must be handled directly at NCR. | Realize the modification in accordance with the FTG -8264. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 214 Dias | Franck Rubis | EJ |  | NO |  |  | 2021-05-12 19:10 | Franck Rubis
NCR-ICN-ESC-12-0453-2021 | 53B | STW | 2021-04-29 11:43 | Nível 2 | COS-SMB-319367, COS-SMB-319750 |  | TA 7.2 | During the execution of the pre-test regarding S02ULZ0001, it was identified a leak on the aft part of the trunk, more specifically at the handle/lever, just above the gasket. (See Photo attached for more details). Since this equipmment is part of the Imersion Circuit, please send to Patrick Daliguet We suggest to dismount this handle to verify its seals. NG to inform next Steps. | Não |  |  |  |  | We suggest to dismount this handle to verify its seals. NG to inform next Steps. | Agree with proposal: - Dismount handle with cutter (item:41 see annex. - Scrap both 2 O-Rings (item:42) and replace by new ones. - Raise a NCR REGRESS to redo inspections and tests. - Update the traceability folder. | In accordance with level 2.2 proposal. (David BERNEDE - ISSP) | Matias Lins Maranhão | Matias Lins Maranhão | 214 Dias | Patrick Daliguet | UL | NCR-ICN-REGRESS-12-0058-2021 | NO | NO
NCR-ICN-ESC-12-0459-2021 | 53B | PIPES | 2021-04-30 22:06 | Nível 2 | COS-SMB-200459, COS-SMB-200726 |  | TA 7.2 | During the test it was identified a damage to pipe P4121643 and P4121459. A simple re-weld is enough to guarantee the conformity. | Não |  |  |  |  | NG, please analyze the problem encountered on board. | -Cut the weld -Preparation in accordance with the DMOS -Welding by orbital process -Visual inspection -Radio X |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 212 Dias | Franck Rubis | KT |  | NO
NCR-ICN-ESC-12-0457-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-30 13:09 | Nível 2 | COS-SMB-319721 |  | TA 7.2 | The DA12501N equipment was installed on board and is lost by the construction process. | Não |  |  |  |  | We can install new equipment DA12501N on board to attend the construction process. we take the 53D-DA12501N SBR4 and open the NCRMAT. | Try to find this equipment (it can't disappear) If you can't find take a new one from SBR4 or SBR3. Raise NCR MAT to follow a new purchase. | In accordance with level 2.2 | Vinicius Siqueira dos Santos | Ernanes de Souza | 213 Dias | Patrick Daliguet | DA |  | NO | NO |  |  |  | Informações incorretas ou imprecisas | 2021-09-08 18:55 | Marcus de Lima Elisiario
NCR-ICN-ESC-12-0461-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-03 18:02 | Nível 2 | COS-SMB-200712 |  | TA 7.2 | It was done a pre-test on KT03518 valve before mounting your handle and the CONNECTOR (PLUG ELECTRICAL REF DEUTSCH 951-06R10-6S50A5949) broke, cause it's not possible to adjust the opening and closing valve without this handle. It's needed to pay a new one LIMIT SWITCH CMD 50DD400D00011 5935144580825 (BDM-00018284_B) . And how now the handle it's properly mounted as attachedment, after remount the new LIMIT SWITCH the test B01 can be carried out. The handle also help to define the definitive position opening/closing for after allow the correctly cables connection. | Não |  |  |  |  | The last information was incorrect, cause the NGDs informed are from female electrical parts. So the requirement is paying 1 unit of the CMD 50DD400D00011 that is the LIMIT SWITCH damaged during the pre-test. | Agree with proposal. The traceability folder should be updated with new swithches. | In accordance with level 2.2 proposal. | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 209 Dias | Anthony Jean Marie Georges Gel | KT |  | NO | NO |  | 2021-05-06 11:31 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0465-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-03 19:44 | Nível 2 | COS-SMB-319712 |  | TA 7.2 | During the 12-PTRH-BM-B01_BM00012 test happen a leak between the flanges of the valve BM00010 and the BM00012. So it's necessery remounting this part using a new FIBER/NBR GASKET 147X173X3 - 44JO230D00072. It's important highlighting that the rework will heppen just in the BM00012 valve cause only this one will be disassembled and the BM00010 will be in place. It was considered the installation drawing DEI-319712-80500-14-004 attached. | Não |  |  |  |  | It's necessery remounting the BM00012-P0135970 valve using a new FIBER/NBR GASKET 147X173X3 - 44JO230D00072 and redo the B01 test. Not needed to pay again news lock washer cause they haven't been bended yet. | Agree with proposal. Pay attention of the verification of the coating (F06) and the protection during dismounting. A NCR REGRESS will be raise to carry out inspections and pressure tests. B05 should be updated. | In accordance with ICN and level 2.2 proposal. David BERNEDE - ISSP | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 209 Dias | Patrick Daliguet | BM |  | NO | NO
NCR-ICN-ESC-12-0467-2021 | 53B | STW | 2021-05-04 14:48 | Nível 2 | COS-SMB-200452 |  | TA 7.2 | After replacement and calibration of the EV12152Q (MVZ-015) according to NCR-ICN-ESC-12-0259-2020. An out-of-acceptable reading accuracy greater than 15% was observed. | Não |  |  |  |  | Replacement of MVZ-015 to MVZ-017 is required. Send MVZ-015 for a new calibration after calibration send to stock. Perform inspection regression 12-PTRH-EV-S08_EVZ0002 / 12-PTRH-EV-S02_EVZ0002 | Proceed to a standard exchange of the flowmeter EV12152Q (calibration number MVZ-015) by a new flowmeter (calibration number MVZ-017). Create a NCR MAT to recalibrate the flowmeter dismounted from the SBR1 and refund the stock. Create a NCR REGRESS to manage the inspections and tests to redo. |  | William Jordao Goncalves dos Santos | William Jordao Goncalves dos Santos | 209 Dias | Gildas Le Goff | EV | NCR-ICN-REGRESS-12-0054-2021 | NO
NCR-ICN-ESC-12-0469-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-05 12:49 | Nível 2 | COS-SMB-319712 |  | TA 7.2 | During the 12-PTRH-BM-B01_BM00042 test happen a leak between the flanges of the valve BM00040 and the BM00042. So it's necessery remounting this part using a new (FIBER GASKET 147X173X3) - 44JO230D00072 and 28 news (LOCK WASHER) - 32VI420D00031 that was already bent. It's important highlighting that the rework will heppen just in the BM00042 valve, cause only this one will be disassembled and the BM00040 will be in place. It was considered the installation drawing DEI-319712-80500-14-004 attached. Related to AC32005 as Hull Integrity. | Não |  |  |  |  | It's necessery remounting the BM00042-P0134348 valve using a new FIBER GASKET 147X173X3 - 44JO230D00072 and 28 news (LOCK WASHER) - 32VI420D00031 which will be bent again after the B01 test approval. Redo all inspections related that was carried out. | Agree with proposal. Pay attention of the verification of the coating (F06) and the protection during dismounting. A NCR REGRESS will be raise to carry out inspections and pressure tests. B05 should be updated. | In accordance with ICN and level 2.2 proposal. David BERNEDE - ISSP | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 208 Dias | Patrick Daliguet | BM |  | NO | NO |  |  |  | Outros | 2021-09-08 18:59 | Marcus de Lima Elisiario
NCR-ICN-ESC-12-0470-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-05 17:26 | Nível 2 | COS-SMB-200526 |  | TA 7.2 | Equipment lost during the construction process. Please open NCR-MAT. DT00533 e DT00534 | Não |  |  |  |  | We can install new equipment DT00533 e DT00534 on board to attend the construction process and open the NCRMAT. | Take from SBR4 or SBR3. Raise NCR MAT to purchase new ones |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 207 Dias | Patrick Daliguet | DT |  | NO
NCR-ICN-ESC-12-0471-2021 | 53B | MECHANICAL | 2021-05-06 11:46 | Nível 2 | COS-SMB-330822 |  | TA 7.2 | During dimensional inspection of MB00002 and MB00009 were detected measures out of H7 tolerance. See attachment. | Não |  |  |  |  | MB00002: Accept as it is. 1) The aft holes H7 were remachined due SKF Coupling replacement. See NCR-ICN-ESC-12-208-2020; 2) A new adjustable pin nº 6 were adjusted to attend the NCR-ICN-UFEM-12-258-2018. MB00009: Accept as it is. 1) The Flexible Coupling (VULKAN) is already installed. No impact for operation. | After assembly on board any problem detected. |  | Neimar Mayrink da Silva | Joao Paulo Schneider Gonzaga | 207 Dias | Jean Christophe Laurent | MB | NCR-ICN-UFEM-12-0258-2018 | NO
NCR-ICN-ESC-12-0473-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-06 15:31 | Nível 2 | COS-SMB-206096 |  | TA 7.2 | The material provided for modification contained in order SMB12-MU18B-DB24, was not supplied in accordance with MAT177-0304_EXP FL19, making it necessary to machine the equipment to the project dimensions. Attachment dimensional report of the part that was supplied before and after machining. During the assembly of the FQ00102 SBR2 valve, the zinc protection was released. See Annex 2 | Não |  |  |  |  | To perform the change request contained in order SMB12-MU18B-DB24. 1. Request the supply of a new part to replace the damaged part. 2. Or NG, analyze the possible repair, we can hire a company specializing in protective zinc coating 3. Open NCRMAT. | FQ00102 - CMD: 18CR000D00022 serial number: 16_001 To machin the valve conform to the drawing MAT177-0304. It was checking the no possibility to remove zinc with nail and it was decided to continu the mounting. Open NCR MAT for the modification of dimensions of surfaces galvanized on the drawing. | In accordance for the rework according to level 2 proposal. Document MAT177-0304_EXP_E F19 (BDM-00069651) will be updated. | Vinicius Siqueira dos Santos | Ernanes de Souza | 207 Dias | Patrick Daliguet | FQ |  | NO | NO |  |  |  | Falta de Anexo14 | 2021-11-10 13:03 | Erica de Lima Alves Silva
NCR-ICN-ESC-12-0478-2021 | 53B | ELETRIC | 2021-05-10 18:30 | Nível 2 | COS-SMB-200526 |  | TA 7.2 | The GN02546 equipment was removed from the SBR2 in compliance with NCR-ICN-ESC-11-1058-2021. Please open NCR-MAT | Não |  |  |  |  | USE THE "GN02546" EQUIPMENT, SUPPLIED FOR ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY OF THE SAME. | Agree with decision N1. Open a NCR-MAT to supply o new one 11CD200D000711. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 202 Dias | Stéphane Patrick Philippe Rideau | GN |  | NO |  |  | 2021-05-11 14:49 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0481-2021 | 53B | PIPES | 2021-05-11 12:29 | Nível 2 | COS-SMB-200459 |  | TA 7.2 | During hull integrity inspection it was identified an incoherence with SMB-030510 for the pipe P4121883. We need a new remanufacture. | Não |  |  |  |  | Manufacture the spool according to the project definition. | Agree with the ICN decision | In accordance with proposal. The pipe which is not adapted has to be scrapped. David BERNEDE - ISSP | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 202 Dias | Franck Rubis | KT, BE |  | NO | NO
NCR-ICN-ESC-12-0482-2021 | 53B | PIPES | 2021-05-11 12:37 | Nível 2 | COS-SMB-200459 |  | TA 7.2 | During hull integrity inspection it was identified an incoherence with SMB-030510 for the pipe P4121999. We need a new remanufacture | Não |  |  |  |  | Manufacture the spool according to the project definition. | Agree with the ICN decision | In accordance with proposal. The pipe which is not adapted has to be scrapped. David BERNEDE - ISSP | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 202 Dias | Franck Rubis | KT |  | NO | NO
NCR-ICN-ESC-12-0483-2021 | 53B | PIPES | 2021-05-11 13:15 | Nível 2 | COS-SMB-200726 |  | TA 7.2 | Pipe P4121419 had it thickness compromised due to a surface damage, now a new manufacture is needed to solve the issue. | Não |  |  |  |  | Manufacture the spool according to the project definition. | Agree with the ICN decision |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 202 Dias | Franck Rubis | KT |  | NO
NCR-ICN-ESC-12-0480-2021 | 53B | STW | 2021-05-10 20:07 | Nível 2 | COS-SMB-200542 |  | TA 7.2 | OO24007 - MODULE ASI V3 SIEMENS TYPE 2 damaged according to the file in attachment. | Não |  |  |  |  | Forward to Naval Group. | Dismount and replace the module ASI V3 SIEMENS TYPE 2 Take it on sbr4 Use a bus cable with V1-W-5M-PUR (elbow connector, in annex) Open NCR MAT to refund only the module ASI V3 SIEMENS TYPE 2 Open NCR regress and redo E01 OO24007 F01 OOZ0028 F05 OOZ0019 F01 DAZ0002 for DA12509N and DA12513N |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 202 Dias | Benjamin Louis Dardennes | OO |  | NO
NCR-ICN-ESC-12-0487-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-13 11:15 | Nível 2 | COS-SMB-319712 |  | TA 7.2 | How was highlighted in NCR-ICN-ESC-12-0465-2021, was done a verification of the coating (F06) during the dismounting process and was identified that this is damaged on BM00010-P0135969 valve. This matter is related to hull integrity in AC32009. | Não |  |  |  |  | Replace the valve BM00010 (18SC011D00166) from SBR2 with the valve BM00031 (18SC011D00150) from SBR3. These valves are equivalents, in spite of their different CMDs, but it is necessary rotate the hydraulic actuator of the BM00031 to satisfy the BM00010 orientation assembly. It is important do a new F06 inspection before the mounting and a new B07 inspection after mounting with an appropriate traceability, which will have the information supplied with the valves when it was BM00031 yet. | BM00010 SBR2 18SC011D00166/ISSARTEL/014 was with halar damaged: -Raise a NCR MAT to follow the repairing. -Paid attention to protect correctly valves With the lack of stock of CMD: 18SC011D00166 it's possible to adapte the CMD: 18SC011D00150. BM00031 will be dismounted from SBR3 18SC011D00150/ISSARTEL/022: -Paid attention to protect correctly valve during all the process -Update the positionning M3 B2(switch box) V4(rotating jack) R8 to M3 B3 V3 R8 (MAT171-2727) -Change the label of the fitted valve with the CMD: 18SC011D00166 -Update the traceability folder -Raise NCR REGRESS to redo inspections and pressure tests | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Roberto Alves Assunção Medeiros | Rodrigo Thiago Soares Pereira | 200 Dias | Patrick Daliguet | BM |  | NO | NO
NCR-ICN-ESC-12-0489-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-14 11:02 | Nível 2 | COS-SMB-321710, COS-SMB-331842, COS-SMB-319719, COS-SMB-321709, COS-SMB-339470 |  | TA 7.2 | It was identified that the lock plate ("spider" like is called in ICN), wich is mounted in the middle of overmouldings BESCOND ACs, didn't arrive with the mobile part how was expected. So now, to finalize the electrical mobile parts jobs the ICN will manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. This matter is related to: AC43033 / AC41015 / AC42001 / AC43062 / AC43037 / AC44044 / AC42036 / AC43014 / AC43015 / AC43028 / AC44045 / AC43052 / AC43056 / AC43057 / AC44032 / AC44028 / AC42056 / AC44029 / AC44049. | Não |  |  |  |  | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. Update de B07 inspection of each mobile including the traceability of the material used in the manufacturing and the B13 should indicate this NCR to granted that the inspection of the good mobile lock was done and the "spiders" manufactured is working well. | EISP1 : level 3 for David BERNEDE In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 199 Dias | Patrick Daliguet | AC |  | NO | YES
NCR-ICN-ESC-12-0499-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-18 20:04 | Nível 2 | COS-SMB-331842, COS-SMB-321782, COS-SMB-206066 |  | TA 7.2 | Due the interference with ER pipes P4116455/P4116456/P411457/P4116458 to mount the supPort P4095984 as shown in attachment, it's needed dismounting these pipes, the mobile AC41021-P0151131 and the external pipes P4117135/P4117136/P4117137/P4117139. The mobile part dismounting decision was taken cause, in the welding process of this support, it will be used pre-heating which can induce a warming in the mobile and, maybe, a heat-treatment that can change or jeopardize the integrity mobile structure. | Não |  |  |  |  | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 194 Dias | David Roland Alain Bernede | AC |  | NO | NO
NCR-ICN-ESC-12-0500-2021 | 53B | SEATING | 2021-05-19 17:57 | Nível 2 | COS-SMB-319520, COS-SMB-321775 |  | TA 7.2 | Change in seating welding configuration P4181964 e P4171824. It’s not possible to weld and to install the preheating devices of the seating P4181964 e P4171824. (See annex 1). | Não |  |  |  |  | Agree with 1.2. Weld using austenitic. | REWORK Rework using austenitic electrods cary out 100% VT qnd 100% LP |  | Renato da Silva Goncalves | Felipe Trigueiros Silveira | 193 Dias | Hugues Bourget | EQ |  | NO
NCR-ICN-ESC-12-0504-2021 | 53B | ACOUSTIC DISCRETION | 2021-05-24 16:23 | Nível 2 | COS-SMB-200542 | CTE00756862 | TA 7.2 | During A06 inspection on FR00002 was checked: 1- One shock sensor Label L75 (15G) damaged; 2- One tilt sensor Tiltwatch XTR triggered; 3- Lack of one tilt sensor. | Não |  |  |  |  | The Equipment has a good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR to be send in L3 according to ARE request | Absorption unit FR00002 overturned, but not sensitive to overturning. This material will not undergo further vibration measurements in the future at ICN. (Excluding SHIP11C scope). | Marcos Aurelio Correa Abrantes | Rogerio Milani | 189 Dias | Frederic Pavic | FR |  | NO | NO |  |  |  |  | 2021-06-10 16:26 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0513-2021 | 53B | STW | 2021-05-26 14:05 | Nível 2 | COS-SMB-200426 |  | TA 7.2 | The DOME AIR PRESSURE REDUCING VALVE 250 / 45 BAR DY00313 presented an internal leakage during calibration on workshop. | Não |  |  |  |  | Forward to Naval Group. | Take a new dome air pressure reducing valve 18DP000D00007 in the stock, perform the calibration and mount onboard fo the SBR2. Create a NCR-MAT to manage the expertise of the defective equipment (serial number: P445886) to decide how to solve the problem. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 187 Dias | Gildas Le Goff | DY |  | NO
NCR-ICN-UFEM-12-0548-2021 | 53B | RESISTANT STRUCTURE | 2021-05-27 10:37 | Nível 2 | COS-SMB-330725 |  | TA 7.2 | Inspection S12: Aerostatic Pressure Test, with Internal Pressure. Lower hatch of Escape Trunk (EQ00043) Item 6 of CTEPROV33072502. I request to review the test pressure of 0.1bar. Reason_ When the indicated pressure is applied, the 47Kg Hatch moves from its position, and it is not possible to complete the 0.1 bar / 1 hour test. | Não |  |  |  |  | During the S12 - Test under aerostatic pressure, with internal pressure 0,1 bar (100 mbar), upward movement was observed and some leakage before achieve the pressure requested. The hatch EQ00043 was installed in the test tool (SMB-328815) through of weight itself (40,31 kg - 53B-CTE00825063). There is not locking system for this hatch. At this time, the engineer in charge of the test decided, in agreement with QC inspector, to perform a vacuum test (-0,1 bar/1 hour). The vacuum pressure was checked using a manometer with resolution of 1 mbar, see certificate attached. The measurement remained stabilized during 1 hour. The S10 and S11 tests in hyperbaric chamber were approved. Accept as it is. Send to NG analysis to review the S12 test for EQ00043. | EISP. For ICN : S12 inspection (Non-autoclave pressure testing of hatches) is not applicable for EQ00043. For BO : There is an inconsistency to correct between 2 documents : - EDT SMB-309223_K specify in 5.2.5 point B3 to proceed the internal pressure test - STA MAT424-1528_C (BDM-00062539_C) specify in 9.1.4 "Not applicable." (Fabien RENVOISE) | In accordance with level 2.2 to not perfom the non-autoclave test for this panel. Send the NCR to BO to modify the documentation. (David Bernede) | Fernando Chaves Barreto | Joao Paulo Schneider Gonzaga | 186 Dias | Patrick Daliguet | N/A |  | NO | NO
NCR-ICN-ESC-12-0516-2021 | 53B | MECHANICAL | 2021-05-27 19:22 | Nível 2 | COS-SMB-319705 |  | TA 7.2 | During the optical inspection of the alignment of the electric motor (EPM) after machining the shims and 48 hours of the torque of the screws, deviation was detected in disagreement with the project. See the inspection record in the attached CTEPROV31970580. | Não |  |  |  |  | Accept as it is. Agree with deliberation 1.2. | The control of alignment was done in the VULKAN flange who have one diameter of 1460 mm. The vertival concentricity of the control sheet need to be uptaded at 0,68 and not at 0,56. TDP will be charged with the new values of alignment and the TAF will be modified too. Accept as it is. Send to level 3 in order to inform and validate this situation. | - The vertical Sag between coupling flanges requirement is modified from 0.56 mm to 0.68 mm in phase 23 document MTSI200F03574_F / BDM-00085499_D loaded in TDP IS on 20/10/2021. - Accept as is for the Sag measured value at 0.82 mm. | Silvio Fonseca de Paiva | Ernanes de Souza | 185 Dias | Jean Christophe Laurent |  |  | NO | NO
NCR-ICN-ESC-12-0519-2021 | 53B | PIPES | 2021-05-28 13:53 | Nível 2 | COS-SMB-200443 |  | TA 7.2 | The pipe P4134573 was mechanically damaged on board, and after analysis it is not possible to achieve the quality standards with the pipe. | Não |  |  |  |  | Manufacture the spool according to the project. | -Manufacure a new pipe -Carry out the associated checks for a cat A pipe |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 185 Dias | Franck Rubis | DM |  | NO |  |  |  |  | Falta de Identificação (CTE) | 2021-08-13 14:48 | Frederic Pavic
NCR-ICN-ESC-12-0518-2021 | 53B | PIPES | 2021-05-28 13:43 | Nível 2 | COS-SMB-200273 |  | TA 7.2 | Scenario: during the pre-test of the inspections S02_KTZ0043 and S02_KTZ0044 (TLT5), it was identified these hydraulic lines "KT54145R / P0114678" and "KT54245R / P0114679" are inverted. Solution: 1) Blow the following hydraulic lines "KT54145R / P0114678" and "KT54245R / P0114679", and remove all FHARI oil; 2) Cut these lines, install in their correct positions and perform the welding; 3) Redo all releted inspections; 4) Redo the S01/M04/S02 for those lines and equipment ("KT54145R9 / P0114678", "KT54245R7 / P0114679", and "KT02215 / P0110718"). | Não |  |  |  |  | Scenario: during the pre-test of the inspections S02_KTZ0043 and S02_KTZ0044 (TLT5), it was identified these hydraulic lines "KT54145R / P0114678" and "KT54245R / P0114679" are inverted. Solution: 1) Blow the following hydraulic lines "KT54145R / P0114678" and "KT54245R / P0114679", and remove all FHARI oil; 2) Cut these lines, install in their correct positions and perform the welding; 3) Redo all releted inspections; 4) Redo the S01/M04/S02 for those lines and equipment ("KT54145R9 / P0114678", "KT54245R7 / P0114679", and "KT02215 / P0110718"). Please, send this NCR to NG specialists: Frank Rubis and Patrick Daligue. | There is no design problem and it is not necessary documents update. This NCR reports an assembly problem detected while performing a commissioning test. ICN production team fixed the mounting in order to be conform and re-do the test. |  | Bruno Correa Ferreira | Bruno Correa Ferreira | 185 Dias | Franck Rubis | KT | NCR-ICN-REGRESS-12-0062-2021 | NO
NCR-ICN-ESC-12-0521-2021 | 53B | PIPES | 2021-06-01 11:43 | Nível 2 | COS-SMB-206071, COS-SMB-319334 |  | TA 7.2 | During the pressure retest B01_EL00007, in attendance of the NCR-ICN-ESC-12-0410-2021 and the NCR-ICN-REGRESS-12-0053-2021, a leakage in the internal part of the valve EL00007-18RT020D00007-SN.4-15-001-COYARD was identified when the pressure reached >42 bars. | Não |  |  |  |  | Dismount the valve EL00007-18RT020D00007-SN.4-45-001-COPYARD on SBR2 and remounting a new one. Redo the inspections B06, B01, B07 and B02. ICN questions NG if it's necessary to open a NCR-MAT to ask a new valve to replace the stock or open a NCR-MAT and send the material to be repaired. | Proceed to a standard exchange of the valve EL00007-18RT020D00007 with a new valve from the stock or another SBR. Create a NCR MAT to expertise and repair the valve to refund the stock. Create a NCR-REGRESS to manage the inspections and tests to redo. | In accordance with level 2,2 proposal. Update the traceability folder of the both valves : the damage one and the new mounted valve (David Bernede) | Rodrigo Lino Castro | Roberto Alves Assunção Medeiros | 181 Dias | Gildas Le Goff | EL |  | NO | YES |  | 2021-06-10 16:21 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0528-2021 | 53B | PIPES | 2021-06-07 11:56 | Nível 2 | COS-SMB-206095 |  | TA 7.2 | During assembly P4167453 it was necessary some modifications of clamps and straub position, as sketches attached. | Não |  |  |  |  | NG, please review the solution found by ICN. | On piping line P4167453: -For the modification of the clamp P4183896 refere to the FTG 9482 -Modified position of the clamp P4183897: accepted |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 175 Dias | Franck Rubis | FQ |  | YES
NCR-ICN-ESC-12-0526-2021 | 53B | RESISTANT STRUCTURE | 2021-06-02 17:04 | Nível 2 | COS-SMB-319088 | CTE00851436 | TA 7.2 | During the inspection of the height of the DSRV with respect to deck line after machining on board, deviation was detected in disagreement with the design tolerance. See CTE00851436-2 attached. | Não |  |  |  |  | ICN propose to accept as it is, because flatness is conform. | Accedpted as it is, Adjust the hight of GRP panel using shim on the support |  | Silvio Fonseca de Paiva | Felipe Trigueiros Silveira | 179 Dias | Hugues Bourget |  | NCR-ICN-ESC-12-0324/2021 | NO
NCR-ICN-ESC-12-0529-2021 | 53B | STW | 2021-06-07 18:29 | Nível 2 | COS-SMB-206056 |  | TA 7.2 | During the EF2 test (Trial in remote mode with the CO2 bottle EF00018) in the aft battery room, a large CO2 gas leak was identified by the connection of the EF50045O pipe to the 5-way valve EF20038. | Não |  |  |  |  | Remover e reparar | make the standard exchange of the seal, check the misalignement of the pipe make a ncr regress |  | Daniel Fernando Fernandes Simoes | Daniel Fernando Fernandes Simoes | 174 Dias | Frederic Guevel | EF | NCR-ICN-REGRESS-12-0064-2021 | NO
NCR-ICN-ESC-12-0533-2021 | 53B | INTEGRATION EQUIPMENT | 2021-06-11 13:54 | Nível 2 | COS-SMB-200221 |  | TA 7.2 | During the assembly of the fastening elements of 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, the impossibility of locking the fastening screws item 22 and the need for screws with length was identified major item 26 of MAT321-0234 and MAT321-0235. Where the specified bolts must be replaced and complemented by bolts and washers as listed. | Não |  |  |  |  | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | see the anexe document attached |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 171 Dias | Anthony Jean Marie Georges Gel | KT |  | NO
NCR-ICN-ESC-12-0540-2021 | 53B | ELETRIC | 2021-06-15 18:27 | Nível 2 | COS-SMB-206085 |  | TA 7.2 | It was identified during the preparation of the DJ00002 valve adjustment that the energizing (supply) board of the 5.1 AUMA actuator has the varistor burnt. | Não |  |  |  |  | The actuator must be repaired or replaced with a new one. The problem has already been identified and detailed with NG team electrical expert Mr. Etienne Alexandre. Please get in touch with him for further explanation if you have any questions about how I managed to get to the next step. | Due of a supply issue of the actuator DJ00002 during trials at workshop, found that the PCB SUPPLY is burned (varistance) picture attached OM 121319 to replace the valve by a new actuator 07.1 Open NCR MAT to buy a new PCB SUPPLY for AUMA 05.1 in order to repair the actuator and put back in warehouse. |  | Rafael Thome da Silva | Rafael Thome da Silva | 166 Dias | Etienne Alexandre Sebastien Rene Berot | DJ |  | NO |  |  | 2021-06-28 19:37 | Stéphane Patrick Philippe Rideau
NCR-ICN-ESC-12-0542-2021 | 53B | PIPES | 2021-06-16 14:43 | Nível 2 | "COS-SMB-206139", COS-SMB-206139, COS-SMB-206139 |  | TA 7.2 | During adjust of P4168612 to avoid a touch with electrical panel it was necessary a bend with closer radius as presented in attached pictures. | Não |  |  |  |  | NG, please validate the solution found by ICN; | Iso of the new pipe is out of design because of the manufacture with a weld curve Request level 3 analysis for decision. Photo of the identification of the curve to be welded in the appendix. | The pipe P4168612 EQ50001M2 is under traceability. The use of the weld on elbow is acceptable; The M01 has to indicate the 2 weld; The M03 manufacture has to indicate the traceability of the weld on elbow and the reference of NCR; The M03 of EQ50001M2 of SBr1 has to be analyzed regarding the pipe on board. ( No NCR seems to have be raised). David Bernerde | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 166 Dias | Franck Rubis | EQ |  | NO | NO
NCR-ICN-ESC-12-0546-2021 | 53B | INTEGRATION EQUIPMENT | 2021-06-19 18:20 | Nível 2 | COS-SMB-206188, COS-SMB-319771 |  | TA 7.2 | The pitch diameter rods which join the flanges of the spool EJ50031J3-P4169746 (18LT100D00176-LOT.447549-17/614 + 2 units 18RO110D00055-17/01433-AF24869 both) and the deck plug EQ00412-P0120631 (18RO110D00751-16/003-MAT167-0152/MAT167-0154-Without Supplier) are not balanced how it is specified in "PROCEDURE FOR THE INSPECTION OF PRESSURE HULL BOLTING MATERIAL - SMB-200960" in its topic 8.1. This matter is related to hull integrity in AC32038. | Não |  |  |  |  | Dismounting the studs and remounting correctly and being sure that the pitch diameter rods protruding from nuts is equal (in length) and with less then 2 threads. Use a new fiber gasket 44JO230D00059 and 12 lock washers 32VI420D00030 (6 for each flanges side) how is specified by project. Redo inspections B06-CTE00994755 and update the B07-CTE00953235 of the deck plug EQ00412 and of the M03-CTE00994675 of the spool to granted the material traceability, paying attention in good filling. Raise the NCR-REGRESS for the tests already carried out and one, of the type NCR-MAT, to replace the materials used, if it's needed. | In accordance with N1. A NCR-REGRESS has to be raised. B05 has to be updated. (Fabien RENVOISE) | In accordance wih level 1 and 2 – raise a NCR REGRESS and update all inspections concerned (David Bernède) | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 162 Dias | Patrick Daliguet | EQ, EJ | NCR-ICN-REGRESS-12-0070-2021 | NO | NO |  | 2021-06-23 18:33 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0547-2021 | 53B | PIPES | 2021-06-21 18:46 | Nível 2 | COS-SMB-200424 |  | TA 7.2 | During W99 inspection it was identified two non-conformity for pipes P4057932 and P4051911. We kindly request NG evaluation to accept as it is in view that for P4057932 we are 19% higher (62 mm instead of 52 mm) and for P4051911 we are 14% higher (126 mm instead of 110 mm). | Não |  |  |  |  | ICN proposes that the NG accept as it is in view that for P4057932 we are 19% higher (62 mm instead of 52 mm) and for P4051911 we are 14% higher (126 mm instead of 110 mm).” | ACCEPT AS IT IS This problem is already known by NG and these differences between the requested dimension and that noted on board have already been accepted for similar cases. |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 160 Dias | Franck Rubis | EJ |  | NO |  | Sem deliberação ICN | 2021-08-26 17:41 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0549-2021 | 53B | ELETRIC | 2021-06-24 18:56 | Nível 2 | COS-SMB-319693 |  | TA 7.2 | KD68001D cable connector lost to construction process. | Não |  |  |  |  | USE THE SUPPLIED CONNECTOR FOR THE "SBR4" AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY. | See Deliberação N1 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 157 Dias | Stéphane Patrick Philippe Rideau | KT |  | NO
NCR-ICN-ESC-12-0553-2021 | 53B | INTEGRATION EQUIPMENT | 2021-06-29 14:55 | Nível 2 | COS-SMB-200572 |  | TA 7.2 | The thread M22 x 1 mm (MAT214-1488_Ref. 9) of PRESS ROD/OPERATING ROD CONNECTION (AP419157) was damaged during assembly onboard. See Annex 1. | Não |  |  |  |  | 1. Repair the internal thread M22x1mm to M24x1mm and manufacture new SCREW (MAT214-1488_Ref. 7) and NUT (MAT214-1488_Ref. 8) accordingly. NG must inform the material specification. The piece can be used in SBR 4 after repair. 2. If the material is not available, take the piece from SBR 4 and install in SBR 2. Pay attention with the traceability. Open NCR-MAT to supply a new complete set for SBR 4. | Use material of SBR4 in SBR2. Pay attention of the traceability . 2 solutions for the damaged M22/1: 1) Repair: Modify the M22/1 by M24/1 and open one NCR-MAT in order to supply a new screw and nut M24/1 This screw have an air hardening operation and a tempering process. Modify the torque for the assembly time. 2) Scrap: Open one NCR MAT in order to supply new material for SBR4 Item 7/8/9/10 of MAT214-1489 Send to level 3 for decision | Destroy the damaged part. Taken from SBR4 to serve SBR2. Open an NCR MAT in connection with this NCR ESC for restocking of REP: 7/8/9/10 of MAT214-1488 / 9 | Vinicius Siqueira dos Santos | Ernanes de Souza | 153 Dias | Jean Christophe Laurent | DP |  | NO | NO
NCR-ICN-ESC-12-0555-2021 | 53B | PIPES | 2021-07-01 17:46 | Nível 2 | COS-SMB-200470 |  | TA 7.2 | The valve DV00043-P0107806 (01PM300D00007-SN.17/010-ISSARTEL)-REV.B was partially dismounted to attend the NCR-ICN-ESC-12-0534-2021 and the NCR-ICN-REGRESS-12-0065-2021 . After remounting and redo the B11.27, during the test process, a damage in the mashroom AP458204 happened (photos attached), internal valve part. This matter is related to hull integrity in AC34004. | Não |  |  |  |  | Dismount completely the valve DV00043-P0107806 (01PM300D00007-SN.17/010-ISSARTEL)-REV.B of the hull submarine and redo the mounting using a new valve. Redo the steps following the sequence of mounting and inspections: Mount the valve in hull filling the B11.19 > dismount the internal parts of the valve how indicated in SBR-ETM-00000M0007 > do S03_DVZ0003, B02_DV00073 and B02_DV01033 > remount the internal parts remembering to fill the B11.27 > do S02_DVZ00003 and B02_DV00043 > do new B07 and attach, in B05 book, the declaration of material conformity corresponding. | In accordance with level 2.1 proposal. For locking the NRV nut inside hull, ICN can manufacture specific tab lock washer according to drawing in annex "Washer for DV NRV.pdf" : - material : X6CrNiTi18-10 - thickness : 1,5 mm Please add the material certificate and tab washer conformity in annex of NCR and in traceability file. (Fabien RENVOISE) | In accordance with level 2.2 proposal. Raise a NCR MAT to manage the repairing of the NRV 17/010 damaged. Raise a NCR Regress to manage the inspections to be redone. | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 150 Dias | David Roland Alain Bernede | DV |  | NO | NO
NCR-ICN-ESC-12-0559-2021 | 53B | ELETRIC | 2021-07-07 20:19 | Nível 2 | COS-SMB-200493, COS-SMB-200497, COS-SMB-CAB-EF-EZ |  | TA 7.2 | Equipment connectors ER00009, ER00010, ER00011 and ER00012 lost during the construction process. | Não |  |  |  |  | PROVIDE NEW CONNECTORS. | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 144 Dias | Stéphane Patrick Philippe Rideau | ER |  | NO
NCR-ICN-ESC-12-0560-2021 | 53B | STW | 2021-07-09 12:21 | Nível 2 | COS-SMB-200511, COS-SMB-200244 |  | TA 7.2 | The mechanical level detectors DT14120N, DT14220N and DT14320N are presenting incoherences during their functional verification, providing two contacts/signals of low level. | Não |  |  |  |  | Forward to Naval Group to verify and indicate the corrective actions. | The 3 sensors delivered by the supplier PROTAIS/VIGIL (level sensor 20028 with expansion) are not working well. Take 3 new sensors in RMS stock. CMD: 50DD500D00012 NGD: 0870118236680 Open NCR MAT to repair the 3 sensors with new internal parts. Attached pictures of internal part who is not working. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 143 Dias | Etienne Alexandre Sebastien Rene Berot | DT |  | NO
NCR-ICN-ESC-12-0562-2021 | 53B | ELETRIC | 2021-07-12 16:15 | Nível 2 | COS-SMB-200493, COS-SMB-CAB-KT-ME |  | TA 7.2 | KT63480D cable belonging to KT23480 and GN02551 equipment was damaged on board during the construction process. | Não |  |  |  |  | USE A NEW CABLE FROM ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR NEW SUPPLY. | Change and redo connectorization, Rais e a NCR MAT to re-order Cable and plug if necessary |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 140 Dias | Paul Fosse | KT |  | NO
NCR-ICN-ESC-12-0582-2021 | 53B | ELETRIC | 2021-08-12 19:58 | Nível 2 | COS-SMB-319724 |  | TA 7.2 | Protective cover screw broke inside the equipment housing. | Não |  |  |  |  | It's important highlight that this break problem with the screw fan cover probably occured cause someones constantly stepped on it, walking inside of the aft auxiliary room, at the time that the clean (EL00001) and dirty (EL00002) oil electrical pumps stay at the way in A130. And as this cover works like a protection of the fan, it should be mounting well and properly fixed. For it use 8 units of the screw 5305143973525 - STAINLESS SCREW H M5X8X8, 4 to each fan cover pump. And ICN team should sensitize our team with this case. The QC team should do a vibration analizes during the test F03_ELZ0003 or STW tests to grant that the noise limits is within tolerance. | request the assistance of the mechanical specialist to extract the broken screw |  | Jair de Barros Sena de Araujo | Roberto Alves Assunção Medeiros | 108 Dias | Stéphane Patrick Philippe Rideau | EL |  | NO
NCR-ICN-ESC-12-0565-2021 | 53B | STW | 2021-07-15 12:15 | Nível 2 | COS-SMB-200526, COS-SMB-200276 |  | TA 7.2 | The CP341 communications processor modules with RS422/485 interface of MCS PLC do not have dongle to activate the modbus RTU. | Não |  |  |  |  | Forward to Naval Group to verify and send the required dongles. | Normally, these 3 dongles should be mounted by the manufacturer. In the COC, these 3 dongles were declared mounted. Naval Group FO agrees with ICN proposal to take it from boat 3. Send to Naval Group BO supply chain to provide the 3 missing dongles (Siemens ref C79459-A1715-B210). | 5 dongles will be replenished in RMS. Edit a NCR MAT | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 137 Dias | Benjamin Louis Dardennes | OO |  | NO | YES
NCR-ICN-ESC-12-0570-2021 | 53B | ELETRIC | 2021-07-21 18:14 | Nível 2 | COS-SMB-CAB-KE-KO |  | TA 7.2 | KO60511B cable connector lost during construction process. | Não |  |  |  |  | USE THE SUPPLIED CONNECTOR FOR ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY OF THIS CONNECTOR. | Naval Group suggest ICN to use another connector from another SBR and edit NCR-MAT. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 130 Dias | Herve Gerard de Backer | KO |  | NO
NCR-ICN-ESC-12-0573-2021 | 53B | PIPES | 2021-07-26 16:45 | Nível 2 | COS-SMB-200463 |  | TA 7.2 | During pipe manufacturing it was force bended. It is necessary a new manufacture according to template. | Não |  |  |  |  | NG, please review the problem found on board. | Manufacture a new pipe with the associated controle |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 126 Dias | Franck Rubis | DW |  | NO
NCR-ICN-ESC-12-0576-2021 | 53B | PIPES | 2021-07-27 13:29 | Nível 2 | COS-SMB-200459 |  | TA 7.2 | After board inspections was observed that the spool KT50328Y6-P4121999 was damaged. This matter is related to hull integrity in AC34024. As information, it was already opened the NCR-ICN-REGRESS-12-0074-2021 to treat the B01 retest. | Não |  |  |  |  | Remanufacture the spool following the project construction docs properly. Redo the M01, M05 and B01_KT03518 that was already carried out. Take care during new mounting to not denting the material. Update the NCR-ICN-REGRESS-12-0074-2021 mentioning this NCR-CQ, the spool reworked and the B01 test like reason. | Agree with the ICN decision | The B01 pressure test is not suffisant, it is necessary to pressurise the spool at 250B with KT00818 closed, KT05018open in accordance with PTRH SMB-051122 concerning KT sub-system. The damaged spool has to be scrapped. | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 125 Dias | Franck Rubis | KT |  | NO | NO | Informações incorretas ou imprecisas | 2021-07-27 14:02 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0577-2021 | 53B | PIPES | 2021-07-27 13:34 | Nível 2 | COS-SMB-206091 |  | TA 7.2 | After board inspections was observed that the spool KT50327Y6-P4121610 was damaged. This matter is related to hull integrity in AC34025. As information, it was already opened the NCR-ICN-REGRESS-12-0075-2021 to treat the B01 retest." | Não |  |  |  |  | Remanufacture the spool following the project construction docs properly. Redo the M01, M05 and B01_KT03517 that was already carried out. Take care during new mounting to not denting the material. Update the NCR-ICN-REGRESS-12-0075-2021 mentioning this NCR-CQ, the spool reworked and the B01 test like reason. | Agree with the ICN decision. |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 125 Dias | Franck Rubis | KT |  | NO |  | Informações incorretas ou imprecisas | 2021-07-27 14:03 | Franciellen da Silva Braga
NCR-ICN-ESC-12-0586-2021 | 53B | ELETRIC | 2021-08-17 18:37 | Nível 2 | COS-SMB-339062, COS-SMB-CAB-OO-RM |  | TA 7.2 | RC60014D cable connector belonging to RC00001 equipment was lost during the construction process. | Não |  |  |  |  | Provide a new connector. | Check if connector D38999-26-W-J-29-PN is available on SBR4 Open an NCR-MAT to supply a new connector |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 103 Dias | Stéphane Patrick Philippe Rideau | RC |  | NO
NCR-ICN-ESC-12-0588-2021 | 53B | PIPES | 2021-08-23 17:00 | Nível 2 | COS-SMB-206089, COS-SMB-206090 |  | TA 7.2 | During the final assembly of EJ00132 it was identified that the flange rotation was not in agreement with what was done, now we need to disassembly the lower pipe (EJ50048E2) and rotate the flange. Today is impossible to remove the pipe without cutting it, there is no room for disassembly. Also another interference was found, it is impossible to perform the assembly of EJ50048E2 and EJ00132 with the clamp P4126696 welded in final position. To adjust the pipe to the new condition it was necessary to add a straub union on P4126686 as presented in the drawing (annex 1). | Não |  | Tubulação | Anomalia de Aplicação | Defeito de solda | ICN propose to dismantle the bottom tube (EJ50048E2) and rotate the flange in the corresponding position. To adjust the tube to the new condition, it is necessary to add a straub gasket on P4126686 as shown in the drawing (annex 1). | Remove the pipe P4126686 to put the flange in the correct position . Realize the inspection N01. NG autorize the addition of a Straub to make possible the mounting of the pipe P4126686 because it is a circuit without pressure (0.5 b). |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 98 Dias | Franck Rubis | EJ |  | NO |  | Sem deliberação ICN | 2021-09-13 13:02 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0590-2021 | 53B | INTEGRATION EQUIPMENT | 2021-08-27 18:58 | Nível 2 | COS-SMB-200569 |  | TA 7.2 | the KT08371 (limit switch) belonging to the KT03121 equipment. The limit switch was not found on board, being lost in the construction process. | Não |  |  |  |  | Rework, perform the installation with new equipment on board to meet the SBR2 construction process. Open the NCR MAT to complement the other SBR. | The lost of this limit switch is attributable to ICN; Naval Group suggests to edit NCR MAT in order to use this kind of limit switch from another SBR (3 or 4). |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 93 Dias | Herve Gerard de Backer | KT |  | NO
NCR-ICN-ESC-12-0595-2021 | 53B | ELETRIC | 2021-08-31 18:14 | Nível 2 | COS-SMB-200502, COS-SMB-CAB-KE-KO |  | TA 7.2 | KF62506I cable belonging to KF00004 and BF02540 equipment was damaged on board during the construction process. | Não |  |  |  |  | Use the supplied cable for another Submarine and open an "NCR-MAT" for a new supply. | Replace with a new cable. |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 89 Dias | Stéphane Patrick Philippe Rideau | KF |  | NO
NCR-ICN-ESC-12-0591-2021 | 53B | ELETRIC | 2021-08-30 16:30 | Nível 2 | COS-SMB-319757 |  | TA 7.2 | The BE0300AM equipment was lost during the construction process. | Não |  |  |  |  | Use the equipment provided for another Submarine and open an "NCR-MAT" for a new supply. | Agree with decision N1. Use one available. Open a NCR-MAT to supply a nes one 11BR000D00013 |  | Jair de Barros Sena de Araujo | Jair de Barros Sena de Araujo | 91 Dias | Stéphane Patrick Philippe Rideau | BE |  | NO
NCR-ICN-ESC-12-0597-2021 | 53B | PAINTING | 2021-09-01 12:53 | Nível 2 | COS-SMB-319315, COS-SMB-325862 |  | TA 7.2 | The base AM00004 of the B202 compartment was painted according to Construction Book DEI-319315-63110-12-001 Revision A with the C3 paint systems (upper part) and D3 paint system (lower part). In revision B of the Construction Book DEI-319315-63110-12-001 the Base AM00004 is treated as a support above the 500mm line painted with diagram D1 and not as an access platform according to Revision A. | Não |  |  |  |  | The applied schene paint is enough for the integrity of the anti-corrosive protection as it is not a critical area according to SMB-002345 | accepted as it is |  | Elaine Maria Ignacio da Silva | Annelize Lyra Nobre | 89 Dias | Hugues Bourget | AM |  | NO |  | Falta de registro fotográfico do produto danificado | 2021-09-01 13:00 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0594-2021 | 53B | PIPES | 2021-08-31 17:37 | Nível 2 | COS-SMB-206139 |  | TA 7.2 | During the work related to NCR-ICN-ESC-12-0542-2021 it was necessary to displace the seating P4168612 to follow the pipe geometry. To do so we request authorization to weld a new clamp and not redo the scape trunk test. | Não |  |  |  |  | NG, please analyze the problem found on board. | REPAIR It´s not aload to weld new seating on the tank after strenght test. Naval-group /TA propose to Use the seating P4170165 to weld the clamp P4502764. Adapt the clamp if necessary. | The new geometry of the pipe makes it pass close to the clamping 01CA000F00016 / P4501894 and allows it to be supported on this clamping. This solution eliminates the need to attach a new clamping to the EQ trunk and has no impact on the validation tests. | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 89 Dias | Hugues Bourget | EQ | NCR-ICN-ESC-12-0542-2021 | NO | YES
NCR-ICN-ESC-12-0596-2021 | 53B | STW | 2021-09-01 11:27 | Nível 2 | COS-SMB-319720 |  | TA 7.2 | One BELT VSX 2134 L10 of the HP Air Compressors were found damaged. (Girodin Sauer ref. - Compressor belt Part Nr: 01200231) | Não |  |  |  |  | Use a new belt from another submarine and request the deliverya new one. (Girodin Sauer ref. - Compressor belt Part Nr: 01200231) NGD 0930930267103 | The belt was replaced on the compressor DY00200. Need to create a NCR-MAT to refund the SBR3 (Girodin Sauer ref. - Compressor belt Part Nr: 01200231) - NGD 0930930267103. Scrap the old belt. |  | Lucas Abrantes Conde | Lucas Abrantes Conde | 89 Dias | Gildas Le Goff | DY |  | NO
NCR-ICN-ESC-12-0600-2021 | 53B | PIPES | 2021-09-03 17:03 | Nível 2 | COS-SMB-319452 |  | TA 7.2 | To remove the pipe it was necessary to remove the seating P4169456. Now we need to re-weld it. | Não |  |  |  |  | Reinstall the seating again using the cte´s annexed. | Rework, rework as per original, carry out the NDT required |  | Vladimir Gianotti Lopes | Luiz Felipe Silva Moreira | 86 Dias | Hugues Bourget | FQ |  | NO
NCR-ICN-ESC-12-0610-2021 | 53B | STW | 2021-09-14 11:44 | Nível 2 | COS-SMB-206090, COS-SMB-200241 |  | TA 7.2 | During a calibration attempt of DY00304/18DP000D00007 it was identified that it is impossible to calibrate the valve due to internal leakage | Não |  | Tubulação | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | Change Pressure reduction with a new one | The reducing pressure valve DY00304 - 18DP000D00013 (serial number: 20163001) was already replaced onboard regarding the NCR-ICN-ESC-11-0563-2021, by a new one valve (serial number: 20150909). The new reducing pressure valve is also not good. The valve was calbrated to reduce the pressure from 245 to 45 bar, but onboard, the pressure not stabilized and increase up at 45 bar. Perform a new standard exchange of the valve. Create a NCR-MAT to repair the valve and refund yhe stock. Create a NCR REGRESS to manage the inspections and tests to redo. |  | Gustavo Magarao Sambaquy | Gustavo Magarao Sambaquy | 76 Dias | Gildas Le Goff | DY |  | YES
NCR-ICN-ESC-12-0614-2021 | 53B | PIPES | 2021-09-16 14:50 | Nível 2 | COS-SMB-206070 |  | TA 7.2 | As declared in NCR-ICN-UFEM-12-0409-2019 The design of the spools P4153061, P4153059, P4156293 And P4156292 do not respect the rule of minimum distance between welds (IT-33-04-13E G, item 10.8.6). | Não |  | Tubulação | Anomalia de Aplicação | Defeito de solda | To resolve the issue, ICN proposes to accept it as is, as described in NCR-ICN-UFEM-12-0409-2019. and perform the radiographic inspection procedure as if they were category "A" tubes, for products P4153061, P4153059, P4156293, P4128926 and P4156292 see attached list. | ACCEPT AS IS Agree with te ICN Decision |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 74 Dias | Franck Rubis | EG | NCR-ICN-UFEM-12-0409-2019 | NO
NCR-ICN-UFEM-12-0551-2021 | 53B | NON RESISTANT STRUCTURE | 2021-09-21 18:15 | Nível 2 | COS-SMB-349504 |  | TA 7.2 | Alloy X2 CrNiMo 17 12 03 indicated in MAT 442-0003 is not available for use in item 04, 840 x 110 x 5 plate. ICN requests authorization for replacement, to use alloy X6CrNiTi 18-10. The appendix shows the correlations between the materials. The same problem occurred in SBR2, SBR3 and SBR4. CMD: 01PE200D00093. | Não |  | Isolamento, pintura, revestimento | Outras Anomalias | Vários defeitos | Do the change in the material as accorded in the email annexed. | Accepted as it is |  | Guilherme Brandao Matos | Luiz Felipe Silva Moreira | 68 Dias | Hugues Bourget |  |  | NO
NCR-ICN-ESC-12-0619-2021 | 53B | ELETRIC | 2021-09-21 18:54 | Nível 2 | COS-SMB-200512 |  | TA 7.2 | Fixing screw of the EJ00052 equipment cover was lost during the construction process. The screw is equipment specific, as shown in the attached image. | Não |  |  |  |  | Provide a new screw to continue the construction process. | See with mecanical team if it's possible to manufacture a new one |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 68 Dias | Stéphane Patrick Philippe Rideau | EJ |  | NO |  |  |  |  | Informações incorretas ou imprecisas | 2021-11-22 17:57 | Marcus de Lima Elisiario
NCR-ICN-ESC-12-0621-2021 | 53B | ELETRIC | 2021-09-21 19:04 | Nível 2 | COS-SMB-319750 |  | TA 7.2 | Damaged OO24301 equipment module, as shown in the attached image. | Não |  |  |  |  | Provide a new module to continue the construction process. | Replace the broken module Open an NCR-MAT to provision a new one |  | Jair de Barros Sena de Araujo | Geraldo Alves Simoes Filho | 68 Dias | Stéphane Patrick Philippe Rideau | OO |  | NO
NCR-ICN-ESC-12-0626-2021 | 53B | STW | 2021-09-23 16:22 | Nível 2 | COS-SMB-200544, COS-SMB-200276 |  | TA 7.2 | The MINI MCR-SL-RPS-I-I-SP MODULE (X32) card detected damaged during the F01_EZZ0002 test, according to the ANNEX 1 file. | Não |  | Eletricidade | Anomalia de Teste | Disfuncionamento do sistema, ..., do produto | ICN replaced the damaged card applying the respective item from SBR3 (OO02534). CTE of F01_EZZ0002 in attachment. NCR-MAT to recompose the stock of SBR3.. Forward to Naval Group. | Agree with deliberacao N1 Change the module X32 phoenix contact MINI MCR-SL-RPS-I-I-SP. Open NCR MAT to refund the module taken on OO02534 sbr3. NGD: 5963930154491 |  | Marcelo Fonseca Arantes | Luiz Felipe Silva Moreira | 67 Dias | Etienne Alexandre Sebastien Rene Berot | OO |  | NO
NCR-ICN-ESC-12-0661-2021 | 53B | SEATING | 2021-10-19 20:07 | Nível 2 | COS-SMB-319542 |  | TA 7.2 | Seating adjustment P4121692 in ballast tank 2. It was necessary to re-weld the holes, due to misalignment of the holes. | Não |  | Chapa, suporte, antepara leve | Outras Anomalias | Vários defeitos | Close the holes. Inspect 100% VT and 100% LP. Redo the hole with the correct dimensions. | Rework. Close the holes using SMB-200046 parameter, carry out 100% VT and 100%MT. Re-do the new holes. | In accordance with level 2,2 proposal | Renato da Silva Goncalves | Luiz Felipe Silva Moreira | 40 Dias | Hugues Bourget | DW |  | YES | YES
NCR-ICN-ESC-12-0667-2021 | 53B | STW | 2021-10-25 16:40 | Nível 2 | COS-SMB-200243, COS-SMB-200569 |  | TA 7.2 | Solenoid plug of DS14311 found damaged/missing on SBR02. Check the photo in attachment. | Não |  | Eletricidade | Outras Anomalias | Vários defeitos | Forward to Naval Group. | Take a new the connector STRAIGHT PLUG VG95234 M 10SL 3SN. Follow handbook SMB-EQUIPMENT-P0137971 to reconnect it. Open NCR MAT to refund the connector taken. |  | Marcelo Fonseca Arantes | Marcelo Fonseca Arantes | 35 Dias | Etienne Alexandre Sebastien Rene Berot | DS |  | NO
NCR-ICN-ESC-12-0671-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-27 18:44 | Nível 2 | COS-SMB-321703 |  | TA 7.2 | The current position of the DA10001N equipment is not according to the 3D model update. therefore, this interferes with onboard mounting. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | For equipment 53B- DA10001N - P0102959 - CMD 50MD500D00015 - INDIC. LEVEL TAP ED 15MM. Modification suggestion for the DA10001N equipment: Carry out the machining of 04 new Ø 16mm holes in the flange of DA10001N. This way, the flange will pass from 4 to 8 holes and it will be possible to rotate the equipment for on-board assembly. See annex 1. | Perform 4 new hole in the flange of thr DA10001N. Bend the transparent spool to match with the good angle. |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 32 Dias | Frederic Guevel | DA |  | YES
NCR-ICN-ESC-12-0493-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-14 14:02 | Nível 2 | COS-SMB-331842 |  | TA 7.2 Unfounded | The NRV DV00041 was not protected by cap, so there is a rick of pollution. The impact of a leak of this kind of equipment can jeopardize diving safety milestones (COR-2021-900343). | Não |  |  |  |  | In compliance with (COR-2021-900343) for NRV 53B-DV00041 valve, perform visual inspection and internal cleaning if necessary of the equipment, will be done during the commissioning process pneumatic test S03 for cleaning the system. |  |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 199 Dias | Patrick Daliguet | DV |  |  |  |  | 2021-06-14 17:47 | Patrick Daliguet
NCR-ICN-ESC-12-0425-2021 | 53B | INTEGRATION EQUIPMENT | 2021-03-30 14:02 | Nível 2 | COS-SMB-319712 |  | TA 7.2 Unfounded | During the assembly of BQ00001, BQ00002, BQ00003 and BQ00004, the metallic gasket used on the mounting came with no evidence from fabrication and expiration date | Não |  |  |  |  | Sent to L2 for analysis | For metallic gaskets information of validity date it's not necessary |  | Renato Trabach da Cunha | Renato Trabach da Cunha | 244 Dias | Patrick Daliguet | BQ |  | NO
NCR-ICN-ESC-12-0433-2021 | 53B | MECHANICAL | 2021-03-31 19:07 | Nível 2 | COS-SMB-200763 |  | TA 7.2 Unfounded | It was identified a divergence between the CMD filled in the B07 and in the F06 for valve DM00013-P0105294, traceability 18SC011D00156-019-ISSARTEL This matter is related to AC33001 Hull Integrity. | Não |  | Mecânico | Anomalia de Integração | Documentação inapropriada (referência errada, indicio errado, ...) | Send to LVL 2 for analysis |  |  | Renato Trabach da Cunha | Roberto Alves Assunção Medeiros | 242 Dias |  | DN |  |  |  |  | 2021-04-07 18:59 | Gildas Le Goff
NCR-ICN-ESC-12-0446-2021 | 53B | INTEGRATION EQUIPMENT | 2021-04-19 13:35 | Nível 1 | COS-SMB-200229 |  | TA 7.2 Unfounded | It was not possible to mount the optronic mast as it touches the screws fixing the operation Jack. | Não |  |  |  |  | It is necessary update document DEI-200229-80500-12-001_0. | NCR LEVEL 1 |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 224 Dias |  | RM |  | NO
NCR-ICN-ESC-12-0460-2021 | 53B | PIPES | 2021-04-30 22:20 | Nível 2 | COS-SMB-327464, COS-SMB-319693 |  | TA 7.2 Unfounded | After the mounting phase it was identified the touch of the flange nut (P4123639) on TLT body (P0126934). ICN need guidance of what to do in this case. | Não |  |  |  |  | ICN need guidance of what to do in this case. |  |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 212 Dias | Patrick Daliguet | KT |  |  |  | Informações incorretas ou imprecisas | 2021-08-02 14:33 | Felipe Gonçalves Sequeira
NCR-ICN-ESC-12-0476-2021 | 53B | INTEGRATION EQUIPMENT | 2021-05-07 15:20 | Nível 2 | COS-SMB-200395, COS-SMB-200581 |  | TA 7.2 Unfounded | A cut was identified in the Seating not described in the process for folding the washers that are part of the fixing elements of the ampoules. | Não |  |  |  |  | For cuts in the supports, accept as it is. Check that the bottles are in the orientation of positioning the internal immersion tube in a vertical position. For this, the “T” mark engraved on the hexagonal part of the lower adapter must be on the upper part. Check the tor tightness and locking of the rod threads. | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Vinicius Siqueira dos Santos | Luiz Felipe Silva Moreira | 206 Dias |  | DY |  | NO | YES |  | 2021-11-09 12:59 | Juliana Reis de Assis Quintino
NCR-ICN-ESC-12-0534-2021 | 53B | PIPES | 2021-06-11 18:40 | Nível 2 | COS-SMB-200470 |  | TA 7.2 Unfounded | The valve DV00043-P0107806 (01PM300D00007-SN.17/010-ISSARTEL) was difinitely mounted following the SBR-ETM-00000M0007 and the finals tests S02_DVZ0003/B02_DV00043 was carried out. But the inspection B11.27 (CTE01040296) was not filled. | Não |  |  |  |  | Dismount the valve DV00043-P0107806 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040296/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0003/B02_DV00043 tests and a NCR-MAT to replace the material (o-ring). |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 170 Dias | Patrick Daliguet | DV | NCR-ICN-REGRESS-12-0065-2021
NCR-ICN-ESC-12-0566-2021 | 53B | STW | 2021-07-15 15:25 | Nível 2 | COS-SMB-319326, COS-SMB-200710 |  | TA 7.2 Unfounded | Naval Group supplied the new batteries for the BS system and accessories. The amount of connection link of the battery element poles were not enough to complete the closing of the connection of the two battery (AFT and FWD). Attached is the list of supplied accessories and photos of the battery (AFT and FWD). Below is the number of outstanding battery links: 31 - (CNX DRT 12 35x3 E67 CU) | Não |  |  |  |  | Provide the amount of material (CNX DRT 12 35x3 E67 CU) that is outstanding. Send to NG specialist. |  |  | Paulo Roberto de Souza | Paulo Roberto de Souza | 137 Dias | Benoit Guillaume Pierre Cuquemelle | BS |  |  |  |  | 2021-07-15 16:40 | Christophe Marret
NCR-ICN-ESC-12-0630-2021 | 53B | PIPES | 2021-09-30 16:59 | Nível 2 | COS-SMB-206076, COS-SMB-206077 |  | TA 7.2 Unfounded | The mounting between the spool EL50001L1-P4165281 + AC31014-P4123479 and EL50001L1-P4165281 + EL00006-P0141690 is not properly done. The stud rods, type 2, should have its hexagonal head turned up to ease the identification and the tab of the lock washers should be bent in straight position on flange how it's guide by TA-NG and the SMB-200960_I about the pressure hull bolting procedure. This matter is related to hull integraty in AC31014. | Não |  | Tubulação | Anomalia de Aplicação | Modo operatório errado | Dismount the deck plug EL00006-P0141690 and remount respecting the stud rods orientations, with hexagonal head turned up and the tab of the washer straight on flange. Redo the B06 and B07 inspections. Dismount the spool EL50001L1-P4165281 and and remount respecting the stud rods orientations, with hexagonal head turned up. Redo B06, M05 and M03. Open a NCR-REGRESS to redo the tests already carried out: B01/B02/S02/S03. |  |  | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 60 Dias | Patrick Daliguet | EL |  |  |  | Outros | 2021-10-07 18:09 | Carmelo Alves Batista
NCR-ICN-ESC-12-0631-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-01 11:10 | Nível 2 | COS-SMB-319737 |  | TA 7.2 Unfounded | The SBR2 equipment (FV00500) was used in another SBR, according to NCR-ICN-ESC-11-1395-2021 and will be done through NCR-MAT-001669-2021. As CMD 17FA000D00008 is tracked, authorization request to use 17FA000D00008_4007 - EV COOLING OF FV00500 SERIAL NUMBER: 14M001-401 of SBR4 in SBR2. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | Perform the installation of new one equipment on board to attend the construction process of the SBR 2. As CMD 17FA000D00008 is tracked, authorization request to use 17FA000D00008_4007 - EV COOLING OF FV00500 SERIAL NUMBER: 14M001-401 from SBR3 in SBR2. | Agree with level 1. ICN can use the material (NGD 9980000098471) from SBR4 |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 59 Dias |  | FV | NCR-ICN-ESC-11-1395-2021 | NO |  | Outros | 2021-10-14 16:20 | Carmelo Alves Batista
NCR-ICN-ESC-12-0679-2021 | 53B | PRESERVATION | 2021-11-04 19:07 | Nível 2 | COS-SMB-200512 |  | TA 7.2 Unfounded | Concerning the MT03 Task: "CHECK INTERNAL JUNCTION BOX CONNECTION TIGHTENING AND WATERTIGHTNESS" - BE2400AC - SBR-MRC-000BEM0000-T015 It was not possible to perform the task because there is an access issue concerning the Junction Box cover. There is interference with tubulation or ducts. Even if it was possible to open the cover, there is no physical space to inspect the Junction Box. | Não |  | Eletricidade | Anomalia de Integração | Defeito de posicionamento, interferência, ... | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 24 Dias | Franck Heidel | BE
NCR-ICN-ESC-12-0680-2021 | 53B | PRESERVATION | 2021-11-04 19:09 | Nível 2 | COS-SMB-200512 |  | TA 7.2 Unfounded | Concerning the MT03 Task: "CHECK INTERNAL JUNCTION BOX CONNECTION TIGHTENING AND WATERTIGHTNESS" - BE2400AS - SBR-MRC-000BEM0000-T016 It was not possible to perform the task because there is an access issue concerning the Junction Box cover. There is interference with tubulation or ducts. Even if it was possible to open the cover, there is no physical space to inspect the Junction Box. | Não |  | Eletricidade | Anomalia de Integração | Defeito de posicionamento, interferência, ... | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 24 Dias | Franck Heidel | BE
NCR-ICN-ESC-12-0681-2021 | 53B | PRESERVATION | 2021-11-04 19:12 | Nível 2 | COS-SMB-200512 |  | TA 7.2 Unfounded | Concerning the MT03 Task: "CHECK INTERNAL JUNCTION BOX CONNECTION TIGHTENING AND WATERTIGHTNESS" - BE2400AB - SBR-MRC-000BEM0000-T010 It was not possible to perform the task because there is an access issue concerning the Junction Box cover. There is interference with tubulation or ducts. Even if it was possible to open the cover, there is no physical space to inspect the Junction Box. | Não |  | Eletricidade | Anomalia de Integração | Defeito de posicionamento, interferência, ... | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  | Fernando Martins de Azevedo | Fernando Martins de Azevedo | 24 Dias | Franck Heidel | BE
NCR-ICN-ESC-12-0704-2021 | 53B | STW | 2021-11-24 17:00 | Nível 2 | COS-SMB-337143 |  | TA 7.2 Unfounded | During the sea outing, was identified that the safety valve EG00237 is opening during the transfer of fuel to the feed tank, was performed an onboard test and found that the EG00237 is opening with 1.8bar and not with 2.3bar. | Não |  | Tubulação | Outras Anomalias | Vários defeitos | -It is necessary to dismont the safety valve and calibrate on the bench; -Open NCR-REGRESS to retest the circuit S02 EGZ0018 after monting. |  |  | Rodrigo Lino Castro | Rodrigo Lino Castro | 4 Dias |  | EG
NCR-ICN-ESC-12-0423-2021 | 53B | PIPES | 2021-03-29 18:28 | Nível 2 | COS-SMB-206114, COS-SMB-206112 |  | Tratamento 6.1 (FS) | During the first vacuum test a leakage was seen on the Straub coupling of pipes EW50019M5 and EW50019M3. There was clearly a misalignment of the pipes (COR-2021-900343). | Não |  |  |  |  | It is necessary to dismount the Straub coupling, and to modify the clamps of pipes EW50019M5 and EW50019M3 to align them. All inspections (mounting, pressure tests…) have to be redone. | -Disassembly the straub connection : -checking the alignment according to requirement in the SEFC 33-04-21/AIC 702E E -modify clamp or pipes if necessary -remounting the straub conection in acordance with the mounting rules - IMPORTANT :do not forget to grease the screw after disassembly |  | Vladimir Gianotti Lopes | Sharles Gomes Silveira | 244 Dias | Franck Rubis | EW |  | NO | [5 empty] | 2021-06-15 11:02 | Frederic Pavic
NCR-ICN-ESC-12-0618-2021 | 53B | INTEGRATION EQUIPMENT | 2021-09-21 17:08 | Nível 2 | COS-SMB-200716 |  | Tratamento 6.1 (FS) | The equipment 53B-KD07010 - P0110035 - CMD 11TD300D00147 and 53B-KD07020 - P0110031 – CMD 11TD300D00147 SBR 2, was removed and installed in SBR1 as per NCR-ICN-ESC-11-1480-2021. | Não |  | Mecânico | Outras Anomalias | Vários defeitos | The equipment 53B-KD07010 and 53B-KD07020 SBR 2, was removed and installed in SBR1 as per NCR-ICN-ESC-11-1480-2021. Perform the installation of new one equipment on board to attend the construction process of the SBR 2. Take the equipment of SBR 3 to install in SBR 2. Ref. CC-200716-30700-12-009 1) Item 1 - 53B-KD07010 - P0110035 - CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM 2) Item 30 - 53B-KD07020 - P0110031 – CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM Open NCR MAT for material replacement. | agree with level 2.1 |  | Vinicius Siqueira dos Santos | Ernanes de Souza | 68 Dias | Anthony Jean Marie Georges Gel | KD |  | NO
NCR-ICN-ESC-12-0653-2021 | 53B | INTEGRATION EQUIPMENT | 2021-10-14 19:34 | Nível 2 | COS-SMB-200710, COS-SMB-CAB-HD-KD |  | Tratamento 6.1 (FS) | The cable HL22105D-HL22105D-11LS572D00118-ADS-SN:N/A-LOT:18CH1016300-ORDER:CFE-1704067, which was dismounted from SBR1-RANAE to be mounted on SBR2, had the BESCOND cone damaged and should be completely changed by a new cable. Some others items should also be manufactured to finish the hatch HL40080 and mobile AC32500. The SN. was not informed on DOC-2018-903821. | Não |  | Casco Resistente | Outras Anomalias | Vários defeitos | 1.Remount a new cable HL22105D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB36010; B25, B13 and B07 for cable HL22105D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. 2. The manufacturing of the item 1 will solve the problem reported by NCR-MAT-001742-2021, which are blocking all the CMD cable 11LS572D00118 because it has reached the expiry date. 3. Open a NCR-MAT to send the damaged cable to repair. It’s important always having a new spare cable of hull leak to be used on demand. | Open a NCR-MAT to send the HL22105D cable as soon as possible (risk of blocking point for SBR3) to the BO for expertise and repair if possible> Use a new cable 11LS572D00118 for SBR2 | In accordance with proposal Raise NCR regress for inspections (there is no B07 inspection for AB36010) | Roberto Alves Assunção Medeiros | Roberto Alves Assunção Medeiros | 45 Dias | Stéphane Patrick Philippe Rideau | HL |  | YES | YES
NCR-ICN-ESC-12-0694-2021 | 53B | ACOUSTIC DISCRETION | 2021-11-16 19:38 | Nível 1 | COS-SMB-200542 | CTE00933677 | Tratamento 6.1 (FS) | During MS02 inspection on BB00031 it was checked the following items: 1- Thread rod M8 welded on seating is excessively long and corroded; 2- The height of the rod weld prevents the mount from touching the seating; 3- The two parts of the resilient mounts MN03 (top and bottom) are not mounted in the holes correctly. See attached photos and CTE (annexes 1 and 2). | Não |  | Mecânico | Anomalia de Integração | Montagem incompleta, desordenada, degradada | NCR Level 1 - According description it's necessary to do rework. See photo annex. | NCR LEVEL 1 |  | Marcos Aurelio Correa Abrantes | Rogerio Milani | 12 Dias |  | BB |  | NO

## Produtos
Número NCR | Produto | IM | Ação N1 | Decisão N1 | Ação N2 | Decisão N2 | Ação N3 | Decisão N3 | Rastreável | Serial
NCR-ICN-UFEM-12-0506-2019 | P4031158 |  | REWORK | Remove the seating and Install again. | REWORK | rework |  |  | Não
NCR-ICN-UFEM-12-0513-2019 | P4030791 |  | REWORK | Rework the seating in accordance with the last revision of the document SBH-PLM-3B22-000617_F (F27 e F35) | REWORK | Rework using the last TDP version of drawing. |  |  | Não
NCR-ICN-UFEM-12-0516-2019 | P4172352 |  | REWORK | Rework according to item 1.2 | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0516-2019 | P4172360 |  | REWORK | Rework according to item 1.2 | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0516-2019 | P4172361 |  | REWORK | Rework according to item 1.2 | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0516-2019 | P4172362 |  | REWORK | Rework according to item 1.2 | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0516-2019 | P4172419 |  | REWORK | Rework according to item 1.2 | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0517-2019 | P0129430 | DA00004 | REPAIR | Replace the screw CHC M8x45x28 CL 8.8 CMD: 32VI110D01976 by the screw M8x50 CL 8.8 CMD: 32VI110D00792 | REWORK |  |  |  | Não
NCR-ICN-UFEM-12-0519-2019 | P4020367 |  | REWORK | Reinstall again in the correct position. | REWORK | Rework |  |  | Não
NCR-ICN-UFEM-12-0520-2019 | P4140190 |  | REPAIR | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, and modulus with concordant values to the datasheet and results in Annex. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR | This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  |  | Não
NCR-ICN-UFEM-12-0521-2019 | P4138558 |  | REPAIR | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR | This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  |  | Não
NCR-ICN-UFEM-12-0522-2019 | P4140184 |  | REPAIR | The tissues were evaluated with respect to weight, interlaminar shear strength and flexural strength, modulus with concordant values to the datasheet and results in annex 1. Generally, specimens fabricated with 105.0 g / m2 fabric presented higher values than those fabricated with 205.0 g / m2 tissue. This may be due to the possibility of a better distribution of the resin in the 105.0 g / m 2 tissue, which presents greater spacing between the fiber cables, also facilitating a better wettability of these resins (by the fiber). | REPAIR | This process change is allowed only for reinforcing laminates. In no case to arm a gelcoat |  |  | Não
NCR-ICN-ESC-12-0012-2019 | P0118828 | EJ00003 | [6 empty] | Não
NCR-ICN-ESC-12-0012-2019 | SMB-P0142323 | [7 empty] | Não
NCR-ICN-UFEM-12-0532-2019 | P4007509 |  | SCRAP AND RE-MANUFACTURE | Manufacture a new one according SMB-325993_E | SCRAP | Rework a new one |  |  | Não
NCR-ICN-UFEM-12-0533-2019 | SC1-APGV00567.7A |  | REMOVE AND REWORK | As agreed with the production team, we proposes to remove the trailing edge, remove all the GRP skin of the blade, produce a new and restart the process from its positioning. | REWORK | Rework Remove the GRP Skin and the edge . Carry out an inspection form of the premix resin in relation with mechanical part. Correct it if necessary. Rework all the stpes as per original process. |  |  | Não
NCR-ICN-ESC-12-0017-2019 | SMB-P0110035 |  | NCR LEVEL 1 | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0017-2019 | SMB-P0110031 |  | NCR LEVEL 1 | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0018-2019 | SMB-P0124257 |  | NCR LEVEL 1 | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0058-2020 | P0126831 | GV22501D | REWORK | Supplier delivery | REMOVE AND REWORK | See NCR-ICN-ESC-11-0705-2019 |  |  | Não
NCR-ICN-ESC-12-0058-2020 | P0126832 | GV22502D | REWORK | Supplier delivery | REMOVE AND REWORK | See NCR-ICN-ESC-11-0705-2019 |  |  | Não
NCR-ICN-ESC-12-0058-2020 | P0126833 | GV22503D | REWORK | Supplier delivery | REMOVE AND REWORK | See NCR-ICN-ESC-11-0705-2019 |  |  | Não
NCR-ICN-ESC-12-0044-2020 | N/A |  | REPAIR |  | REWORK | After inspection the seating hight is not in acordance with the drawing . rework as per original. |  |  | Não
NCR-ICN-UFEM-12-0205-2018 | P0111242 | DT20167 | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0267-2018 | P4048701 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0333-2018 | P4171824 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0341-2018 | SC4-BA34 |  | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | Não
NCR-ICN-UFEM-12-0370-2018 | P0116117 | KT01448 | REPLACE | REPLACE | REPLACE | REPLACE | REPLACE | REPLACE | Não
NCR-ICN-UFEM-12-0384-2018 | MS2-EL694 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0406-2019 | Z00002270 |  | Agree with 2.1 | Agree with 2.1 | Agree with 2.1 | Agree with 2.1 | Agree with 2.1 | Agree with 2.1 | Não
NCR-ICN-UFEM-12-0425-2019 | DP02500 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0425-2019 | P4167453 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0425-2019 | FQ50106A2 |  | NCR CANCELLED | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0456-2019 | P4146263 |  | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | Não
NCR-ICN-UFEM-12-0478-2019 | P4176091 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0495-2019 | P0104575 | BH20005 | AGRRE WITH 2.1 | AGRRE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | Não
NCR-ICN-ESC-12-0048-2020 | P4503093 |  | REPAIR | Wait for NG orientation | REPAIR | Replace the assembly P4503093-P4148895 with straub union by a welding |  |  | Não
NCR-ICN-ESC-12-0048-2020 | P4148895 |  | REPAIR | Wait for NG orientation | REPAIR | Cut the pipe and insert straub union as per detail shown in anexo of this NCR |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102419 | BE00001 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102420 | BE00002 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102430 | BE00004 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102431 | BE00006 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102432 | BE00003 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102433 | BE00005 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102434 | BE00007 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102471 | BE00008 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0051-2020 | P0102472 | BE00009 | REWORK | Modify the internal connection of the transformers according to the project documentation (BDM-00076908_A and BDM-00060389_A PAG. 29) which shows the 115V / 120V transformation ratio. | REWORK | Rework according to NCR-ICN-ESC-11-0555-2019. |  |  | Não
NCR-ICN-ESC-12-0053-2020 | P4128829 |  | REWORK |  | REPAIR | Repair, Close with an circular insert plate. with REP2 bevel. Weld it using SMB-200853. Carry out welding inspections requered. Take care of the cut. to respect the para C-6-23 of IT21-02-10-E the center of the repair will be different that the center of the passage. Carry out leak test inspection S05 |  |  | Não
NCR-ICN-ESC-12-0055-2020 | P0146852 | AM00002S | REWORK | Rework the compression of the resilient mounts using shims according to SMB-200965. See annex data. | NCR LEVEL 1 | NCR LEVEL 1 | ACCEPT AS IT IS | Accepted as it is. | Não
NCR-ICN-ESC-12-0065-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0068-2020 | P0105262 | MB20300 | REMOVE AND REPAIR | NG. please inform how to proceed. | REPAIR | Adjust the length of the pipe P4129698 (add a straight part ) in order to get a correct mounting of the flexible hose MB20300. Carry all all new inspections required as M01, welding sheet, X ray, traçability, pressure test and passivation... |  |  | Não
NCR-ICN-ESC-12-0070-2020 | P4031069 |  | REPAIR |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0071-2020 | P4180259 |  | REPAIR |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0071-2020 | P4180263 |  | REPAIR |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0071-2020 | P4180262 |  | REPAIR |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0078-2020 | P4169971 |  | REWORK |  | REWORK | Rework as per original |  |  | Não
NCR-ICN-ESC-12-0078-2020 | P4169967 |  | REWORK |  | REWORK | Rework as per original |  |  | Não
NCR-ICN-ESC-12-0078-2020 | P4169957 |  | REWORK |  | REWORK | Rework as per original |  |  | Não
NCR-ICN-ESC-12-0085-2020 | N/A |  | MANUFACTURE | Manufacture the nuts according BDM-00024963 - FL7. Fill a CTE with CQ inspection to register the dimensions and attach the certificate to be sure that the material is correct. | REWORK | The quantity of NRV for the batch of SBR2 is 13 items: the needing is for the total batch. Nut (rep:6 MAT177-0297) and seal (rep:7 MAT177-0297) should be supplied with the complete set. NVG have to provide nuts and seals, in case of the arrival time is too far it's possible to manufacture localy in respect of material, and provide material certificate for each item. |  |  | Não
NCR-ICN-ESC-12-0086-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0087-2020 | N/A | [7 empty] | Não
NCR-ICN-UFEM-12-0538-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0100-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0100-2020 | P0101741 | OO04027 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0100-2020 | P0122382 | FH02623 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0100-2020 | P0122383 | FH02625 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0100-2020 | P0122385 | FH02521 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0100-2020 | P0122386 | FH02523 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0100-2020 | P0122387 | FH02525 | ACCEPT AS IT IS |  | REPAIR | Temporary mounting of the equipments listed can be done without the elastic mounting. However the elastic mounting have to be replaced by temporary shims in order to respect the location constraints and the interferences with the other equipements. STW and HCT Only can be carried out in this configuration, not valid for Batteries embarkation New NCR must be raised to extend the temporary configuration untill J1/J3 milestone As soon as it is received, the elastic mounting must be put in place |  |  | Não
NCR-ICN-ESC-12-0102-2020 | P0104221 | BC22501 | REWORK |  | AGREE WITH LEVEL 2.1 | In accordance with the declaration, the bj does not correspond to the BDM. Please clarify. Please note this bj is a prerequisite for J1 and J3 (battery boarding) | REWORK | kits must be provided to the front office for October 2020 for final modification of the SBR2 junction box see annex | Não
NCR-ICN-ESC-12-0103-2020 | P0105197 | DM00001 | REWORK | After reassembling the mount, redo the inspections according to the especific CTE list. DM00001: Inspections A03, MS02_1 and MS02_2 must be redone. DM00002: Inspections A03, MS02_1 and MS02_2 must be redone. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 12EE000D00041-18819-ENSIVAL
NCR-ICN-ESC-12-0103-2020 | P0138399 | DM00001H | REWORK | After reassembling the mount, redo the inspections according to the especific CTE list. DM00001: Inspections A03, MS02_1 and MS02_2 must be redone. DM00002: Inspections A03, MS02_1 and MS02_2 must be redone. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0103-2020 | P0105198 | DM00002 | REWORK | After reassembling the mount, redo the inspections according to the especific CTE list. DM00001: Inspections A03, MS02_1 and MS02_2 must be redone. DM00002: Inspections A03, MS02_1 and MS02_2 must be redone. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 12EE000D00041-18818-ENSIVAL
NCR-ICN-ESC-12-0106-2020 | P0130541 | FC00527 | REWORK |  | REWORK | Provided standardized terminal strip (to replace adhesif labelling) | REWORK | Naval Group will send WMB multiple marking system Horizontal printing 9905930185410 | Sim | 17CA000D00082
NCR-ICN-ESC-12-0211-2020 | P0121089 | EM02501 | REWORK | [5 empty] | Sim
NCR-ICN-UFEM-12-0540-2020 | P4124839 |  | REWORK | disconnect everything and add connections for the junction. Necessary connections. 18RO230D00566 18RO230D00577 44JO312D00002 18RO230D00587 |  |  |  |  | Não
NCR-ICN-ESC-12-0115-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0130-2020 | P0108340 | DY02511 | REWORK |  | REWORK | Replace the BIPOLAR REVERSER 2 POSITIONS LOCKING LEVER by a new one. Open a NCR-MAT to supply NGD 0930930255198 => see the BDM-00063900 COMPRESSOR STARTER UNIT-PARTS LIST |  |  | Sim
NCR-ICN-ESC-12-0130-2020 | P0108341 | DY02512 | REWORK |  | REWORK | Replace the BIPOLAR REVERSER 2 POSITIONS LOCKING LEVER by a new one. Open a NCR-MAT to supply NGD 0930930255198 => see the BDM-00063900 COMPRESSOR STARTER UNIT-PARTS LIST |  |  | Sim
NCR-ICN-ESC-12-0136-2020 | N/A |  |  |  | REWORK | ICN must clarified the situatiopn - identified the date of galvanisation - compare with the welding date - if discrepancy check if a new CTE had been issue after welding Situation not acceptable as it is |  |  | Não
NCR-ICN-ESC-12-0145-2020 | P0103632 | BF02505 | REMOVE AND REWORK |  | REMOVE AND REWORK | FO decided temporary to glue 2 blind rivet nuts (tubtara) diameter 4. We machined the 2 screws in order to tight the circuit breaker on the base See the attached photos of the job The base should be replaced by OEM or ICN during the RANAE Open NCR MAT to buy a new base breaker: SCHNEIDER ELECTRIC BASE NS630 3P Manufacturer Ref: 2988502 §6.4 | REPAIR | The following items are Ordered and will be sent to the ICN for repair: - 1x NSX630 LV432516 circuit breaker base (NGD 5925930231348) - 2x M5x85 screws | Sim
NCR-ICN-ESC-12-0152-2020 | P0114145 | KT40001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115842 | KT40002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115418 | KT40003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114831 | KT40004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114628 | KT40005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0133721 | KT40006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114147 | KT41001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115843 | KT41002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115419 | KT41003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114832 | KT41004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114629 | KT41005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0133712 | KT41006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114148 | KT42001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115844 | KT42002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115420 | KT42003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114833 | KT42004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114630 | KT42005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115632 | KT42006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114150 | KT43001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115846 | KT43002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115422 | KT43003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114835 | KT43004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114632 | KT43005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115634 | KT43006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114149 | KT44001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115845 | KT44002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115421 | KT44003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114834 | KT44004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114631 | KT44005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0115635 | KT44006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075688
NCR-ICN-ESC-12-0152-2020 | P0114151 | KT45001 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115847 | KT45002 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115423 | KT45003 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114836 | KT45004 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0114633 | KT45005 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0152-2020 | P0115638 | KT45006 | REWORK | REWORK |  |  | REMOVE AND REWORK | The declaration of conformity including the configuration annex is sent to the BN The BN makes the materials available to ICN ICN must request the information from the BN | Sim | 11RS1075687
NCR-ICN-ESC-12-0159-2020 | P0143660 | DA01011 | REMOVE AND REWORK | Dismounting the equipment DA01011 from SBR 3 and assembly in SBR 2. Raise a NCR-MAT for SBR 3. |  |  |  |  | Não
NCR-ICN-ESC-12-0164-2020 | P4119253 |  | REMOVE AND REPAIR | NG, please analyze the problem. | REPAIR |  |  |  | Sim
NCR-ICN-ESC-12-0164-2020 | P4119255 |  | REMOVE AND REPAIR | NG, please analyze the problem. | REPAIR |  |  |  | Sim
NCR-ICN-ESC-12-0227-2020 | P0108907 | RH62597D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | coaxial cable damaged, risk of insulation failure replace cables |  |  | Não
NCR-ICN-ESC-12-0227-2020 | P0108908 | RH62600D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | coaxial cable damaged, risk of insulation failure replace cables |  |  | Não
NCR-ICN-ESC-12-0165-2020 | P0127387 | EQ00003 | AGREE WITH LEVEL 2.1 | NG please analyze this problem. | REWORK |  | REWORK | According to paragraph 2.2 the COS Text SMB-206140 will be updated : 1- Mechanical assembly of the EQ00003 valve with its control through the AC32084 passage 2- Presentation of pipes EQ50001M2 and EQ50001M3 without their connection flange to EQ00003 3- adjustment / positioning of the flanges and pointing thereof with the pipes on board 4- Removal of the pipes and final welding of the flanges in the workshop 5- Reassembly of the pipes on board and final connection to the valve | Sim | 0004
NCR-ICN-ESC-12-0165-2020 | P0156013 | AC32084 | AGREE WITH LEVEL 2.1 | NG please analyze this problem. | REWORK |  | REWORK | According to paragraph 2.2 the COS Text SMB-206140 will be updated : 1- Mechanical assembly of the EQ00003 valve with its control through the AC32084 passage 2- Presentation of pipes EQ50001M2 and EQ50001M3 without their connection flange to EQ00003 3- adjustment / positioning of the flanges and pointing thereof with the pipes on board 4- Removal of the pipes and final welding of the flanges in the workshop 5- Reassembly of the pipes on board and final connection to the valve | Não
NCR-ICN-ESC-12-0170-2020 | P0145119 | BD02527 | ACCEPT AS IT IS | Send to level 2. | REWORK | The grounding of the cabinet was forgotten during the design The problem has been solved with the FTG-7158 before to receive the OM110635 Awaiting BO decision to confirm : 1 - acceptance as is 2 - rework now, with all the regressions that implies 3 - rework at RANAE | REWORK | Carry out a ground continuity check to be carried out in order to validate the provisional assembly. OM-110635 to be carried out during the RANAE on SBR2. | Não
NCR-ICN-ESC-12-0170-2020 | P0145117 | BD02528 | ACCEPT AS IT IS | Send to level 2. | REWORK | The grounding of the cabinet was forgotten during the design The problem has been solved with the FTG-7158 before to receive the OM110635 Awaiting BO decision to confirm : 1 - acceptance as is 2 - rework now, with all the regressions that implies 3 - rework at RANAE | REWORK | Carry out a ground continuity check to be carried out in order to validate the provisional assembly. OM-110635 to be carried out during the RANAE on SBR2. | Não
NCR-ICN-ESC-12-0176-2020 | P0124837 | BB22511 | REWORK | REWORK. | REWORK | The copper bar J1 received are not compliant with the required design, see annex. Could not be fixed on board. Solution given by ICN 2,1 is not avalaible Tempory mounting solution given by TA : use 3 cables CEI 1x150 mm² per pole, meaning 9 cables per battery, 18 per boat HOW EVER THIS SOLUTION NOT ALLOW TO USE FULL POWER MAXIMUM ALLOW IS 1250A PER BATTERY | SCRAP | See corrective maintenance sheet C13 of the technical manual (page 99/109) "Only use three bridging connectors of the same length to bridge a cell" So use of one cable per pole. Or 3 cables of the same length to replace a J1 connector. Total need 6 cables for SBR2 (same length) Where does the power limitation requirement come from? No contraindication to use cables under 2500A. | Não
NCR-ICN-ESC-12-0176-2020 | P0125563 | BB22510 | REWORK | REWORK. | REWORK | The copper bar J1 received are not compliant with the required design, see annex. Could not be fixed on board. Solution given by ICN 2,1 is not avalaible Tempory mounting solution given by TA : use 3 cables CEI 1x150 mm² per pole, meaning 9 cables per battery, 18 per boat HOW EVER THIS SOLUTION NOT ALLOW TO USE FULL POWER MAXIMUM ALLOW IS 1250A PER BATTERY | SCRAP |  | Não
NCR-ICN-ESC-12-0178-2020 | P0125441 | FP00100 | ACCEPT AS IT IS | Accept as it is. |  |  |  |  | Sim | 01SA000D00001
NCR-ICN-ESC-12-0180-2020 | P4129703 |  | REWORK | NCR LEVEL 1 Rework according to SBH.3B22.SMD.004549. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0180-2020 | P4129948 |  | REWORK | NCR LEVEL 1 Rework according to SBH.3B22.SMD.004549. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0194-2020 | P0145859 | AG00013 | AGREE WITH LEVEL 2.1 | Send to NG | REWORK | Manufacture 2 new pins with length below head 50mm from material bar delivered by NG. The conformity file of the panel will be updated The design will be updated by NG | REWORK | Agree with the modification in paragraph 2.2, rework. | Sim | 01PE200D00041
NCR-ICN-ESC-12-0199-2020 | P0124313 | GN22701 | REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0190-2020 | P0119322 | RM00116 | SCRAP |  | REINSPECT THE ELEMENT | If the pressure reductor RM00116 has an internal leakage is certainly due to some dust. So unmount and inspect it at your workshop, and redo a calibration, if is alway bad, replace it by a new, and do a NCR Mat to order a new one. |  |  | Não
NCR-ICN-ESC-12-0254-2020 | P0120353 | EQ00043 | ACCEPT AS IT IS | The o’ring CMD 44JO110D00540 (O-RING 56,52X5,33-20A8-GN), belonging of the CMD 44JO312D00010 (RUCH SEAL PLAIN OD57) was used in the mounting of the Hatch EQ00043. The Hatch was already tested in the hyperbaric chamber and the tests were approved. Raise a NCR MAT to supply new item. | ACCEPT AS IT IS | A item for mounting EQ00043 is a O-RING 56,52X5,33-20A8-GN CMD:44JO110D00540 -A item of RUCH gasket OD57 is the same O-ring 56,52X5,33-20A8-GN NNO:5331143135502 -If the the validity date of the gasket is not expired it's possible to use the O-ring of RUCH gasket insted of CMD:44JO110D00540. (Patrcik Daliguet) | REWORK | The traceability reference of the panel is missing in accordance to use O Ring NN0 5331143135502 This information have to be indicated in the traceability folder of the panel D BERNEDE | Sim | SN0000051303
NCR-ICN-ESC-12-0249-2020 | P4117673 |  | SCRAP AND RE-MANUFACTURE | As aligned with Vladimir Gianotti and Robson Andrade the tube will be remanufactured. | REWORK |  |  |  | Sim
NCR-ICN-ESC-12-0249-2020 | P4148296 |  | SCRAP AND RE-MANUFACTURE | As aligned with Vladimir Gianotti and Robson Andrade the tube will be remanufactured. | REWORK |  |  |  | Sim
NCR-ICN-ESC-12-0249-2020 | P4148295 |  | SCRAP AND RE-MANUFACTURE | As aligned with Vladimir Gianotti and Robson Andrade the tube will be remanufactured. | REWORK |  |  |  | Sim
NCR-ICN-ESC-12-0196-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0203-2020 | P0109676 | KE28000 | REWORK | Follow level 2.2 guidelines. | REWORK | Naval Group suggests to use the same connector from SBR4 if available. If not, from SBR3, then edit a NCR MAT |  |  | Não
NCR-ICN-ESC-12-0210-2020 | N/A |  | ACCEPT AS IT IS | Replace the Upper Platform of DSRV for SBR 3. |  |  |  |  | Não
NCR-ICN-ESC-12-0213-2020 | P0106336 | DN00212 | ACCEPT AS IT IS | Accept as it is. | ACCEPT AS IT IS | The length 85mm is not sufficient to respect 2 minimum threads visible. The upper size is 90mm, this size will be used on board. It's necessary to modify the nomenclature. | REWORK | Change the 2 screws interfacing with the seating to change to 90mm length, in accordance with the paragraph 2.2. (type 1 bolts). | Sim | 021
NCR-ICN-ESC-12-0217-2020 | P0152759 | AC43064 | REWORK | Send to level 2. |  |  |  |  | Sim | 01PM100D00010
NCR-ICN-ESC-12-0220-2020 | SC1-AD-AJ-LOW |  | ACCEPT AS IT IS | Accept as it is. The lower surface was not machined to avoid impact in the welded structure (see annex 1). This overlength will not affect the mounting of the gudgeon. | REWORK | Accept as it is only with this over dimension not impact on the installation of the CVR protection cover. ICN must make a analysis before to accept as it is and please send the analysis to Naval Group. If not re-machine to be in tolerance. (Charles Boucher) |  |  | Não
NCR-ICN-ESC-12-0226-2020 | P0125147 | RM00813 | ACCEPT AS IT IS | Accept as it is. This assembly was authorized by TA Naval Group. | REWORK | That is important and necessary to respect it is the height of radar beam in order to have the Radar Pod at the good height. For that following the thickness of the shim s hydraulic jack we adjust the heights of the beam with the adjustable Radar mast extension. So your CTE must take into account this value, like that we are be able to know if Thickness Shim + adjustable Radar mast extension + Radar mast Beam are correct to put in place the Radar POD. |  |  | Não
NCR-ICN-ESC-12-0230-2020 | P0151877 | AC43031 | REPAIR | Follow the temporary solution that was proposed for SBR 1 in NCR-ICN-ESC-11-0554-2019. See attachments. Wait for NAVAL GROUP orientation. | REPAIR | Naval Group is in accordance with ICN. Deliberation N1 can be applied. Use FTG-7268 - AC33031 already attached within NCR. Regarding following boats SBR3 and SBR4, ICN has to properly add the Nut retainer defined in folios 7 and 26 of MAT425-0513, during mounting of Mobile part, in order to avoid this problem to occur again. | REWORK | Solution applied for SBR1 is a temporary solution till RANAE. For present NCR-ICN-ESC-12-0230-2020 related to SBR2, rework must be performed: mounting has to be conform to the initial and standard prescription before floating. | Sim | 01PM300D00041
NCR-ICN-ESC-12-0228-2020 | P0145859 | AG00013 | SCRAP AND RE-MANUFACTURE | Manufacture new pin axis with Ø12x50 mm in CuAL10Ni5Fe4 according porposed by TA Patrick Daliguet. | REWORK | -In accordance with level 2.1: Manufacture new pin axis with Ø12 lenght below head:50 mm (Total lenght:53mm) in CuAL10Ni5Fe4 -The disign will be updated by NG ( Patrick Daliguet) | REWORK | Agree with the modification in paragraph 2.2, rework. | Sim | 01PE2000D00041
NCR-ICN-ESC-12-0228-2020 | P0145848 | AG00016 | SCRAP AND RE-MANUFACTURE | Manufacture new pin axis with Ø12x50 mm in CuAL10Ni5Fe4 according porposed by TA Patrick Daliguet. | REWORK | -In accordance with level 2.1: Manufacture new pin axis with Ø12 lenght below head:50 mm (Total lenght:53mm) in CuAL10Ni5Fe4 -The disign will be updated by NG ( Patrick Daliguet) | REWORK | Agree with the modification in paragraph 2.2, rework. | Sim | 01PE200D00028
NCR-ICN-ESC-12-0231-2020 | P0136469 | BQ00003 | REPAIR | Repair. 1) Clean/degrease the surface using WD 40 or equivalent; 2) Smooth grinding with Carborundum Stone 400/1000 and sandpaper 320/500 in order to reduce/remove the scratches and achieve a good shape. 3) Carry out flatness inspection on the tightness face. 4) Until to assembly step, keep the surface cleaned and protected to avoid new damages. | REPAIR | -In accordance with level 2.1 ( Patrick Daliguet) | REPAIR | Agree with paragraph 2.1: And redo tightness tests before assembly. If ICN does not have the capacity to conduct them, then tests B01 and B02 to be done on board in the presence of Naval Group. | Sim | 18SC000D00157
NCR-ICN-ESC-12-0231-2020 | P0137110 | BQ00004 | REPAIR | Repair. 1) Clean/degrease the surface using WD 40 or equivalent; 2) Smooth grinding with Carborundum Stone 400/1000 and sandpaper 320/500 in order to reduce/remove the scratches and achieve a good shape. 3) Carry out flatness inspection on the tightness face. 4) Until to assembly step, keep the surface cleaned and protected to avoid new damages. | REPAIR | -In accordance with level 2.1 ( Patrick Daliguet) | REPAIR | Agree with paragraph 2.1: And redo tightness tests before assembly. If ICN does not have the capacity to conduct them, then tests B01 and B02 to be done on board in the presence of Naval Group. | Sim | 18SC000D00156
NCR-ICN-ESC-12-0229-2020 | P4156706 | [7 empty] | Não
NCR-ICN-ESC-12-0299-2020 | P0101822 | OO64027B | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Replace the damage cable by a new one |  |  | Não
NCR-ICN-ESC-12-0234-2020 | P0124156 | GN02560 | MANUFACTURE | Proceed as per drawings attached. The porposed solution is the same according NCR-ESC-11-0945-2020. | REWORK | The mechanical modification of GN02560 will be done regarding the OM 118496, as soon as the modification kit will be received. |  |  | Não
NCR-ICN-ESC-12-0240-2020 | N/A |  |  |  | REWORK | Due to the gap betweenthe uper and lower part of DSRV plateform, it ´s necessarry to build up the lower part and ajust by grinding to avoid any gap. |  |  | Não
NCR-ICN-ESC-12-0253-2020 | P0138399 | DM00001H | SCRAP AND RE-MANUFACTURE | Send to NG analysis. | REWORK | -Elastic mount (MN03-260) of DM00001S and DM00002S were tightened by normal value following SMB-200949: 923Nm -bumpers were destroyed. -Check the number of lot and isolate all in store, change all elastic mount by new ones with a different lot. -Ask to the manufacturer to supply new elastic mount conform and follow this by NCR MAT (Patrick Daliguet) 19/03/2021: After analyse the back office the damage of the rubber was due to didn't use of special tool to immobilize buffer ring during the tightening. see the document in annex (extract of SMB-200949). | REWORK | The damage of the rubber is not due to a manufacturing problem on the elastic mount, but is due to the fact that the mount "head" was not handle in place with the associate tool during the mounting of the mount. Damage of the rubber is due to the twisting of the mount as it can be seen by the "lines" at the surface of the damaged material. Not acceptable as it is. Mounts are to be replaced by new ones that are going to be orderd (costs will be charged to ICN), and are to be mounted according to SMB-200949. | Não
NCR-ICN-ESC-12-0253-2020 | P0105198 | DM00002 | SCRAP AND RE-MANUFACTURE | Send to NG analysis. | REWORK | -Elastic mount (MN03-260) of DM00001S and DM00002S were tightened by normal value following SMB-200949: 923Nm -bumpers were destroyed. -Check the number of lot and isolate all in store, change all elastic mount by new ones with a different lot. -Ask to the manufacturer to supply new elastic mount conform and follow this by NCR MAT (Patrick Daliguet) 19/03/2021: After analyse the back office the damage of the rubber was due to didn't use of special tool to immobilize buffer ring during the tightening. see the document in annex (extract of SMB-200949). | REWORK | The damage of the rubber is not due to a manufacturing problem on the elastic mount, but is due to the fact that the mount "head" was not handle in place with the associate tool during the mounting of the mount. Damage of the rubber is due to the twisting of the mount as it can be seen by the "lines" at the surface of the damaged material. Not acceptable as it is. Mounts are to be replaced by new ones that are going to be orderd (costs will be charged to ICN), and are to be mounted according to SMB-200949. | Sim | 12EE000D00041
NCR-ICN-ESC-12-0250-2020 | P0146676 | AG00066 | REWORK | We request to Naval Group the serial number to be engraved on the equipment and the delivery of the Certificate and Declaration of Conformity to validate the B07. | REWORK | -In accordance with level 2.1 -Traceability will be provide by NG and engraved by ICN. ( Patrcick Daliguet) | REWORK | Traceability of the quick release must be ensured in accordance with SMB-2000052 as follows: CMD / Unique manufacturer serial number / Body supplier contract number For the naked body: As it is not possible to differentiate the parts which were machined in sets of 3, ICN must engrave the following information on the body: 01PM000C0922 (CMD Bare body) / number to follow 001 to 003/6418493 (supplier contract no. ) For the mobile part: Once assembled, ICN will have to engrave at the place deemed most suitable: 14VM000D00011 (CMD PM complete) / same serial number as the body (001, 002, 003) / ICN (to identify that ICN made the assembly ) After test: ICN must engrave at least PEH and the value of the test. Note: ICN must verify that the instructions relating to the tests of the mobile part (see MAT424-0800_K §9,1,5) have been respected. | Sim | THERE IS NO SERIAL NUMBER
NCR-ICN-ESC-12-0255-2020 | P0151979 | AC44031 | REWORK | [5 empty] | Sim | 01PM000D00022-6409900-004 004
NCR-ICN-ESC-12-0265-2020 | P0104859 | BS02501 | REWORK |  | REWORK | Need a reforming of batteries fwd and aft as sbr1 | REWORK | Replace defective batteries with new ones. Electrical measurements to be carried out on the charger according to the written protocol. Electrical monitoring of the batteries to be carried out every 1 to 3 months. Expertise of defective batteries to be carried out according to a written procedure. Return to France of 3 SPH 115 batteries and 3 SPH190 batteries for expertise according to RTE-2021-08-117. (Packaging procedure before return transport attached to the RTE) | Não
NCR-ICN-ESC-12-0265-2020 | P0104861 | BS02500 | REWORK |  | REWORK | Need a reforming of batteries fwd and aft as sbr1 | REWORK | Replace defective batteries with new ones. Electrical measurements to be carried out on the charger according to the written protocol. Electrical monitoring of the batteries to be carried out every 1 to 3 months. Expertise of defective batteries to be carried out according to a written procedure. Return to France of 3 SPH 115 batteries and 3 SPH190 batteries for expertise according to RTE-2021-08-117. (Packaging procedure before return transport attached to the RTE) | Não
NCR-ICN-ESC-12-0266-2020 | P0125410 | EX00001 | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Sim | 20AR000D00042
NCR-ICN-ESC-12-0266-2020 | P4173409 |  | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Não
NCR-ICN-ESC-12-0266-2020 | P0151979 | AC44031 | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Sim | 01PM000D00022
NCR-ICN-ESC-12-0266-2020 | P0127270 | EX00002 | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Sim | 20AR000D00088
NCR-ICN-ESC-12-0266-2020 | P0150598 | EX00224 | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Não
NCR-ICN-ESC-12-0266-2020 | P0154557 | AC42042 | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Sim | 01PM000D00022
NCR-ICN-ESC-12-0266-2020 | P4130548 |  | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Não
NCR-ICN-ESC-12-0266-2020 | P4056675 |  | ACCEPT AS IT IS | Accept as it is for ceremony. |  |  |  |  | Não
NCR-ICN-ESC-12-0267-2020 | P0104861 | BS02500 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the switch SC1 of the BS02500 on the SBR2. On the other hand, Naval Group confirms that this switch can be used as is while waiting for its replacement. |  |  | Não
NCR-ICN-ESC-12-0267-2020 | P0104240 | BC02500 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the protections cover Red and Black of the buttons of the DM1 / DM2 / DT1 of the BC02500 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. |  |  | Sim
NCR-ICN-ESC-12-0267-2020 | P0105108 | BC02550 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the protections cover Red and Black of the buttons of the De1 of the BC02550 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. ICN needs to open an NCR MAT to replace the White Led 28Vdc +D1A-H1 of the BC02550 on the SBR2. Naval Group asks ICN to take on SBR4 while awaiting replenishment ICN needs to open an NCR MAT to replace the voltmeter +P2A-P3 of the BC02550 on the SBR2. On the other hand, Naval Group confirms that it can be used as in this state while waiting for its replacement. |  |  | Sim
NCR-ICN-ESC-12-0267-2020 | P0105126 | BC02660 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the protections cover Red and Black of the buttons of the DB4 of the BC02660 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. ICN needs to open an NCR MAT to replace the White Led 115Vdc +D1A-H7 of the BC02550 on the SBR2. Naval Group asks ICN to take on SBR4 while awaiting replenishment |  |  | Sim
NCR-ICN-ESC-12-0267-2020 | P0103629 | BF02501 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the acrylic protection and sealing rubber associated of the BF02501 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. |  |  | Sim | 001186-IV91-01-003
NCR-ICN-ESC-12-0267-2020 | P0103630 | BF02502 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the acrylic protection and sealing rubber associated of the BF02502 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. |  |  | Sim | 001186-IV91-01-004
NCR-ICN-ESC-12-0267-2020 | P0112821 | BF02504 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the protection cover Black of the button of the Da2 of the BF02504 on the SBR2. On the other hand, Naval Group confirms that it can be used as in this state while waiting for its replacement. ICN needs to open an NCR MAT to replace the Temperature Led of the BF02504 on the SBR2. Naval Group asks ICN to take on SBR4 while awaiting replenishment |  |  | Sim
NCR-ICN-ESC-12-0267-2020 | P0103632 | BF02505 | REWORK |  | REWORK | ICN needs to open an NCR MAT to replace the protections cover Red and Black of the buttons of the De1 / Da3 / Da5 of the BF02505 on the SBR2. On the other hand, Naval Group confirms that they can be used as in this state while waiting for their replacement. ICN needs to open an NCR MAT to replace the White Led 115Vdc +D1A-H7 of the BF02505 on the SBR2. Naval Group asks ICN to take on SBR4 while awaiting replenishment |  |  | Sim
NCR-ICN-ESC-12-0282-2020 | P0106853 | GF02504 | REWORK | USE THE SBR4 GF02504 LUMINAIRE, IF APPROVED BY THE NAVAL GROUP. | REMOVE AND REWORK | Take on sbr 4 the light GF02504 (cmx 48ES300D00098) Open the the defective light at workshop for investigation and put the report in the NCR Open NCR MAT for the defective part after investigation. |  |  | Não
NCR-ICN-ESC-12-0285-2020 | N/A |  |  |  | REWORK | For EV02501, in accordance with decision N1, replace the "local / remote" inverter, make an NCR-MAT to supply a new 5930930151289 "INVERTER DIAM6 UNIPOLAR YELLOW LATCH LEVER" For EV02500 and EV03500, open the cabinet door and put the inverter in place, see photo in appendix. As a reminder: some small fragile equipment is deliberately kept (pre-equipped) inside the cabinet to avoid being broken during transport. |  |  | Não
NCR-ICN-ESC-12-0288-2020 | N/A |  |  |  | REWORK | In agreement with EXIDE, Naval Group confirms that the density corrections (to have 1,300g/l at 30°C) will be made between 6 and 12 months after the activation of the SBR2 batteries knowing that they will not enter in "Operational mode" before 1 year. Naval Group confirms that the BDMAT-BDM-00080876-B2 formulas have been confirmed in the V1.9 release to be transmitted in the next Documents Batch |  |  | Não
NCR-ICN-ESC-12-0292-2020 | P0137798 | FQ00101F | REWORK | Rework. Open a NCR Regress and redo the inspections B01 and B02. | REWORK - UPDATE JOB ORDER | Rework. Make a NCR regress and performed the necessary tests | REWORK | The topic is not only the handweel but the whole reducer (gearbox). Inspections B01 and B02 have to be perfomed again but not only : according to MAT171-2727E, the closed position of the valve is setting by the "stop" of the reducer, so, after assembly on the valve it's necessary to perform §5.2, §5.3, §5.4 of MAT171-2727_EXP (BDM-00035068). Nota : §5.4 include the test of leaktight integrity of the valve. | Não
NCR-ICN-ESC-12-0305-2021 | P0156227 | EG24340 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143697 | HG02561 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117191 | KT14082P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117198 | KT15082P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117171 | KT15084P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117160 | KT15086P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108981 | GS22502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157004 | HL12720 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157005 | HL12721 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157001 | HL12717 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118182 | UA04100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118181 | UA04110 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118180 | UA04120 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118183 | UA04200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118184 | UA04210 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118185 | UA04220 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118179 | UA07100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118079 | RM12513P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118080 | RM12514P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118081 | RM12515P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136812 | FC00031 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101451 | OO22600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104732 | DA12511N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104731 | DA12512N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104730 | DA12513N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140096 | EJ12509N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157002 | HL12718 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157003 | HL12719 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157006 | HL12722 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157007 | HL12723 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118252 | UW03008 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118253 | UW03009 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102207 | BB22502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102433 | BE00005 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103042 | BE0500BF | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103054 | BE0710CB | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103123 | BE0720AA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103015 | BE0720BA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103124 | BE2500CA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120786 | EQ03100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120792 | EQ04500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0133619 | EQ05200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123691 | GN02515 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124257 | GN02522 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123723 | GN02546 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123724 | GN02547 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123694 | GN02551 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124161 | GN02554 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0141011 | GN02563 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124148 | GN22546 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140948 | GN22748 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140947 | GN22756 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124217 | GV02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109051 | HE02510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107416 | HJ02511 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107420 | HJ02515 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0146725 | HJ02561 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146726 | HJ02563 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107745 | HP02500 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107746 | HP02504 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107777 | HP02528 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126526 | HQ02703 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125990 | HQ02711 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143258 | HQ02716 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0113284 | KL00300 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109770 | KO02610 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109772 | KO02630 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109860 | KO022610 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0141634 | OO22811 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118138 | RE02504 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108774 | RH02546 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146607 | RH02548 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108784 | RH02635 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118069 | RM02507 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108835 | UE02000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108822 | UE02220 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108836 | UE03000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0194932 | UE26010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0194931 | UE26020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108977 | UN03000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195144 | UP02500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0159324 | UP02600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104773 | BH12506N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104774 | BH12507N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107842 | HP22501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126512 | HQ22715 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108771 | RH02542 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109054 | HE22510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108782 | RH02530 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140824 | RH02532 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140713 | RH22518 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140764 | RH22521 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126784 | DA02560 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132279 | EF02600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120026 | EF12519B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120027 | EF12520B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120039 | EF12531B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121609 | ER00002F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121610 | ER00002O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122394 | EV12503N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107025 | HG02502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107421 | HJ02516 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107441 | HK02506 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107444 | HK02508 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146697 | HP02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143003 | HP02516 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107760 | HP02535 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125994 | HQ02706 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101619 | OO24002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101623 | OO24008 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101622 | OO24009 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101617 | OO24033 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101628 | OO24218 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101629 | OO24304 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108727 | RF20001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118251 | UW03007 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120029 | EF12521B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118152 | UA04000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0194929 | UA04400 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118000 | UA05000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118160 | UA06000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120025 | EF12518B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120037 | EF12529B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143563 | HQ02605 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119505 | RA00011 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0153514 | RA00013 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108671 | RF00023 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108716 | RF00024 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108718 | RF00026 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108719 | RF00027 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108721 | RF00033 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108787 | RH04310 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146615 | GN02737 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143700 | HG02562 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143701 | HG02563 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143702 | HG02564 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143698 | HG02565 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0152276 | HJ02507 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0152277 | HJ02509 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0146701 | HJ02527 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0150701 | HJ02567 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107775 | HP02526 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143564 | HQ02600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143472 | HQ02601 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0153192 | HQ02602 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143580 | HQ02603 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0155604 | HQ02606 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124911 | HQ02700 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0153217 | HQ02704 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125993 | HQ02705 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118137 | RE02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118139 | RE02506 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108769 | RH02531 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0146708 | RH02549 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146709 | RH02550 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146710 | RH02551 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146707 | RH02556 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102471 | BE00008 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102472 | BE00009 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0113049 | DP02500 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0112797 | DP03300 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120788 | EQ03200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106867 | GF02513 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146611 | GN02738 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0147545 | GN02741 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108979 | GS02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107027 | HG02504 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107004 | HG02509 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107061 | HG02515 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107067 | HG02554 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107413 | HJ02510 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107419 | HJ02514 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107776 | HP02527 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126035 | HQ02717 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109799 | KD05050 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109746 | KO02510 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109748 | KO02520 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109747 | KO02530 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109745 | KO02540 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109742 | KO02550 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109740 | KO02560 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0109771 | KO02620 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109773 | KO02640 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109774 | KO02650 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0113401 | KO02710 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0113400 | KO02720 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117285 | RC00001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125889 | RC00005 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117363 | RC20010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118142 | RD02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108773 | RH02543 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118888 | RM00058 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118025 | RM02505 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0118026 | RM02506 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0118068 | RM02508 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0157357 | UA04001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157358 | UA05001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123561 | UA06600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123548 | UA07000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118254 | UW03010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143536 | UW04000 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0119529 | UW05000 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0194935 | UE07000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101927 | BB12501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101945 | BB12519 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101962 | BB12537 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101979 | BB12555 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101996 | BB12573 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102013 | BB12591 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102030 | BB12609 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102047 | BB12627 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102064 | BB12645 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102081 | BB12663 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0153336 | KD26577 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0153337 | KD26578 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195187 | KE25010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0113118 | KE25020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195190 | KE25201 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195191 | KE25202 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109483 | KE25203 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195188 | KE25204 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195196 | KE25205 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195192 | KE25206 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195195 | KE25208 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195194 | KE25309 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195193 | KE25310 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195189 | KE25800 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131107 | FC12570T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124564 | FR12511 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104738 | DA12515N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108314 | DS14300 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108313 | DS14310 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120031 | EF12523B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107006 | HG02510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109796 | KD05010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109797 | KD05020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109798 | KD05030 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0110408 | KD09010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0110410 | KD22590 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109790 | KD25000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114261 | KT01041 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115426 | KT01043 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114636 | KT01045 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114035 | KT01141 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115379 | KT01143 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114589 | KT01145 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114263 | KT01241 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115427 | KT01243 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114638 | KT01245 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114408 | KT01341 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115484 | KT01343 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114707 | KT01345 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114264 | KT01441 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115428 | KT01443 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114639 | KT01445 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114034 | KT01541 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115378 | KT01543 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114588 | KT01545 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114029 | KT01641 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115376 | KT01643 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114586 | KT01645 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119594 | KT06171 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119668 | KT06173 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119731 | KT06175 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119597 | KT06271 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119670 | KT06273 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119733 | KT06275 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119615 | KT06371 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119700 | KT06373 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119789 | KT06375 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119713 | KT06377 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119715 | KT06477 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123284 | KT08371 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119707 | KT08373 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119743 | KT08375 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117264 | KT09480 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117500 | KT23171 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117484 | KT23173 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117451 | KT23175 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117534 | KT23271 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117516 | KT23273 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117467 | KT23275 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117584 | KT23371 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117572 | KT23373 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117561 | KT23375 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117252 | KT23480 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117249 | KT23580 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117439 | KT23677 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117607 | KT23777 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117237 | KT23788 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112737 | DP14311 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112738 | DP14312 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112739 | DP14313 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106709 | DB23002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120033 | EF12525T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120035 | EF12527B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157012 | HL12728 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157013 | HL12729 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157014 | HL12730 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157016 | HL12731 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157017 | HL12732 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157018 | HL12733 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157041 | HL12735 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157040 | HL12840 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107778 | HP02529 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0195203 | KE25400 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101612 | OO24215 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104729 | DA12514N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104737 | DA12516N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104743 | DA12520N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108311 | DS14100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108315 | DS14110 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120034 | EF12526T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120036 | EF12528B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122373 | FH22513 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107028 | HG02505 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107010 | HG02512 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107422 | HJ02517 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107442 | HK02507 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157036 | HL12734 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157034 | HL12802 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157037 | HL12803 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157039 | HL12804 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157035 | HL12820 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157038 | HL12830 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107779 | HP02530 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109786 | KD03010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109789 | KD03020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109800 | KD06020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109817 | KD06030 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109819 | KD06040 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109823 | KD06050 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109824 | KD06060 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109802 | KD06070 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109793 | KD26571 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109791 | KD26572 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115850 | KT01042 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114839 | KT01044 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115642 | KT01046 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115809 | KT01142 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114791 | KT01144 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115594 | KT01146 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115851 | KT01242 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114840 | KT01244 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115643 | KT01246 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115899 | KT01342 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114898 | KT01344 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115689 | KT01346 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115852 | KT01442 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114841 | KT01444 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115644 | KT01446 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115808 | KT01542 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114790 | KT01544 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115592 | KT01546 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115807 | KT01642 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0114788 | KT01644 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0115591 | KT01646 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129795 | KT06182 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129796 | KT06184 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129797 | KT06186 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123268 | KT06282 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129799 | KT06284 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129800 | KT06286 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123274 | KT06382 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123261 | KT06384 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123250 | KT06386 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123245 | KT06388 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123246 | KT06488 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123272 | KT08382 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123259 | KT08384 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123248 | KT08386 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117099 | KT23182 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117083 | KT23184 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117039 | KT23186 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117136 | KT23282 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117115 | KT23284 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117063 | KT23286 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117192 | KT23382 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117175 | KT23384 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117164 | KT23386 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117026 | KT23688 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117275 | KX25000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103275 | BE0800BB | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103276 | BE0900CB | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103622 | BE0900DB | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103624 | BE0900DD | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132914 | DP00301 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0106909 | DP00302 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107098 | DV22502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120032 | EF12524T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122372 | FH22512 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124165 | GN02534 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146612 | GN02734 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107007 | HG02511 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107014 | HG02521 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143626 | HJ02521 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146727 | HJ02565 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157010 | HL12726 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157011 | HL12727 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125991 | HQ02702 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109795 | KD04010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0110035 | KD07010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0110031 | KD07020 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0109676 | KE28000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118166 | UA06100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118169 | UA06200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117583 | KT15071P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117589 | KT14071P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117568 | KT15073P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117557 | KT15075P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146616 | GN02735 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107411 | HJ02508 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107780 | HP02521 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107766 | HP02525 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126037 | HQ02712 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126026 | HQ02724 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117853 | UA05101 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117855 | UA05102 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117858 | UA05103 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117860 | UA05104 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117862 | UA05105 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117864 | UA05106 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117866 | UA05107 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117868 | UA05108 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117874 | UA05109 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117876 | UA05110 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117878 | UA05111 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117880 | UA05112 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117882 | UA05113 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117884 | UA05114 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117886 | UA05115 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117888 | UA05116 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117891 | UA05117 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117893 | UA05118 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117895 | UA05119 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117897 | UA05120 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117899 | UA05121 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117901 | UA05122 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117903 | UA05123 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117905 | UA05124 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117996 | UA05125 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117994 | UA05126 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117992 | UA05127 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117990 | UA05128 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117988 | UA05129 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117986 | UA05130 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117984 | UA05131 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117982 | UA05132 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117978 | UA05133 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117976 | UA05134 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117974 | UA05135 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117972 | UA05136 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117970 | UA05137 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117968 | UA05138 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117966 | UA05139 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117964 | UA05140 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117925 | UA05141 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117923 | UA05142 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117921 | UA05143 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117919 | UA05144 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117917 | UA05145 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117915 | UA05146 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117913 | UA05147 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117911 | UA05148 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105437 | DM00004F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105438 | DM00004O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105439 | DM00005F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105440 | DM00005O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105441 | DM00013F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105442 | DM00013O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105443 | DM00014F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105444 | DM00014O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119827 | EN00010F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119828 | EN00010O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119829 | EN00013F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119847 | EN00013O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121079 | EM00007F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121081 | EM00007O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121082 | EM00013F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121083 | EM00013O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104715 | DA12531P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108344 | DY12506P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156489 | EJ11050R | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156410 | UL00027 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104717 | DA12533P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117218 | EF12602P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119610 | KT05471 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119690 | KT05473 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119778 | KT05475 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123275 | KT05482 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123262 | KT05484 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123251 | KT05486 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119642 | KT06471 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119712 | KT06473 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119741 | KT06475 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123273 | KT06482 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123260 | KT06484 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123249 | KT06486 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119608 | KT06771 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123276 | KT06782 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119682 | KT06873 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119740 | KT06875 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123258 | KT06884 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123244 | KT06886 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119644 | KT06971 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123271 | KT06982 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117549 | KT08471 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119673 | KT08473 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119738 | KT08475 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123266 | KT08482 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123257 | KT08484 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123243 | KT08486 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119643 | KT08971 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123270 | KT08982 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102557 | BE0200CF | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106701 | DB23001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140427 | DP00101 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0106116 | DP00102 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106235 | DP00201 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0106253 | DP00202 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106257 | DP00230 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112773 | DP24100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112777 | DP24200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112781 | DP24400 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107096 | DV22501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119995 | EF12500B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120007 | EF12507B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107022 | HG02500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107018 | HG02526 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107402 | HJ02501 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0146724 | HJ02559 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107438 | HK02503 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107452 | HK02510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156976 | HL12700 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156971 | HL12801 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156975 | HL12810 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0142980 | HP02507 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107754 | HP02512 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143005 | HP02533 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118247 | UW03003 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118248 | UW03004 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118249 | UW03005 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118250 | UW03006 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118274 | UW23002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121108 | ER00007 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102419 | BE00001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102420 | BE00002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102586 | BE0200AG | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103442 | BE2100BM | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103438 | BE2200AA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103479 | BE2200BA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136960 | BM00001F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136959 | BM00001O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136962 | BM00002F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136961 | BM00002O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136956 | BM00007F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136955 | BM00007O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136958 | BM00008F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136957 | BM00008O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136952 | BM00010F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136951 | BM00010O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136948 | BM00011F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136947 | BM00011O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136954 | BM00012F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136953 | BM00012O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136950 | BM00016F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136949 | BM00016O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136761 | BM00031F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136760 | BM00031O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136759 | BM00032F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136758 | BM00032O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136757 | BM00037F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136756 | BM00037O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136755 | BM00038F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136754 | BM00038O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136753 | BM00040F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136752 | BM00040O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136740 | BM00041F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136739 | BM00041O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136751 | BM00042F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136750 | BM00042O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136737 | BM00046F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0136733 | BM00046O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0135507 | BQ22505 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0134347 | BQ22509 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104742 | DA12525N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104741 | DA12526N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104740 | DA12527N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104739 | DA12528N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104734 | DA12529N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104719 | DA12530N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120004 | EF12505 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120006 | EF12506 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120010 | EF12509B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120014 | EF12510B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120015 | EF12511 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120017 | EF12512 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107068 | HG02522 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107195 | HG02550 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107476 | HJ02503 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107404 | HJ02504 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0143627 | HJ02525 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143628 | HJ02526 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107437 | HK02502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156981 | HL12703 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156982 | HL12704 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156983 | HL12705 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156985 | HL12706 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156984 | HL12707 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156988 | HL12708 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156989 | HL12709 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156990 | HL12710 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0142999 | HP02506 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107758 | HP02514 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107759 | HP02515 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125996 | HQ02708 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101452 | OO22609 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101453 | OO22611 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101456 | OO22902 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101455 | OO22903 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107447 | HK02509 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151088 | DY00541 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151095 | DY00542 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151099 | DY00543 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151100 | DY00841 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151101 | DY00842 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151102 | DY00843 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0151103 | DY00844 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118244 | UW03001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104723 | DA12500N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104722 | DA12501N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104721 | DA12502N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104728 | DA12505N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121777 | ES12504N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107060 | HG02546 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146723 | HJ02557 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156977 | HL12701 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156980 | HL12702 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107753 | HP02511 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101586 | OO24312 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118245 | UW03002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102228 | BB12698 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102245 | BB12716 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102262 | BB12734 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102279 | BB12752 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102296 | BB12770 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102313 | BB12788 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102330 | BB12806 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102347 | BB12824 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102364 | BB12842 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102381 | BB12860 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131798 | FC12550T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124563 | FR12510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119607 | EL02013 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104221 | BC22501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102581 | BE0200CD | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102576 | BE0200CE | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103706 | BF22701 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119997 | EF12501B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119998 | EF12502B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119999 | EF12503B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120002 | EF12504B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124048 | GN02540 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146619 | GN02740 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107024 | HG02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107015 | HG02524 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107016 | HG02525 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107403 | HJ02502 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0143000 | HP02513 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107755 | HP02534 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125989 | HQ02710 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105449 | ME25002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103776 | BS02510 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120008 | EF12508B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120018 | EF12513B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120019 | EF12514B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143267 | HJ02519 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107439 | HK02504 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107455 | HK02511 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138424 | ME12911Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138422 | ME12912Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138428 | ME13011P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138426 | ME13012P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101588 | OO24122 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103476 | BE2640CD | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104727 | DA12506N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104726 | DA12507N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104725 | DA12508N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120038 | EF12530B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125424 | FP12500M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0137801 | FQ02500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0137321 | FQ12510N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124141 | GN02539 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146618 | GN02739 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156995 | HL12713 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101603 | OO24306 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101600 | OO24323 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120022 | EF12516B | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122351 | FH02721F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122352 | FH02721O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122353 | FH02723F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122354 | FH02723O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122355 | FH02821F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122356 | FH02821O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122357 | FH02823F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122358 | FH02823O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107406 | HJ02505 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107440 | HK02505 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107456 | HK02512 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156991 | HL12711 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156992 | HL12712 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156997 | HL12714 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107762 | HP02517 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0128355 | FV00101 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0128346 | FV00102 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0128803 | FV00214 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129043 | FV02500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129044 | FV02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0159584 | [7 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125995 | HQ02707 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102991 | BE0640DA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120643 | EQ03300 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120647 | EQ03400 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127439 | FG02600 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107062 | HG02551 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107764 | HP02518 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101607 | OO24208 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101609 | OO24301 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101608 | OO24330 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132283 | UL00005 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131424 | UL01000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131416 | UL01001 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131417 | UL01002 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132142 | UP02800 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122349 | FH02517F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0122350 | FH02517O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103007 | BE0630DA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0155353 | BE2400AD | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103707 | BF22703 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119980 | EF02504 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0142984 | HP02538 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0145961 | HP02550 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0145963 | HP02551 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101616 | OO24034 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0148205 | DM22501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0142983 | HP02519 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107769 | HP02523 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107771 | HP02536 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107774 | HP02537 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102989 | BE0640DB | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0120023 | EF12517T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127474 | FG22551 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127476 | FG22554 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127481 | FG22555 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127482 | FG22556 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127479 | FG22558 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127486 | FG22559 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127485 | FG22560 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127445 | FG22561 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0127480 | FG22562 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140392 | FG22563 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0129325 | FV02503 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0125997 | HQ02709 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0103004 | BE0610DA | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126703 | EQ00282 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108722 | RF00036 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104780 | BH12508M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104781 | BH12509M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0102918 | BH22509 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106000 | DP00100 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106872 | DP00104 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106249 | DP00200 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106674 | DP00204 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106908 | DP00300 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0106921 | DP00304 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112774 | DP24103 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112778 | DP24203 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112780 | DP24303 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112784 | DP24700 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0140986 | GN02552 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0140987 | GN02553 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0124313 | GN22701 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107026 | HG02503 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107417 | HJ02512 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107418 | HJ02513 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0107429 | HK02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157008 | HL12724 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101610 | OO23819 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101625 | OO24203 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118634 | RM00011 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119132 | RM00012 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119112 | RM00013 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118030 | RM12511M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118031 | RM12512M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118033 | RM12519M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118034 | RM12520M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118035 | RM12521M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0148198 | DM22500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0148202 | DM22502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124142 | GN02536 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0146617 | GN02736 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107063 | HG02552 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0143873 | HG02553 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107408 | HJ02506 | [6 empty] | Sim
NCR-ICN-ESC-12-0305-2021 | P0142982 | HP02522 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107770 | HP02524 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0142981 | HP02532 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126029 | HQ02713 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107765 | HP02531 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0126031 | HQ02714 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112742 | DP13001M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112744 | DP13002M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112751 | DP13003M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112690 | DP14111 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112731 | DP14112 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112732 | DP14113 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112734 | DP14211 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112735 | DP14212 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0112736 | DP14213 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0148345 | DA22502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105446 | DM12506N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117735 | UA03101 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117762 | UA03102 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117785 | UA03103 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117790 | UA03104 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117737 | UA03105 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117764 | UA03106 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117828 | UA03107 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117788 | UA03108 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117739 | UA03109 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117766 | UA03110 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117830 | UA03111 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117805 | UA03112 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117741 | UA03113 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117768 | UA03114 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117832 | UA03115 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117826 | UA03116 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117743 | UA03117 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117822 | UA03118 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117834 | UA03119 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117783 | UA03120 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117745 | UA03121 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117824 | UA03122 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117836 | UA03123 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117809 | UA03124 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117747 | UA03125 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117771 | UA03126 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117819 | UA03127 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117800 | UA03128 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117749 | UA03129 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117773 | UA03130 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117817 | UA03131 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117802 | UA03132 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117754 | UA03133 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117775 | UA03134 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117815 | UA03135 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117798 | UA03136 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117756 | UA03137 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117777 | UA03138 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117813 | UA03139 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117796 | UA03140 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117758 | UA03141 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117779 | UA03142 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117811 | UA03143 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117792 | UA03144 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117760 | UA03145 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117781 | UA03146 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117807 | UA03147 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117794 | UA03148 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123263 | KT05182 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123252 | KT05184 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123238 | KT05186 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123264 | KT05282 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123253 | KT05284 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123239 | KT05286 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123265 | KT05382 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123254 | KT05384 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123240 | KT05386 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123247 | KT06288 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0123267 | KT06882 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117151 | KT18082Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117130 | KT18084Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117078 | KT18086Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117034 | KT18188P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117262 | KT19587P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104718 | DA12534P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117699 | KT19070P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119582 | KT05171 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119650 | KT05173 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119720 | KT05175 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119585 | KT05271 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119653 | KT05273 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119726 | KT05275 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119590 | KT05371 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119656 | KT05373 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119728 | KT05375 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119718 | KT06277 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0119818 | KT06871 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117548 | KT18071Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117531 | KT18073Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117481 | KT18075Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117447 | KT18177P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0156999 | HL12715 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157000 | HL12716 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132346 | ME10111M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132342 | ME10112M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132357 | ME10212M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132358 | ME10312M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105771 | ME11411M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105772 | ME11412M | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105965 | ME16110T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105967 | ME16210T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131488 | ME16310Q | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131487 | ME16710P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105749 | ME25003 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105748 | ME25004 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105765 | ME25005 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105763 | ME25007 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105764 | ME25008 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105950 | ME25009 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105951 | ME25010 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105766 | ME25011 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0157009 | HL12725 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101443 | OO22605 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0101446 | OO22610 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118950 | RM00087 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118065 | RM02500 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118066 | RM02501 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0118067 | RM02502 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0108988 | UN24000 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0145962 | HP02549 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0104716 | DA12532P | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117446 | KT16177N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0117033 | KT16188N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107086 | DV12501F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107095 | DV12502F | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107087 | DV12601O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0107088 | DV12602O | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0121286 | ER10001N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138230 | EV02102 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0124144 | GN02537 | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138472 | ME11611T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138481 | ME11612T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138473 | ME11711T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138482 | ME11712T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138474 | ME11811T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138483 | ME11812T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138475 | ME11911T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138484 | ME11912T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138476 | ME12011T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0138485 | ME12012T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132203 | ME12512N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132202 | ME12611N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0132204 | ME12612N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105969 | ME15510T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131482 | ME15610N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105954 | ME15710T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105956 | ME15810T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105958 | ME15910T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131480 | ME16010N | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105985 | ME16410T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0105980 | ME16510T | [6 empty] | Não
NCR-ICN-ESC-12-0305-2021 | P0131485 | ME16610N | [6 empty] | Não
NCR-ICN-ESC-12-0297-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0298-2020 | P0119458 | RM00008 | REPAIR | [5 empty] | Não
NCR-ICN-ESC-12-0308-2021 | P0136618 | BQ00017H | REWORK | Replace the shim by OD 20 NGD: 5365143084793. Update the nomenclature. | REWORK | A temporary shim in CuAl10Ni5Fe4 will be define in replacement of the definitive ones to allow the manufacture of pipes. NCR MAT will be raise to update nomenclature and provided the good shims |  |  | Não
NCR-ICN-ESC-12-0308-2021 | P0137721 | BQ00018H | REWORK | Replace the shim by OD 20 NGD: 5365143084793. Update the nomenclature. | REWORK | A temporary shim in CuAl10Ni5Fe4 will be define in replacement of the definitive ones to allow the manufacture of pipes. NCR MAT will be raise to update nomenclature and provided the good shims |  |  | Não
NCR-ICN-ESC-12-0430-2021 | P0104214 | BT62578I | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK - UPDATE JOB ORDER | The BT sockets are mounted on the GN02522C, cables BT62578I and BT64210I routing needs to be redefined. Waiting orientation BO, please transmit the new route and the new lengths | REWORK | No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-500189 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. 07/07/2021: ANSWER V2: No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-330521 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. | Não
NCR-ICN-ESC-12-0430-2021 | P0104210 | BT64210I | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK - UPDATE JOB ORDER | The BT sockets are mounted on the GN02522C, cables BT62578I and BT64210I routing needs to be redefined. Waiting orientation BO, please transmit the new route and the new lengths | REWORK | No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-500189 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-500189 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. 07/07/2021: ANSWER V2: No non-compliance was reported by ICN on SBR1, Naval Group therefore does not understand why an NCR is issued on SBR2. The shipyard must apply the same solution as on SBR1 and the update of SMB-330521 cannot be pre-requisite for the work to be carried out by ICN. This documentary update will be made in early 2022. | Não
NCR-ICN-ESC-12-0323-2021 | P0127270 | EX00002 | ACCEPT AS IT IS | Repair according to soluction 1. See coments. | ACCEPT AS IT IS | Accept as it is, No problem with the equipment | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Sim | 20AR000D00088
NCR-ICN-ESC-12-0323-2021 | P0154556 | AC32042 | ACCEPT AS IT IS | Repair according to soluction 1. See coments annex 1. | REWORK | Rework as per original | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Não
NCR-ICN-ESC-12-0323-2021 | P0154557 | AC42042 | ACCEPT AS IT IS | Repair according to soluction 1. See coments. | REWORK |  | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Sim | 01PM000D00022
NCR-ICN-ESC-12-0323-2021 | SP0009328 |  | ACCEPT AS IT IS | Repair according to soluction 1. See coments. | REWORK |  | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Não
NCR-ICN-ESC-12-0323-2021 | SP0009323 |  | ACCEPT AS IT IS | Repair according to soluction 1. See coments. | REWORK |  | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Não
NCR-ICN-ESC-12-0323-2021 | SP0009331 |  | ACCEPT AS IT IS | Repair according to soluction 1. See coments. | REWORK |  | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Não
NCR-ICN-ESC-12-0323-2021 | P4152046 |  | ACCEPT AS IT IS | Repair according to soluction 1. See coments annex 1. | ACCEPT AS IT IS | Accept as it is | REWORK | According to paragraph 2.2, rework : - cut the passage and machine the rest, redo the bevels using the maximum tolerance then re-weld a new passage AC32042 bushing in accordance with drawing SMB-104520. Replenishment of a Ø300 X300 blank in 80HLES material and shipment to the ICN site which will be responsible for manufacturing the AC32042 passage according toSMB-309243_E. | Não
NCR-ICN-ESC-12-0322-2021 | N/A | [5 empty] | REWORK | According to specialist : Rework -As soon as the boat's availability allows it (RANAE) the retrofit of the valve described in OM 127497 is to be applied. Kits were sent to the site in SAH for repair and modernization of SBR1 and SBR2 equipment. SAH: Ref UR: UR-SBR-2021.02-00105 Batch: SMB-MU18B-DB50-SAH | Não
NCR-ICN-ESC-12-0325-2021 | P0113923 | DY00430 | REPAIR | REPLACE O-RING |  |  |  |  | Não
NCR-ICN-ESC-12-0328-2021 | P4161842 |  | SCRAP AND RE-MANUFACTURE | Manufacture a new pipe and replace. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0365-2021 | P0152211 | AC30030 | ACCEPT AS IT IS | Deviation will be corrected during machining onboard. | REWORK | will be correct during machining on board |  |  | Não
NCR-ICN-ESC-12-0339-2021 | P4169911 |  | REMOVE AND REWORK |  | REWORK | Agree to dismount the pipes EV51215J4, EV51238J4, remount them and create a NCR REGRESS to report the remounting inspections M05, the pipes coupling (straub) mounting inspections and to manage the tests to redo on the EV circuit. |  |  | Não
NCR-ICN-ESC-12-0339-2021 | P4169912 |  | REMOVE AND REWORK |  | REWORK | Agree to dismount the pipes EV51215J4, EV51238J4, remount them and create a NCR REGRESS to report the remounting inspections M05, the pipes coupling (straub) mounting inspections and to manage the tests to redo on the EV circuit. |  |  | Não
NCR-ICN-ESC-12-0346-2021 | P0125624 | BB02506 | AGREE WITH LEVEL 2.1 | ICN Preservation Team believes that the problem is the ventilation calibration. | REINSPECT THE ELEMENT | Make an inspection in aft battery: * Control the air flow of grids => use the anemometer with parameter 2 and the cone. * Write the result of flow in the excel file to check the correct balance of the system => send the the result to the back office. * Redo the ventilation Chart *After received the comments from the back office => maybe necessary to modify the flow of the grids. * the Pitot Aft battery system need also be checked ( the value of the pitot in low speed is not nominal) => need to check the lines of the pitot system with soap and water at 0,5bar. | REWORK | The latest H2 rate results from the last AR battery charge are much lower (around 0.5%). Continuation of the subject to be piloted directly via the ITRs by updating the PPE FH2C and creation of a new high and low speed wind map (to be carried out by ICN with AT support and communication to the BO at each stage) . | Não
NCR-ICN-ESC-12-0352-2021 | P0118522 | EG01320 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Check if 18SC016D00036 available at the store. Replace and open an NCR-MAT to provision a new one. |  |  | Não
NCR-ICN-ESC-12-0351-2021 | P0118209 | UA66640D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REINSPECT THE ELEMENT | TA NGV would to know, why there were some water in this area. Where came this water? So it is necessary to check the cables: 1- visually check if there are some oxidation. Make a picture for each cable (where we see the wires and their terminaison). 2- Check the insulation (under 500 V cc) between each wire and the others, and the earthing too, record the results. 3 Check the continuity. Following the results we will decide if it is necessary to change these cables or not. See, the complement in annexure |  |  | Não
NCR-ICN-ESC-12-0351-2021 | P0118174 | UA67500D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REINSPECT THE ELEMENT | TA NGV would to know, why there were some water in this area. Where came this water? So it is necessary to check the cables: 1- visually check if there are some oxidation. Make a picture for each cable (where we see the wires and their terminaison). 2- Check the insulation (under 500 V cc) between each wire and the others, and the earthing too, record the results. 3 Check the continuity. Following the results we will decide if it is necessary to change these cables or not. See, the complement in annexure |  |  | Não
NCR-ICN-ESC-12-0351-2021 | P0144968 | UA63331D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REINSPECT THE ELEMENT | TA NGV would to know, why there were some water in this area. Where came this water? So it is necessary to check the cables: 1- visually check if there are some oxidation. Make a picture for each cable (where we see the wires and their terminaison). 2- Check the insulation (under 500 V cc) between each wire and the others, and the earthing too, record the results. 3 Check the continuity. Following the results we will decide if it is necessary to change these cables or not. See, the complement in annexure |  |  | Não
NCR-ICN-ESC-12-0351-2021 | P0144967 | UA63332D | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REINSPECT THE ELEMENT | TA NGV would to know, why there were some water in this area. Where came this water? So it is necessary to check the cables: 1- visually check if there are some oxidation. Make a picture for each cable (where we see the wires and their terminaison). 2- Check the insulation (under 500 V cc) between each wire and the others, and the earthing too, record the results. 3 Check the continuity. Following the results we will decide if it is necessary to change these cables or not. See, the complement in annexure |  |  | Não
NCR-ICN-UFEM-12-0543-2021 | P0154396 | AC32065 | REPAIR | Waiting for TA analysis | REWORK | build up by TIG process with W69. WPS 141/3B-3B/30/RCA3 . take care of temperature, always < 120 degree. Carry out 100% VT , 100% US and 100% MT |  |  | Não
NCR-ICN-ESC-12-0383-2021 | P4127359 |  | REMOVE AND REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0357-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0366-2021 | P4133168 |  | MANUFACTURE |  | ACCEPT AS IT IS |  | REWORK | Rework according to SMB-TDP-PR-6817922, SMB-TDP-PR-6817923 and SMB-TDP-PR-6817917. | Não
NCR-ICN-ESC-12-0367-2021 | P0132772 | DW01110 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0108993 | DW01111 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0108996 | DW01112 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0109089 | DW01113 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109096 | DW01117 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0132886 | DW01120 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109715 | DW01121 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0109725 | DW01122 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0109794 | DW01123 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0132777 | DW01210 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18SC102D00001
NCR-ICN-ESC-12-0367-2021 | P0108999 | DW01211 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0109004 | DW01212 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0132885 | DW01220 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109728 | DW01222 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0367-2021 | P0109097 | DW01315 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109805 | DW01316 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109098 | DW01317 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Não
NCR-ICN-ESC-12-0367-2021 | P0109726 | DW01221 | REWORK | Rework. Disassembly all IM's and proceed according "Action/Recommendation" described in COR-2021-900344. All activities must be done under NG AT support. | REWORK | All elements will be dismounted (SAR, NRV, diaphragm ) A endoscopic control will be done to inspect if dust are inside valves (SAR): if dust are discover inside, valves will be changed and NCR MAT will be raise to follow the repairing. A special double lock washer will be maufacture for the valve DW01210. NRV will be changed by new ones, NCR MAT will be raise to follow the repairing. NCR Regress will be raise to redo inspections and tests. | REWORK | In accordancce with level 2 proposal. | Sim | 18CR000D00007
NCR-ICN-ESC-12-0370-2021 | P0129884 | FC00522 | REWORK | Replace the DECOUPLING WASHER - ELASTOMER - TYPE MN03- 40 (CMD 14SE200D00005); During assembly, all works must be done according procedure SMB-200949; Scrap the damaged pieces (send back to warehouse); Raise a NCR-MAT to supply new parts. | REWORK | In accordancwe with level 1.2 |  |  | Sim | 14SE200D00005
NCR-ICN-ESC-12-0373-2021 | P0134095 | BM21031 | ACCEPT AS IT IS | NG, please advise us how to proceed. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0375-2021 | P0137500 | FQ00101 | REMOVE AND REWORK | Remove FQ00101, remount according SMB-200960 using new gasket and new tab washers, redo new inspections B06, B02 and update B07 NCR-REGRESS will be open to invalidate old inspections B06 and B02 of FQ00101 | REWORK | Agree with level 1.2. Dismount and remount conform, take new gasket and new lock washers. Raise NCR regress to redo inspections and tests | REWORK | - The bolts in contact with the hull can damage. Dismounting and remounting with new bolts. - In accordance with level 2 proposal - dismount the valve, change the gasket, redo all integrity inspections for this hull passage | Sim | 621676-002
NCR-ICN-ESC-12-0376-2021 | P0103335 | DA02604 | REMOVE AND REWORK | Remove and replace with a new one. |  |  |  |  | Não
NCR-ICN-ESC-12-0378-2021 | P0122307 | FH00012 | REMOVE AND REPAIR | ICN suggests to replace the mentioned equipment applying a new one from other submarine. NCR Regress to open. Forward to Naval Group. |  |  |  |  | Não
NCR-ICN-ESC-12-0378-2021 | P0122308 | FH00013 | REMOVE AND REPAIR | ICN suggests to replace the mentioned equipment applying a new one from other submarine. NCR Regress to open. Forward to Naval Group. |  |  |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118872 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118894 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118876 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118871 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118896 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118851 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118897 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118848 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118919 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118858 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118877 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118861 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118918 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118902 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118907 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118878 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118855 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118866 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118884 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118892 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118890 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118914 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118889 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118915 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118846 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118913 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118850 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118893 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118856 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118904 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118899 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118917 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118854 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118903 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118836 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118882 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118895 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118887 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118881 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118883 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118841 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118911 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118906 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118901 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118909 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118908 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118886 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118910 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118849 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118875 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118873 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118888 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118885 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118916 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118905 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118912 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118857 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118891 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118898 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118879 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118900 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118852 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118859 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118860 |  | REMOVE AND REPAIR |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118802 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118803 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118801 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118800 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118828 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118825 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118827 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118826 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118874 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118830 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118853 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118829 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118847 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118845 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118840 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118844 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118839 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118835 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118834 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118838 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118842 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118843 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118833 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118837 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118832 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118831 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118808 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118806 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118809 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118824 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118807 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118804 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0379-2021 | P4118805 |  | REMOVE AND REWORK |  | REWORK | REWORK |  |  | Não
NCR-ICN-ESC-12-0380-2021 | P0134355 | BM00031 | [6 empty] | Sim | 18SC011D00150-011_ISSARTEL
NCR-ICN-ESC-12-0382-2021 | P4128829 |  | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0389-2021 | P0118608 | RM00003 | REWORK | Send to level 2. | REMOVE AND REWORK | No as well SBR 1 than SBR 2, it is just necessary to redo orperform a CTE pertaining to: The tightening and bending the lock washer, for the beam on the jack, For the Zero mechanical device, For the deplumer For the POD. The verification of good working (Hoisting/Lowering time and indication limit switch, Radar POD) will be done by commissionning Team. In order to replace the Radar beam took on SBR 2, take this one of SBR 3, befor to put in place the new Radar beam (this one of SBR 3) check the inner diameter (162 . 0/+1). |  |  | Não
NCR-ICN-ESC-12-0384-2021 | P0134072 | BM00175 | ACCEPT AS IT IS | The IM BM00175 is inside the B01 and B02 circuit of valve BM00042 and BM00040. Since the B01_BM00042, B02_BM00042, B02_BM00040 was done on 28/07/2020, 03/08/2020 respectively and there is no PTRH yet, accept as it is for SBR2. For SBR3 and SBR4 the latest revision from PTRH should be updated and the inspections must be done | REWORK | B02 for BM00175 was asking in the last version of SMB-002930. -Duplicate the B02 of BM00040 with provisory number. action ICN -Update PTRH SMB-005544 to add B02 of NRVs. action NG | REWORK | The SMB-005544-F will be delivred with COS-SMB-319324-H on batch 39. The corresponding inspections will be added with the update of - COS-SMB-206080 / COS-SMB-206081 for BM00176 and BM00175 - COS-SMB-206082 / COS-SMB-206083 for BM00202 and BM00201. | Não
NCR-ICN-ESC-12-0386-2021 | P0134401 | BM00032H | REMOVE AND REWORK | Open NCR-REGRESS to invalidate inspections F06, B06, B01 and B02 of BM00031 and BM00032 Remove BM00031 and BM00032, remount according SMB-200960 using new gasket and new tab washers, redo inspection F06, B06, B01, B02 and update B07 | REWORK | Agree with level 1.2: -Dismount and remount conform -Raise NCR Regress to redo inspections and tests | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Não
NCR-ICN-ESC-12-0386-2021 | P0134400 | BM00031H | REMOVE AND REWORK | Open NCR-REGRESS to invalidate inspections F06, B06, B01 and B02 of BM00031 and BM00032 Remove BM00031 and BM00032, remount according SMB-200960 using new gasket and new tab washers, redo inspection F06, B06, B01, B02 and update B07 | REWORK | Agree with level 1.2: -Dismount and remount conform -Raise NCR Regress to redo inspections and tests | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Não
NCR-ICN-ESC-12-0391-2021 | P0131520 | MB00003 | REWORK | Send to level 2. |  | After verify the good assembly of the PELA and all the O-ring ICN/NGFO try to do a new leak test: PELA was good assembly and the leak continu. Remove PELA with traceability AP435534 (SBR4) and use PELA with traceability AP419848 (SBR3) to assembly on board. Change all the O-ring and perform a new test. Open one NCR-MAT in order to supply new O-ring. | REWORK | Agreement on LVL2 decision to replace with the PELA initially planned for SBR3. The DTR of the PELA SBR4 does not show any non-conformity that could induce these leaks, which did not exist during the FAT of the PELA in the presence of the Brazilian Navy before its expedition. Actions to be carried out and results to be reported to BO Naval Group: - use an endoscope on the spreaders for seeing the potential spacing between the 2 rings - realize a spring dimensional control and compare the values with the DTR values | Sim | 15PE000D00001
NCR-ICN-ESC-12-0392-2021 | P0107803 | DV00062 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107799 | DV00041 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107807 | DV00042 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107806 | DV00043 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107802 | DV00063 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107805 | DV00044 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0392-2021 | P0107804 | DV00054 | REWORK | Send to level 2. | REWORK | -Protection adapted to the DV NRV to avoid the pollution inside have to be put in place: the tape is not a good protection and it can not protect of shock moreover it can go inside the circuit and cause damage. -Following the PTRH SMB-051109, NRVs should be disassembly before S03: During the desassembly a inspection and a cleaning inside should be carry out. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM300D00007
NCR-ICN-ESC-12-0397-2021 | P0145859 | AG00013 | REWORK | Send to level 2. | REWORK | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | REWORK | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Sim | 01PE200D00041
NCR-ICN-ESC-12-0398-2021 | P0145860 | AG00014 | REWORK | Send to level 2. | REWORK | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | REWORK | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Sim | 01PE200D00030
NCR-ICN-ESC-12-0399-2021 | P0145848 | AG00016 | REWORK | Send to level 2. | REWORK | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | REWORK | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Sim | 01PE200D00028
NCR-ICN-ESC-12-0401-2021 | P0145852 | AG00019 | REWORK | Send to level 2. | REWORK | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | REWORK | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Sim | 01PE200D00029
NCR-ICN-ESC-12-0404-2021 | P0154556 | AC32042 | REWORK |  | REWORK | rework a new seating and replace after the end of NCR 12-323 |  |  | Não
NCR-ICN-ESC-12-0404-2021 | P4171847 |  | REWORK |  | REWORK | rework a new seating and replace after the end of NCR 12-323 |  |  | Não
NCR-ICN-ESC-12-0407-2021 | P0109137 | DW00106 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00151
NCR-ICN-ESC-12-0407-2021 | P0109136 | DW00104 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00144
NCR-ICN-ESC-12-0407-2021 | P0109141 | DW00102 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00151
NCR-ICN-ESC-12-0407-2021 | P0109140 | DW00202 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00148
NCR-ICN-ESC-12-0407-2021 | P0109138 | DW00201 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00145
NCR-ICN-ESC-12-0407-2021 | P0109131 | DW00204 | REWORK | Agree with 1.2. Rework according COR-2021-900343. | REINSPECT THE ELEMENT | New borescope has to be done. Clean if necessary. Protect the adaptators with plastic cape or connect it directly with the pipes. Record the result on the inspection sheet Finalyse the final mounting of the bottle on his seating | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim | 22BA000D00145
NCR-ICN-ESC-12-0417-2021 | P4118556 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118559 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118558 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117129 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117144 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117138 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117132 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117130 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117128 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117127 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117143 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117142 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117139 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117136 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117135 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117137 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118547 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117133 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117131 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117134 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118546 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118548 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118545 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117145 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117140 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117146 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4117141 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118561 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118562 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118563 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118551 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118550 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118549 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118557 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118555 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118560 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118833 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118554 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0417-2021 | P4118553 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0418-2021 | P4116977 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0418-2021 | P4116980 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0418-2021 | P4116974 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0418-2021 | P0151127 | AC41019 | REMOVE AND REWORK |  | REWORK |  |  |  | Sim | 01PM100D00052
NCR-ICN-ESC-12-0418-2021 | P4116978 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0420-2021 | P4162341 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0420-2021 | P4162339 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0141800 | ER00055 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130809 | DP02204 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130811 | DP02202 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130812 | DP02201 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P4147649 |  | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130810 | DP02203 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130805 | DP02205 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0141798 | ER00053 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130804 | DP02206 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P4147648 |  | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130803 | DP02207 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130802 | DP02208 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0141797 | ER00052 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P4147647 |  | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0141799 | ER00054 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P4147646 |  | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129918 | DP02105 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129919 | DP02106 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129920 | DP02107 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129916 | DP02103 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129914 | DP02101 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129915 | DP02102 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129921 | DP02108 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0129917 | DP02104 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P4147695 |  | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130020 | DP02111 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0120902 | ER00210 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0409-2021 | P0130019 | DP02110 | REWORK | According COR-2021-900344, Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. | REWORK | Agree with the proposition: Change the block in order to clean it because the junctions are not protected for pollution. After cleaning (or mounting a new one), remount the block with the adapted bolted. |  |  | Não
NCR-ICN-ESC-12-0410-2021 | P0119674 | EL00007 | REWORK | Proceed according 1.2. | REWORK | Following instruction gave by ISP: Check the torque, if during the checking none nut turn, proceed to the strength test B01 even if the pipes outside the pressure hull are not mounted and then bend the tab washers. lt is necessary to complete the B06 inspection file to indicate all operations done. lf any nuts turn, the valve should be dismounted and NCR regress will be raise | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 18RT020D00007
NCR-ICN-ESC-12-0412-2021 | P0151172 | AC41016 | REWORK | Follow 1.2. | REWORK | According decision of Diving Safety Engineer: Check of the torque of the mobile part nut: -lf the nut doesn't turn, bend the lock washer and indicate all the operations done in the B11-19 inspection file of the hull passage AC31016. -lf the nut of the mobile part turns, it is necessary to dismount the mobile part. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 01PM000D00001
NCR-ICN-ESC-12-0411-2021 | P0109352 | DY00021 | REWORK | Follow 1.2. | REINSPECT THE ELEMENT |  |  |  | Sim | 22BA000D00146
NCR-ICN-ESC-12-0411-2021 | P0109354 | DY00022 | REWORK | Follow 1.2. | REINSPECT THE ELEMENT |  |  |  | Sim | 22BA000D00147
NCR-ICN-ESC-12-0411-2021 | P0109351 | DY00011 | REWORK | Follow 1.2. | REINSPECT THE ELEMENT |  |  |  | Sim | 22BA000D00146
NCR-ICN-ESC-12-0411-2021 | P0109353 | DY00012 | REWORK | Follow 1.2. | REINSPECT THE ELEMENT |  |  |  | Sim | 22BA000D00147
NCR-ICN-ESC-12-0411-2021 | P0109137 | DW00106 | REWORK | Follow 1.2. | REINSPECT THE ELEMENT |  |  |  | Sim | 22BA000D00151
NCR-ICN-ESC-12-0422-2021 | P0132173 | EF00018 | REMOVE AND REWORK |  | REWORK |  |  |  | Sim | 18CR000D00048
NCR-ICN-ESC-12-0422-2021 | P0132175 | EF00017 | REMOVE AND REWORK |  | REWORK |  |  |  | Sim | 18CR000D00048
NCR-ICN-ESC-12-0413-2021 | P4116932 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116926 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106300 | DP00215 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106293 | DP00208 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106295 | DP00210 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116933 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116927 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116928 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106296 | DP00211 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106294 | DP00209 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116930 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106301 | DP00216 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P0106292 | DP00207 | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0413-2021 | P4116929 |  | REWORK | Agree with item 1.2. | REWORK |  | REWORK | In accordance with level 2,2 and ICN proposal. Except for DP00216, it is not possible to clean the valve only by flushing. Raise a NCR MAT to determine what will be done for the DP00216. For the moment change the valve by a new one, put a label on the old one indicating “Can not be mounted on board” (or something similar) and put it in quarantine. (David Bernede) | Não
NCR-ICN-ESC-12-0427-2021 | P0120883 | EM21002 | SCRAP AND RE-MANUFACTURE |  | REWORK |  | REWORK | - Remove the screws concerned. - Inspect the tapping in holes of the screws concerned: if tapping OK continue with the following steps, if tapping NOK write a new NCR. - Machine screws NGD 5305145376477 CMD 32VI120D00246 according to drawing FTG-9418. - Refit the machined screws with a new ring BS A8 PC851 NGD 5330142349929 CMD 44JO311D00034. | Sim | 18LF100D00003
NCR-ICN-ESC-12-0427-2021 | P0120886 | EM21004 | SCRAP AND RE-MANUFACTURE |  | REWORK |  | REWORK | - Remove the screws concerned. - Inspect the tapping in holes of the screws concerned: if tapping OK continue with the following steps, if tapping NOK write a new NCR. - Machine screws NGD 5305145376477 CMD 32VI120D00246 according to drawing FTG-9418. - Refit the machined screws with a new ring BS A8 PC851 NGD 5330142349929 CMD 44JO311D00034. | Sim | 18LF100D00003
NCR-ICN-ESC-12-0425-2021 | P0136468 | BQ00001 | ACCEPT AS IT IS | Sent to L2 for analysis | ACCEPT AS IT IS | For metallic gaskets information of validity date it's not necessary |  |  | Sim | 48209301816390008
NCR-ICN-ESC-12-0425-2021 | P0134771 | BQ00002F | ACCEPT AS IT IS | Sent to L2 for analysis | ACCEPT AS IT IS | For metallic gaskets information of validity date it's not necessary |  |  | Não
NCR-ICN-ESC-12-0425-2021 | P0136469 | BQ00003 | ACCEPT AS IT IS | Sent to L2 for analysis | ACCEPT AS IT IS | For metallic gaskets information of validity date it's not necessary |  |  | Sim | 48209301816390006
NCR-ICN-ESC-12-0425-2021 | P0137110 | BQ00004 | ACCEPT AS IT IS | Sent to L2 for analysis | ACCEPT AS IT IS | For metallic gaskets information of validity date it's not necessary |  |  | Sim | 48209301816400006
NCR-ICN-UFEM-12-0544-2021 | P0145846 | AG00017 | REWORK | Rework. See comments and solution in attachment "2.1 ICN SOLUTION". | REWORK | Agree with proposal in anex: 2.1 ICN SOLUTION - NCR-ICN-UFEM-12-0544-2021 | REWORK | In accordance with level 2.2 : 1- Recess for lock (Rep.1) --> ACCEPT AS IS under conditions. Potential bad working / blocking of safety lock (Rep.23). Proposition of Accept as is of Rep.1 with adding a checking phase of complete safety latch adjustment --> If the gap between the 2 parts is consistent with the initial gap, Accept as is also for Rep.23 --> If not, re-manufacturing of Rep.23 with engraving the NCR number on this specific part and picture + dimensional report and certificate of conformity of the part to be joined to the NCR. 2- Gear shaft (pin) and 3- Stopper --> REWORK Re-manufacture the parts according to ICN proposal in annex. Engrave the NCR number on a non-functional area. Dimensional report and certificate of conformity of the part to be joined to the NCR. | Sim | 01PE200D00040
NCR-ICN-ESC-12-0432-2021 | P0135831 | BQ00119 | REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0432-2021 | P0136708 | BQ00064 | REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0431-2021 | P0119082 | EJ00210 | SCRAP | For analysis by Naval Group. |  |  |  |  | Não
NCR-ICN-ESC-12-0431-2021 | P0139323 | EJ00211 | SCRAP | For analysis by Naval Group. |  |  |  |  | Não
NCR-ICN-ESC-12-0437-2021 | P0129884 | FC00522 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | The FC00522 was received with the wago terminals marked with the felt. Kindly provide printed plastic labels suitable for wago terminals, please. Wait for BO orientation. | REWORK | Refer to NCR-ICN-ESC-12-0106-2020-Answer. Multiple marking systems horizontal printing NGD 9905930185410, have been sent. | Sim | 17CA000D00078
NCR-ICN-ESC-12-0434-2021 | P0131520 | MB00003 | REWORK | Regarding the shaft line stern gland (MB00003, CMD 15PE000D00001) delivered for SBR3 (AP419848) and assembled in SBR2. During the hydrostatic resistance test (70 bar) and the water tightness test (52,5 bar) a leakage was detected between 0 – 5 bar. To reach the test, It was necessary to open and close the cam holder (MAT422-0109, position 30), when the pressure overtaken 5 bar, the pressure remains constant without any leakage, the pressure was increased step by step until the maximum pressures requested in each test. Decreasing pressure, around 8 bar the leakage appear again, the leakage was quantified around one liter per hour. This phenomenal does not happen in the SBR1 tests. | REWORK | If we consider the leak of 1L/H, the PELA is inside the tolerance of test during the last test done after some try before . The problem is during the first test it was impossible to rise the pressure until 5 bar due to a leak to important out of tolerance. ICN and NGFO are asking NGBO if it's acceptable as is or not. To be forwarded in level 3 to analyze | REWORK | Regarding the photo added to the NCR, the pressure test can't be validated because of the orientation of the tab washers which can't be bend in this position. To re-orientate the tab washers it is necessary to untight the nuts, so put the tab washers in the good position to be bend properly and reperform the pressure test 70 bar, bend the tab wahers and perform the B02 pressure test (52,5 bar). Regarding a leakage, it is acceptable if in the tolerance. Factory Acceptance Tests were performed successfully with Brazilian Navy and DGA for this stern gland, so there is no manufacturing reason for a leakage over the tolerance. | Sim | 15PE000D00001
NCR-ICN-ESC-12-0436-2021 | P0118606 | RM00001 | ACCEPT AS IT IS | Agree with item 1.2, the quipment will be installed pending component 09EP000D00035_2012, according to NCR-ICN-CONFIG-11-3027-2018 and replacement through NCR-MAT (awaiting issuance). Replacement of the missing componete can be carried out on board. | REWORK | Please apply the SMB-TDP-PR-5635148 (OM-96298) on SBR1, as written in the Modification Order, it is already done on SBR2 |  |  | Não
NCR-ICN-ESC-12-0438-2021 | N/A |  | REWORK | The STARBOARD EXTERNAL GAS EXHAUST VALVE BQ00005 53B-P0136477 - CMx 18SC000D00158 manufacturing drawing BDM-00024118 and PORTSIDE EXTERNAL GAS EXHAUST VALVE BQ00006 53B-P0136946 - CMx 18SC000D00159 manufacturing drawing BDM-00016755. Were checked the dimensions of positioning of the valves BQ00005 and BQ00006 in the submarine SBR2 on board. The measurements found are not in accordance with the manufacturing drawing BDM-00024118 and BDM-00016755. NG, please analyze the problem found. | REWORK | Following drawing BDM-00016754 of BQ00005 and dimensions taken in annex 1: -The positionning of BQ00005 is not correct on 2 axis (X and Z). -For axis X: it's necessarry to update thickness ofshims to respect the dimension 205 +ou- 0,5mm. -For axis Z: a adjustment is possible on the actuator; can be accept as it is. Following drawing BDM-00016755 of BQ00006 and dimensions taken in annex 1: -The positionning of BQ00006 is not correct on 3 axis -For axis X: it's necessarry to update thickness ofshims to respect the dimension 205 +ou- 0,5mm. -For axis Y: a gap exist on both side between clevis and pushrod (0,5 and 2mm); can be accept as it is. -For axis Z: a adjustment is possible on the actuator; can be accept as it is. For both BQ valves a production document and inspection from quality are required: D85 To avoid this problem for others submarines the D85 should be updated with a report of dimensions listed in annex 1. | REWORK | For BQ00005 : - for axis X : adjust the position in accordance with level 2.2 proposal - for axis Y : acceptable - for axis Z : it is necessary to adjust the position of the actuator For BQ00006 : - for axis X : adjust the position in accordance with level 2.2 proposal - for axis Y : adjust the position of the valve - for axis Z : it is necessary to adjust the position of the actuator The "caderno" of mounting have to be updated to modified inspection files. First the inspection files have to be completed by quality so it is necessary to have D85-2 inspection and not seff inspection D85-1. The D85-2 inspection files have to present the interface documentation BDM-00016754 and BDM-00016755 for BQ00005 and BQ00006 and as required by level 2.2, it is necessary to have a table indicating the values expected in X, Y and Z axes and the results found by qualitiy specialists in this kind of measurement. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0441-2021 | P0102204 | BB02501 | REWORK | ICN requests NG support to resolve the issue with BMS_SOFT_PMU_SCORPENE \ BMS_PMU_IPMS_V1.17. | REWORK | On 15-04-2021 the SBR2 PMU was landed by ICN. The 16-04-2021 Naval Group has connected the PMU with external keyboard/ screen/ mouse to check operation. 1) When the PMU started, it froze on the "DISK BOOT FAILURE" error when the BIOS was started => Naval Group has put the BIOS start priorities in order 1 - mini disc "mSATA mini 3ME3" 2 - External Hard Drive "Data" 2) After starting Windows, when launching the application "BMS_PMU_IPMS_1.17.exe", the error "Run time error 6 - Overflow" appeared. => Naval Group saved the following files journal_of_AFT_alarms.log journal_of_alarms_historic.log journal_of_all_alarms.log journal_of_FWD_alarms.log 3) The application "BMS_PMU_IPMS_1.17.exe" has been relaunched without problems and the alarm files have been renewed => Naval Group must take over the PMU maintenance document to add the archiving of the 4 files every year => Naval Group has verified the absence of viruses on the "Black" Laptop of the SBR2: No problem detected On 19-04-2021 the PMU was brought back on board the SBR2 1) The PMU did not communicate with the Laptop or IPMS. => Naval Group "opened" the PMU to directly connect the laptop. Everything was working normally => Naval Group connected the Laptop to the PMU output. Everything was working normally 2) Naval Group found with ICN that the problem was with the BB62871B cable plug => Naval Group asks ICN to redo the connector 3) Naval Group found with ICN that the OO62584B cable plug was missing => Naval Group asks ICN to redo all the connector | REWORK | There was a communication problem on the BMS system due to a weak communication protocol and a bad connexion of optical fibres. In order to fix this issue, it is necessary to apply two Modification Orders to SBR2: - OM-136780 (SMB-TDP-PR-6862721, applicable SBR1-2, loaded in TDP IS on 05/11/2021) consists in flashing a new firmware on the 360 probes. It will be done in week 46-47 by the supplier DEVELEC. - OM-136776 (SMB-TDP-PR-6862720, applicable SBR1-2-3-4, loaded in TDP IS on 05/11/2021) consists in changing the PMU software. This can be done by ICN. Both OM must be applied at the same time. When re-installing the probes onboard, optical fibers must be carefully cut and tightened. | Sim
NCR-ICN-ESC-12-0446-2021 | P0119458 | RM00008 | REWORK | Adjusting the thread of the operating jack, reassembling fixing threadeds rod with two threads fillet on the upper side. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0445-2021 | P0106489 | DN00341 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0105163 | DM00032 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0134072 | BM00175 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0134073 | BM00176 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0124350 | DN00141 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0120126 | EQ00014 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0113038 | KT00717 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0116254 | KT00718 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0445-2021 | P0106487 | DN00241 | REWORK |  | REWORK | In accordance with level 1.2: The painting should be redone ( see MAT177-0312) A NCR REGRESS will be raise for each hull passage to redo inspections and pressure tests. | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0448-2021 | P0136081 | BM00201 | AGREE WITH LEVEL 2.1 | Using the RMS material in SBR2. | REWORK | In accordance with level 1.2 2 years ago 2 NRV on SBR1 were lost and replace by 2 of lot SBR2. Now we have to use RMS to replace on this 2 on SBR2. The both RMS were supply with gasket without packaging and information ( validity date, provenance..). NCR MAT should be raise to follow the purchase of 2 new fiber gasket and inform of the strange color (salmon) of both NRV. | ACCEPT AS IT IS | The traceability of the seals is well in the technical acceptance file of the material. The salmon colour is not a problem. | Não
NCR-ICN-ESC-12-0448-2021 | P0135968 | BM00202 | AGREE WITH LEVEL 2.1 | Using the RMS material in SBR2. | REWORK | In accordance with level 1.2 2 years ago 2 NRV on SBR1 were lost and replace by 2 of lot SBR2. Now we have to use RMS to replace on this 2 on SBR2. The both RMS were supply with gasket without packaging and information ( validity date, provenance..). NCR MAT should be raise to follow the purchase of 2 new fiber gasket and inform of the strange color (salmon) of both NRV. | ACCEPT AS IT IS | The traceability of the seals is well in the technical acceptance file of the material. The salmon colour is not a problem. | Não
NCR-ICN-ESC-12-0458-2021 | P4166802 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0453-2021 | P0156424 | UL00001H | REWORK | We suggest to dismount this handle to verify its seals. NG to inform next Steps. | REWORK | Agree with proposal: - Dismount handle with cutter (item:41) - Scrap both 2 O-Rings (item:42) and replace by new ones. - Raise a NCR REGRESS to redo inspections and tests. - Update the traceability folder. | REWORK | In accordance with level 2.2 proposal. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0454-2021 | P0104240 | BC02500 | REWORK | A new cable must be supplied, and installed on the BC02500 panel according to the Scheneider plans. Make adequacy. | REPAIR | As for SBR1, the cabling and connection done by the manufacturer Schneider is wrong, for the supply U2 of DM1, DM2, DT1, leading to a burning of the card if serial coupling is activated. At this time, the cards are OK. Schneider will come to correct the problem of connection. This NCR is being sent to level 3(Back Office specialist) It is mandatory that ICN blocks the serial coupling, in order to prevent another burning of card, until the manufacturer has corrected the problem. | REWORK | Prohibit the serial coupling of the BC02500 cabinet. The mufacturer (Schneider) will come to correct the wiring of the BC02500. | Sim
NCR-ICN-ESC-12-0459-2021 | P4121643 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0459-2021 | P4121459 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0465-2021 | P0135970 | BM00012 | REWORK | It's necessery remounting the BM00012-P0135970 valve using a new FIBER/NBR GASKET 147X173X3 - 44JO230D00072 and redo the B01 test. Not needed to pay again news lock washer cause they haven't been bended yet. | REWORK | Agree with proposal. Pay attention of the verification of the coating (F06) and the protection during dismounting. A NCR REGRESS will be raise to carry out inspections and pressure tests. B05 should be updated. | REWORK | In accordance with ICN and level 2.2 proposal. David BERNEDE - ISSP | Sim | 004
NCR-ICN-ESC-12-0466-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0467-2021 | P0123020 | EV12152Q | REMOVE AND REPAIR |  | REPAIR | Proceed to a standard exchange of the flowmeter EV12152Q (calibration number MVZ-015) by a new flowmeter (calibration number MVZ-017). Create a NCR MAT to recalibrate the flowmeter dismounted from the SBR1 and refund the stock. Create a NCR REGRESS to manage the inspections and tests to redo. |  |  | Não
NCR-ICN-ESC-12-0470-2021 | P0109426 | DT00533 | REWORK | We can install new equipment DT00533 e DT00534 on board to attend the construction process and open the NCRMAT. | REWORK | Take from SBR4 or SBR3. Raise NCR MAT to purchase new ones |  |  | Não
NCR-ICN-ESC-12-0470-2021 | P0109428 | DT00534 | REWORK | We can install new equipment DT00533 e DT00534 on board to attend the construction process and open the NCRMAT. | REWORK | Take from SBR4 or SBR3. Raise NCR MAT to purchase new ones |  |  | Não
NCR-ICN-ESC-12-0471-2021 | P0104796 | MB00002 | ACCEPT AS IT IS | Accept as it is. 1) The aft holes H7 were remachined due SKF Coupling replacement. See NCR-ICN-ESC-12-208-2020; 2) A new adjustable pin nº 6 were adjusted to attend the NCR-ICN-UFEM-12-258-2018. | REMOVE AND REWORK | After assembly on board any problem detected. |  |  | Não
NCR-ICN-ESC-12-0471-2021 | P0104803 | MB00009 | ACCEPT AS IT IS | Accept as it is. 1) The Flexible Coupling (VULKAN) is installed. No impact for operation. | REMOVE AND REWORK | After assembly on board any problem detected. |  |  | Não
NCR-ICN-ESC-12-0474-2021 | P0156986 | HL12661 | REPAIR | It's necessary to repair before using on SBR2. Please open a NCR MAT for NVG to organize this repair | REPAIR | It's necessary to repair before using on SBR2. Please open a NCR MAT for NVG to organize this repair |  |  | Não
NCR-ICN-ESC-12-0475-2021 | P0106087 | ME03102 | REWORK | A small pin is missing to lock the connection plate, we must provide a new pin. | REMOVE AND REPAIR | Forward to level 3 | REWORK | Take the same Power Plate 1-4 on CC2 SBR4 and install it on SBR2. Create a NCR MAT for the damaged Power Plate (NGD = 0930930253995 and 9980000002849) . As recalled in sheet C1 of the maintenance manual, the handling, removal and insertion of Power Plates must be the subject of special attention. An exhaustive check must be planned to be carried out on the other SBR2 Power Plates during the STW of the supplier Jeumont to come. | Sim
NCR-ICN-UFEM-12-0545-2021 | N/A |  | REWORK | ICN request to use BORFLEX Lip Seal delivered in Batches SMB-RMS-CUR-DB34 or SMB-RMS-CUR-DB35 to continue the inspections and tests. The NCR-MAT-001652-2021 was opened to supply new part. |  |  |  |  | Não
NCR-ICN-UFEM-12-0545-2021 | SC4-AG00017-MT |  | REWORK | ICN request to use BORFLEX Lip Seal delivered in Batches SMB-RMS-CUR-DB34 or SMB-RMS-CUR-DB35 to continue the inspections and tests. The NCR-MAT-001652-2021 was opened to supply new part. | REWORK | Agree with proposal. | SCRAP | The supplied lip seal is compliant to MAT424-1296_A applicable at the time of procurement, but however non-compliant to MAT424-1296_B now applicable. It was detected that lip seals procured according to MAT424-1296_A (large diameter and extended tolerance) could sometimes create waves in the hatch groove, but not at the level observed on the photo received for another hatch "Pb montage joint SMAC_AG00017_SBR2.jpg", so the lip seal has been stretched. Please scrap (even if it conforms to its specification) the lip seal according to MAT424-1296_A and replace it with a lip seal in stock according to MAT424-1296_B. A new lip seal will be supplied for replenishment. In addition, it is almost impossible to obtain such a wave if the seal is fitted correctly: - in view of the assembly, it was stretched from a single point A on the perimeter of the hatch towards the diametrically opposite point; - it can appear waves at 1/4 or 1/8 turn but not such a shape. Please contact the AT Naval Group so that it reminds the ICN fitters on the method of fitting the lip seal in the hatches grooves. | Não
NCR-ICN-ESC-12-0481-2021 | P4121883 |  | MANUFACTURE | Manufacture the spool according to the project definition. | REWORK |  | REWORK | In accordance with proposal. The pipe which is not adapted has to be scrapped. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0482-2021 | P4121999 |  | MANUFACTURE | Manufacture the spool according to the project definition. | REWORK |  | REWORK | In accordance with proposal. The pipe which is not adapted has to be scrapped. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0483-2021 | P4121419 |  | MANUFACTURE | manufacture the spool according to the project definition. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0480-2021 | P0101620 | OO24007 | REMOVE AND REWORK | ICN suggests to replace the K20 module with the dedicated item from other submarine and the bus cable with V1-W-5M-PUR in order to avoid future damage. | REMOVE AND REWORK | Dismount and replace the module ASI V3 SIEMENS TYPE 2 Take it on sbr4 Use a bus cable with V1-W-5M-PUR (elbow connector, in annex) Open NCR MAT to refund only the module ASI V3 SIEMENS TYPE 2 Open NCR regress and redo E01 OO24007 F01 OOZ0028 F05 OOZ0019 F01 DAZ0002 for DA12509N and DA12513N |  |  | Não
NCR-ICN-ESC-12-0486-2021 | N/A |  | REWORK | To correct the position of the bolts lock hole, consequence of the jig deformation. The ICN suggests. 1. Perform the assembly and torque of 680 N.m. of the bolts on board. 2. Mark the position of the nut stop hole at 120 ° on two sides. 3. Remove the bolts for the workshop and drill the Ø6.3mm diameter bolts in the marked area. Remove two bolts at a time. 4. Reinstall the bolts, tighten the nut until the hole is in position and install the locking pin. | REWORK | Agree with the proposition L1. It's important to confirm the torque on board before mark the new position of the pin. The number of the nut need to correspond with the bolt, if not do a new one in order to don't mix the material. |  |  | Não
NCR-ICN-ESC-12-0484-2021 | P0133575 | BD00014 | AGREE WITH LEVEL 2.1 | A "half moon" cut in the support may be a solution. A 90° tool could be adapted as well. | REWORK | The connexion can't be done because the lenght of the tool is too long. I suggest you to change the connexion by one with one angle of 90° and the task will be possible. |  |  | Sim | n/a
NCR-ICN-ESC-12-0494-2021 | N/A |  |  |  | REWORK | Send to level 3 Waiting for BO orientation |  |  | Não
NCR-ICN-ESC-12-0485-2021 | P4168228 |  | REWORK | Scenario: during the flushing activity, it was verified that the lines KT51382RB / P0115900 and KT51042R / P0116185 are inverted. Solution: ICN proposes in the closest position, and most accessible point, cut/increase the length and invert the lines/and weld them. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0485-2021 | P4121787 |  | REWORK | Scenario: during the flushing activity, it was verified that the lines KT51382RB / P0115900 and KT51042R / P0116185 are inverted. Solution: ICN proposes in the closest position, and most accessible point, cut/increase the length and invert the lines/and weld them. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0601-2021 | P0105755 | DB00113 | REWORK | Provide new complete connectors. |  |  |  |  | Não
NCR-ICN-ESC-12-0601-2021 | P0105754 | DB00114 | REWORK | Provide new complete connectors. |  |  |  |  | Não
NCR-ICN-ESC-12-0601-2021 | P0104554 | BH00011 | REWORK | Provide new complete connectors. |  |  |  |  | Não
NCR-ICN-ESC-12-0487-2021 | P0135969 | BM00010 | REWORK |  | REWORK | BM00010 SBR2 18SC011D00166/ISSARTEL/014 was with halar damaged: -Raise a NCR MAT to follow the repairing. -Paid attention to protect correctly valves With the lack of stock of CMD: 18SC011D00166 it's possible to adapte the CMD: 18SC011D00150. BM00031 will be dismounted from SBR3 18SC011D00150/ISSARTEL/022: -Paid attention to protect correctly valve during all the process -Update the positionning M3 B2(switch box) V4(rotating jack) R8 to M3 B3 V3 R8 (MAT171-2727) -Change the label of the fitted valve with the CMD: 18SC011D00166 -Update the traceability folder -Raise NCR REGRESS to redo inspections and pressure tests | REWORK | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Sim | 014
NCR-ICN-ESC-12-0488-2021 | P0134348 | BM00042 | REWORK | The BM00042 valve that was mounted in SBR2 was 18SC011D00141-SN.016(ISSARTEL) but because of this coating problem it was dismounted and returned to the warehouse. And, to solve the problem, it will be used the BM00032-SN.021(MICROMASSA) of the SBR3 that will be mounted in SBR2-BM00042 place. It will already be applicated the OM-118711/SMB-TDP-PR-6650723 to use the new hydraulic actuator CMD: 14VE200D00034 and 2 new units of the O-ring 16.90x2.70 20A8 CMD: 44JO110D00009. The procedure is SMB-371504 and it's needed doing a workshop test M09 and after new F06, B06, B07,B01 and B02. | REWORK | Agree with proposal. A NCR MAT will be raise to follow the repairing of the valve A NCR REGRESS will be raise to carry out inspections and tests |  |  | Sim | 016
NCR-ICN-ESC-12-0489-2021 | P0151943 | AC43033 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6260350-2016-01-MP
NCR-ICN-ESC-12-0489-2021 | P0151223 | AC41015 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-03-MP
NCR-ICN-ESC-12-0489-2021 | P0154471 | AC42001 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-02-MP
NCR-ICN-ESC-12-0489-2021 | P0152760 | AC43062 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6260350-2016-01-MP
NCR-ICN-ESC-12-0489-2021 | P0152073 | AC43037 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6260350-2016-01-MP
NCR-ICN-ESC-12-0489-2021 | P0152027 | AC44044 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-04-MP
NCR-ICN-ESC-12-0489-2021 | P0154455 | AC42036 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6284904-2016-02-MP
NCR-ICN-ESC-12-0489-2021 | P0151890 | AC43014 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-08-MP
NCR-ICN-ESC-12-0489-2021 | P0151934 | AC43015 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-05-MP
NCR-ICN-ESC-12-0489-2021 | P0151894 | AC43028 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6284904-2016-02-MP
NCR-ICN-ESC-12-0489-2021 | P0152029 | AC44045 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-04-MP
NCR-ICN-ESC-12-0489-2021 | P0151930 | AC43052 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-03-MP
NCR-ICN-ESC-12-0489-2021 | P0151940 | AC43056 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-03-MP
NCR-ICN-ESC-12-0489-2021 | P0151814 | AC43057 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-03-MP
NCR-ICN-ESC-12-0489-2021 | P0152097 | AC44032 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | AP418393-F3013
NCR-ICN-ESC-12-0489-2021 | P0152088 | AC44028 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | AP418394-F3013
NCR-ICN-ESC-12-0489-2021 | P0154439 | AC42056 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6278499-2016-04-MP
NCR-ICN-ESC-12-0489-2021 | P0152092 | AC44029 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | AP418392-F3013
NCR-ICN-ESC-12-0489-2021 | P0152070 | AC44049 | MANUFACTURE | Manufacture this lock plate, respecting all material especifications and project discription given in MAT-References of each CMD attached. Make the correct material treceability to ensure the conformety of the material used in the manufacture process is good or not, and this information will also used to make the B05 book of this ACs. | MANUFACTURE | In accordance with level 2.1 proposal. B06 inspection will also have to be done. (Fabien RENVOISE) | REWORK | In accordance with level 2.1 proposal. B06 inspection will also have to be done. David BERNEDE | Sim | 6289252-2016-04-MP
NCR-ICN-ESC-12-0490-2021 | P0122827 | EV00100 | REWORK |  | REWORK | The CMD of the valve EV00100 changed regarding the modification order OM-108713 (SMB-TDP-PR-6650629). 18SC000D00104 replaced by 18SC000D00198 (NGD 9980000066618). Need to apply this modification on board of the SBR2. |  |  | Não
NCR-ICN-ESC-12-0491-2021 | P0122107 | ES00024 | REWORK |  | REWORK | The CMD of the valve ES00024 changed regarding the modification order OM-108713 (SMB-TDP-PR-6650629). 18SC000D00105 replaced by 18SC000D00197 (NGD 9980000066615). Need to apply this modification on board of the SBR2. |  |  | Não
NCR-ICN-ESC-12-0497-2021 | P0136019 | BM00001 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 010
NCR-ICN-ESC-12-0497-2021 | P0136018 | BM00002 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 013
NCR-ICN-ESC-12-0497-2021 | P0136065 | BM00007 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 023
NCR-ICN-ESC-12-0497-2021 | P0136066 | BM00008 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 018
NCR-ICN-ESC-12-0497-2021 | P0135969 | BM00010 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 014
NCR-ICN-ESC-12-0497-2021 | P0135944 | BM00011 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 022
NCR-ICN-ESC-12-0497-2021 | P0135970 | BM00012 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 004
NCR-ICN-ESC-12-0497-2021 | P0135945 | BM00016 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 019
NCR-ICN-ESC-12-0497-2021 | P0134355 | BM00031 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 011
NCR-ICN-ESC-12-0497-2021 | P0134354 | BM00032 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 012
NCR-ICN-ESC-12-0497-2021 | P0134350 | BM00037 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the componentes of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 025
NCR-ICN-ESC-12-0497-2021 | P0134352 | BM00038 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 045
NCR-ICN-ESC-12-0497-2021 | P0134346 | BM00040 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 009
NCR-ICN-ESC-12-0497-2021 | P0134351 | BM00041 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 024
NCR-ICN-ESC-12-0497-2021 | P0134348 | BM00042 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 016
NCR-ICN-ESC-12-0497-2021 | P0134353 | BM00046 | REWORK | This identification is necessary for the traceability reference to become unique making it possible to exchange components if necessary and also facilitating the identification of the components of the valves. | REWORK | As is explained under SMB-316007 or SMB-200052 the traceability of hull valves is constited of: General rule: CMD(orNGD).XXXXXX.Contract number. The contract number is engraved on body, mobile flange and cap. ICN have to update the traceability on documents in adding the contract number to become a unique reference. | REWORK | In accordance with level 2.2 proposal. In complement, it is necessary to create labels woth the traceability reference CMD.XXXXX.contract number for all valves and accesories. For actuatorsin CuAL in addition of the label, it is required to engrave the traceability reference. (David Bernerde) | Sim | 016
NCR-ICN-ESC-12-0498-2021 | P0126750 | EW00008 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0126751 | EW00009 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0126752 | EW00010 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122048 | EG00110 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122044 | EG00130 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0143452 | EG00143 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122062 | EG00140 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0143451 | EG00144 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122027 | EG00205 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122063 | EG00234 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122065 | EG00236 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0136464 | EG01110 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0136467 | EG01120 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122150 | EG01130 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122151 | EG01140 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122147 | EG01159 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0122116 | EG01165 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0105286 | DM00009 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0105287 | DM00010 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0105288 | DM00011 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0498-2021 | P0115999 | DJ00004 | REWORK | REWORK | REWORK | Agree with Deliberação N1 USE 11AC100D00255 - CABLE GLAND ISO 20 POLYAMIDE IP66 |  |  | Não
NCR-ICN-ESC-12-0499-2021 | P0151131 | AC41021 | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Sim | 01PM100D00047-6227186-2015-01
NCR-ICN-ESC-12-0499-2021 | P4116455 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4116456 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4116457 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4116458 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4117135 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4117136 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4117137 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0499-2021 | P4117139 |  | REWORK | Dismount the pipes and the mobile parts. To remounting, use new gasket and lock washers, do new B06 and B07 for mobile and the others pertinents pipes inspections. | REMOVE AND REWORK | All inspections linked with the pipes and the MP have to be redone, including M05, B01, B02, S02... The B05 should be updated after remounting. Raise a NCR regress to identify all inspections required | REWORK | In accordance with level 2.2. Raise a NCR regress to identify all inspections required (David Bernède) | Não
NCR-ICN-ESC-12-0501-2021 | P0151979 | AC44031 | REWORK | For the assembly of the AC44031 equipment. Necessary replace new nuts and rod threads, according to (items 6 and 8) referring to MAT427-0026 and MAT427-0027. Open NCR MAT. | REWORK | Raise NCR MAT to launch the purchase of new nuts and stud rods | REWORK | In accordance with level 2.2 proposal (David Bernerde) | Sim | 01PM000D00022
NCR-ICN-ESC-12-0500-2021 | P4171824 |  | REWORK | Agree with 1.2. Weld using austenitic. | REWORK | Rework using austenitic electrods cary out 100% VT qnd 100% LP |  |  | Não
NCR-ICN-ESC-12-0500-2021 | P4181964 |  | REWORK | Agree with 1.2. Weld using austenitic. | REWORK | Rework using austenitic electrods cary out 100% VT qnd 100% LP |  |  | Não
NCR-ICN-ESC-12-0503-2021 | P4127403 |  | REWORK | Pipe already manufactured. Redo test B01 RM00078 and B02 RM00078 | REWORK | Raise NCR REGRESS to redo inspections and pressure tests. B05 should be updated | REWORK | In accordance with level 2.2 proposal (David Bernerde). | Não
NCR-ICN-ESC-12-0505-2021 | P4149847 |  | REWORK | agree with 1.2. Rework according job order. | REWORK | Rework as per original For the area where the old seating was welded ICN must apply the SMB-200043 |  |  | Não
NCR-ICN-ESC-12-0512-2021 | P0109281 | DW01116V | REMOVE AND REWORK |  | REPAIR | Regarding the defects found on the SAR of the SBR1 regarding the cleaness of the circuits DW, ICN has to take all precautions possible to keep the circuits clean. All outs must absolutely be plugged. Before to peform the pressure test, need to blow the lines with air and connecte them to the valves. No need to perform a new pickling operation | REWORK | Wrong Product Marks given in this NCR : are quoted the marks of operating restrictions and weldings : P0109281 -> DW01116V / OPERATING RESTRICTION VALVE DW01116 P0109296 -> DW01215V / OPERATING RESTRICTION VALVE DW01215 SP0024018 -> SOUDURE_DW50113Y1_003_023 SP0024014 -> SOUDURE_DW50220Y1_003_023 But the concerned marks are valves and NRV : P0109110 / DW01116 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109126 / DW01215 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109146 / DW50113Y / DW01110 VALVE DISCHARGE NRV LEAK INDICATOR P0109167 / DW50220Y / DW01210 VALVE DISCHARGE NRV LEAK INDICATOR In any case disagree, if dirt found it is necessary to redo a pickling. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0512-2021 | P0109296 | DW01215V | REMOVE AND REWORK |  | REPAIR | Regarding the defects found on the SAR of the SBR1 regarding the cleaness of the circuits DW, ICN has to take all precautions possible to keep the circuits clean. All outs must absolutely be plugged. Before to peform the pressure test, need to blow the lines with air and connecte them to the valves. No need to perform a new pickling operation | REWORK | Wrong Product Marks given in this NCR : are quoted the marks of operating restrictions and weldings : P0109281 -> DW01116V / OPERATING RESTRICTION VALVE DW01116 P0109296 -> DW01215V / OPERATING RESTRICTION VALVE DW01215 SP0024018 -> SOUDURE_DW50113Y1_003_023 SP0024014 -> SOUDURE_DW50220Y1_003_023 But the concerned marks are valves and NRV : P0109110 / DW01116 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109126 / DW01215 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109146 / DW50113Y / DW01110 VALVE DISCHARGE NRV LEAK INDICATOR P0109167 / DW50220Y / DW01210 VALVE DISCHARGE NRV LEAK INDICATOR In any case disagree, if dirt found it is necessary to redo a pickling. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0512-2021 | SP0024018 |  | REMOVE AND REWORK |  | REPAIR | Regarding the defects found on the SAR of the SBR1 regarding the cleaness of the circuits DW, ICN has to take all precautions possible to keep the circuits clean. All outs must absolutely be plugged. Before to peform the pressure test, need to blow the lines with air and connecte them to the valves. No need to perform a new pickling operation | REWORK | Wrong Product Marks given in this NCR : are quoted the marks of operating restrictions and weldings : P0109281 -> DW01116V / OPERATING RESTRICTION VALVE DW01116 P0109296 -> DW01215V / OPERATING RESTRICTION VALVE DW01215 SP0024018 -> SOUDURE_DW50113Y1_003_023 SP0024014 -> SOUDURE_DW50220Y1_003_023 But the concerned marks are valves and NRV : P0109110 / DW01116 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109126 / DW01215 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109146 / DW50113Y / DW01110 VALVE DISCHARGE NRV LEAK INDICATOR P0109167 / DW50220Y / DW01210 VALVE DISCHARGE NRV LEAK INDICATOR In any case disagree, if dirt found it is necessary to redo a pickling. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0512-2021 | SP0024014 |  | REMOVE AND REWORK |  | REPAIR | Regarding the defects found on the SAR of the SBR1 regarding the cleaness of the circuits DW, ICN has to take all precautions possible to keep the circuits clean. All outs must absolutely be plugged. Before to peform the pressure test, need to blow the lines with air and connecte them to the valves. No need to perform a new pickling operation | REWORK | Wrong Product Marks given in this NCR : are quoted the marks of operating restrictions and weldings : P0109281 -> DW01116V / OPERATING RESTRICTION VALVE DW01116 P0109296 -> DW01215V / OPERATING RESTRICTION VALVE DW01215 SP0024018 -> SOUDURE_DW50113Y1_003_023 SP0024014 -> SOUDURE_DW50220Y1_003_023 But the concerned marks are valves and NRV : P0109110 / DW01116 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109126 / DW01215 / BLOWING NRV LEAK INDICATOR HULL VALVE P0109146 / DW50113Y / DW01110 VALVE DISCHARGE NRV LEAK INDICATOR P0109167 / DW50220Y / DW01210 VALVE DISCHARGE NRV LEAK INDICATOR In any case disagree, if dirt found it is necessary to redo a pickling. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0508-2021 | P0104606 | BH00106 | ACCEPT AS IT IS |  | ACCEPT AS IT IS | The coating is present on all of the surface. The water tightness is not compromised by the defect. | REWORK | In accordance with level 2.2 proposal, The reference of the NCR has to be added to traceability folder of the valve. Alert : there is no reference of the Traceability of the valve concerned. Update the NCR to indicate the Traceability Reference. David BERNEDE - ISSP | Sim | 18RT010D00817-001-MICROMAZZA
NCR-ICN-ESC-12-0510-2021 | P0150008 | DA02500 | NCR LEVEL 1 | A new selector button for the panel must be provided. NG must outline the button for a new supply. | REMOVE AND REWORK | Take the commutator S1 (AUTO/MAN) of the panel DA02500 of SBR4 Open NCR MAT to refund it |  |  | Não
NCR-ICN-ESC-12-0514-2021 | N/A |  | ACCEPT AS IT IS | Agree with deliberation 1.2. Send to naval group analyze. | REMOVE AND REWORK | Agree with level 1. The alignment was done with the definitive material and according to the quality control the alignment is OK. |  |  | Não
NCR-ICN-ESC-12-0513-2021 | P0113898 | DY00313 | REPAIR | Forward to Naval Group for repairing. | REPAIR | Take a new dome air pressure reducing valve 18DP000D00007 in the stock, perform the calibration and mount onboard fo the SBR2. Create a NCR-MAT to manage the expertise of the defective equipment (serial number: P445886) to decide how solve the problem. |  |  | Não
NCR-ICN-UFEM-12-0548-2021 | SC2A-EQ00043 |  | ACCEPT AS IT IS | During the S12 - Test under aerostatic pressure, with internal pressure 0,1 bar (100 mbar), upward movement was observed and some leakage before achieve the pressure requested. The hatch EQ00043 was installed in the test tool (SMB-328815) through of weight itself (40,31 kg - 53B-CTE00825063). There is not locking system for this hatch. At this time, the engineer in charge of the test decided, in agreement with QC inspector, to perform a vacuum test (-0,1 bar/1 hour). The vacuum pressure was checked using a manometer with resolution of 1 mbar, see certificate attached. The measurement remained stabilized during 1 hour. The S10 and S11 tests in hyperbaric chamber were approved. Accept as it is. Send to NG analysis to review the S12 test for EQ00043. | OK - UPDATE JOB ORDER | For ICN : S12 inspection (Non-autoclave pressure testing of hatches) is not applicable for EQ00043. For BO : There is an inconsistency to correct between 2 documents : - EDT SMB-309223_K specify in 5.2.5 point B3 to proceed the internal pressure test - STA MAT424-1528_C (BDM-00062539_C) specify in 9.1.4 "Not applicable." | REWORK | In accordance with level 2.2 to not perfom the non-autoclave test for this panel. Send the NCR to BO to modify the documentation. (David Bernede) | Não
NCR-ICN-ESC-12-0515-2021 | P0151127 | AC41019 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Sim | 01PM100D00052-6227186-2015-01
NCR-ICN-ESC-12-0515-2021 | P0151731 | AC43054 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Sim | 01PM200D00026-AP418392-F3013
NCR-ICN-ESC-12-0515-2021 | P0152757 | AC43026 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0106726 | DB23111R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0120806 | EQ22501R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0120803 | EQ22502R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0101532 | OO22500I | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0120713 | EQ23900R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0120705 | EQ23950R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0154387 | AC42060 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0154391 | AC42061 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0103208 | BE27100I | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0109080 | HE22500R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0101538 | OO22510R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0118297 | UW24111D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0118298 | UW24112D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0152073 | AC43037 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0108903 | UE22000D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0124167 | GN22577D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0152760 | AC43062 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0108755 | RF22501D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 |  |  | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 |  |  | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 |  |  | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0152092 | AC44029 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0106725 | DB23112R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0112858 | DP24361D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0112859 | DP24362D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0112860 | DP24363D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0129201 | EX22501R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0124189 | GN22587R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0129334 | EX22500R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0101544 | OO22504R | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0109026 | UN22800D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0132233 | UP23000D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0132193 | UP24000D | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0515-2021 | P0154397 | AC42065 | REWORK | COC must be updated. | REWORK | The COC for the 3 NRVs have to pe provide by NG. For the others, if the serial number can't be associated with COC the SMB-002930 have to be updated by NG with removing of the product in column COC. |  |  | Não
NCR-ICN-ESC-12-0516-2021 | N/A |  | ACCEPT AS IT IS | Agree with deliberation 1.2. Accept as it is. | ACCEPT AS IT IS | The control of alignment was done in the VULKAN flange who have one diameter of 1460 mm. The vertival concentricity of the control sheet need to be uptaded at 0,68 and not at 0,56. TDP will be charged with the new values of alignment and the TAF will be modified too. Accept as it is. Send to level 3 in order to inform and validate this situation. |  |  | Não
NCR-ICN-ESC-12-0518-2021 | N/A |  |  |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0520-2021 | N/A | [7 empty] | Não
NCR-ICN-UFEM-12-0550-2021 | SC4-AG00017-MT |  | REWORK | Replace the non-conform gasket by NGD 5330145107997 - FLAT GASKET 60 X 79 X 3 FIBER / NBR delivered in Batch SMB-RMS-CUR-DB19. See attached the NG authorization to use the spare part. Raise a NCR-MAT to supply new parts (minimum 2 units), update the nomenclature and part list. | REWORK | In accordance with proposal: raise NCR MAT to supply new gaskets | REWORK | In accordance with proposal - change the gasket, identify the operation in the traceability folder of the panel | Não
NCR-ICN-ESC-12-0524-2021 | P0122065 | EG00236 | REWORK | To replace. | REMOVE AND REWORK | Due of no protection, the connectors on both were damaged. Change the 2 electric actuators. Take on SBR4 and protect the pins of connectors. Open NCR MAT to refund the actuators. |  |  | Não
NCR-ICN-ESC-12-0524-2021 | P0122116 | EG01165 | REWORK | To replace | REMOVE AND REWORK | Due of no protection, the connectors on both were damaged. Change the 2 electric actuators. Take on SBR4 and protect the pins of connectors. Open NCR MAT to refund the actuators. |  |  | Não
NCR-ICN-ESC-12-0522-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0523-2021 | P0104240 | BC02500 | REWORK | According to the response of RD-08410: Use the pcb UM of the rack DM1: MIQ02013/15-02 (NCR-ICN-ESC-11-1297-2021) to make some test. | REMOVE AND REWORK | Use the pcb UM of the rack DM1: MIQ02013/15-02 (NCR 1297) to make some test and report the result to TA Naval Group. Update 29/09/2021: Put back the original UM pcb and adjust the zero scale and full scale in order to obtain values inside tolerance. Report the new values of adjustment to NG TA. |  |  | Sim
NCR-ICN-ESC-12-0525-2021 | P0107633 | DV00001 | REPAIR | ICN proposes to change the respective items manufacturing new ones according to the proposed in NCR-ICN-ESC-11-0617-2019. The came of all DV valves for the other submarines should be changed accordingly in order to keep the same configuration. | MANUFACTURE | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | REWORK | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Não
NCR-ICN-ESC-12-0525-2021 | P0107640 | DV00003 | REPAIR | ICN proposes to change the respective items manufacturing new ones according to the proposed in NCR-ICN-ESC-11-0617-2019. The came of all DV valves for the other submarines should be changed accordingly in order to keep the same configuration. | MANUFACTURE | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | REWORK | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Não
NCR-ICN-ESC-12-0525-2021 | P0107639 | DV00004 | REPAIR | ICN proposes to change the respective items manufacturing new ones according to the proposed in NCR-ICN-ESC-11-0617-2019. The came of all DV valves for the other submarines should be changed accordingly in order to keep the same configuration. | MANUFACTURE | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | REWORK | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Não
NCR-ICN-ESC-12-0525-2021 | P0107638 | DV00093 | REPAIR | ICN proposes to change the respective items manufacturing new ones according to the proposed in NCR-ICN-ESC-11-0617-2019. The came of all DV valves for the other submarines should be changed accordingly in order to keep the same configuration. | MANUFACTURE | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | REWORK | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Não
NCR-ICN-ESC-12-0525-2021 | P0107641 | DV00002 | REPAIR | ICN proposes to change the respective items manufacturing new ones according to the proposed in NCR-ICN-ESC-11-0617-2019. The came of all DV valves for the other submarines should be changed accordingly in order to keep the same configuration. | MANUFACTURE | Agree to apply the OM-114913_SMB-TDP-PR-6115393 (Reference: RAI-SBR1-04054-319702) to the SBR2, SBR3 and SBR4. Machine the cams following the modification Order for the distributors DV00001, DV00002, DV00003, DV00004 e DV00093. | REWORK | OM-114913_SMB-TDP-PR-6115393 (Reference: RAISBR1- 04054-319702) will be corrected and reissued. It will mention the quantity of cams to be manufactured to modify all equipment for all functions on all boats. | Não
NCR-ICN-ESC-12-0528-2021 | P4167453 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0526-2021 | N/A |  |  |  | REWORK | Accedpted as it is, Adjust the hight of GRP panel using shim on the support |  |  | Não
NCR-ICN-ESC-12-0527-2021 | P0145898 | AG00033 | REWORK | For hatch 53B-AG00013 - P0145898 - CMD 01PE200D00049, provide new materials as attached. Open NCR MAT. | REWORK | Agree with proposal. A NCR MAT will be raise to order new parts The traceability folder of the panel will be updated |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0136464 | EG01110 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122150 | EG01130 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122151 | EG01140 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122063 | EG00234 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122062 | EG00140 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122044 | EG00130 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122048 | EG00110 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0558-2021 | P0122027 | EG00205 | REWORK | OPEN "NCR-MAT" FOR NEW SUPPLY OF THIS MATERIAL. | REWORK | this M3 x 30 screw has no particular property. it can be replaced by a local purchase |  |  | Não
NCR-ICN-ESC-12-0548-2021 | P0105641 | DM62543I | REWORK | USE THE SUPPLIED DM62543I AND DM62544R (DM00009) CABLE CONNECTORS FOR THE "SBR4" AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY. | REWORK | NCR unfounded No connector problem because the motorisation must be replaced according to OM 107086 |  |  | Não
NCR-ICN-ESC-12-0548-2021 | P0105642 | DM62544R | REWORK | USE THE SUPPLIED DM62543I AND DM62544R (DM00009) CABLE CONNECTORS FOR THE "SBR4" AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY. | REWORK | NCR unfounded No connector problem because the motorisation must be replaced according to OM 107086 |  |  | Não
NCR-ICN-ESC-12-0529-2021 | P0116694 | EF20038 | REMOVE AND REPAIR | Remover e reparar | REMOVE AND REWORK | make the standard exchange of the seal, check the misalignement of the pipe make a ncr regress |  |  | Não
NCR-ICN-ESC-12-0530-2021 | P0123068 | EV12151Q | REPAIR | [5 empty] | Não
NCR-ICN-ESC-12-0530-2021 | P0123020 | EV12152Q | REPAIR | [5 empty] | Não
NCR-ICN-ESC-12-0533-2021 | P0130883 | KT00051 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0533-2021 | P0126922 | KT00052 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0533-2021 | P0130891 | KT00053 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0533-2021 | P0126923 | KT00054 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0533-2021 | P0130892 | KT00055 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0533-2021 | P0126924 | KT00056 | REWORK | For the assembly of equipment 53B-KT00051, 53B-KT00052, 53B-KT00053, 53B-KT00054, 53B-KT00055 and 53B-KT00056, modify items 22 and 26 referring to MAT321-0234 and MAT321 -0235. The screws and washers must be replaced and complemented according to the annex list. | AGREE WITH LEVEL 2.1 | see the anexe document attached |  |  | Não
NCR-ICN-ESC-12-0534-2021 | P0107806 | DV00043 | REWORK | Dismount the valve DV00043-P0107806 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040296/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0003/B02_DV00043 tests and a NCR-MAT to replace the material (o-ring). |  |  |  |  | Não
NCR-ICN-ESC-12-0535-2021 | P0107802 | DV00063 | REWORK | Dismount the valve DV00063-P0107802 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040298/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0004/B02_DV00063 tests and a NCR-MAT to replace the material (o-ring). | REWORK | Agree with proposal. |  |  | Não
NCR-ICN-ESC-12-0536-2021 | P0107805 | DV00044 | REWORK | Dismount the valve DV00044-P0107805 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040297/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0005/B02_DV00044 tests and a NCR-MAT to replace the material (o-ring). | REWORK | Agree with proposal. |  |  | Sim | 01PM300D00007-SN.17/014
NCR-ICN-ESC-12-0537-2021 | P0107804 | DV00054 | REWORK | Dismount the valve DV00054-P0107804 and in eminence of remounting, do the B11.27 inspection filling porperly all fields. For remounting, use a new o-ring 106x3.55-20A8 as it's specified in the CTE01040295/MAT425-0581_B/MAT425-0853_EXP and with the appropriated CMD: 44JO110D00420. Raise a NCR-REGRESS for S02_DVZ0005/B02_DV00054 tests and a NCR-MAT to replace the material (o-ring). | REWORK | Agree with proposal. |  |  | Sim | 01PM300D00007-SN.17/013
NCR-ICN-ESC-12-0538-2021 | P0131806 | FR00002 | REWORK | USE FIXING ELEMENTS SUPPLIED FOR "SBR4" AND OPEN "NCR-MAT" FOR NEW SUPPLY. | REWORK | Take the power terminals from SBR4 if available. Open an NCR-MAT to supply new terminals |  |  | Sim | 13AC000D00012
NCR-ICN-ESC-12-0541-2021 | P0105591 | DM00008L | REMOVE AND REWORK | The actuator must be repaired or replaced with a new one. | REWORK | Due of a supply issue of the actuator DM0008 during trials at workshop, found that the PCB SUPPLY is burned (varistance) picture attached Take a new actuator on SBR4 Open NCR MAT to buy a new PCB SUPPLY for AUMA 05.1 |  |  | Não
NCR-ICN-ESC-12-0542-2021 | P4168612 |  | REMOVE AND REWORK |  | REPAIR |  | REWORK | The pipe P4168612 EQ50001M2 is under traceability. The use of the weld on elbow is acceptable; The M01 has to indicate the 2 weld; The M03 manufacture has to indicate the traceability of the weld on elbow and the reference of NCR; The M03 of EQ50001M2 of SBr1 has to be analyzed regarding the pipe on board. ( No NCR seems to have be raised). David Bernerde | Sim
NCR-ICN-ESC-12-0543-2021 | P0126934 | KT03612 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Take those on of SBR 4 or 3, and the news will replace those take on SBR 3 or 4 |  |  | Sim | 91AE000D00038_2005
NCR-ICN-ESC-12-0543-2021 | P0131031 | KT03611 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Take those on of SBR 4 or 3, and the news will replace those take on SBR 3 or 4 |  |  | Sim | 91AE000D00041_2005
NCR-ICN-ESC-12-0544-2021 | P0109797 | KD05020 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109798 | KD05030 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109786 | KD03010 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109789 | KD03020 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109800 | KD06020 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109817 | KD06030 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109819 | KD06040 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109823 | KD06050 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0544-2021 | P0109824 | KD06060 | REWORK | Use the connectors provided for the SBR4 and direct the supply of the existing NCR-MAT to meet the need created in the SBR4. | REWORK | Naval Group asks ICN to open NCR MAT to provide connectors for SBR4. (Agathe BOYCE) |  |  | Não
NCR-ICN-ESC-12-0549-2021 | P0127095 | KT20951 | REWORK | USE THE SUPPLIED CONNECTOR FOR THE "SBR4" AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY. | REWORK | See Deliberação N1 |  |  | Não
NCR-ICN-ESC-12-0551-2021 | P0112997 | HE00181 | REWORK | Commisioning will remove the valves and Mechanical team will soften the valve | REPAIR | The soften of the internal surface of the valves HE00162, HE00180, HE00181 can be extend on the SBR2, SBR3 and SBR4. |  |  | Não
NCR-ICN-ESC-12-0551-2021 | P0112976 | HE00180 | REWORK | Commisioning will remove the valves and Mechanical team will soften the valve | REPAIR | The soften of the internal surface of the valves HE00162, HE00180, HE00181 can be extend on the SBR2, SBR3 and SBR4. |  |  | Não
NCR-ICN-ESC-12-0551-2021 | P0112985 | HE00162 | REWORK | Commisioning will remove the valves and Mechanical team will soften the valve | REPAIR | The soften of the internal surface of the valves HE00162, HE00180, HE00181 can be extend on the SBR2, SBR3 and SBR4. |  |  | Não
NCR-ICN-ESC-12-0553-2021 | P0131327 | DP00375 | REWORK | 1. Repair the internal thread M22x1mm to M24x1mm and manufacture new SCREW (MAT214-1488_Ref. 7) and NUT (MAT214-1488_Ref. 8) accordingly. NG must inform the material specification. The piece can be used in SBR 4 after repair. 2. If the material is not available, take the piece from SBR 4 and install in SBR 2. Pay attention with the traceability. Open NCR-MAT to supply a new complete set for SBR 4. | REWORK | Use material of SBR4 in SBR2. Pay attention of the traceability . 2 solutions for the damaged M22/1: 1) Repair: Modify the M22/1 by M24/1 and open one NCR-MAT in order to supply a new screw and nut M24/1 This screw have an air hardening operation and a tempering process. Modify the torque for the assembly time. 2) Scrap: Open one NCR MAT in order to supply new material for SBR4 Item 7/8/9/10 of MAT214-1489 Send to level 3 for decision | REWORK | Destroy the damaged part. Taken from SBR4 to serve SBR2. Open an NCR MAT in connection with this NCR ESC for restocking of REP: 7/8/9/10 of MAT214-1488 / 9 | Não
NCR-ICN-ESC-12-0554-2021 | P0129485 | KT00528 | REWORK | During the leak test (S02 PTRH) on the pneumatic lines, some leakage was identified. Some connections were opened to check the presence of o'rings and rush seal. On the air distribution panel (KT00528/P0129485/10AC000D00006) it was verified the absence of o'rings and rush seal on some connections. Solution: Put the rush seal on the connections and the o'rings on the niples: 1) 03 units of ruch seals: 44JO312D00002; 2) 09 units of o-rings: 44JO110D00009. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0555-2021 | P0107806 | DV00043 | REWORK | Dismount completely the valve DV00043-P0107806 (01PM300D00007-SN.17/010-ISSARTEL)-REV.B of the hull submarine and redo the mounting using a new valve. Redo the steps following the sequence of mounting and inspections: Mount the valve in hull filling the B11.19 > dismount the internal parts of the valve how indicated in SBR-ETM-00000M0007 > do S03_DVZ0003, B02_DV00073 and B02_DV01033 > remount the internal parts remembering to fill the B11.27 > do S02_DVZ00003 and B02_DV00043 > do new B07 and attach, in B05 book, the declaration of material conformity corresponding. | REWORK | In accordance with level 2.1 proposal. For locking the NRV nut inside hull, ICN can manufacture specific tab lock washer according to drawing in annex "Washer for DV NRV.pdf" : - material : X6CrNiTi18-10 - thickness : 1,5 mm Please add the material certificate and tab washer conformity in annex of NCR and in traceability file. (Fabien RENVOISE) | REWORK | In accordance with level 2.2 proposal. Raise a NCR MAT to manage the repairing of the NRV 17/010 damaged. Raise a NCR Regress to manage the inspections to be redone. | Sim | SN.17/010
NCR-ICN-ESC-12-0556-2021 | P0112997 | HE00181 | REPAIR | Repair Valve Support, in order to be able to fix the valve in its support. | REWORK | The work already done accordlying FTG-9491 attachment |  |  | Não
NCR-ICN-ESC-12-0556-2021 | P0112976 | HE00180 | REPAIR | Repair Valve Support, in order to be able to fix the valve in its support. | REWORK | The work already done accordlying FTG-9491 attachment |  |  | Não
NCR-ICN-ESC-12-0557-2021 | P0115551 | DJ12513N | REMOVE AND REPAIR | It is necessary to remove the sensor to perform a new calibration. Replace it with one already calibrated. | REMOVE AND REPAIR | In accord with ICN for replace sensor SBR1 with a new sensor (warehouse) Do a Recalibration sensor SBR1 If the sensor sbr1 after recalibration is not satisfaction replace the sensor Open NCR regress |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121722 | ER62501R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121730 | ER62514R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121731 | ER62513R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121729 | ER62512R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121724 | ER62511R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121723 | ER62509R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121725 | ER62507R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0559-2021 | P0121728 | ER62515R | REWORK | PROVIDE NEW CONNECTORS. | REWORK | check availability at the store, take on SBR4, if in stock. open a NCR-MAT to supply lost connectors |  |  | Não
NCR-ICN-ESC-12-0560-2021 | P0106979 | DT14120N | REMOVE AND REWORK | ICN suggests to perform the standard exchange of the level sensors or replace their internal components. | REMOVE AND REWORK | The 3 sensors delivered by the supplier PROTAIS/VIGIL (level sensor 20028 with expansion) are not working well. Take 3 new sensors in RMS stock. CMD: 50DD500D00012 NGD: 0870118236680 Open NCR MAT to repair the 3 sensors with new internal parts. Attached pictures of internal part who is not working. |  |  | Não
NCR-ICN-ESC-12-0560-2021 | P0106980 | DT14220N | REMOVE AND REWORK | ICN suggests to perform the standard exchange of the level sensors or replace their internal components. | REMOVE AND REWORK | The 3 sensors delivered by the supplier PROTAIS/VIGIL (level sensor 20028 with expansion) are not working well. Take 3 new sensors in RMS stock. CMD: 50DD500D00012 NGD: 0870118236680 Open NCR MAT to repair the 3 sensors with new internal parts. Attached pictures of internal part who is not working. |  |  | Não
NCR-ICN-ESC-12-0560-2021 | P0106981 | DT14320N | REMOVE AND REWORK | ICN suggests to perform the standard exchange of the level sensors or replace their internal components. | REMOVE AND REWORK | The 3 sensors delivered by the supplier PROTAIS/VIGIL (level sensor 20028 with expansion) are not working well. Take 3 new sensors in RMS stock. CMD: 50DD500D00012 NGD: 0870118236680 Open NCR MAT to repair the 3 sensors with new internal parts. Attached pictures of internal part who is not working. |  |  | Não
NCR-ICN-ESC-12-0562-2021 | P0117256 | KT63480D | REWORK | USE A NEW CABLE FROM ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR NEW SUPPLY. | REWORK | Change and redo connectorization |  |  | Não
NCR-ICN-ESC-12-0561-2021 | P0113082 | KE20021 | AGREE WITH LEVEL 2.1 | ICN request authorization to apply the ones from SBR3. | NCR CANCELLED | Missing pipes were delivered. Find in warehouse under : SMB2-MA20-DB1/05 0 52 19AM000D00140_2020 "T" INTERFACE BOARD LINK SMB2-MA20-DB1/05 0 53 19AM000D00140_2021 "P" INTERFACE BOARD LINK (Fabien RENVOISE) |  |  | Não
NCR-ICN-ESC-12-0561-2021 | P0113083 | KE20022 | AGREE WITH LEVEL 2.1 | ICN request authorization to apply the ones from SBR3. | NCR CANCELLED | Missing pipes were delivered. Find them in warehouse under : SMB2-MA20-DB1/05 0 52 19AM000D00140_2020 "T" INTERFACE BOARD LINK SMB2-MA20-DB1/05 0 53 19AM000D00140_2021 "P" INTERFACE BOARD LINK (Fabien RENVOISE) |  |  | Não
NCR-ICN-ESC-12-0563-2021 | P0113896 | DY00304 | SCRAP AND RE-MANUFACTURE |  | SCRAP | The leak rate is about 2bar/minute To canibalize a 250-45 bar air pressure reducing valve 18DP000D00007 on SBR4 To initiate a NCR MAT |  |  | Não
NCR-ICN-ESC-12-0582-2021 | P0119602 | EL00002 | REWORK | It's important highlight that this break problem with the screw fan cover probably occured cause someones constantly stepped on it, walking inside of the aft auxiliary room, at the time that the clean (EL00001) and dirty (EL00002) oil electrical pumps stay at the way in A130. And as this cover works like a protection of the fan, it should be mounting well and properly fixed. For it use 8 units of the screw 5305143973525 - STAINLESS SCREW H M5X8X8, 4 to each fan cover pump. And ICN team should sensitize our team with this case. The QC team should do a vibration analizes during the test F03_ELZ0003 or STW tests to grant that the noise limits is within tolerance. | REWORK | request the assistance of the mechanical specialist to extract the broken screw |  |  | Não
NCR-ICN-ESC-12-0582-2021 | P0119848 | EL00001 | REWORK | It's important highlight that this break problem with the screw fan cover probably occured cause someones constantly stepped on it, walking inside of the aft auxiliary room, at the time that the clean (EL00001) and dirty (EL00002) oil electrical pumps stay at the way in A130. And as this cover works like a protection of the fan, it should be mounting well and properly fixed. For it use 8 units of the screw 5305143973525 - STAINLESS SCREW H M5X8X8, 4 to each fan cover pump. And ICN team should sensitize our team with this case. The QC team should do a vibration analizes during the test F03_ELZ0003 or STW tests to grant that the noise limits is within tolerance. | REWORK | request the assistance of the mechanical specialist to extract the broken screw |  |  | Não
NCR-ICN-ESC-12-0564-2021 | P0119589 | EL00012 | REWORK | Check the possibility of installing another pressure differential device from other SBR and open a NCR-MAT to request a new device. | REWORK | To canibalize on SBR4 a clugging indicator (Rep 6 on SBR-ETM-00000M0011 rev.C page 236/636) for fillter EL00012 (18FL200D00001) To create a NCR MAT to provide a new item. |  |  | Não
NCR-ICN-ESC-12-0565-2021 | P0101583 | OO02500 | REWORK | ICN suggests to take the dongles (C79459-A1715-B21) from SBR3 MCS pack and instal on SBR2. | REPAIR | Normally, these 3 dongles should be mounted by the manufacturer. In the CoC, these 3 dongles were declared mounted. Naval Group FO agrees with ICN proposal to take it from boat 3. Send to Naval Group BO supply chain to provide the 3 missing dongles (Siemens ref C79459-A1715-B210). | REWORK | 5 dongles will be replenished in RMS. Edit a NCR MAT | Sim
NCR-ICN-ESC-12-0567-2021 | P0105343 | ME00001 | MANUFACTURE |  | REWORK |  |  |  | Sim | 18DL000D00080
NCR-ICN-ESC-12-0570-2021 | P0141080 | KO60511B | REWORK | USE THE SUPPLIED CONNECTOR FOR ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR A NEW SUPPLY OF THIS CONNECTOR. | REWORK | Naval Group suggest ICN to use another connector from another SBR and edit NCR-MAT. |  |  | Não
NCR-ICN-ESC-12-0568-2021 | P0105161 | DM20002 | REWORK | Wait for NG orientation |  |  |  |  | Sim | 18LF100D00003-25804-5259905
NCR-ICN-ESC-12-0568-2021 | P0120024 | EN20005 | REWORK | Wait for NG orientation |  |  |  |  | Sim | 18LF100D00003-24617-5259905
NCR-ICN-ESC-12-0569-2021 | P4148846 |  | REMOVE AND REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0569-2021 | P4148861 |  | REMOVE AND REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0571-2021 | P0102205 | BB02505 | REWORK | The computer started to have problems as soon as it was available, even without long use. As it will be delivered to the customer in the future, I suggest replacing it. | REPAIR | The computer shall be repaired. Also, this computer will be removed from the use of SBR, because it is very fragile. ICN can continue to use this computer as a tool, removing its name of BB02505 A new computer has been delivered for SBR2 which be name BB02505. ICN to open an NCR MAT to follow the process. |  |  | Não
NCR-ICN-ESC-12-0575-2021 | P0146853 | AM00003S | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Não
NCR-ICN-ESC-12-0575-2021 | P0133574 | BD00013 | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Sim | S000216509
NCR-ICN-ESC-12-0575-2021 | P0133575 | BD00014 | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Sim | S000216508
NCR-ICN-ESC-12-0575-2021 | P4151297 |  | REWORK | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. | REWORK | See N2 |  |  | Não
NCR-ICN-ESC-12-0575-2021 | P4151886 |  | REWORK | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. | REWORK | See N2 |  |  | Não
NCR-ICN-ESC-12-0575-2021 | P4151881 |  | REWORK | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. | REWORK | See N2 |  |  | Não
NCR-ICN-ESC-12-0573-2021 | P4120895 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0574-2021 | P0141340 | AM00005 | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Não
NCR-ICN-ESC-12-0574-2021 | P0133571 | BD00015 | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Sim | S000216510
NCR-ICN-ESC-12-0574-2021 | P0133568 | BD00016 | OK - NOT MODIFIED |  | OK - NOT MODIFIED |  |  |  | Sim | S000216511
NCR-ICN-ESC-12-0574-2021 | P4151875 |  | REWORK | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. | REWORK | See N2 |  |  | Não
NCR-ICN-ESC-12-0574-2021 | P4129588 |  | REWORK | According to SMB-204507 the minimum longitudinal and transversal distances are not in compliance. | REWORK | See N2 |  |  | Não
NCR-ICN-ESC-12-0580-2021 | P0122916 | EV20304 | REMOVE AND REWORK |  | REPAIR | apply 44BO220D00141 |  |  | Não
NCR-ICN-ESC-12-0580-2021 | P0138023 | EV22019 | REMOVE AND REWORK |  | REPAIR | to apply 44BO220D00141 |  |  | Não
NCR-ICN-ESC-12-0580-2021 | P0123094 | EV22020 | REMOVE AND REWORK |  | REPAIR | to apply 44BO220D00141 |  |  | Não
NCR-ICN-ESC-12-0580-2021 | P0123202 | EV22025 | REMOVE AND REWORK |  | REPAIR | to apply 44BO220D00144 |  |  | Não
NCR-ICN-ESC-12-0580-2021 | P0123186 | EV22102 | REMOVE AND REWORK |  | REPAIR | to apply 44BO220D00141 |  |  | Não
NCR-ICN-ESC-12-0583-2021 | P0131520 | MB00003 | REWORK | Agree with action 1.2. Disassemble the PELA - AP435534 and remove its parts according to annex A, install it in the AP402618 SBR 2. Replace all the items per new listed in ANNEX B. Perform a new hydrostatic test to validate the assembly. | REWORK | Install items (REF: MAT422-0109): REP 2 TIGHTNESS PIECE, REP 28 POLISHED SURFACE-CARBON FRICTION SUB-ASSEMBLY of PELA 2 with the PELA 3 on SBR2. Use new O-ring (REP 46/9/34/11/13/29/35) for assembly and perform test (70 bar and 52,5 bar) to validate the new assembly. Record all the numbers of each item for traceability. Send in level 3 for validation | REWORK | Agreement for the use of the polished surface-carbon assembly of PELA 2 with PELA 3 mounted on SBR2. ICN has to ensure a follow-up of the traceability files of each PELA. NG will replenish item 13 NGD 5331145330432 O-RING 493,00X7,00 20A8-AN in quantity 2 (for use on SBR3 and SBR4). Other components of ANNEX B will be replenished through NCR-MAT-001859-2021. | Sim | 15PE000D00001
NCR-ICN-ESC-12-0584-2021 | P0118888 | RM00058 | REPAIR | Provide the connectors. | REWORK | DEI-331623-80500-12-007 / DEI-200551-80500-12-014 are ICN job orders, they are not material definition documents. Look for missing connectors at the store. |  |  | Não
NCR-ICN-ESC-12-0584-2021 | P0118950 | RM00087 | REPAIR | Provide the connectors. | REWORK | DEI-331623-80500-12-007 / DEI-200551-80500-12-014 are ICN job orders, they are not material definition documents. Look for missing connectors at the store. |  |  | Não
NCR-ICN-ESC-12-0586-2021 | P0117352 | RC60014D | REWORK | Provide a new connector. | REWORK | Check if connector D38999-26-W-J-29-PN is available on SBR4 Open an NCR-MAT to supply a new connector |  |  | Não
NCR-ICN-ESC-12-0589-2021 | P0136276 | FR12503 | REWORK | Rework as described. perform the installation of equipment with pending component according to NCR-ICN-ESC-11-1034-2020. From the NCR-MAT-001120-2020 take the components and complete the installation on board. | REMOVE AND REWORK | Agree with Deliberaçao N1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110072 | KT10127P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110074 | KT10227P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110075 | KT10327P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110076 | KT10427P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110086 | KT00327 | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110089 | KT01027 | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0110090 | KT01127 | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0129435 | KT10128P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0129437 | KT10228P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0129438 | KT10328P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0129439 | KT10428P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0114173 | KT11047P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0114174 | KT11147P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0115743 | KT11048P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0115745 | KT11148P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0116346 | KT10618P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0130319 | KT10617P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117557 | KT15075P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117568 | KT15073P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117583 | KT15071P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117589 | KT14071P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117160 | KT15086P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117198 | KT15082P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0587-2021 | P0117171 | KT15084P | REWORK | Putting sealing gasket and fixing the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0590-2021 | P0123284 | KT08371 | REWORK | Rework, perform the installation with new equipment on board to meet the SBR2 construction process. Open the NCR MAT to complement the other SBR. | REWORK | The lost of this limit switch is attributable to ICN; Naval Group suggests to edit NCR MAT in order to use this kind of limit switch from another SBR (3 or 4). |  |  | Não
NCR-ICN-ESC-12-0593-2021 | P0140390 | DB02501 | REWORK | Rework. Perform the assemble of the 53B-DB02501 equipment with the new item 53B-DB02501S - 53B-P4124785 - CMD 14SE300D00084 - CABLE SHOCK ABSORBERS HELICAL-TYPE 20-15 as specified. NG Please check the project specifications if it changes. | REWORK | Assembly with the material with the CMD:14SE300D00006 like SBR1 |  |  | Não
NCR-ICN-ESC-12-0595-2021 | P0118398 | KF62506I | REWORK | Use the supplied cable for another Submarine and open an "NCR-MAT" for a new supply. | REWORK | Replace with a new cable. |  |  | Não
NCR-ICN-ESC-12-0591-2021 | P0143078 | BE0300AM | REWORK | Use the equipment provided for another Submarine and open an "NCR-MAT" for a new supply. | REWORK | Agree with decision N1. Use one available. Open a NCR-MAT to supply a nes one 11BR000D00013 |  |  | Não
NCR-ICN-ESC-12-0592-2021 | P0108667 | RF00008 | ACCEPT AS IT IS |  | REWORK | NCR REGRESS have to be raise NCR MAT have to be raise to order new spare parts changed during dismounting (gasket, lock washers..) |  |  | Não
NCR-ICN-ESC-12-0594-2021 | P4168612 |  | REWORK |  | REPAIR | It´s not aload to weld new seating on the tank after strenght test. Naval-group /TA propose to Use the seating P4170165 to weld the clamp P4502764 Adapt the clamp if necessary. | ACCEPT AS IT IS | The new geometry of the pipe makes it pass close to the clamping 01CA000F00016 / P4501894 and allows it to be supported on this clamping. This solution eliminates the need to attach a new clamping to the EQ trunk and has no impact on the validation tests. | Sim
NCR-ICN-ESC-12-0596-2021 | P0112581 | DY00001 | SCRAP | Scrap and replace by a new one | SCRAP | The belt was replaced on the compressor DY00200. Need to create a NCR-MAT to refund the SBR3 (Girodin Sauer ref. - Compressor belt Part Nr: 01200231) - NGD 0930930267103. Scrap the old belt. |  |  | Não
NCR-ICN-ESC-12-0600-2021 | P4169456 |  | REWORK |  | REWORK | Rework, rework as per original, carry out the NDT required |  |  | Não
NCR-ICN-ESC-12-0603-2021 | P0128216 | FC00525 | REWORK | Rework the assembly and positioning of the MN45-60 see DEI-000000-80500-12-181 page 5. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 0930930250275/FC00525_2
NCR-ICN-ESC-12-0602-2021 | P0111174 | KT02211 | AGREE WITH LEVEL 2.1 | Prepare an NCR-MAT to request the material for NG. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0604-2021 | P0156214 | DA02000H | REWORK | Rework compression of damper disks to specified tolerance. (9.1mm to 11.5mm). | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0605-2021 | P4156613 |  | REWORK | Equipment mounted without resilient mount - Rework | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0606-2021 | P0142323 | EJ00007 | REWORK | Equipment mounted without resilient mount - Rework | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 087/13-03
NCR-ICN-ESC-12-0608-2021 | P4173080 |  | REMOVE AND REWORK | According to field description, incorrect material applied. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0609-2021 | P4183657 |  | REWORK | Rework in accordance with SMB-200949 and see tolerances for mount MN03_14 (8.4mm to 10.7mm). | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0610-2021 | P0113896 | DY00304 | SCRAP | Cannot be calibrated due to lack of seal in conic screw tip | REPAIR | The reducing pressure valve DY00304 - 18DP000D00013 (serial number: 20163001) was already replaced onboard regarding the NCR-ICN-ESC-11-0563-2021, by a new one valve (serial number: 20150909). The new reducing pressure valve is also not good. The valve was calbrated to reduce the pressure from 245 to 45 bar, but onboard, the pressure not stabilized and increase up at 45 bar. Perform a new standard exchange of the valve. Create a NCR-MAT to repair the valve and refund yhe stock. Create a NCR REGRESS to manage the inspections and tests to redo. |  |  | Não
NCR-ICN-ESC-12-0612-2021 | P0131182 | KT00010 | REWORK | For the assembly and adjustment of link arm of bow shutters TLT 5. The link arm 53B-KT00155 - P0130899 CMD 14CD000D00069 - According MAT321-0072 and MAT321-0073, perform to adjust the length total to 1816,00 mm. For the adjustment of link arm, use the machining and to cut 10mm from the extrem and open the thread in 13mm. See annex 2. | REPAIR | Agree with proposal to machine the connecting rod to allow the correct adjustment. |  |  | Não
NCR-ICN-ESC-12-0612-2021 | P0130899 | KT00155 | REWORK | For the assembly and adjustment of link arm of bow shutters TLT 5. The link arm 53B-KT00155 - P0130899 CMD 14CD000D00069 - According MAT321-0072 and MAT321-0073, perform to adjust the length total to 1816,00 mm. For the adjustment of link arm, use the machining and to cut 10mm from the extrem and open the thread in 13mm. See annex 2. | REPAIR | Agree with proposal to machine the connecting rod to allow the correct adjustment. |  |  | Não
NCR-ICN-ESC-12-0614-2021 | P4156293 |  | ACCEPT AS IT IS | To resolve the issue, ICN proposes to accept it as is, as described in NCR-ICN-UFEM-12-0409-2019. and perform the radiographic inspection procedure as if they were category "A" tubes, for products P4153061, P4153059, P4156293, P4128926 and P4156292 see attached list | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0616-2021 | P4029629 |  | REWORK |  | REPAIR | Cut as per annex 10 Install the new pipe build up the removed part of the seating Ajust on board check with the bottle Weld 100% VT and 100% LP Weld |  |  | Não
NCR-ICN-ESC-12-0617-2021 | P0137393 | FQ10400P | REWORK | Install new pressure gauges for the SBR2. 1) New pressure gauge in ref. 53B-FQ10400P - P0137393 - CMD 50MD200D00030 - PRESSURE MANOMETER CONCERNING 0 TO 4BAR M20 STAINLESS TYPE. 2) New pressure gauge ref. 53B-FQ10500P - P0137386 - CMD 50MD200D00034 - RELATIVE PRESSURE MANOMETER 0 TO 60 BAR M20 STAINLESS STEEL TYPE A. Open NCR MAT. | REWORK | Agree with proposal. |  |  | Não
NCR-ICN-ESC-12-0617-2021 | P0137386 | FQ10500P | REWORK | Install new pressure gauges for the SBR2. 1) New pressure gauge in ref. 53B-FQ10400P - P0137393 - CMD 50MD200D00030 - PRESSURE MANOMETER CONCERNING 0 TO 4BAR M20 STAINLESS TYPE. 2) New pressure gauge ref. 53B-FQ10500P - P0137386 - CMD 50MD200D00034 - RELATIVE PRESSURE MANOMETER 0 TO 60 BAR M20 STAINLESS STEEL TYPE A. Open NCR MAT. | REWORK | Agree with proposal. |  |  | Não
NCR-ICN-ESC-12-0618-2021 | P0110035 | KD07010 | REWORK | The equipment 53B-KD07010 and 53B-KD07020 SBR 2, was removed and installed in SBR1 as per NCR-ICN-ESC-11-1480-2021. Perform the installation of new one equipment on board to attend the construction process of the SBR 2. Take the equipment of SBR 4 to install in SBR 2. Ref. CC-200716-30700-12-009 1) Item 1 - 53B-KD07010 - P0110035 - CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM 2) Item 30 - 53B-KD07020 - P0110031 – CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM Open NCR MAT for material replacement. | AGREE WITH LEVEL 2.1 |  |  |  | Não
NCR-ICN-ESC-12-0618-2021 | P0110031 | KD07020 | REWORK | The equipment 53B-KD07010 and 53B-KD07020 SBR 2, was removed and installed in SBR1 as per NCR-ICN-ESC-11-1480-2021. Perform the installation of new one equipment on board to attend the construction process of the SBR 2. Take the equipment of SBR 4 to install in SBR 2. Ref. CC-200716-30700-12-009 1) Item 1 - 53B-KD07010 - P0110035 - CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM 2) Item 30 - 53B-KD07020 - P0110031 – CMD 11TD300D00147 - TORPEDO INTERFACE MODULE TIM Open NCR MAT for material replacement. | AGREE WITH LEVEL 2.1 |  |  |  | Não
NCR-ICN-UFEM-12-0551-2021 | N/A |  | REWORK |  | ACCEPT AS IT IS | Accepted as it is |  |  | Não
NCR-ICN-ESC-12-0621-2021 | P0101609 | OO24301 | REWORK | Provide a new module to continue the construction process. | REWORK | Replace the broken module Open an NCR-MAT to provision a new one |  |  | Não
NCR-ICN-ESC-12-0625-2021 | P0106674 | DP00204 | REWORK | ICN added the ANNEX 2 file with corrective suggestions for Naval Group verification, which consists on: (1) Reduce the length of the remote control support or/and (2) Reduce the length of the screw thread of the slide valve shaft. | REWORK | 1) Concerning the axis of DP00204, we can cut a part of the threaded rod of the distributor necessary to keep 11,5 mm in engagement (10 mm of threads + 1.5 mm of bevel) + the lenght to instal the lock nut. ICN must write the real value of the threaded in engagement in the NCR level 3 and the lenght of the threaded cutting. 2) we can also reduce the length of the remote control support => maximum 3mm |  |  | Não
NCR-ICN-ESC-12-0626-2021 | P0101413 | OO02534 | REMOVE AND REWORK | ICN replaced the damaged card applying the respective item from SBR3 (OO02534). | REMOVE AND REWORK | Agree with deliberacao N1 Change the module X32 phoenix contact MINI MCR-SL-RPS-I-I-SP. Open NCR MAT to refund the module taken on OO02534 sbr3. NGD: 5963930154491 |  |  | Sim
NCR-ICN-ESC-12-0627-2021 | P0105754 | DB00114 | AGREE WITH LEVEL 2.1 | Replace valve by a new one. | REPAIR | The distributor DB00114-18SC173D00001 (serial number: 15/002, pilot stage: 15/007) presents leakage at the ports P1 and U1 in standby position. In standby position, normally, the air cannot pass from A1 cannot pass to U1 and P1. This wrong passage of air can be explain by o-ring damaged (items 3, 4, 7, 8, 17, 18 ? on the drawing added in the NCR). Proceed to a standard exchange of the distributor. Create a NCR MAT to manage the expertise and the reparation. Create a NCR REGRESS to manage the inspections and tests to redo. |  |  | Não
NCR-ICN-ESC-12-0629-2021 | P0110250 | KT02517 | REMOVE AND REWORK | It is necessary to change by new one from SBR3 or SBR4 and raise a NCR MAT. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0629-2021 | P0116321 | KT02518 | REMOVE AND REWORK | It is necessary to change by new one from SBR3 or SBR4 and raise a NCR MAT. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0629-2021 | P0130346 | KT02217 | REMOVE AND REWORK | It is necessary to change by new one from SBR3 or SBR4 and raise a NCR MAT. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0629-2021 | P0116312 | KT02218 | REMOVE AND REWORK | It is necessary to change by new one from SBR3 or SBR4 and raise a NCR MAT. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0634-2021 | P0106089 | ME03101 | REWORK | I suggest performing the tests described in document 6EM21458 and after verification, replace the referring card or power plate according to the test result. |  |  |  |  | Sim
NCR-ICN-ESC-12-0635-2021 | P0155116 | BD00016H | AGREE WITH LEVEL 2.1 | ICN Preservation Team requests NG orientation on how to proceed to fix the issue. |  | To repair this part I suggest one intervention of MTU (Laurent J. C. - 23/09/2020) |  | MTU GERMANY will be consulted first, because the engine is still under warranty until 04/15/2021. Kindly make a more precise photos report on the degraded area to optimize MTU's future intervention. (EUSTACHE. J - 18/12/2020) | Não
NCR-ICN-ESC-12-0638-2021 | EASS0000870 |  | REPAIR | Probable retraction of mastic CLR. We suggest don use of manual CLR. | REWORK | Remove the mastic with dommage, re-do a new joint with CLR mastic |  |  | Não
NCR-ICN-ESC-12-0638-2021 | EASS0000871 |  | REPAIR | Probable retraction of mastic CLR. We suggest don use of manual CLR. | REWORK | Remove the mastic with dommage, re-do a new joint with CLR mastic |  |  | Não
NCR-ICN-ESC-12-0638-2021 | EASS0000894 |  | REPAIR | Probable retraction of mastic CLR. We suggest don use of manual CLR. | REWORK | Remove the mastic with dommage, re-do a new joint with CLR mastic |  |  | Não
NCR-ICN-ESC-12-0639-2021 | P0115743 | KT11048P | REWORK | It is necessary to put another one. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0639-2021 | P0115745 | KT11148P | REWORK | It is necessary to put another one. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0640-2021 | P4166955 |  | REMOVE AND REWORK | ICN requests that NG accept the modifications, so that the modifications can be updated via NCR or update the project again, as without one of these options we cannot reissue the CTE's of unofficial documents. see attached. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0640-2021 | P4184016 |  | REMOVE AND REWORK | ICN requests that NG accept the modifications, so that the modifications can be updated via NCR or update the project again, as without one of these options we cannot reissue the CTE's of unofficial documents. see attached. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0122151 | EG01140 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG01140 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0136467 | EG01120 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG01120 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0122048 | EG00110 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG00110 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0122063 | EG00234 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG00234 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0122044 | EG00130 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG00130 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0643-2021 | P0143452 | EG00143 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the EG00143 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0645-2021 | P0126752 | EW00010 | REWORK | Use the electrical connection base of these same equipment supplied for the “SBR4” and open an “NCR-MAT” for a new supply. | REWORK | Replace the motor of the EW0010 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0646-2021 | P0119505 | RA00011 | REMOVE AND REPAIR | replace the visor | REMOVE AND REWORK | -Take a glass from SBR 3 or 4 -Issue a NCR MAT for replenishment -Apply TAF-2015-0582 and TAF-2017-0827 for material and equipment protection. |  |  | Não
NCR-ICN-ESC-12-0647-2021 | P0145201 | EJ00006 | REWORK | Carry out instalation of a new one equipment EJ00006 – CMD 22RE000D00100. Open NCRMAT of material supply to SBR2. |  |  |  |  | Não
NCR-ICN-ESC-12-0649-2021 | P0131917 | HL22100D | REWORK | 1. Remount the cable HL22100D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB36010; B25, B13 and B07 for cable HL22100D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | N/A
NCR-ICN-ESC-12-0650-2021 | P0131858 | HL22102D | REWORK | 1.Remount a new cable HL22102D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B06 and B07 for hatch HL40053; B25, B13 and B07 for cable HL22102D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. 2. Open a NCR-MAT to send the damaged cable to repair. It’s important always having a new spare cable of hull leak to be used on demand. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | N/A
NCR-ICN-ESC-12-0650-2021 | P0131825 | HL40053 | REWORK | 1.Remount a new cable HL22102D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B06 and B07 for hatch HL40053; B25, B13 and B07 for cable HL22102D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. 2. Open a NCR-MAT to send the damaged cable to repair. It’s important always having a new spare cable of hull leak to be used on demand. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | C0001
NCR-ICN-ESC-12-0651-2021 | P0131859 | HL22103D | REWORK | 1.Remount the cable HL22103D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL44030; B25, B13 and B07 for cable HL22103D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | N/A
NCR-ICN-ESC-12-0651-2021 | P0194592 | HL44030 | REWORK | 1.Remount the cable HL22103D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL44030; B25, B13 and B07 for cable HL22103D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | N/A
NCR-ICN-ESC-12-0652-2021 | P0131860 | HL22104D | REWORK | 1.Remount the cable HL22104D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB32501; B25, B13 and B07 for cable HL22104D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. |  |  | Sim | N/A
NCR-ICN-ESC-12-0653-2021 | P0131861 | HL22105D | REWORK | 1.Remount a new cable HL22105D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do M12 or similar and B07 for mobile AB36010; B25, B13 and B07 for cable HL22105D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. 2. The manufacturing of the item 1 will solve the problem reported by NCR-MAT-001742-2021, which are blocking all the CMD cable 11LS572D00118 because it has reached the expiry date. 3. Open a NCR-MAT to send the damaged cable to repair. It’s important always having a new spare cable of hull leak to be used on demand. | REWORK | Open a NCR-MAT to send the HL22105D cable as soon as possible (risk of blocking point for SBR3) to the BO for expertise and repair if possible> Use a new cable 11LS572D00118 for SBR2 | REWORK | In accordance with proposal Raise NCR regress for inspections (there is no B07 inspection for AB36010) | Sim | N/A
NCR-ICN-ESC-12-0654-2021 | P0131920 | HL22124D | REWORK | 1.Remount the cable HL22124D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B25, B13 and B07 for cable HL22124D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided. |  |  | Sim | N/A
NCR-ICN-ESC-12-0655-2021 | P0131856 | HL22101D | REWORK | 1.Remount the cable HL22101D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL42087; B25, B13 and B07 for cable HL22101D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided |  |  | Sim | N/A
NCR-ICN-ESC-12-0655-2021 | P0131834 | HL42087 | REWORK | 1.Remount the cable HL22101D on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B11.19 and B07 for mobile HL42087; B25, B13 and B07 for cable HL22101D and; the B06 and B07 for bolting hatch HL40080 will be done on NCR-ICN-ESC-12-0648-2021. | REWORK | Agree with proposal. If new spare parts were taken from store a NCR MAT will be raise. For parts manufactured the material certificate have to be provided |  |  | Sim | N/A
NCR-ICN-ESC-12-0656-2021 | P0104562 | BH10007N | REWORK | For the level indicator equipment 53B-BH10007N - 53B-P0104562 - CMD 50MD500D00015 - LEVEL INDIC. TAP ED 15MM. The sealing rubber that damaged, perform change a new one sealing rubber NGD: 5330143029900. same solution to NCR-ICN-ESC-12-0443-2021. Take a new-one in the stock (NGD: 5330143029900) to remount onboard. If no stock canibalize SBR3 or SBR4 and create a NCR-MAT to refund the stock. |  |  |  |  | Não
NCR-ICN-ESC-12-0657-2021 | P0154292 | FA22004 | REPAIR |  | REPAIR | performed the FTG-9312. It's the same thing of SBR1 (NCR-ICN-ESC-11-1264-2020) |  |  | Não
NCR-ICN-ESC-12-0657-2021 | P0154298 | FA22006 | REPAIR |  | REPAIR | performed the FTG-9312. It's the same thing of SBR1 (NCR-ICN-ESC-11-1264-2020) |  |  | Não
NCR-ICN-ESC-12-0657-2021 | P0154297 | FA22005 | REPAIR |  | REPAIR | performed the FTG-9312. It's the same thing of SBR1 (NCR-ICN-ESC-11-1264-2020) |  |  | Não
NCR-ICN-ESC-12-0657-2021 | P0154299 | FA22007 | REPAIR |  | REPAIR | performed the FTG-9312. It's the same thing of SBR1 (NCR-ICN-ESC-11-1264-2020) |  |  | Não
NCR-ICN-ESC-12-0658-2021 | P4122496 |  | SCRAP | ICN proposes to discard spool P4122496 and clamp P4116375 to connect CAP P0147630 directly to the valve as well as the example of P0133276. | REPAIR | See FTG-9613. | REWORK | Temporarily: agreement to put a cap (CMD 44BO230D00259) directly on the valve P0104826. The pipe plan P4122496 will be updated to include CMD 18RO230D00632. However, ICN needs to open an NCR for SBR1 as it appears from the photo attached to the FTG that the valve, P0133272, which should be mounted uncoupled, is not. As per drawing SBH-PLM-3B10-000453 folio 1. Furthermore, this rigid mounting is not correct, the Ø19 holes should have been filled in before drilling the holes for the screws. | Não
NCR-ICN-ESC-12-0660-2021 | P0120841 | ER00052H | REWORK | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | REWORK | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  |  | Não
NCR-ICN-ESC-12-0660-2021 | P0120847 | ER00053H | REWORK | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | REWORK | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  |  | Não
NCR-ICN-ESC-12-0660-2021 | P0120850 | ER00054H | REWORK | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | REWORK | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  |  | Não
NCR-ICN-ESC-12-0660-2021 | P0120852 | ER00055H | REWORK | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | REWORK | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  |  | Não
NCR-ICN-ESC-12-0660-2021 | P0120901 | ER00210H | REWORK | The suggest taking the larger length screws and re-machine to the required length and thread. Supply new screws CMD 32VI120D00637 - SCREW H M14X120X34A4L-80 – Total: 24 units. | REWORK | Agree with level 1 This problem was already solve for other material.NCR-ICN-ESC-12-0409-2021. |  |  | Não
NCR-ICN-ESC-12-0661-2021 | P4121692 |  | REWORK |  | REWORK | Rework. Close the holes using SMB-200046 parameter, carry out 100% VT and 100%MT. Re-do the new holes. | REWORK | In accordance with level 2,2 proposal | Não
NCR-ICN-ESC-12-0662-2021 | P0115556 | DJ00002L | REMOVE AND REWORK | Substituir a placa de controle do atuador AUMA 7.1 por outra nova. | REMOVE AND REWORK | ICN in accordance with NG FO used the pcb control of the previous motor 05.1 to repair the new motor 07.1 who is not working in remote mode. Open NCR MAT to refund the pcb taken. Report attached in annex. |  |  | Não
NCR-ICN-ESC-12-0663-2021 | P0118606 | RM00001 | REWORK | Perform an upward offset of 20 mm in the Grounding Supports (BDM-00031571_Ref. 8 and Ref. 11) from the origin in order to increase the thickness of the resin chocking; Note: The resin thickness will be between 15mm to 20mm with the new positioning of supports. Counter mark the holes and drill the new threaded holes M16; Manufacture slotted set screws M16 CL 8.8 and fix with Loctite 270; Suggestion: Apply a layer of epoxy resin (for example: DEVCON) and grind to good profile; Apply painting according specific plan for the equipment. | REPAIR | Agree with proposal already applied for SBR1. Documentation will be updated. |  |  | Não
NCR-ICN-ESC-12-0664-2021 | P0130119 | DP00159 | REWORK | Rework. The steering rudder axiometric alignment must be redone. For adjustment, take the piece MAT214-1418_Ref. 29 (CMD 21AG000D00016 - CONNECTION PIECE) from SBR 3 or SBR 4. 1) Remove the connecting piece. 2) Align the rudder steering gear with the optical team support. 3) Perform a dimensional alignment inspection before installing the connecting piece part. 4) Carry out the machining of the connecting piece in the workshop; 5) Make the fitting and install the connecting piece. 6) Carry out the dimensional alignment inspection after installing the connecting piece before locking with the weld. 7) Once the alignment is approved, carry out the welding of the connection piece. 8) Perform the final dimensional inspection of the alignment of the Rudder Blades. Open NCR MAT to supply new part or material 80HLES to manufacture a new one. | REWORK | Agree with level 1. Use the TAF-TA-2019-1013 for ensure the process. Open one NCR-MAT for supply the material. ICN can confirm the alignment in the middle of the adjusting process (blue matching)to verify the good alignment of the rudder. |  |  | Não
NCR-ICN-ESC-12-0665-2021 | P0144849 | ES00020 | REPAIR |  | REPAIR | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  |  | Não
NCR-ICN-ESC-12-0665-2021 | P0144845 | ES00041 | REPAIR |  | REPAIR | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  |  | Não
NCR-ICN-ESC-12-0665-2021 | P0144844 | ES00042 | REPAIR |  | REPAIR | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  |  | Não
NCR-ICN-ESC-12-0665-2021 | P0144843 | ES00043 | REPAIR |  | REPAIR | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  |  | Não
NCR-ICN-ESC-12-0665-2021 | P0144839 | ES00044 | REPAIR |  | REPAIR | Replace the opening indicator of the valves ES00020 (18RT000D00050), ES00041, ES00042, ES00043, ES00044 (18RT000D00048). Need to buy complete handwheels (STAD, Article No: 52 186-003, EAN: 7318792834905) by the RMS file to repair these valves and to have a stock in Itaguai. |  |  | Não
NCR-ICN-ESC-12-0666-2021 | P0147267 | DP00192 | REWORK | Forward to Naval Group to assist ICN in order to repair or replace the damaged item | REWORK | Reconnect the cable DP24180D of the sensor DP14113 according to SMB-EQUIPMENT-P0131513 (wire white on pin1and wire pink on pin6). |  |  | Não
NCR-ICN-ESC-12-0667-2021 | P0137971 | DS14311 | REWORK | Replace the plug and open a NCR-Regress. | REWORK | Take a new the connector STRAIGHT PLUG VG95234 M 10SL 3SN. Follow handbook SMB-EQUIPMENT-P0137971 to reconnect it. Open NCR MAT to refund the connector taken. |  |  | Não
NCR-ICN-ESC-12-0669-2021 | P4148294 |  | MANUFACTURE | Remanufacture the spools according to the project. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0669-2021 | P4148293 |  | MANUFACTURE | Remanufacture the spools according to the project. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0669-2021 | P4147749 |  | MANUFACTURE | Remanufacture the spools according to the project. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0669-2021 | P4147748 |  | MANUFACTURE | Remanufacture the spools according to the project. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0669-2021 | P4148802 |  | MANUFACTURE | Remanufacture the spools according to the project. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0670-2021 | P0145852 | AG00019 | REWORK | For assembly of the hatch AG00019 with the balancing bearings AG00039 SBR2. Perform a new adjustment of the holes in the seating P4128742 provided for fitting the 12mm for 13mm diameter pins. The supports P4128742 (Drawing SBH.4D30.SAD.003126). Agree should only be drilled after mounting the panel and adjusting its position. Necessary the supply of four pins 13mm diameter new. Carry out the assembly the new pins in order. | REPAIR | Agree with proposal. On the SBH.4D30.SMD.003124 the 4 holes Ø12 0/+0,2 for pins are present, it's necessary to update this drawing to remove these 4 holes to allow the good positioning and drill after the mounting validated. | REWORK | Agreement with the solution proposed by LVL1 and validated by LVL2 for mounting on SBR2. Drawing SBH.4D30.SMD.003124 of seating P4128742 will be updated in BO to indicate that the holes for the positioning pins are to be counter-drilled on board during assembly. | Sim | 01PE200D00029
NCR-ICN-ESC-12-0671-2021 | P0102959 | DA10001N | REWORK | For equipment 53B- DA10001N - P0102959 - CMD 50MD500D00015 - INDIC. LEVEL TAP ED 15MM. Modification suggestion for the DA10001N equipment: Carry out the machining of 04 new Ø 16mm holes in the flange of DA10001N. This way, the flange will pass from 4 to 8 holes and it will be possible to rotate the equipment for on-board assembly. See annex 1. | REPAIR | Perform 4 new hole in the flange of thr DA10001N. Bend the tranparent spool to match with the good angle |  |  | Não
NCR-ICN-ESC-12-0673-2021 | P0148449 | EJ00017 | REWORK | Use the required component from the one supplied for the equipment "EJ00017" referring to the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Agree with decision N1 Used an 50TA000D00157 available Open a NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0675-2021 | P0103207 | BE0900BA | REWORK | Exchange the complete equipment supplied to the SBR4 and open an "NCR-MAT" for a new supply. | REWORK | NCR-ICN-ESC-11-1465-2021 is treating the issue. It was asking to dismount the switch BE0900BA on sbr3or sbr4 but ICN dismount on sbr2. ICN commissioning should replace the switch with the one of sbr4 to solve this NCR. NCR-MAT-001542-2021is already open to refund the item. |  |  | Não
NCR-ICN-ESC-12-0676-2021 | N/A |  | ACCEPT AS IT IS | Accept as it is. The current position of the valve has been adjusted to suit assembly of the pipe P4164088. | ACCEPT AS IT IS | Agree with proposal. A checking of the good shutting of BQ00005 will be carry out during the B02BQZ0011 and S02BQZ0004 |  |  | Não
NCR-ICN-ESC-12-0677-2021 | N/A |  | ACCEPT AS IT IS | Accept as it is. The current position of the valve has been adjusted to suit assembly of the pipe P4164085. | ACCEPT AS IT IS | Agree with proposal. A check of the good closing of BQ00006 will be carry out during the B02BQZ0009 and S02BQZ0003 |  |  | Não
NCR-ICN-ESC-12-0678-2021 | P0115554 | DJ10007 | REMOVE AND REWORK | O equipamento deve ser substituído por outro novo. | REMOVE AND REWORK | Standard exchange of the panel DJ10007 is required Open NCR MAT to purchase a new one. |  |  | Não
NCR-ICN-ESC-12-0679-2021 | P0102687 | BE2400AC | AGREE WITH LEVEL 2.1 | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  |  |  | Não
NCR-ICN-ESC-12-0680-2021 | P0102689 | BE2400AS | AGREE WITH LEVEL 2.1 | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  |  |  | Não
NCR-ICN-ESC-12-0681-2021 | P0102686 | BE2400AB | AGREE WITH LEVEL 2.1 | Preservation Team requests NG orientation on how to access the Junction Boxes to perform the task if there is any way possible. If not, wishes to inform that the task cannot be done. |  |  |  |  | Não
NCR-ICN-ESC-12-0684-2021 | P4126613 |  | MANUFACTURE | Remanufacture the spool according to the document issued by CEDOC. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0686-2021 | P0105474 | DM00006L | REMOVE AND REWORK | The problem must be evaluated by the NG specialist. | REMOVE AND REWORK | Agree with deliberacao N1 Add picture of serial number of the AUMA where the pcb was taken |  |  | Não
NCR-ICN-ESC-12-0687-2021 | P0153476 | DY01906 | AGREE WITH LEVEL 2.1 | Need to replace dew point sensor. | SCRAP | Agree to canibalize the dew point sensor DY11905 CMX: 50AM800A00002, item 2 of the drawing (PARKER, product code: EA2-ZHM-100, Art.-no: ZHM-100/450, Range: -100/+20) on the air dryer of the SBR3. Need to create a new NCR-MAT to refund the SBR3, (scrap the old sensor). |  |  | Não
NCR-ICN-ESC-12-0687-2021 | P0195174 | DY11905 | AGREE WITH LEVEL 2.1 | Need to replace dew point sensor. | SCRAP | Agree to canibalize the dew point sensor DY11905 CMX: 50AM800A00002, item 2 of the drawing (PARKER, product code: EA2-ZHM-100, Art.-no: ZHM-100/450, Range: -100/+20) on the air dryer of the SBR3. Need to create a new NCR-MAT to refund the SBR3, (scrap the old sensor). |  |  | Não
NCR-ICN-ESC-12-0688-2021 | P0102204 | BB02501 | REWORK | We should evaluate driver v1.20 as it appeared in the message when trying to access the PMU. It will be necessary to remove the on-board PMU BB02501 for bench evaluation, as the space on board does not allow for a better analysis. |  |  |  |  | Sim
NCR-ICN-ESC-12-0689-2021 | P0134073 | BM00176 | REWORK | 1. Retest the inspection B02_BM00031. Fit the test device over the hull passage AC32007. Dismount the pipe BM50103Y1-P4147627 and be sure that valve BM00073-P0134117 is OPEN. Apply the leak pressure considering +2% according to IT34-00-01E_B, 53.5 bar during 5 min. The leak inspection between the BM00178 and BM00032 flanges will be ensured through the pressure drop in test manometer. 2. The ICN DT should be updated for others SBRs. 3. After retest, the pipe BM50103Y1-P4147627 should be remounted and M05 and S02 redone and updated. | REWORK | Agree with proposal. In complement NCR REGRESS will be raise and B05 will be updated. | REWORK | In accordance with proposal | Não
NCR-ICN-ESC-12-0689-2021 | P4147627 |  | REWORK | 1. Retest the inspection B02_BM00031. Fit the test device over the hull passage AC32007. Dismount the pipe BM50103Y1-P4147627 and be sure that valve BM00073-P0134117 is OPEN. Apply the leak pressure considering +2% according to IT34-00-01E_B, 53.5 bar during 5 min. The leak inspection between the BM00178 and BM00032 flanges will be ensured through the pressure drop in test manometer. 2. The ICN DT should be updated for others SBRs. 3. After retest, the pipe BM50103Y1-P4147627 should be remounted and M05 and S02 redone and updated. | REWORK | Agree with proposal. In complement NCR REGRESS will be raise and B05 will be updated. | REWORK | In accordance with proposal | Não
NCR-ICN-ESC-12-0690-2021 | P0152167 | AC43065 | REWORK | 1. Retest the leakage circuit PTRH-S02. To be sure that the O-ring inspected on B11.28 is good for each valve, redo the tests S02_HEZ0004/5/6/7, feeding the pressure during 30 minutes and following the IT34-00-01E_B orientations. External leaks is not acceptable. Moreover, the external pipes, after NRVs, should be properly purged at the tests end. 2. Even though the retests approved, do every B11.28 mentioning this NCR and attach them to B05 books. And attach over there the S02_HEZ0004/5 for AC33065 and S02_HEZ0006/7 for AC33059. |  |  |  |  | Sim | 01PM000D00069-6359238-MEGA-P/001
NCR-ICN-ESC-12-0690-2021 | P0152168 | AC43059 | REWORK | 1. Retest the leakage circuit PTRH-S02. To be sure that the O-ring inspected on B11.28 is good for each valve, redo the tests S02_HEZ0004/5/6/7, feeding the pressure during 30 minutes and following the IT34-00-01E_B orientations. External leaks is not acceptable. Moreover, the external pipes, after NRVs, should be properly purged at the tests end. 2. Even though the retests approved, do every B11.28 mentioning this NCR and attach them to B05 books. And attach over there the S02_HEZ0004/5 for AC33065 and S02_HEZ0006/7 for AC33059. |  |  |  |  | Sim | 01PM000D00069-6359238-MEGA-P/004
NCR-ICN-ESC-12-0691-2021 | P0104562 | BH10007N | REMOVE AND REWORK | ICN request authorization to rework the pipe according to conditions on board, and if necessary add non forecast weld. |  |  |  |  | Não
NCR-ICN-ESC-12-0692-2021 | P0145860 | AG00014 | REWORK | For the assembly process of AG00014 and AG00034 SBR2, carry out supply of materials for the fabrication of new pins ref. position 13 of SMB-361762_23 / 51 (MAT424-0715 / MAT424-0717). Perform manufacturing of pins larger in PIN size AXIS 12x45 - Qty: 02 units and assemble in order. | REWORK | NCR-ICN-ESC-12-0194-2020 treat of the similar problem. All nomenclatures of panel involved will be updated. Pin axis 12x45 NGD: 9980000005612 material: CuAl10Ni5Fe4 can be used if it's in stock or manufacture with the good material with material certificate and traceability folder updated. |  |  | Sim | 01PE200D00030
NCR-ICN-ESC-12-0692-2021 | P0145868 | AG00034 | REWORK | For the assembly process of AG00014 and AG00034 SBR2, carry out supply of materials for the fabrication of new pins ref. position 13 of SMB-361762_23 / 51 (MAT424-0715 / MAT424-0717). Perform manufacturing of pins larger in PIN size AXIS 12x45 - Qty: 02 units and assemble in order. | REWORK | NCR-ICN-ESC-12-0194-2020 treat of the similar problem. All nomenclatures of panel involved will be updated. Pin axis 12x45 NGD: 9980000005612 material: CuAl10Ni5Fe4 can be used if it's in stock or manufacture with the good material with material certificate and traceability folder updated. |  |  | Não
NCR-ICN-ESC-12-0693-2021 | P4019056 |  | REWORK | Agree with 1.2. As per SMB-200387, the seating AG00017C (P4019056) - All holes will be counter-drilled when mounting with the equipment. For seat P4019057, it is rework. Close the holes with welding and make the holes according to the procedure. | REWORK | Change de Element 001 and 006 of the seating AG00037C Weld following SMB-200856 Carry out 100% VT 100% DP |  |  | Não
NCR-ICN-ESC-12-0693-2021 | P4019057 |  | REWORK | Agree with 1.2. As per SMB-200387, the seating AG00017C (P4019056) - All holes will be counter-drilled when mounting with the equipment. For seat P4019057, it is rework. Close the holes with welding and make the holes according to the procedure. | ACCEPT AS IT IS | No defect on this seating |  |  | Não
NCR-ICN-ESC-12-0694-2021 | P0105174 | BB00031 | NCR LEVEL 1 | According description it's necessary to do rework. See photo annex. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | BN10387301001
NCR-ICN-ESC-12-0695-2021 | P0131454 | KT03721 | REWORK | 1. Dismount the longest stud rods and use M14x90 CMD: 32VI220D00152, use a new O-ring for each pneumatic ram too CMD: 44JO110D00455. 2. Redo the B06 correctly and update the B07. 3. Raise a NCR-MAT for material replacing. |  |  |  |  | Sim | 1550259
NCR-ICN-ESC-12-0695-2021 | P0129809 | KT03722 | REWORK | 1. Dismount the longest stud rods and use M14x90 CMD: 32VI220D00152, use a new O-ring for each pneumatic ram too CMD: 44JO110D00455. 2. Redo the B06 correctly and update the B07. 3. Raise a NCR-MAT for material replacing. |  |  |  |  | Sim | 1458182
NCR-ICN-ESC-12-0696-2021 | P0108341 | DY02512 | AGREE WITH LEVEL 2.1 | Replace the pcb control and retest | REMOVE AND REWORK | After further investigation, it was found that the thyristor of the pre-charge doesnt close. After change the control card, the pre-charge is working well and no more incident variator with the start stop button. Change the control card on sbr3 DY02512. Open NCR MAT to purchase a new one. |  |  | Sim
NCR-ICN-ESC-12-0697-2021 | P0148449 | EJ00017 | REMOVE AND REWORK |  | SCRAP | Replace the modular analysis chamber damaged (EJ00017, CMX: 50AM906D00026, NGD; 0930930263891) by a new one from the stock or SBR4. Create a NCR MAT to provide a new modular and refound the stock. Scrap the modular analysis chamber damaged. |  |  | Não
NCR-ICN-ESC-12-0698-2021 | P0133568 | BD00016 | REWORK | PCP, please provide material for production as attached; | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 05DD000D00001
NCR-ICN-ESC-12-0698-2021 | P0133574 | BD00013 | REWORK | PCP, please provide material for production as attached; | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 05DD000D00001
NCR-ICN-ESC-12-0699-2021 | P0103119 | BE0710DB | REWORK | This interference has to be verify In the project by Level 2.2. |  |  |  |  | Não
NCR-ICN-ESC-12-0699-2021 | P0104608 | BH00003 | [6 empty] | Não
NCR-ICN-ESC-12-0700-2021 | P0108667 | RF00008 | [6 empty] | Não
NCR-ICN-ESC-12-0701-2021 | P4135014 |  | NCR LEVEL 1 | According to the description, the screws must be mounted correctly. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0702-2021 | P4135015 |  | NCR LEVEL 1 | According to SMB-200949 there can be no paint on the resilient pads. Rework on the torque of the fastening screws. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0703-2021 | P0102196 | BB00600 | AGREE WITH LEVEL 2.1 | The pipe needs to be fixed. |  |  |  |  | Não
NCR-ICN-ESC-12-0704-2021 | P0117309 | EG00237 | REPAIR | -It is necessary to dismont the safety valve and calibrate on the bench; -Open NCR-REGRESS to retest the circuit S02 EGZ0018 after monting. |  |  |  |  | Não
NCR-ICN-ESC-12-0705-2021 | P4113570 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4113571 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4113572 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4113573 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116948 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116951 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116954 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116956 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116959 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116960 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116967 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116972 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116942 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116958 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4116968 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117155 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117159 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117185 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117153 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117154 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117157 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4117203 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4118538 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4120734 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4120742 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4120743 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4120945 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | P4120730 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | SP0000285 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0705-2021 | SP0000286 |  | OK - NOT MODIFIED | [5 empty] | Não
NCR-ICN-ESC-12-0706-2021 | P4115329 |  | NCR LEVEL 1 | Remove residual ink from the shims. According to SMB-200949 decoupling disks should not have paint marks or damage. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0707-2021 | P4019069 |  | REWORK | PERFORM THE SPECIFIC PAINT TREATMENT FOR EACH SPRING, AS PER SMB-002345. REFERENCES: 1) 53B-AG00037 - P0145870 - CMD 01PE200D00035 - EQUALISING SYSTEM OF 01PE200D00040 HATCH. Item 41 - Compression Spring Ø18xØ196x930 - ref. MAT424-1437 / MAT424-0845. 2) 53B-AG00034 - P0145868 CMD 01PE200D00034 - HULL HATCHES - BALANC. OF MID. ACC. HATC. Item 28 - Compression Spring Ø18xØ121x652 - ref. MAT424-0860 / MAT424-0857. 3) 53B-AG00039 - P0145871 - CMD 01PE200D00036 - EQUALISING SYSTEM OF 01PV000C0106 HATCH Item 8 - Compression Spring Ø14xØ120x531 - 0 0000 ref. MAT424-1480 / MAT424-0859. 4) 53B-AG00036 - P0145876 CMD 01PE200D00032 - EQUALISING SYSTEM OF 01PE200D00028 HATCH. Item 14 - Compression Spring Ø15xØ120x532 - ref. MAT424-1365 / MAT424-0802 |  |  |  |  | Não
NCR-ICN-ESC-12-0707-2021 | P4169309 |  | REWORK | PERFORM THE SPECIFIC PAINT TREATMENT FOR EACH SPRING, AS PER SMB-002345. REFERENCES: 1) 53B-AG00037 - P0145870 - CMD 01PE200D00035 - EQUALISING SYSTEM OF 01PE200D00040 HATCH. Item 41 - Compression Spring Ø18xØ196x930 - ref. MAT424-1437 / MAT424-0845. 2) 53B-AG00034 - P0145868 CMD 01PE200D00034 - HULL HATCHES - BALANC. OF MID. ACC. HATC. Item 28 - Compression Spring Ø18xØ121x652 - ref. MAT424-0860 / MAT424-0857. 3) 53B-AG00039 - P0145871 - CMD 01PE200D00036 - EQUALISING SYSTEM OF 01PV000C0106 HATCH Item 8 - Compression Spring Ø14xØ120x531 - 0 0000 ref. MAT424-1480 / MAT424-0859. 4) 53B-AG00036 - P0145876 CMD 01PE200D00032 - EQUALISING SYSTEM OF 01PE200D00028 HATCH. Item 14 - Compression Spring Ø15xØ120x532 - ref. MAT424-1365 / MAT424-0802 |  |  |  |  | Não
NCR-ICN-ESC-12-0707-2021 | P4128742 |  | REWORK | PERFORM THE SPECIFIC PAINT TREATMENT FOR EACH SPRING, AS PER SMB-002345. REFERENCES: 1) 53B-AG00037 - P0145870 - CMD 01PE200D00035 - EQUALISING SYSTEM OF 01PE200D00040 HATCH. Item 41 - Compression Spring Ø18xØ196x930 - ref. MAT424-1437 / MAT424-0845. 2) 53B-AG00034 - P0145868 CMD 01PE200D00034 - HULL HATCHES - BALANC. OF MID. ACC. HATC. Item 28 - Compression Spring Ø18xØ121x652 - ref. MAT424-0860 / MAT424-0857. 3) 53B-AG00039 - P0145871 - CMD 01PE200D00036 - EQUALISING SYSTEM OF 01PV000C0106 HATCH Item 8 - Compression Spring Ø14xØ120x531 - 0 0000 ref. MAT424-1480 / MAT424-0859. 4) 53B-AG00036 - P0145876 CMD 01PE200D00032 - EQUALISING SYSTEM OF 01PE200D00028 HATCH. Item 14 - Compression Spring Ø15xØ120x532 - ref. MAT424-1365 / MAT424-0802 |  |  |  |  | Não
NCR-ICN-ESC-12-0707-2021 | P4019056 |  | REWORK | PERFORM THE SPECIFIC PAINT TREATMENT FOR EACH SPRING, AS PER SMB-002345. REFERENCES: 1) 53B-AG00037 - P0145870 - CMD 01PE200D00035 - EQUALISING SYSTEM OF 01PE200D00040 HATCH. Item 41 - Compression Spring Ø18xØ196x930 - ref. MAT424-1437 / MAT424-0845. 2) 53B-AG00034 - P0145868 CMD 01PE200D00034 - HULL HATCHES - BALANC. OF MID. ACC. HATC. Item 28 - Compression Spring Ø18xØ121x652 - ref. MAT424-0860 / MAT424-0857. 3) 53B-AG00039 - P0145871 - CMD 01PE200D00036 - EQUALISING SYSTEM OF 01PV000C0106 HATCH Item 8 - Compression Spring Ø14xØ120x531 - 0 0000 ref. MAT424-1480 / MAT424-0859. 4) 53B-AG00036 - P0145876 CMD 01PE200D00032 - EQUALISING SYSTEM OF 01PE200D00028 HATCH. Item 14 - Compression Spring Ø15xØ120x532 - ref. MAT424-1365 / MAT424-0802 |  |  |  |  | Não
NCR-ICN-ESC-12-0708-2021 | P0119530 | UW24301D | REWORK | A check on the problem by level 2.2 is required. |  |  |  |  | Não
NCR-ICN-ESC-12-0709-2021 | P0109351 | DY00011 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28750
NCR-ICN-ESC-12-0709-2021 | P0109353 | DY00012 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28714
NCR-ICN-ESC-12-0709-2021 | P0109352 | DY00021 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28749
NCR-ICN-ESC-12-0709-2021 | P0109354 | DY00022 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28724
NCR-ICN-ESC-12-0709-2021 | P0109355 | DY00031 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28713
NCR-ICN-ESC-12-0709-2021 | P0109356 | DY00032 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28725
NCR-ICN-ESC-12-0709-2021 | P0109359 | DY00041 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28718
NCR-ICN-ESC-12-0709-2021 | P0109361 | DY00042 | REWORK | 1. Follow the TAF-TA-2021-1378 orientations. 2. Raise a NCR-REGRESS for all QC inspections and commissioning tests carried out. 3. Raise a NCR-MAT to replenish the materials that will be used on this rework. |  |  |  |  | Sim | 28726
NCR-ICN-ESC-12-0110-2020 | P0105315 | MB20307 | REMOVE AND REWORK | Rework | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim
NCR-ICN-ESC-12-0258-2020 | P0146853 | AM00003S | REWORK | Rework according to SMB-200965_E | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0258-2020 | P0146854 | AM00005S | REWORK | Rework according to SMB-200965_E | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0337-2021 | P4156549 |  | REWORK | Request a new data card and reinstall on the equipment. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0532-2021 | P0103744 | BK02500 | REWORK | According to the description the cables must be separated to allow inspection A04. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 001186-IV9-02-006
NCR-ICN-UFEM-12-0549-2021 | SC2A-AG00013 |  | REWORK | 1) The machining missing on boss of maneuver shaft must be machined following MAT424-0703 (section A-A); 2) The recess for lock of Threaded Ring must be redone to achieve the final measurements according MAT424-0704 (section C-C); 3) Replace the gasket by NGD 5330145107997 FLAT GASKET 60 X 79 X 3 FIBER / NBR from batch SMB-RMS-CUR-DB19. NCR-MAT-001065-2020 was opened to supply new gasket; 4) Mark the serial number on cover label according NCR-MAT-001065-2020 answer: SN: AP427130. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0400-2021 | P0145846 | AG00017 | REWORK | Send to level 2. | REWORK | Due to the experience return from SBR1: A control dimensional of parts of balancing system should be done. A particular attention should be paid for the correct position of upper bearings and lower bearings. A control of the arm movement should be done after remounting: the movement should be without hard point and fluid. | REWORK | In accordance with LEVEL 2.2 proposition, please proceed to a dimensional report of the whole components of SBR2 hatches. Provide to Naval Group Cherbourg the report. Raise a NCR if deviation noticed. | Sim | 01PE200D00040
NCR-ICN-ESC-12-0473-2021 | P0137364 | FQ00102 | REWORK | To perform the change request contained in order SMB12-MU18B-DB24. 1. Request the supply of a new part to replace the damaged part. 2. Or NG, analyze the possible repair, we can hire a company specializing in protective zinc coating 3. Open NCRMAT. | ACCEPT AS IT IS | FQ00102 - CMD: 18CR000D00022 serial number: 16_001 To machin the valve conform to the drawing MAT177-0304. It was checking the no possibility to remove zinc with nail and it was decided to continu the mounting. Open NCR MAT for the modification of dimensions of surfaces galvanized on the drawing. | REWORK | In accordance for the rework according to level 2 proposal. Document MAT177-0304_EXP_E F19 (BDM-00069651) will be updated. | Sim | 18CR000D00022
NCR-ICN-UFEM-12-0511-2019 | SMB-P4130876 |  | REWORK | Check the positioning of the equipment and resize the shims. | ACCEPT AS IT IS | Maximum out of tolerance it's +0,9mm. | ACCEPT AS IT IS | This concerns decoupling washers MN03-40 type for an auxiliary fitted decoupled on a suspended cradle on hull (room A130). Accept as is. | Não
NCR-ICN-ESC-12-0469-2021 | P0134348 | BM00042 | REWORK | It's necessery remounting the BM00042-P0134348 valve using a new FIBER GASKET 147X173X3 - 44JO230D00072 and 28 news (LOCK WASHER) - 32VI420D00031 which will be bent again after the B01 test approval. Redo all inspections related that was carried out. | REWORK | Agree with proposal. Pay attention of the verification of the coating (F06) and the protection during dismounting. A NCR REGRESS will be raise to carry out inspections and pressure tests. B05 should be updated. | REWORK | In accordance with ICN and level 2.2 proposal. David BERNEDE - ISSP | Sim | 016
NCR-ICN-ESC-12-0619-2021 | P0156490 | EJ00052 | REWORK | Provide a new screw to continue the construction process. | REWORK | See with mecanical team if it's possible to manufacture a new one |  |  | Não
NCR-ICN-ESC-12-0423-2021 | P4503096 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0423-2021 | P4503098 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0519-2021 | P4134573 |  | SCRAP AND RE-MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0027-2019 | P4165367 |  | REMOVE AND REPAIR | It is necessary to take the bolting from SBR2 on EG50100G1 Type 2 lenght 80 dto do the mounting. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0023-2019 | P4148969-B-26279-7256-18LT100D00175 |  | REWORK | Make a template for closing the pipe with the valve. This pipe has to be adjusted on board as it is in the junction area. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0023-2019 | P4148951-A-24386-7384-18LT100D00175 |  | REWORK | Make a template for closing the pipe with the valve. This pipe has to be adjusted on board as it is in the junction area. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-UFEM-12-0354-2018 | P4165868 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0443-2019 | P4157955 |  | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | Não
NCR-ICN-UFEM-12-0479-2019 | P0132254 | UL00002 | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0054-2020 | P4178063 |  | REMOVE AND REPAIR | Modifique a tubulação EZ51023 (P4178063 e P4177025) de acordo com o FTG-5193, | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0067-2020 | P0121680 | FH20201 | REMOVE AND REPAIR | NG. please advise how to proceed. | OK - NOT MODIFIED |  |  |  | Não
NCR-ICN-ESC-12-0067-2020 | P4169228 |  | REMOVE AND REPAIR | NG. please advise how to proceed. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0082-2020 | N/A | [5 empty] | ACCEPT AS IT IS | Accept as it is. The modifications or additional information made in the traceability files are consistent with the expectations. | Não
NCR-ICN-ESC-12-0090-2020 | P4134950 |  | NCR LEVEL 1 | The equipment must have complete assemblies, resilient mount, completion of the seatings and electrical cables. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0099-2020 | P0126367 | AM00003 | REWORK | Rework according to SMB-200965_D | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0099-2020 | P0141340 | AM00005 | REWORK | Rework according to SMB-200965_D | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0108-2020 | P0122383 | FH02625 | REWORK |  | REWORK | Pegar o SBR4 os itens abaixo: 4 itens rep 40 1 itens rep 43 1 itens rep 46 1 itens rep 42 BDM-00060105 BDM-00060109 Abra o NCR MAT para reconstituir itens canibalizados |  |  | Sim
NCR-ICN-ESC-12-0117-2020 | N/A |  | REWORK | Machining 0,5 mm (radius) or as less as possible to achieve values bigger than the theoretical gap (7,5 mm): • The coaming first in priority; • The bush after if for the coaming it’s too late, but take care because on this diameter there is the traceability; • Record the traceability and after machining, stamp back. |  |  |  |  | Não
NCR-ICN-ESC-12-0126-2020 | P0137114 | EV03500 | REWORK |  | REINSPECT THE ELEMENT | The commutator local/remote is inside the panel as per picture attached NCR can be cancelled |  |  | Sim
NCR-ICN-ESC-12-0138-2020 | P0131031 | KT03611 | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Sim | SN00012
NCR-ICN-ESC-12-0138-2020 | P0156812 | KT03612H | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Não
NCR-ICN-ESC-12-0138-2020 | P0194590 | KT03613H | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Não
NCR-ICN-ESC-12-0138-2020 | P0156827 | KT03614H | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Não
NCR-ICN-ESC-12-0138-2020 | P0194591 | KT03615H | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Não
NCR-ICN-ESC-12-0138-2020 | P0126936 | KT03616 | ACCEPT AS IT IS | Send to leval 2 to validate the modification. | REWORK | The continuity of holes missing will be drill in workshop. NG will be informed of these missing of holes continuity. | REWORK | Rework the drillings according to the drawing. | Sim | SN00013
NCR-ICN-UFEM-12-0496-2019 | P4028879 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0313-2021 | P0108954 | UE63704D | REWORK | Provide two new cables (UE63704D and UE63705D). | REWORK | If the armour of these cable are not damaged you can repair with a heat shrinkable see protocol SMB-325107. If not change them |  |  | Não
NCR-ICN-ESC-12-0313-2021 | P0108958 | UE63705D | REWORK | Provide two new cables (UE63704D and UE63705D). | REWORK | If the armour of these cable are not damaged you can repair with a heat shrinkable see protocol SMB-325107. If not change them |  |  | Não
NCR-ICN-ESC-12-0349-2021 | P0131520 | MB00003 | REWORK | Send to level 2. | REWORK | The length (a=36) of the stud are too big and don't allow one good assembly. The time to receive new conform stud is a minimum of 6 months. After discuss about the situation with NG BO the solution is to assembly the stud with Loctite and a distance, between the end of the stud and the face of the coaming, of 82mm (0+0,5) . When it will be supply new stud, the easier solution to remove and replace the non-conform stud without disassembly the PELA can be to change 2 stud per 2 stud in opposite side and re-do the resistance and leak test at the end. With this solution we don't need to remove the SKF coopling. Use loctite 270 because after test the process with loctite 243 we saw that was not enough strong and the stud were turning during torque tight. | REWORK | in accordnace with level2 proposal , the position of all studs has to be mesured and indicated in the B11 inspection file A work has to be made between the studs , the nuts and the body of sterngland to be sure that the studs will be not umthightered during sea trial. The solution is acceptable until RANAE if there is no problems The decision for a new solution on this particular mounting will be decided at the RANAE. D BERNEDE | Sim | 15PE000D00001
NCR-ICN-ESC-12-0457-2021 | P0104722 | DA12501N | REWORK | We can install new equipment DA12501N on board to attend the construction process. we take the 53D-DA12501N SBR4 and open NCRMAT. | REWORK | Try to find this equipment (it can't disappear) If you can't find take a new one from SBR4 or SBR3. Raise NCR MAT to follow a new purchase. | REWORK | In accordance with level 2.2 | Não
NCR-ICN-UFEM-12-0526-2019 | P0113778 | KT03415 | REWORK |  | REMOVE AND REPAIR | CMX: 18RT010D00716 Serial number: ???? The valve will be change by a new one. The serial number of the valve with the defect one have to be mentionned inside this NCR. All tracability document will be updated, control and pressure tests carry out again. The belzona will be repair in respect of rules of repairing. | REPAIR | Follow 2.2 decision | Não
NCR-ICN-UFEM-12-0526-2019 | P0113539 | KT03415R | REWORK |  | REMOVE AND REPAIR | CMX: 18RT010D00716 Serial number: ???? The valve will be change by a new one. The serial number of the valve with the defect one have to be mentionned inside this NCR. All tracability document will be updated, control and pressure tests carry out again. The belzona will be repair in respect of rules of repairing. | REPAIR | Follow 2.2 decision | Não
NCR-ICN-ESC-12-0026-2019 | P4176099 |  | NCR LEVEL 1 | Make the necessary adjustments to obtain shim compression according to SMB-200965. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-UFEM-12-0152-2018 | P0121273 | ER00001H | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0306-2018 | P4134328 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0361-2018 | DJ50015J3A |  | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | Não
NCR-ICN-UFEM-12-0361-2018 | P0115970 | DJ00003 | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | UNFOUNDED | Não
NCR-ICN-UFEM-12-0446-2019 | P4114592 |  | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | Não
NCR-ICN-UFEM-12-0489-2019 | EL1110 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0056-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0075-2020 | P4107187 |  | MANUFACTURE | Manufacture Spools according to the design issued by the design.. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0084-2020 | P4171688 |  | ACCEPT AS IT IS |  | REWORK | Apply the solution given by TA in annex |  |  | Não
NCR-ICN-ESC-12-0084-2020 | P4164000 |  | ACCEPT AS IT IS |  | REWORK | Apply the solution given by TA in annex |  |  | Não
NCR-ICN-ESC-12-0084-2020 | P4168393 |  | ACCEPT AS IT IS |  | REWORK | Apply the solution given by TA in annex |  |  | Não
NCR-ICN-ESC-12-0091-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0101-2020 | P4501605 |  | SCRAP AND RE-MANUFACTURE | Manufactures the spool according to the issued drawing. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0109-2020 | P0121758 | FH20033 | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0109-2020 | P0121679 | FH20035 | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0109-2020 | P0121677 | FH20031 | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0121-2020 | P4127155 |  | OK - UPDATE JOB ORDER | Wait for NG orientation. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0127-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0139-2020 | P0124835 | BB02507 | ACCEPT AS IT IS | Accept as it is. Send to level 2 to validate. | REPAIR | The grinding process is updated and this process not increase the temperature. According to the results in annex the floor is not aceptable as it is. The solution to repair: - mark on the ground each position of the batterie; - check the planeity one by one square (500x360); -check the horizontability; -take optic measurement to validate the rectification send to level 3 (Charles Boucher) Additional comments on 14/09/2020 by JACQUIN.S: Based on the annex 2 measurements, an analysis has been done following the aft battery connections in order to ensure a proper connection between the accumulators (SMB-000737). A repair proposal has been done on some identified seatings in order to respect as much as possible the tolerances of the batteries connectors. Annex”20200903-C100 - Etat avant reprise”: The cells to be reworked are in red background, and in orange background are highlighted the gap >1mm compared to the nominal high of each floors Upon rework done, new measurements have been taken and reported: Annex”20200904-C100 - Etat après reprise”. Based on these new measurements, the tolerance reported are within the connector tolerances. We would like to propose to accept as it is. | ACCEPT AS IT IS | Agreement with 2.2 proposed solution of chocking rework. A specific follow-up with Electrical TA et Mechanical TA is required in order to ensure that all electrical connections can be mounted without any deviation to the required gap, namely : - each electrical connection between battery elements - battery head connection Open a new NCR in case of discrepancie regarding the electrical connection mounting gap or battery theorical height. V2 of 01/10/2020: Following the V2 of this NCR received on 15/09/2020 after chocking rework and last measurements done, decision to Accept as is. | Não
NCR-ICN-ESC-12-0149-2020 | P4157124 |  | REMOVE AND REPAIR | ICN suggested redoing 3 welds. One already provided on the flange to adjust the drill position, on the x axis, and another for the z axis. See the photo of the proposal cut in the attachment ” | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0155-2020 | N/A |  |  |  | REPAIR | During the work following the SMB-104502 updated rev. C , ICN opened the limber on the wrong side of Frame 59. Portside instead of starbord side. Close the wrong opening following the IT 21-02-10-E and SMB-001386 Carry out all the tests required . 100% VT and 100%MT ( open an NCR/RO to record the welding information) Open the limber Hole on the good side, carry out inspections 100% VT ; 100% MT |  |  | Não
NCR-ICN-ESC-12-0320-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0504-2021 | P0131806 | FR00002 | ACCEPT AS IT IS | The Equipment has a good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 | ACCEPT AS IT IS | Absorption unit FR00002 overturned, but not sensitive to overturning. This material will not undergo further vibration measurements in the future at ICN. (Excluding SHIP11C scope). | Sim | 024/16-02
NCR-ICN-ESC-12-0032-2019 | P4125601 |  | REPAIR | To dictate the necessary length to get out of the interference, it will be necessary to create a CTEPROD | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0032-2019 | P4140160 |  | REPAIR | To dictate the necessary length to get out of the interference, it will be necessary to create a CTEPROD | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0060-2020 | P0126217 | EW03002 | REWORK | Wait for response from NG | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-UFEM-12-0258-2018 | P0104796 | MB00002 | REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-UFEM-12-0331-2018 | P4162648 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0400-2019 | P0132441 | FH01000 | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0470-2019 | P4154488 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-ESC-12-0052-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0063-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0081-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0089-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0095-2020 | N/A | [5 empty] | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0107-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0116-2020 | P0110262 | DT04310 | REWORK |  | REWORK | Take module Z02 in the DT04310 on SBR4 Open MAT to replenish it Rep 42 of drawing attached in annex NGD: 6620930195387 |  |  | Não
NCR-ICN-ESC-12-0125-2020 | P0122389 | EV02500 | REWORK |  | REINSPECT THE ELEMENT | The commutator local/remote is inside the panel as per picture attached NCR can be cancelled |  |  | Sim
NCR-ICN-ESC-12-0132-2020 | P0118609 | RM00803 | ACCEPT AS IT IS | Accept as it is. Machine a new pin accordingly the hole dimensions respecting the tolerance H7. | REMOVE AND REWORK | Adjust the size in order to be in tolerances H7 |  |  | Não
NCR-ICN-ESC-12-0141-2020 | N/A | [7 empty] | Não
NCR-ICN-UFEM-12-0542-2020 | N/A |  | REPAIR | Repair the Blade Solid Cone according 2.1 ICN SOLUTION / DECISION and annex 1. Send to TA Charles Boucher to validate. | REWORK | TA agree with this solution proposed by ICN (scratch the cone of the blade to perform better perpendicularity of the shaft). Make a new inspection and add here to close the NCR. (Charles Boucher) |  |  | Não
NCR-ICN-ESC-12-0158-2020 | P4164781 |  | REWORK |  | REWORK | Rework carefully remove the support by grinding. carry out the following inspections, 100% visual, 100% MT and nital attack. Open an NCR / RO if necessary to reconstitute the base metal. Position the new seating in the right place. carry out the inspections requested as per original |  |  | Não
NCR-ICN-ESC-12-0169-2020 | N/A |  |  |  | REPAIR | repair as per annex |  |  | Não
NCR-ICN-UFEM-12-0530-2019 | P0154463 | AC42016 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0156023 | AC42039 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0154455 | AC42036 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0154471 | AC42001 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0156007 | AC42081 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0154439 | AC42056 | REWORK | [5 empty] | Não
NCR-ICN-UFEM-12-0530-2019 | P0156010 | AC42082 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0064-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0120-2020 | P4169961 |  | REWORK |  | AGREE WITH LEVEL 2.1 | carry out of inspections. |  |  | Não
NCR-ICN-ESC-12-0120-2020 | P4169959 |  | REWORK |  | AGREE WITH LEVEL 2.1 | carry out of inspections |  |  | Não
NCR-ICN-ESC-12-0120-2020 | P4169969 |  | REWORK |  | AGREE WITH LEVEL 2.1 | carry out of inspections |  |  | Não
NCR-ICN-ESC-12-0179-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0198-2020 | P0124882 | BB22520 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124881 | BB22521 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124879 | BB22524 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124878 | BB22525 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124876 | BB22527 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124875 | BB22528 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124874 | BB22529 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124871 | BB22537 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124873 | BB22530 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124858 | BB22536 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124856 | BB22538 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124855 | BB22539 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124854 | BB22540 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124853 | BB22541 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124852 | BB22542 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124851 | BB22543 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124863 | BB22531 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124862 | BB22532 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124861 | BB22533 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124860 | BB22534 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124859 | BB22535 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124870 | BB22523 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0198-2020 | P0124880 | BB22522 | REWORK | FOLLOW LEVEL 2.2 GUIDANCE. | REINSPECT THE ELEMENT | ICN should measure the cable connector gap (20mm +0 / -0.5mm) Naval Group confirms that the individual measurements of the 2 extremities of the 24 makeshift cables are required before this NCR can be sent to Level 3 | ACCEPT AS IT IS | Ensure that the recommended tightening of the connectors is respected (torque 80N/m). If the phenomenon is observed again, call in TA for measurement before switching to LV3 again. | Não
NCR-ICN-ESC-12-0247-2020 | P0101461 | OO22906 | REWORK | Follow level 2.2 guidelines. | REWORK | For UPS internal modules integrated in junction boxes according to document SMB-201629 (DEFINITIONS OF UPS MODULES) Call the wiring kit 49AU100D00072. In this case, apply the wiring described in BDM-00073923 To connect, use the cables rep 43 and 44 mentioned in this plan. Cable rep 43: NGD 0930930277886 => quantity 2 Cable rep 44: NGD 9980000062323 => quantity 4 | REWORK | 07/07/2021 : Please apply repair order OR-282037 delivered in answer to NCR-MAT-001336-2021 (Fabien RENVOISE) | Não
NCR-ICN-ESC-12-0247-2020 | P0101439 | OO22604 | REWORK | Follow level 2.2 guidelines. | REWORK | For UPS internal modules integrated in junction boxes according to document SMB-201629 (DEFINITIONS OF UPS MODULES) Call the wiring kit 49AU100D00072. In this case, apply the wiring described in BDM-00073670 To connect, use the cables rep 35 and 36 mentioned in this plan. Cable rep 35: NGD 0930930277886 => quantity 1 Cable rep 36: NGD 9980000062323 => quantity 1 | REWORK | 07/07/2021 : Please apply repair order OR-282037 delivered in answer to NCR-MAT-001336-2021 (Fabien RENVOISE) | Não
NCR-ICN-ESC-12-0247-2020 | P0101458 | OO22900 | REWORK | Follow level 2.2 guidelines. | REWORK | For UPS internal modules integrated in junction boxes according to document SMB-201629 (DEFINITIONS OF UPS MODULES) Call the wiring kit 49AU100D00072. In this case, apply the wiring described in BDM-00073674 To connect, use the cables rep 41 and 42 mentioned in this plan. Cable rep 41: NGD 0930930277886 => quantity 1 Cable rep 44: NGD 9980000062323 => quantity 2 | REWORK | 07/07/2021 : Please apply repair order OR-282037 delivered in answer to NCR-MAT-001336-2021 (Fabien RENVOISE) | Não
NCR-ICN-ESC-12-0264-2020 | P0101600 | OO24323 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Take an NGD 49AU100D00074 on SBR4, if available Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0115999 | DJ00004 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0105286 | DM00009 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0105287 | DM00010 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0105288 | DM00011 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122048 | EG00110 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122044 | EG00130 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0143452 | EG00143 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0143451 | EG00144 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122027 | EG00205 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122063 | EG00234 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122062 | EG00140 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122065 | EG00236 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0136467 | EG01120 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122150 | EG01130 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122151 | EG01140 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122147 | EG01159 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0122116 | EG01165 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0126750 | EW00008 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0126751 | EW00009 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0126752 | EW00010 | REWORK | FOLLOW LEVEL GUIDELINES 2.2. | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0279-2020 | P0136464 | EG01110 | REWORK |  | REINSPECT THE ELEMENT | The two drawings BDM-00076571 and BDM-00078234 do not mention ISO 20 POLYAMIDE IP66 CABLE PRESS, please check the need |  |  | Não
NCR-ICN-ESC-12-0293-2020 | P0154420 | AC32010 | REWORK | A new pack with 20 washers (DN10 LOCK TAB 35SA000D00008_3002) is needed in order to reinstall the Hull Passage(AC32010) for the J6 Cerimony. Please proceed with the requesition. | REWORK | Item dismounted is not AC32010 (welded on hull) but UL00114. To fix UL00114 on AC32010, 20 Tab washers (32VI420D00028) were used as explain PR-5707023. NCR MAT will be raise to launch a new purchase of 20 tab washers 32VI420D00028. |  |  | Não
NCR-ICN-ESC-12-0343-2021 | N/A |  |  |  | REPAIR | insert a round element , diameter 60 thickness of 25mm in S355 steel Weld with E42 fillet weiding Carry out 100% VT, and 100%MT Drill a new drilling with the good coordonates It's possible to manufacture locally with integrality followed STF 33-04-30-TS017E. The construction folder will be done since the beginning (material certificate, qualification,...) Welding following SMB-030501 Inspections of welding following IT33-04-13E. Tests as explained in STF 33-04-30-TS017E The complete construction folder with all elements will be supplied for the closure of NCR |  |  | Não
NCR-ICN-ESC-12-0374-2021 | P0106322 | DN00112 | REWORK | Remove DN00112, remount according SMB-200960 using new gasket and new tab washers, redo new inspections B06, B01, B02 and update B07 NCR-REGRESS will be open to invalidate old inspections B06, B01 and B02 of DN00112 |  |  | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0414-2021 | P4095705 |  | ACCEPT AS IT IS |  | REMOVE AND REWORK | Apply the painting protection |  |  | Não
NCR-ICN-ESC-12-0414-2021 | P4095704 |  | ACCEPT AS IT IS |  | REMOVE AND REWORK | Apply the painting protection |  |  | Não
NCR-ICN-ESC-12-0439-2021 | P0132369 | FH00010 | REWORK | Remove valve FH00010 provided for the SBR2 and replace a new one. | REMOVE AND REWORK | repair the valve FH00010 in workshop make ncr regress |  |  | Não
NCR-ICN-ESC-12-0451-2021 | P0130114 | DP00160 | REWORK | Request assembly items for the DP00159, DP00160 and DP00259 of the SBR4 indicated in Annex (kit - DP00259 - DP00160 - DP00159 SBR02) to complete the assembly of the DPs of the SBR2. Open NCR MAT SBR4 to supply new materials. | REWORK | ICN need to use the all the material necessary from SBR 3. Raise one NCR MAT with all the good information necessary in order to replace the material in the stock. | REWORK | In accordance with level 2.2 proposal. (David BERNEDE) The NCR MAT has to quote the NGD and quantities of requested items. | Não
NCR-ICN-ESC-12-0451-2021 | P0131101 | DP00259 | REWORK | Request assembly items for the DP00159, DP00160 and DP00259 of the SBR4 indicated in Annex (kit - DP00259 - DP00160 - DP00159 SBR02) to complete the assembly of the DPs of the SBR2. Open NCR MAT SBR4 to supply new materials. | REWORK | ICN need to use the all the material necessary from SBR 3. Raise one NCR MAT with all the good information necessary in order to replace the material in the stock. | REWORK | In accordance with level 2.2 proposal. (David BERNEDE) The NCR MAT has to quote the NGD and quantities of requested items. | Não
NCR-ICN-ESC-12-0451-2021 | P0130119 | DP00159 |  | Request assembly items for the DP00159, DP00160 and DP00259 of the SBR4 indicated in Annex (kit - DP00259 - DP00160 - DP00159 SBR02) to complete the assembly of the DPs of the SBR2. Open NCR MAT SBR4 to supply new materials. | REWORK | ICN need to use the all the material necessary from SBR 3. Raise one NCR MAT with all the good information necessary in order to replace the material in the stock. | REWORK | In accordance with level 2.2 proposal. (David BERNEDE) The NCR MAT has to quote the NGD and quantities of requested items. | Não
NCR-ICN-ESC-12-0476-2021 | P4022210 |  | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Não
NCR-ICN-ESC-12-0476-2021 | P4022239 |  | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Não
NCR-ICN-ESC-12-0476-2021 | P0109355 | DY00031 | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Sim | 22BA000D00147
NCR-ICN-ESC-12-0476-2021 | P0109356 | DY00032 | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Sim | 22BA000D00147
NCR-ICN-ESC-12-0476-2021 | P0109359 | DY00041 | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Sim | 22BA000D00147
NCR-ICN-ESC-12-0476-2021 | P0109361 | DY00042 | ACCEPT AS IT IS | Accept as it is. | REMOVE AND REWORK | Send to level 3 to officialise or not the solution used on SBR1 during RANAE using screw 8.8 rather than thread studs For the machining done, it has to be confirmed by level 3. | REPAIR | Temporary acceptance of the solution made in RANAE on SBR1, to be replicated also temporarily on SBR2. - CHC screw class 8.8, min. length 90 mm - fastening between the collar and the upper part of the seating - use Nord Lock washers | Sim | 22BA000D00147
NCR-ICN-ESC-12-0479-2021 | P0108787 | RH04310 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. |  |  |  |  | Não
NCR-ICN-ESC-12-0496-2021 | P0109075 | DY20104 | REMOVE AND REWORK | Replace the hose. Apply CMD 18FG205D00042 (according to SMB-000598_R). | REWORK | Need to respect the SMB-000598 at the last version (R currently). In this case, several flexibles' CMD changed since the version N (DY20103, DY20104, DY20100, DY20110, DY20111, DY20100 and DY20210). Please check the conformity of the flexibles onboard with the SMB-000598_R. |  |  | Não
NCR-ICN-ESC-12-0496-2021 | P0109071 | DY20110 | REMOVE AND REWORK | Replace the hose. Apply CMD 18FG205D00042 (according to SMB-000598_R). | REPAIR | Need to respect the SMB-000598 at the last version (R currently). In this case, several flexibles' CMD changed since the version N (DY20103, DY20104, DY20100, DY20110, DY20111, DY20100 and DY20210). Please check the conformity of the flexibles onboard with the SMB-000598_R. |  |  | Não
NCR-ICN-ESC-12-0496-2021 | P0109072 | DY20210 | REMOVE AND REWORK | Replace the hose. Apply CMD 18FG205D00042 (according to SMB-000598_R). | REPAIR | Need to respect the SMB-000598 at the last version (R currently). In this case, several flexibles' CMD changed since the version N (DY20103, DY20104, DY20100, DY20110, DY20111, DY20100 and DY20210). Please check the conformity of the flexibles onboard with the SMB-000598_R. |  |  | Não
NCR-ICN-ESC-12-0521-2021 | P0119674 | EL00007 | REWORK | Dismount the valve EL00007-18RT020D00007-SN.4-45-001-COPYARD on SBR2 and remounting a new one. Redo the inspections B06, B01, B07 and B02. ICN questions NG if it's necessary to open a NCR-MAT to ask a new valve to replace the stock or open a NCR-MAT and send the material to be repaired. |  | Proceed to a standard exchange of the valve EL00007-18RT020D00007 with a new valve from the stock or another SBR. Create a NCR MAT to expertise and repair the valve to refund the stock. Create a NCR-REGRESS to manage the inspections and tests to redo. | REWORK | In accordance with level 2,2 proposal. Update the traceability folder of the both valves : the damage one and the new mounted valve | Não
NCR-ICN-ESC-12-0566-2021 | P0103773 | BS02507 | REWORK | Provide the amount of material (CNX DRT 12 35x3 E67 CU) that is outstanding. Send to NG specialist. |  |  |  |  | Não
NCR-ICN-ESC-12-0577-2021 | P4121610 |  | REWORK | Remanufacture the spool following the project construction docs properly. Redo the M01, M05 and B01_KT03517 that was already carried out. Take care during new mounting to not denting the material. Update the NCR-ICN-REGRESS-12-0075-2021 mentioning this NCR-CQ, the spool reworked and the B01 test like reason. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0597-2021 | P0126204 | AM00004 | ACCEPT AS IT IS | The applied schene paint is enough for the integrity of the anti-corrosive protection as it is not a critical area according to SMB-002345 | ACCEPT AS IT IS | Accepted as it is |  |  | Não
NCR-ICN-ESC-12-0620-2021 | P0107646 | HJ62532R | REWORK | Provide a new connector to continue the construction process. | REWORK | Use connector from SBR4 if available Open a NCR-MAT to supply a new one connector D38999 / 26 FB 35 SN |  |  | Não
NCR-ICN-ESC-12-0630-2021 | P4165281 |  | REWORK | Dismount the deck plug EL00006-P0141690 and remount respecting the stud rods orientations, with hexagonal head turned up and the tab of the washer straight on flange. Redo the B06 and B07 inspections. Dismount the spool EL50001L1-P4165281 and and remount respecting the stud rods orientations, with hexagonal head turned up. Redo B06, M05 and M03. Open a NCR-REGRESS to redo the tests already carried out: B01/B02/S02/S03. |  |  |  |  | Sim
NCR-ICN-ESC-12-0630-2021 | P0141690 | EL00006 | REWORK | Dismount the deck plug EL00006-P0141690 and remount respecting the stud rods orientations, with hexagonal head turned up and the tab of the washer straight on flange. Redo the B06 and B07 inspections. Dismount the spool EL50001L1-P4165281 and and remount respecting the stud rods orientations, with hexagonal head turned up. Redo B06, M05 and M03. Open a NCR-REGRESS to redo the tests already carried out: B01/B02/S02/S03. |  |  |  |  | Sim | 16-006
NCR-ICN-ESC-12-0637-2021 | P0152199 | AC30005 | REMOVE AND REWORK | Paint the garbage ejector coaming, as shown in the attached sketch. | REWORK | rework as per croquis ( conform with SMB-002525). To paint the zone between the coaming and the equipment, it will necessary to remove the screws , clean, and take care to paint till the maximum of the possibility without touch the joint. On the seating and the equipment paint the machined not fonctional area Open a NCR regress. |  |  | Não
NCR-ICN-ESC-12-0637-2021 | P0122380 | FH02621 | REWORK | 1.The sleeve of passage AC30005 should be painted according to SMB-002525. As this work was not done in properly time sequence. Today is needed to move away the panels FH02621 and FH02623, without disconnecting them, dismounting the STUD RODS of the garbage ejector FP00100, paint the structure sleeve, without affecting the seal (O-ring). Remounting the stud rods and return the panels for theirs place. 2. Raise a NCR-REGRESS for redo the B06 inspection, updated the B07 and retest the B01/B02 following IT34-00-01E_B orientations. Redo, also, the E01 of electrical panels. | REWORK | Remove and rework |  |  | Não
NCR-ICN-ESC-12-0637-2021 | P0122382 | FH02623 | REWORK | 1.The sleeve of passage AC30005 should be painted according to SMB-002525. As this work was not done in properly time sequence. Today is needed to move away the panels FH02621 and FH02623, without disconnecting them, dismounting the STUD RODS of the garbage ejector FP00100, paint the structure sleeve, without affecting the seal (O-ring). Remounting the stud rods and return the panels for theirs place. 2. Raise a NCR-REGRESS for redo the B06 inspection, updated the B07 and retest the B01/B02 following IT34-00-01E_B orientations. Redo, also, the E01 of electrical panels. | REWORK | remove and rework |  |  | Não
NCR-ICN-ESC-12-0659-2021 | P4160281 |  | REMOVE AND REPAIR | ICN suggested changing CMD 18RO000D00439 to 18RO230D00566 between the tube and adapter 18RO000D00439 and that it is also possible to update the CTEs and document SBH.2A21.ISO.01.P4160281 as well. | REPAIR | See FTG-9614. |  |  | Não
NCR-ICN-ESC-12-0683-2021 | P0140161 | FQ00803 | REWORK | 1. Dismount the spool P4176456 and valve FQ00803. 2. Remount the valve FQ00803 using new fiber gasket and lock washers and following the B06 inspection orientations, remembering of doing the F06 before. 3. Raise a NCR-REGRESS to redo the F06, B06, B07, M05 and the PTRH/2 already carried out, as the S02. | REWORK | Agree with proposal. In complement NCR MAT will be raise to purchase new gasket and lock washers. |  |  | Sim | 6216726-007
NCR-ICN-ESC-12-0033-2019 | P0107006 | HG02510 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0033-2019 | P0107007 | HG02511 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0033-2019 | P0107010 | HG02512 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0033-2019 | P0107014 | HG02521 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0057-2020 | P0102154 | BB00040 | REMOVE AND REWORK | ICN suggest to machine a single piece female M45x1,5 and male OD25 RBS 24 from a CuAl Hexagonal bar. | OK - NOT MODIFIED | N/A - No connection problems. |  |  | Não
NCR-ICN-ESC-12-0057-2020 | P0102173 | BB21031 | REMOVE AND REWORK | ICN suggest to machine a single piece female M45x1,5 and male OD25 RBS 24 from a CuAl Hexagonal bar. | OK - NOT MODIFIED | N/A - No connection problems. |  |  | Não
NCR-ICN-ESC-12-0057-2020 | P0102171 | BB21032 | REMOVE AND REWORK | ICN suggest to machine a single piece female M45x1,5 and male OD25 RBS 24 from a CuAl Hexagonal bar. | OK - NOT MODIFIED | N/A - No connection problems. |  |  | Não
NCR-ICN-ESC-12-0057-2020 | P0102172 | BB21033 | REMOVE AND REWORK | ICN suggest to machine a single piece female M45x1,5 and male OD25 RBS 24 from a CuAl Hexagonal bar. | OK - NOT MODIFIED | N/A - No connection problems. |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157358 | UA05001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105439 | DM00005F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117766 | UA03110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117747 | UA03125 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146707 | RH02556 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107444 | HK02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122065 | EG00236 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146697 | HP02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146710 | RH02551 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107014 | HG02521 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117164 | KT23386 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118152 | UA04000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0145963 | HP02551 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143005 | HP02533 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123264 | KT05282 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0149962 | DA02000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148441 | EJ01008F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0151088 | DY00541 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105110 | BC02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103123 | BE0720AA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115426 | KT01043 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102430 | BE00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131424 | UL01000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105287 | DM00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146543 | BT26543 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115379 | KT01143 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112777 | DP24200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102444 | BE07100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118512 | EG01154 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123254 | KT05384 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107004 | HG02509 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107001 | DT14331P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103437 | BE2100BA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104554 | BH00011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0194932 | UE26010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108719 | RF00027 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117783 | UA03120 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110261 | DT04210 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119682 | KT06873 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156984 | HL12707 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136228 | BX00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146607 | RH02548 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124257 | GN02522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103699 | BF02552 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119112 | RM00013 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106979 | DT14120N | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103014 | BE00018 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104240 | BC02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109791 | KD26572 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107442 | HK02507 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122807 | FH00022 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122151 | EG01140 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108769 | RH02531 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106701 | DB23001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127080 | EZ10004P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146616 | GN02735 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103006 | BE00016 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107759 | HP02515 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143564 | HQ02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129044 | FV02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0149869 | DA22503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102990 | BE00017 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105125 | MB10111T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122147 | EG01159 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118782 | EG12610P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124384 | FR22300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137097 | EV02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104835 | BE00014 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102557 | BE0200CF | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123239 | KT05286 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122027 | EG00205 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103696 | BF02543 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119731 | KT06175 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114034 | KT01541 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137132 | EV03501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129800 | KT06286 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102432 | BE00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117897 | UA05120 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108782 | RH02530 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107016 | HG02525 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108314 | DS14300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117500 | KT23171 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102474 | BE08000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102204 | BB02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108671 | RF00023 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123272 | KT08382 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156991 | HL12711 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157007 | HL12723 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119590 | KT05371 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110410 | KD22590 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107440 | HK02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115376 | KT01643 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157035 | HL12820 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103629 | BF02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117992 | UA05127 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117860 | UA05104 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104035 | BT22512 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121233 | EM02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155197 | EF00501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124165 | GN02534 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117363 | RC20010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124048 | GN02540 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125169 | FH00011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0145119 | BD02527 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104221 | BC22501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124381 | FR22900 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118510 | EG01150 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106985 | DT14141T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107198 | DT00202 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157001 | HL12717 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107188 | DT00109 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132357 | ME10212M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114586 | KT01645 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157036 | HL12734 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118828 | EJ00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112529 | DW22500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102108 | BB02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117589 | KT14071P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124217 | GV02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102689 | BE2400AS | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117699 | KT19070P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106989 | DT14341T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122867 | EV00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120899 | ER00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119585 | KT05271 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0142323 | EJ00007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109793 | KD26571 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143472 | HQ02601 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105965 | ME16110T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146617 | GN02736 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103054 | BE0710CB | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107438 | HK02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121474 | FH00050 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138422 | ME12912Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122377 | FH02601 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133570 | BD00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123238 | KT05186 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112774 | DP24103 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117743 | UA03117 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143099 | BM00303 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119707 | KT08373 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107775 | HP02526 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102687 | BE2400AC | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157357 | UA04001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120431 | EM00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105464 | DM13004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102670 | BE2300AA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117788 | UA03108 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107764 | HP02518 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105174 | BB00031 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108311 | DS14100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115689 | KT01346 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132369 | FH00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109786 | KD03010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143267 | HJ02519 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135901 | BM00300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118446 | EG01156 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120675 | EQ00100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155353 | BE2400AD | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103438 | BE2200AA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117882 | UA05113 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117754 | UA03133 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117737 | UA03105 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106867 | GF02513 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106988 | DT14340T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118069 | RM02507 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122355 | FH02821F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105766 | ME25011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156995 | HL12713 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157014 | HL12730 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120893 | ER00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136865 | BD02522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0130251 | FC02521 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146725 | HJ02561 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195144 | UP02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120792 | EQ04500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117798 | UA03136 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153476 | DY01906 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107421 | HJ02516 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143743 | BX10017P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117968 | UA05138 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115592 | KT01546 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122373 | FH22513 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114791 | KT01144 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138359 | BX02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102686 | BE2400AB | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123262 | KT05484 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135337 | BX00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103779 | BS02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137624 | BD02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121711 | FH10201T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120786 | EQ03100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103814 | BT02522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104553 | BH00009 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105279 | DM00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105164 | MB25001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121616 | ER02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112531 | DW22501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117531 | KT18073Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122357 | FH02823F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122308 | FH00013 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153192 | HQ02602 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115850 | KT01042 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157000 | HL12716 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105157 | DM10003Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107002 | DT14332P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117262 | KT19587P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129432 | DA00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104391 | BC02522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117921 | UA05143 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117878 | UA05111 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125994 | HQ02706 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117925 | UA05141 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117862 | UA05105 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107755 | HP02534 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107098 | DV22502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122353 | FH02723F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155909 | FV02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121761 | ES02510 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107766 | HP02525 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107437 | HK02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138356 | BX02507 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114589 | KT01145 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108357 | DY13022P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112731 | DP14112 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102313 | BB12788 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119850 | EN02515 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107190 | DT00209 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117237 | KT23788 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118142 | RD02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117568 | KT15073P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146615 | GN02737 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108988 | UN24000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124345 | EZ00272 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126512 | HQ22715 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0194931 | UE26020 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117911 | UA05148 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121108 | ER00007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103745 | BK02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132017 | FC02524 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107774 | HP02537 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157003 | HL12719 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133568 | BD00016 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117768 | UA03114 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125995 | HQ02707 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137500 | FQ00101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125989 | HQ02710 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118184 | UA04210 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123244 | KT06886 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131487 | ME16710P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107753 | HP02511 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117866 | UA05107 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117099 | KT23182 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129795 | KT06182 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157005 | HL12721 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146619 | GN02740 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106000 | DP00100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121910 | FH02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108722 | RF00036 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107199 | DT00302 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105763 | ME25007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102471 | BE00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119668 | KT06173 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119738 | KT08475 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117990 | UA05128 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114408 | KT01341 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128153 | EJ00205 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121811 | FH00025 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122351 | FH02721F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112780 | DP24303 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124142 | GN02536 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103746 | BK02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106116 | DP00102 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118318 | HX02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118513 | EG01157 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114588 | KT01545 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117439 | KT23677 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112736 | DP14213 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125993 | HQ02705 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132346 | ME10111M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103632 | BF02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122044 | EG00130 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131417 | UL01002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103010 | BE00015 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117984 | UA05131 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117964 | UA05140 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117171 | KT15084P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136196 | BX00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136230 | BX00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138223 | BX02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107777 | HP02528 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102408 | BB02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153419 | DY23500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103697 | BF02550 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129426 | DA00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102434 | BE00007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132342 | ME10112M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157016 | HL12731 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115428 | KT01443 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0134084 | BM00049 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103004 | BE0610DA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133575 | BD00014 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103778 | BS02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125990 | HQ02711 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102245 | BB12716 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108787 | RH04310 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143563 | HQ02605 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114638 | KT01245 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102443 | BE07000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122380 | FH02621 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114029 | KT01641 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118320 | HX02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107476 | HJ02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104834 | BE00012 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103015 | BE0720BA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122063 | EG00234 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115899 | KT01342 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146409 | FC00523 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138426 | ME13012P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146723 | HJ02557 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117830 | UA03111 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117794 | UA03148 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127959 | EJ02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107200 | DT00110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143332 | BX10019P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118799 | EG12630N | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117880 | UA05112 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156976 | HL12700 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133613 | EQ05100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109824 | KD06060 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127482 | FG22556 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114035 | KT01141 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103622 | BE0900DB | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107404 | HJ02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108774 | RH02546 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140764 | RH22521 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102991 | BE0640DA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129433 | DA00009 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117760 | UA03145 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118000 | UA05000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117777 | UA03138 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103625 | BE00020 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117874 | UA05109 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126029 | HQ02713 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143628 | HJ02526 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119718 | KT06277 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112732 | DP14113 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129102 | EX02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0149511 | EJ00050 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157004 | HL12720 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138428 | ME13011P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107770 | HP02524 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107195 | HG02550 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115968 | DJ00042 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117988 | UA05129 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132283 | UL00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0151095 | DY00542 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135390 | BQ10001T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104778 | BT02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119594 | KT06171 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132358 | ME10312M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105127 | MB10211T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117899 | UA05121 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117886 | UA05115 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122383 | FH02625 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119713 | KT06377 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129796 | KT06184 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107024 | HG02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106986 | DT14142T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109823 | KD06050 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119132 | RM00012 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117974 | UA05135 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117982 | UA05132 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131180 | FC02526 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137801 | FQ02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104055 | BT22549 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103700 | BF02553 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104060 | BT22562 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117919 | UA05144 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106992 | DT14131P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117561 | KT23375 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157013 | HL12729 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137625 | BD02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107429 | HK02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118332 | HX02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125889 | RC00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146709 | RH02550 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118026 | RM02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102228 | BB12698 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119608 | KT06771 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118248 | UW03004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156988 | HL12708 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115591 | KT01646 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108721 | RF00033 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108340 | DY02511 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107842 | HP22501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120895 | ER00009 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140427 | DP00101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0142981 | HP02532 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122809 | FH00014 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117762 | UA03102 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105343 | ME00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104174 | BT02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114840 | KT01244 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118245 | UW03002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122039 | ES00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106998 | DT14330P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107063 | HG02552 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120208 | EL02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117275 | KX25000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109817 | KD06030 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143741 | BX10020P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107780 | HP02521 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108716 | RF00024 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118445 | EG01152 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157011 | HL12727 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106909 | DP00302 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117913 | UA05147 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126037 | HQ02712 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119505 | RA00011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157002 | HL12718 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117800 | UA03128 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119958 | EN00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155907 | FV02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119670 | KT06273 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107408 | HJ02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123263 | KT05182 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117915 | UA05146 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123276 | KT06782 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119712 | KT06473 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124385 | FR22800 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118863 | EG12710Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117976 | UA05134 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114898 | KT01344 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0145117 | BD02528 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140392 | FG22563 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112786 | DP24701 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119700 | KT06373 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121994 | FH00017 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115642 | KT01046 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129884 | FC00522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136812 | FC00031 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135902 | BM00400 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115809 | KT01142 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106253 | DP00202 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119644 | KT06971 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123261 | KT06384 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138273 | BX02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119656 | KT05373 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131806 | FR00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131475 | FC02527 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107402 | HJ02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102918 | BH22509 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121079 | EM00007F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156977 | HL12701 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102436 | BE05000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106996 | DT14231P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110267 | DT04200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133577 | BD00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107640 | DV00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128803 | FV00214 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109819 | KD06040 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132914 | DP00301 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102576 | BE0200CE | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153217 | HQ02704 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143580 | HQ02603 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0152276 | HJ02507 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153514 | RA00013 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103337 | DA02602 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143451 | EG00144 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107403 | HJ02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124148 | GN22546 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124498 | EZ00300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122363 | FH12601Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0134667 | BQ10002T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115851 | KT01242 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109789 | KD03020 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118169 | UA06200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117484 | KT23173 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114707 | KT01345 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122062 | EG00140 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138782 | DJ00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126752 | EW00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133619 | EQ05200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107018 | HG02526 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102440 | BE06100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157010 | HL12726 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106980 | DT14220N | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103707 | BF22703 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0142980 | HP02507 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131616 | FC02523 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107778 | HP02529 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157039 | HL12804 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104051 | BT22513 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103776 | BS02510 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118067 | RM02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136467 | EG01120 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119978 | EF02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122808 | FH00026 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138840 | DJ02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105772 | ME11412M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110031 | KD07020 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109795 | KD04010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103624 | BE0900DD | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123258 | KT06884 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107754 | HP02512 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129098 | FV02601 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103476 | BE2640CD | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117516 | KT23273 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104066 | BT22574 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123268 | KT06282 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129799 | KT06284 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115852 | KT01442 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106990 | DT14342T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117802 | UA03132 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118068 | RM02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103042 | BE0500BF | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103781 | BS02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121089 | EM02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148202 | DM22502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107060 | HG02546 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135967 | BX00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124313 | GN22701 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107406 | HJ02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143452 | EG00143 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112821 | BF02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121082 | EM00013F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117813 | UA03139 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156982 | HL12704 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138272 | BX02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133569 | BD00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121805 | FH00021 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107191 | DT00309 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121763 | ES02517 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119642 | KT06471 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115808 | KT01542 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117192 | KT23382 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117815 | UA03135 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123247 | KT06288 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102421 | BE01000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143511 | BM00302 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118852 | EG12670N | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118137 | RE02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117826 | UA03116 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117828 | UA03107 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123274 | KT06382 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117572 | KT23373 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106087 | ME03102 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105463 | DM13003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132279 | EF02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156989 | HL12709 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127445 | FG22561 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155913 | FV00500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117534 | KT23271 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107007 | HG02511 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102420 | BE00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112734 | DP14211 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117136 | KT23282 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114841 | KT01444 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120643 | EQ03300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117832 | UA03115 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127074 | EZ10008P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156971 | HL12801 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118636 | EG01153 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0113049 | DP02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127476 | FG22554 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118244 | UW03001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118829 | EJ00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104392 | BC02622 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123260 | KT06484 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119610 | KT05471 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114261 | KT01041 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112742 | DP13001M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148449 | EJ00017 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119615 | KT06371 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107737 | DS00113 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105771 | ME11411M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117115 | KT23284 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123249 | KT06486 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117923 | UA05142 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103124 | BE2500CA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129043 | FV02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140947 | GN22756 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120647 | EQ03400 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133571 | BD00015 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119582 | KT05171 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109054 | HE22510 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108322 | DS14221P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117026 | KT23688 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0152277 | HJ02509 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115807 | KT01642 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115644 | KT01446 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123245 | KT06388 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119740 | KT06875 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119556 | EJ00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117970 | UA05137 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117996 | UA05125 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108308 | DS02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0134083 | BM00401 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132142 | UP02800 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128192 | FC00524 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105159 | DM10004Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103336 | DA02603 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117901 | UA05122 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102690 | BE240AAE | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0134082 | BM00301 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117773 | UA03130 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0144272 | BT02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127481 | FG22555 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121261 | ER00500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123250 | KT06386 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102381 | BB12860 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127081 | EZ10002P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123271 | KT06982 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119690 | KT05473 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136227 | BX00007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133574 | BD00013 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110262 | DT04310 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102472 | BE00009 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118249 | UW03005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127439 | FG02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109790 | KD25000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117811 | UA03143 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107455 | HK02511 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114788 | KT01644 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120057 | EF02510 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104836 | BE00013 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124911 | HQ02700 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128346 | FV00102 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114839 | KT01044 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122372 | FH22512 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117584 | KT23371 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117764 | UA03106 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0159324 | UP02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108822 | UE02220 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118166 | UA06100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140002 | FR22400 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148440 | EJ01007F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0150701 | HJ02567 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102435 | BE03000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118319 | HX02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117893 | UA05118 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107456 | HK02512 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124141 | GN02539 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108318 | DS14121P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117853 | UA05101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117063 | KT23286 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106089 | ME03101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117779 | UA03142 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122150 | EG01130 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102419 | BE00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143000 | HP02513 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103698 | BF02551 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143518 | BM00410 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146708 | RH02549 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146618 | GN02739 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119818 | KT06871 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117775 | UA03134 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115484 | KT01343 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109676 | KE28000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117978 | UA05133 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102581 | BE0200CD | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123267 | KT06882 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108315 | DS14110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102623 | BE2300BA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105197 | DM00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138312 | BX02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120058 | EF02511 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119827 | EN00010F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125996 | HQ02708 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126026 | HQ02724 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157012 | HL12728 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112902 | BB02600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107062 | HG02551 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143388 | BM00411 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112784 | DP24700 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102364 | BB12842 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118181 | UA04110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108977 | UN03000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107441 | HK02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118888 | RM00058 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123246 | KT06488 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117895 | UA05119 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132355 | FH00015 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126031 | HQ02714 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119650 | KT05173 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107638 | DV00093 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114264 | KT01441 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114790 | KT01544 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119741 | KT06475 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117756 | UA03137 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106994 | DT14132P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119715 | KT06477 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115427 | KT01243 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128355 | FV00101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117864 | UA05106 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102047 | BB12627 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122349 | FH02517F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106908 | DP00300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106249 | DP00200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112690 | DP14111 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118251 | UW03007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107639 | DV00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108836 | UE03000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118247 | UW03003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127079 | EZ10006P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146282 | BT26282 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119943 | EN00006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110263 | DT02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121609 | ER00002F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114639 | KT01445 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117994 | UA05126 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122578 | FH02550 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127485 | FG22560 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104058 | BT22556 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117781 | UA03146 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107025 | HG02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123275 | KT05482 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118250 | UW03006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118179 | UA07100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123253 | KT05284 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117607 | KT23777 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115554 | DJ10007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115643 | KT01246 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133576 | BD00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118065 | RM02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136799 | FC00030 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110264 | DT04100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122379 | FH02901 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106709 | DB23002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115999 | DJ00004 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102681 | BE2400CA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117809 | UA03124 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138219 | BX02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112797 | DP03300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117836 | UA03123 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118180 | UA04120 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140948 | GN22748 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103090 | BE0720CA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104020 | BT02533 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117771 | UA03126 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104552 | BH00010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0194935 | UE07000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107439 | HK02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106987 | DT14240T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103780 | BS02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117903 | UA05123 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128216 | FC00525 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117790 | UA03104 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156992 | HL12712 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119789 | KT06375 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140713 | RH22518 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117819 | UA03127 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104057 | BT22555 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107411 | HJ02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121815 | ES02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0155421 | EF02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119529 | UW05000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117175 | KT23384 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143231 | BX10018P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118254 | UW03010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117855 | UA05102 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118183 | UA04200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102615 | BE2640BD | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106995 | DT14230P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136866 | BD02521 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148198 | DM22500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102030 | BB12609 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115378 | KT01543 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0130188 | FC02522 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117796 | UA03140 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106737 | DN02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108718 | RF00026 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143873 | HG02553 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117822 | UA03118 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117745 | UA03121 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117888 | UA05116 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118185 | UA04220 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117868 | UA05108 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0194929 | UA04400 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108313 | DS14310 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123548 | UA07000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102431 | BE00006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118252 | UW03008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127486 | FG22559 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104558 | BH00107 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156990 | HL12710 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156981 | HL12703 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108771 | RH02542 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102347 | BB12824 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129188 | FV02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117917 | UA05145 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119653 | KT05273 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143598 | EJ00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123251 | KT05486 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117467 | KT23275 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110260 | DT04110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112778 | DP24203 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136464 | EG01110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0144273 | BT02504 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117805 | UA03112 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106997 | DT14232P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127474 | FG22551 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117758 | UA03141 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0135279 | BX00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108981 | GS22502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105198 | DM00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117249 | KT23580 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118139 | RE02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137623 | BD02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117966 | UA05139 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117876 | UA05110 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108835 | UE02000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146287 | BT26287 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0137620 | BD02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106981 | DT14320N | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119726 | KT05275 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119728 | KT05375 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117749 | UA03129 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118025 | RM02505 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102262 | BB12734 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114263 | KT01241 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0114636 | KT01045 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156975 | HL12810 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107022 | HG02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107762 | HP02517 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122007 | FH00018 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122116 | EG01165 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157018 | HL12733 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102081 | BB12663 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117792 | UA03144 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122024 | ES00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133579 | BD00006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133578 | BD00005 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117785 | UA03103 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0128827 | FC00530 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117252 | KT23480 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117807 | UA03147 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157037 | HL12803 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118321 | HX02506 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121806 | ES02500 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117905 | UA05124 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119829 | EN00013F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115552 | DJ10006Q | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131660 | ME03000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117891 | UA05117 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107452 | HK02510 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0138309 | BX02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156997 | HL12714 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157017 | HL12732 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156985 | HL12706 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0136229 | BX00006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121809 | FH00023 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112735 | DP14212 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195203 | KE25400 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117834 | UA03119 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102915 | BH02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112751 | DP13003M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157034 | HL12802 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102330 | BB12806 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121473 | FH00016 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117451 | KT23175 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133572 | BD00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105128 | MB10311T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118182 | UA04100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102207 | BB22502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117741 | UA03113 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117824 | UA03122 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106991 | DT14130P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118759 | EG12620P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107015 | HG02524 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146724 | HJ02559 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133573 | BD00007 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120905 | ER00012 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0115594 | KT01146 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117817 | UA03131 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0104070 | BT22586 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117735 | UA03101 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0121709 | ER02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123240 | KT05386 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127479 | FG22558 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148205 | DM22501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122868 | EV00011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120788 | EQ03200 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0148443 | EJ00008 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131663 | ME03002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122371 | FH02602 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131416 | UL01001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106983 | DT14140T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105109 | BC02502 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0133757 | EN02516 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118066 | RM02501 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117039 | KT23186 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143536 | UW04000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125794 | FC00520 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0107765 | HP02531 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123252 | KT05184 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0157006 | HL12722 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118253 | UW03009 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0108321 | DS14321P | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119733 | KT06275 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106235 | DP00201 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119778 | KT05475 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117083 | KT23184 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0146701 | HJ02527 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123273 | KT06482 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0112744 | DP13002M | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127480 | FG22562 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0120903 | ER00011 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105437 | DM00004F | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0105199 | DM00003 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0130282 | FC02520 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0129797 | KT06186 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0145201 | EJ00006 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0131804 | FR00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0117739 | UA03109 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0126784 | DA02560 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0140824 | RH02532 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123265 | KT05382 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119720 | KT05175 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0118160 | UA06000 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123561 | UA06600 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0119597 | KT06271 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0102688 | BE0400AA | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0110268 | DT04300 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0127966 | EJ02503 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0122382 | FH02623 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156499 | EJ00152 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0109483 | KE25203 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195187 | KE25010 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156490 | EJ00052 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195196 | KE25205 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195189 | KE25800 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195188 | KE25204 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195194 | KE25309 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132156 | EF00002 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153337 | KD26578 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143697 | HG02561 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195192 | KE25206 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106674 | DP00204 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124144 | GN02537 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195193 | KE25310 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143700 | HG02562 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156497 | EJ00151 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0103774 | BS02508 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0125441 | FP00100 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195190 | KE25201 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195195 | KE25208 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132125 | EF00001 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0153336 | KD26577 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132170 | EF00029 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132173 | EF00018 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0124143 | GN02535 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143701 | HG02563 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106872 | DP00104 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0195191 | KE25202 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0113118 | KE25020 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0156410 | UL00027 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0123076 | EV12000T | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0106921 | DP00304 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143698 | HG02565 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0132175 | EF00017 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0119-2020 | P0143702 | HG02564 | REWORK | Send to level 2. | REWORK | Check and apply if necessary SMB-002443 and SMB-051148 in reference |  |  | Não
NCR-ICN-ESC-12-0191-2020 | P0105110 | BC02501 | REWORK | Send to level 2. | REWORK | The copper bar E4 (pole +) received are not compliant with the required design, see annex. Could not be fixed on board on the Forward Direct Current Main Switchboard BC02501 (pole +) Tempory mounting solution given by TA : use 2 cables CEI 1x120 mm² per pole of battery, meaning 6 cables per BC02501 (pole +), use the same tempory solution like SBR1 HOW EVER THIS SOLUTION NOT ALLOW TO USE FULL POWER MAXIMUM ALLOW IS 1250A PER BATTERY ( Stephane Rideau) | SCRAP | Destruction of non-conforming material. Naval group will replenishment the material conform. According to paragraph 2.2, for the temporary solution : installation of 6 120mm² cables per pole. | Não
NCR-ICN-ESC-12-0371-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0493-2021 | P0107799 | DV00041 | REWORK | In compliance with (COR-2021-900343) for NRV 53B-DV00041 valve, perform visual inspection and internal cleaning if necessary of the equipment, will be done during the commissioning process pneumatic test S03 for cleaning the system. |  |  |  |  | Sim | 01PM300D00007
NCR-ICN-ESC-12-0433-2021 | P0105294 | DM00013 | [6 empty] | Não
NCR-ICN-ESC-12-0433-2021 | P0129902 | EN00010 | [6 empty] | Não
NCR-ICN-ESC-12-0450-2021 | P0136946 | BQ00006 | REWORK | Remove the damaged screw, clean and treat the internal thread of the valve. reassemble install a new screw CMx 32VI110D00167 - SCREW H M39X100X100 CL12.9 FLZN. Repair the drilling, remove the valve and shims for the workshop, machine the valve and shims together to a new diameter and fabricate new guide pins. | REWORK | 'Physical on board: -The mounting is conform to the COS-SMB-319718 rev C (Screws X05T / nuts A4-80 / washers NL stainless steel) instead of COS-SMB-319718 rev D (srews CL12.9 / nuts CL12 / washers NL steel). -Due to the lack of stock of screw X05T it was mounted one srew CL12.9 -Due to the modification of the positioning of the valves, holes of pins are not in line and it's necessary to increase the diameter (initially Ø16). Inconsistencies: - The COS-SMB-319718 rev D specify the using of Nord Lock washers in steel (32VI410D00138 STEEL WASHER N-L ND39 DELTA-PROTEKT) but the mounting drawing SBH.2D30.SAD.005739_L F15 specify stainless steel plain washers. - The COS to manufacture seating COS-SMB-319547 rev C / drawing SBH.2D30.SMD.005740_I F22 specify the manufacturing of centering pins Ø16 (items 27-28-29-30 des carlingages BQ00005C / P4165388 et BQ00006C / P4165387) in steel S355 (01BA110D00142 S355J2 STEEL GRADE CIRCULAR BAR DIA 18MM) but the mounting drawing SBH.2D30.SAD.005739_L F15 specify centering pins Ø16 in stainless steel. Action NG: - Inform which material it's necessary to use (bolting and pin) and confirm torque value on SMB-327319 B - Inform the possibility to increase diameter of centering pins (Ø18 maximum). - Update document to remove inconsistencies Action ICN: -The mounting of SBR1 have to be verified to identify the material of bolting. - Manufacture one screw with X05T to change the screw in 12.9 (with Nord-Lock washers) - ICN have to provide positionning before and after machining holes of pins of BQ valve with dimensions of pins already manufactured and material. - Raise NCR for BQ00005 to follow the same physical mounting and inconsistencies |  |  | Sim | 5170481
NCR-ICN-ESC-12-0460-2021 | P4123639 |  | REMOVE AND REWORK | [5 empty] | Sim
NCR-ICN-ESC-12-0460-2021 | P0126934 | KT03612 | REMOVE AND REWORK | [5 empty] | Sim | 18RT000D00025
NCR-ICN-ESC-12-0495-2021 | P0103773 | BS02507 | AGREE WITH LEVEL 2.1 | ICN Preservation team asks NG for orientation on how to proceed. | REPAIR | Update of the NCR: NG confirms the damage of 4 batteries, instead of 2. From the photos and videos provided by ICN, the torque applied for the tightening to the batteries seems too high( more than 15 Nm) for some batteries, damaging the thread of the screw of two batteries. These batteries, according to ICN, were not untightened since the acceptance from the manufacturer. Naval Group Front Office suggests to take 4 batteries from SBR and equalize with the 16 other batteries. This NCR is being sent for Level 3(Back Office BS system specialist) in order to decide what to do with the manufacturer. | SCRAP | Additional information to be transmitted to level 3: - Communicate to NG on the presence of oxidation / deposits on the pole threads, take pictures if there are any. - Check the presence of oxidation / deposits on the threads of the SBR3 and SBR4 battery poles. Temporary action: - Take 4 accumulators from SBR3 or SBR4 batteries which have a no-load voltage greater than 1.2V, and perform an equalization: discharge all the accumulators from the SBR2 battery and the 4 accumulators up to 1.0V per cell, then charge forced from 8h at 0.2C. Definitive action: - Do NOT create NCR-MAT for replenishment => A full set of BS batteries is already being restocked for the SBR2. Delivery expected Q2-2022. The BS batteries currently in Brazil and identified as defective wil be able to be scrapped by ICN following the delivery of the new accumulators. | Não
NCR-ICN-ESC-12-0495-2021 | P0103774 | BS02508 | AGREE WITH LEVEL 2.1 | ICN Preservation team asks NG for orientation on how to proceed. | REPAIR | Update of the NCR: NG confirms the damage of 4 batteries, instead of 2. From the photos and videos provided by ICN, the torque applied for the tightening to the batteries seems too high( more than 15 Nm) for some batteries, damaging the thread of the screw of two batteries. These batteries, according to ICN, were not untightened since the acceptance from the manufacturer. Naval Group Front Office suggests to take 4 batteries from SBR and equalize with the 16 other batteries. This NCR is being sent for Level 3(Back Office BS system specialist) in order to decide what to do with the manufacturer. | SCRAP | Additional information to be transmitted to level 3: - Communicate to NG on the presence of oxidation / deposits on the pole threads, take pictures if there are any. - Check the presence of oxidation / deposits on the threads of the SBR3 and SBR4 battery poles. Temporary action: - Take 4 accumulators from SBR3 or SBR4 batteries which have a no-load voltage greater than 1.2V, and perform an equalization: discharge all the accumulators from the SBR2 battery and the 4 accumulators up to 1.0V per cell, then charge forced from 8h at 0.2C. Definitive action: - Do NOT create NCR-MAT for replenishment => A full set of BS batteries is already being restocked for the SBR2. Delivery expected Q2-2022. The BS batteries currently in Brazil and identified as defective wil be able to be scrapped by ICN following the delivery of the new accumulators. | Não
NCR-ICN-UFEM-12-0547-2021 | N/A |  | REWORK | 1. The BORFLEX lips seal is out of tolerance and manufactured according MAT424-1296_A. See ANNEX 1; 2. The BORFLEX cannot be installed in the hatch as per ANNEX 2; 3. Continue the hatch assembly with non-conform SMAC lip seal; 4. Check the good assembly of the seal and perform the Resistance Test at PEH (70 bar) in the Hyperbaric Chamber; 5. Open a NCR-MAT to supply new parts; 6. During onboard integration phase replace the SMAC lip seal by a new seal manufactured according MAT424-1296_B. Check the dimensions before mounting; 7. The Leak Test (PEE) will be validate after vacuum test of the submarine; 8. The non-conform seals must be scrapped. | SCRAP | The lip seal is out of tolerance on the external diameter not conform to MAT424-1296 B |  |  | Não
NCR-ICN-UFEM-12-0547-2021 | SC4-AG00017-MT |  | SCRAP | 1. The BORFLEX lips seal is out of tolerance and manufactured according MAT424-1296_A. See ANNEX 1; 2. The BORFLEX cannot be installed in the hatch as per ANNEX 2; 3. Continue the hatch assembly with non-conform SMAC lip seal; 4. Check the good assembly of the seal and perform the Resistance Test at PEH (70 bar) in the Hyperbaric Chamber; 5. Open a NCR-MAT to supply new parts; 6. During onboard integration phase replace the SMAC lip seal by a new seal manufactured according MAT424-1296_B. Check the dimensions before mounting; 7. The Leak Test (PEE) will be validate after vacuum test of the submarine; 8. The non-conform seals must be scrapped. | SCRAP | The lip seal is out of tolerance on the external diameter not conform to MAT424-1296 B |  |  | Não
NCR-ICN-ESC-12-0552-2021 | P0151127 | AC41019 | REWORK | Correct the construction book DEI-331842-80500-12-001 considering that MAT45-0609 informations and the SBH.1A10.TUY.004136_H about the spools which are mounted in the mobile AC41019. Remount the mobile AC41019-P0151127 (01PM100D00052-6227186-2015-01) using the correct orientation using a new FIBER/NBR GASKET 131X157X3 CMD: 44JO230D00243 and news 24 LOCK WHASER CMD: 32VI420D00031, remembering to grease the gasket and to balance well the studs. Check if the internal part of the sleeve is painted, if no, do this properly. Redo B06 and B07 inspection and the B01/B02 don't need be regressed cause for these tests the ruchs already have being disconected, so the ruchs thightness will be verified in the S02 test. | REWORK | Agree with proposal. -The drawing MAT425-0609 folio:42 have to be updated. -But B01 and B02 for the internal pipes were regressed a NCR REGRESS have to be raise. -It's possible to indicate that S02 will be replace B01 and B02 for the ruch connection because valves were not dismounted. |  |  | Sim | 01PM100D00052-6227186-2015-01
NCR-ICN-ESC-12-0552-2021 | P0151126 | AC31019 | REWORK | Correct the construction book DEI-331842-80500-12-001 considering that MAT45-0609 informations and the SBH.1A10.TUY.004136_H about the spools which are mounted in the mobile AC41019. Remount the mobile AC41019-P0151127 (01PM100D00052-6227186-2015-01) using the correct orientation using a new FIBER/NBR GASKET 131X157X3 CMD: 44JO230D00243 and news 24 LOCK WHASER CMD: 32VI420D00031, remembering to grease the gasket and to balance well the studs. Check if the internal part of the sleeve is painted, if no, do this properly. Redo B06 and B07 inspection and the B01/B02 don't need be regressed cause for these tests the ruchs already have being disconected, so the ruchs thightness will be verified in the S02 test. | REWORK | Agree with proposal. -The drawing MAT425-0609 folio:42 have to be updated. -But B01 and B02 for the internal pipes were regressed a NCR REGRESS have to be raise. -It's possible to indicate that S02 will be replace B01 and B02 for the ruch connection because valves were not dismounted. |  |  | Não
NCR-ICN-ESC-12-0576-2021 | P4121999 |  | REWORK | Remanufacture the spool following the project construction docs properly. Redo the M01, M05 and B01_KT03518 that was already carried out. Take care during new mounting to not denting the material. Update the NCR-ICN-REGRESS-12-0074-2021 mentioning this NCR-CQ, the spool reworked and the B01 test like reason. | REWORK |  | REWORK | The B01 pressure test is not suffisant, it is necessary to pressurise the spool at 250B with KT00818 closed, KT05018open in accordance with PTRH SMB-051122 concerning KT sub-system. The damaged spool has to be scrapped. | Não
NCR-ICN-ESC-12-0599-2021 | P0145381 | BT0650BD | REWORK | Use the equipment provided for the "SBR4" available in the warehouse referring to the same "CMD's" and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0599-2021 | P0135498 | BE0300AE | REWORK | Use the equipment provided for the "SBR4" available in the warehouse referring to the same "CMD's" and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0599-2021 | P0143089 | BE0400CR | REWORK | Use the equipment provided for the "SBR4" available in the warehouse referring to the same "CMD's" and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0613-2021 | P0145859 | AG00013 | REWORK | For the AG00013 assembly process, the items 10 and 13 referring to MAT424-1054 / MAT424-1056_EXP_B, Perform manufacture the pins in the larger size than specified and assemble in order. See the length annex 1 in the list. For items 8, 9, 11 and 12 items, supply a new items for SBR2. Open NCR MAT. | REWORK | Take from store new ones Raise NCR MAT to purchase new spare parts |  |  | Sim | 01PE200D00041
NCR-ICN-ESC-12-0613-2021 | P0156477 | AG00033H | REWORK | For the AG00013 assembly process, the items 10 and 13 referring to MAT424-1054 / MAT424-1056_EXP_B, Perform manufacture the pins in the larger size than specified and assemble in order. See the length annex 1 in the list. For items 8, 9, 11 and 12 items, supply a new items for SBR2. Open NCR MAT. | REWORK | Take from store new ones Raise NCR MAT to purchase new spare parts |  |  | Não
NCR-ICN-ESC-12-0628-2021 | P4125767 |  | ACCEPT AS IT IS | ICN suggests accepting it as is, ie changing the flange to 18RO120D00033. |  |  |  |  | Não
NCR-ICN-ESC-12-0636-2021 | P0107516 | HP00001 | REWORK | Dismount the spools P4127236 and the valve HP00001, and remount correctly using the bolting stud and nut style 1 - X6NiCrTiMoVB25-15-2 + lock tab washer made of X6CrNiTi18-10 as it's said on SMB-002930_I and SMB-200960_I for circuits under pressure hull integrity. It’s important redo and update all inspections and tests already done like B06/B07/M05, registering on a NCR-REGRESS. | REWORK |  | REWORK | In accordance with the proposal Don´t forget to redo F06 inspections also. Take care also of the length of the stud rods for the mounting to have the 2 threads on each side of the flange | Não
NCR-ICN-ESC-12-0636-2021 | P4127236 |  | REWORK | Dismount the spools P4127236 and the valve HP00001, and remount correctly using the bolting stud and nut style 1 - X6NiCrTiMoVB25-15-2 + lock tab washer made of X6CrNiTi18-10 as it's said on SMB-002930_I and SMB-200960_I for circuits under pressure hull integrity. It’s important redo and update all inspections and tests already done like B06/B07/M05, registering on a NCR-REGRESS. | REWORK |  | REWORK | In accordance with the proposal Don´t forget to redo F06 inspections also. Take care also of the length of the stud rods for the mounting to have the 2 threads on each side of the flange | Não
NCR-ICN-ESC-12-0648-2021 | P0131827 | HL40080 | REWORK | 1.Remount the hatch HL40080 on SBR2 using news items that can be supplied or manufactured. If manufactured, respect the following drawings with all materials and dimensions specifications, and do a G01 for dimensional inspection or/and a G06 for dimensional inspection of machining process. Do B06 and B07 for hatch HL40080. | REWORK | Agree with proposal. Manufacture new tab washers with the material dedicated and material certificate. For parts not manufactured it's necessary to raise NCR MAT to purchase new ones. |  |  | Sim | C0001
NCR-ICN-ESC-12-0682-2021 | P4121692 |  | REMOVE AND REWORK | ICN propose to adjust the lower support according to the DW ampoule. | REPAIR | Cut the lower stopper Ajust and reweld after adjustment. Carry out 100% VT ,20% RT 100% MT |  |  | Não
NCR-ICN-UFEM-12-0524-2019 | P0109742 | KO02550 | REWORK | Replace the joystick | REWORK | Please send this NCR to level 3 (Patrick Renavot),for analyse and purshase NG will analyse if the damage is due to a design defect or bad treatment of the material The protection team must protect the joystick. | REWORK | Please send this NCR to level 3 (Patrick Renavot),for analyse and purshase NG will analyse if the damage is due to a design defect or bad treatment of the material The protection team must protect the joystick. | Não
NCR-ICN-UFEM-12-0524-2019 | P0109740 | KO02560 | REWORK | Replace the joystick | REWORK | Please send this NCR to level 3 (Patrick Renavot),for analyse and purshase NG will analyse if the damage is due to a design defect or bad treatment of the material The protection team must protect the joystick. | REWORK | Please send this NCR to level 3 (Patrick Renavot),for analyse and purshase NG will analyse if the damage is due to a design defect or bad treatment of the material The protection team must protect the joystick. | Não
NCR-ICN-ESC-12-0111-2020 | P0104825 | MB00307 | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  | REWORK | Please apply following modifications : - PR Addendum SMB-TDP-PR-6782896 and SMB-TDP-PR-6782897 loaded in TDP IS on 10/03/2021 - 32VI310D00299 / 9980000039624 NUT H M14 42CRMO4 to be delivered in batch SMB-US07A-DB90-SAH | Não
NCR-ICN-ESC-12-0111-2020 | P4129698 |  | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  | REWORK | Please apply following modifications : - PR Addendum SMB-TDP-PR-6782896 and SMB-TDP-PR-6782897 loaded in TDP IS on 10/03/2021 - 32VI310D00299 / 9980000039624 NUT H M14 42CRMO4 to be delivered in batch SMB-US07A-DB90-SAH | Sim
NCR-ICN-ESC-12-0143-2020 | P4119026 |  | REPAIR | see annex for repair | REPAIR | - Remove the welding around elements 648 and 649 to prevent deterioration of suport base - Carry out 100%VT - Cut a new element and bend it. - Tack weld new element and verify if the interference is desappeared - Weld and carry out inspection required in IT21-02-10E - Carry out leak test of lower floor. - Carry out leak test of battery room. | REWORK | Please apply PR Addendum loaded in TDP IS on 03/02/2021 : Seating : SMB-TDP-PR-6779506 SMB-TDP-PR-6779507 SMB-TDP-PR-6779488 | Não
NCR-ICN-ESC-12-0204-2020 | SC2-BR-MT |  | ACCEPT AS IT IS | Accept as it is. Send to Level 2 and DA to validate. | ACCEPT AS IT IS | Accept as it is . use a machining shim on the longitudinal flat bar to correct the deviation.( see photo in annex). to be confirmed by L3. | REPAIR | The thicknesses noted at the level of the holes in the edge plate do not affect the structural strength at this stage, however particular attention must be paid to monitoring the thicknesses of the edge plate during the life of SBR2. BUT - standardize the material used for the shims - take a clearance record after placing the shims. - if the shims cannot be of unique geometry, they must be marked to ensure the geographical traceability of these shims. The marking must be proposed to the BO. Repair actions are the responsibility of ICN (through the NCR) but also assigned to the Front Office to guarantee their completion and return to the Back Office. | Não
NCR-ICN-ESC-12-0242-2020 | P4116956 |  | REMOVE AND REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0273-2020 | P0104801 | MB00007 | ACCEPT AS IT IS | Send to level 2. |  |  |  |  | Não
NCR-ICN-ESC-12-0273-2020 | P0104798 | MB00004 | ACCEPT AS IT IS | Send to level 2. |  |  |  |  | Sim | 15LA000D00025
NCR-ICN-ESC-12-0273-2020 | P0131520 | MB00003 | ACCEPT AS IT IS | Send to level 2. |  |  |  |  | Sim | AP398227
NCR-ICN-ESC-12-0289-2020 | P0130936 | KT00751 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126967 | KT00752 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130937 | KT00753 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126969 | KT00754 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130938 | KT00755 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126970 | KT00756 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130939 | KT01A51 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126972 | KT01A52 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153302 | KT01A53 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153314 | KT01A54 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153312 | KT01A55 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153317 | KT01A56 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153296 | KT01B51 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0153320 | KT01B52 | REWORK | The "tightening torque" must be performed according to their respective B11-19. | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0131070 | KT00251 | REWORK | Perform ("again", if applicable) the B02_KT0025X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126914 | KT00252 | REWORK | Perform ("again", if applicable) the B02_KT0025X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130926 | KT00253 | REWORK | Perform ("again", if applicable) the B02_KT0025X and B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126915 | KT00254 | REWORK | Perform ("again", if applicable) the B02_KT0025X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130927 | KT00255 | REWORK | Perform ("again", if applicable) the B02_KT0025X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126916 | KT00256 | REWORK | Perform ("again", if applicable) the B02_KT0025X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0103903 | KT00551 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126931 | KT00552 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130904 | KT00553 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126933 | KT00554 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0130905 | KT00555 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0289-2020 | P0126932 | KT00556 | REWORK | Perform ("again", if applicable) the B02_KT0055X (where the word "X" is the TLT numbers 1-6). | REWORK | KT0075X, KT01A5X and KT01B5X were tight more at the good torque value: Use paint on the nuts after mounting to be sure the nuts will be not untight. B11-19 will be redone for each TLT B02_KT0025X will be carry out for each TLT. After a special tool will be available a pressure test on the internal door at 52,5bar will be carry out Redo B02-KT0025x and B05 will be updated | REWORK | In accordance with the rework on the tightening torques, the pressure test and edition of new inspection sheets (mounting and tests) David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0329-2021 | B02KT03614 |  | REWORK | Scenario: During the activities of the KT, it was identified that the KT21A54 / P0153313 / 11CI120D00052 electrical connector present in the internal door of the TLT4 has more than one of the pins broken. Solution: 1) Replace that conector by new one following the procedure "Remove / Replace the wire guidance & remote adjustment crossings - SBR-ETM-000KTM0001_A pages 744-745 - Work Sheet T06", see the attached document; 2) The inspections B02_KT00554 and B02_KT00254 will be carry out again; 3) After a special tool will be available, a pressure test on the internal door at 52,5bar will be carry out (if this tool is only provided for the internal door); 4) Open a NCR MAT; 5) Perform the following protocols: KD13C / K11C / K11; Observation: see the following NCR "NCR-ICN-ESC-12-0289-2020". | REMOVE AND REWORK | The correct identification is KT01A54, NGD 1045-14-443-6718. It is necessary to raise a NCR MAT in order to have a new one, ok for B02, but it is not necessary to redo KT13C - KT11C or KT 11. | REWORK | In accordance with level 2 proposal - the B07, B05 inspections have to be updated after the pressure test done and traceabiltiy folder of the TLT concerned is updated. ICN has to inform NAVAL GROUP about the root causes of the breakage which has never been encountered with this type of equipment. | Não
NCR-ICN-ESC-12-0329-2021 | B02KT00254 |  | REWORK | Scenario: During the activities of the KT, it was identified that the KT21A54 / P0153313 / 11CI120D00052 electrical connector present in the internal door of the TLT4 has more than one of the pins broken. Solution: 1) Replace that conector by new one following the procedure "Remove / Replace the wire guidance & remote adjustment crossings - SBR-ETM-000KTM0001_A pages 744-745 - Work Sheet T06", see the attached document; 2) The inspections B02_KT00554 and B02_KT00254 will be carry out again; 3) After a special tool will be available, a pressure test on the internal door at 52,5bar will be carry out (if this tool is only provided for the internal door); 4) Open a NCR MAT; 5) Perform the following protocols: KD13C / K11C / K11; Observation: see the following NCR "NCR-ICN-ESC-12-0289-2020". | REMOVE AND REWORK | The correct identification is KT01A54, NGD 1045-14-443-6718. It is necessary to raise a NCR MAT in order to have a new one, ok for B02, but it is not necessary to redo KT13C - KT11C or KT 11. | REWORK | In accordance with level 2 proposal - the B07, B05 inspections have to be updated after the pressure test done and traceabiltiy folder of the TLT concerned is updated. ICN has to inform NAVAL GROUP about the root causes of the breakage which has never been encountered with this type of equipment. | Não
NCR-ICN-ESC-12-0355-2021 | P0154394 | AC32059 | REWORK |  | ACCEPT AS IT IS | refere to the NCR-12-0341-2021 |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P0154382 | AC32062 | REWORK |  | ACCEPT AS IT IS | refere to the NCR -12-0341-2021 |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P0154385 | AC32063 | REWORK |  | ACCEPT AS IT IS | refere to the NCR-12-0341-2021 |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P0154386 | AC32064 | REWORK |  | ACCEPT AS IT IS | refere to the NCR-12-0341-2021 |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P0154396 | AC32065 | REWORK |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4162013 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4162012 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4162003 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4161988 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4161987 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0355-2021 | P4161989 |  | REWORK |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0395-2021 | P4026010 |  | REPAIR |  | REPAIR | Agrees with paragraph 2.1: lenght of the screw adjusted and bolting assembly in steel material. |  |  | Não
NCR-ICN-ESC-12-0444-2021 | P0120399 | EM00013 | REWORK | 1. Retest the inspections B01/B02_EM00013 to validate the resistance and watertightness of the EM00013-P0120399 valve flanges. Dismount the pipe EM50100Y1-P4129081. Fit the test device over the valve EM00018 and let the valve EM00012-P0120301 OPEN. Fit a block flange over hull passage AC32013. Apply the pressure for resistance test (B01) +1% according to IT34-00-01E_B, 71 bar during 30 minutes, if no external leaks, return the pressure to 0 (zero) and performing the watertightness test (B02) feeding 53,5 bar during 30 minutes too. The internal leak inspection between the EM00013-P0120399 flanges will be ensured through the pressure drop in test manometer. External leaks is not acceptable. 2. After retests, the pipe EM50100Y1-P4129081 should be remounted and M05 and S02 updated. | ACCEPT AS IT IS | The pressure test was done without leak. B05 will be updated with new B01 and B02 | REWORK | In accordance with proposal Raise NCR REGRESS and redo all inspections concerning this equipment. (David BERNEDE - ISSP) | Sim | 008-ISSARTEL
NCR-ICN-ESC-12-0444-2021 | P4129081 |  | REWORK | 1. Retest the inspections B01/B02_EM00013 to validate the resistance and watertightness of the EM00013-P0120399 valve flanges. Dismount the pipe EM50100Y1-P4129081. Fit the test device over the valve EM00018 and let the valve EM00012-P0120301 OPEN. Fit a block flange over hull passage AC32013. Apply the pressure for resistance test (B01) +1% according to IT34-00-01E_B, 71 bar during 30 minutes, if no external leaks, return the pressure to 0 (zero) and performing the watertightness test (B02) feeding 53,5 bar during 30 minutes too. The internal leak inspection between the EM00013-P0120399 flanges will be ensured through the pressure drop in test manometer. External leaks is not acceptable. 2. After retests, the pipe EM50100Y1-P4129081 should be remounted and M05 and S02 updated. | ACCEPT AS IT IS | The pressure test was done without leak. B05 will be updated with new B01 and B02 | REWORK | In accordance with proposal Raise NCR REGRESS and redo all inspections concerning this equipment. (David BERNEDE - ISSP) | Não
NCR-ICN-ESC-12-0455-2021 | P0151172 | AC41016 | MANUFACTURE | P0151172- AC41016-17/001 - The nut retainer need to be manufacturing in ICN workshop cause there's not in warehouse, using the MAT425-0513_N, even, the same material. And a new gasket also need to be used in the AC41016 remounting. Ensure that the inspections CTEs will be correctly filled and the B01/B02 retest has be carry out again. | REWORK | Agree with proposal. NCR REGRESS should be raise to carry out inspections and pressure tests. B05 should be updated. |  |  | Sim | 17/001
NCR-ICN-ESC-12-0464-2021 | N/A |  | REWORK | Send to level two. After the problem was identified, some dimensional checks were carried out requested by Naval Grgoup Technical Assistance (TA). | REWORK | After all the verifications done it look like the holes of the soft patch male aren't in the good position. The gap of 0,2 (check done at 0,25 in some forward parts) when the adjust bolt are mount show that don't have any contact in the forward faces under the male and the female at this position. Proposal of NG FO is to adjust the male holes with reamer and machine new adjust bolts in order to maintain the soft patch at this position. After adjust the holes and install all the bolt it will be necessary to machine the surface of the female flex bar (seal support) in order to re-create one plan. Send to level 3 for validation |  |  | Não
NCR-ICN-ESC-12-0478-2021 | P0123723 | GN02546 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Agree with decision N1. Open a NCR-MAT to supply o new one 11CD200D000711. |  |  | Não
NCR-ICN-ESC-12-0507-2021 | N/A |  |  |  | REWORK | It is necessary to: cleaning , degreasing, Change the bolting damaged, brush, to remove the rust, and the dust, after that repaint and greasing |  |  | Não
NCR-ICN-ESC-12-0546-2021 | P4169746 |  | REWORK | Dismounting the studs and remounting correctly and being sure that the pitch diameter rods protruding from nuts is equal (in length) and with less then 2 threads. Use a new fiber gasket 44JO230D00059 and 12 lock washers 32VI420D00030 (6 for each flanges side) how is specified by project. Redo inspections B06-CTE01038955 and B07-CTE00953235 of the deck plug EQ00412 and new M03-CTE00994675 of the spool to granted the material traceability, paying attention in good filling. Raise the NCR-REGRESS for the tests already carried out and one, of the type NCR-MAT, to replace the materials used, if it's needed. | REWORK | In accordance with N1. | REWORK | In accordance wih level 1 and 2 – raise a NCR REGRESS and update all inspections concerned (David Bernède) | Sim
NCR-ICN-ESC-12-0546-2021 | P0120631 | EQ00412 | REWORK | The deck plug will not be dismounted its support out. Just the flange of the spools EJ50031J3 will be disconected of the deck plug flange. |  | In accordance with N1. | REWORK | In accordance wih level 1 and 2 – raise a NCR REGRESS and update all inspections concerned (David Bernède) | Sim | 16/003
NCR-ICN-ESC-12-0572-2021 | P4019157 |  | REWORK | Send to NG to adapt the seating. | REPAIR | After onboard inspection any interference has been identified. As the photos below, ICN manufactured the seating as the 3D model but there is a divergence between the definition plan SBH.PLM.3D30.000166_F (240 mm) and the 3D mockup (203,6 mm). For SBR1 any register of this problem has been identified and according to ICN the dimension used was also the same as the 3D model. | REPAIR | The decision taken to modify the seating according to the 3D mockup to avoid any interference is the right one. For SBR3 and SBR4 do the same. | Não
NCR-ICN-ESC-12-0588-2021 | P4126686 |  | REMOVE AND REWORK | ICN propose to dismantle the bottom tube (EJ50048E2) and rotate the flange in the corresponding position. To adjust the tube to the new condition, it is necessary to add a straub gasket on P4126686 as shown in the drawing (annex 1). | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0588-2021 | P0119080 | EJ00132 | REWORK | ICN propose to dismantle the bottom tube (EJ50048E2) and rotate the flange in the corresponding position. To adjust the tube to the new condition, it is necessary to add a straub gasket on P4126686 as shown in the drawing (annex 1). | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0588-2021 | P4126696 |  | REMOVE AND REWORK | ICN propose to dismantle the bottom tube (EJ50048E2) and rotate the flange in the corresponding position. To adjust the tube to the new condition, it is necessary to add a straub gasket on P4126686 as shown in the drawing (annex 1). | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0611-2021 | P4152783 |  | REPAIR | ICN suggest apply finish paint in the area with lower thickness according scheme paint D2 (see annex). | REPAIR | A painting isn´t a subsitute of galvanisation, In this case it can be o poutside protection of the pipe. |  |  | Não
NCR-ICN-ESC-12-0611-2021 | P4153056 |  | REPAIR | ICN suggest apply finish paint in the area with lower thickness according scheme paint D2 (see annex). | REPAIR | A painting isn´t a subsitute of galvanisation, In this case it can be o poutside protection of the pipe. |  |  | Não
NCR-ICN-ESC-12-0611-2021 | P4133151 |  | REPAIR | ICN suggest apply finish paint in the area with lower thickness according scheme paint D2 (see annex). | REPAIR | A painting isn´t a subsitute of galvanisation, In this case it can be o poutside protection of the pipe. |  |  | Sim
NCR-ICN-ESC-12-0611-2021 | P4153066 |  | REPAIR | ICN suggest apply finish paint in the area with lower thickness according scheme paint D2 (see annex). | REPAIR | A painting isn´t a subsitute of galvanisation, In this case it can be o poutside protection of the pipe. |  |  | Sim
NCR-ICN-ESC-12-0623-2021 | P0131460 | DP04200 | REWORK | Provide the missing item or a new set to continue the construction process. |  |  |  |  | Não
NCR-ICN-ESC-12-0632-2021 | P0131553 | UL00025 | REPAIR | [5 empty] | Não
NCR-ICN-ESC-12-0642-2021 | P0156477 | AG00033H | REWORK | According email historic and attached the alignment report of balancing system AG00033 before machining (NCR-ICN-ESC-12-0397-2021). Rework, carry out machining bearings according tolerances: o Side Ø55 the 2 sets of bearings at Ø55 0/+0,046 o Side Ø48 the 2 sets of bearings at Ø48 +0,07/+0,10 To be reassembly, follow instruction: o Mark the positions of bearings to avoid mixing; o Assembly the Bearing Caps (Rep. 09 and 59) and tight the screws manually; o Note: The ¼ of turning is impossible to apply. o Check the clearance of 0,5 mm after tightening the bearing caps; o Reaming the inner diameters Ø55H8 and Ø44H8 in the same axis. Coaxiality of 0,02 mm between 3 positions; o Assembly the Hinge Axis (Rep. 56) and Hinge Arm (Rep. 07) in the Hinge Support (Rep. 01) and control the arm movement. The movement should be without hard point and fluid. Send report final machining and coaxiality. |  |  |  |  | Não
NCR-ICN-ESC-12-0672-2021 | P0145852 | AG00019 | REPAIR | Repair. For attend the assembly of the hatch 53B-AG00019, Perform new adjust in the pipe P4119245, must be allowing full opening and closing of hatch on board. |  |  |  |  | Sim | 01PE200D00029
NCR-ICN-ESC-12-0672-2021 | P4119254 | [7 empty] | Não
NCR-ICN-UFEM-12-0507-2019 | P0125467 | FP00200 | ACCEPT AS IT IS | Do not remove. | ACCEPT AS IT IS | As the air bottle is now not accessible, TA suggests to blow, with HP dry air, the internal of the bottle. Decision to be validated by specialist level 3 | REPAIR | Naval Group validate the AT proposal to blow with HP dry air the internal of the bottle | Não
NCR-ICN-UFEM-12-0537-2019 | P0133574 | BD00013 | REWORK | See DA 3.2 comments and attachments. The products were added according PROD 6.1 request. |  |  | REWORK | Replace the defective elbows, Naval Group will send new ones - Check the entire SBR 1/2/3/4 series to check if the problem is present on the other SMs. | Não
NCR-ICN-UFEM-12-0537-2019 | P0133575 | BD00014 | REWORK | See DA 3.2 comments and attachments. The products were added according PROD 6.1 request. |  |  | REWORK | Replace the defective elbows, Naval Group will send new ones - Check the entire SBR 1/2/3/4 series to check if the problem is present on the other SMs. | Não
NCR-ICN-UFEM-12-0537-2019 | P0133571 | BD00015 | REWORK | See DA 3.2 comments and attachments. The products were added according PROD 6.1 request. |  |  | REWORK | Replace the defective elbows, Naval Group will send new ones - Check the entire SBR 1/2/3/4 series to check if the problem is present on the other SMs. | Não
NCR-ICN-UFEM-12-0537-2019 | P0133568 | BD00016 | REWORK | See DA 3.2 comments and attachments. The products were added according PROD 6.1 request. |  |  | REWORK | Replace the defective elbows, Naval Group will send new ones - Check the entire SBR 1/2/3/4 series to check if the problem is present on the other SMs. | Não
NCR-ICN-ESC-12-0148-2020 | P4109894 |  | REMOVE AND REPAIR |  | REPAIR | See FTG-8923 |  |  | Não
NCR-ICN-ESC-12-0148-2020 | P4109890 |  | REMOVE AND REPAIR |  | REPAIR | See FTG-8923 |  |  | Não
NCR-ICN-ESC-12-0148-2020 | P4109893 |  | REMOVE AND REPAIR |  | REPAIR | See FTG-8923 |  |  | Não
NCR-ICN-ESC-12-0148-2020 | P4120621 |  | REMOVE AND REPAIR |  | REPAIR | See FTG-8923 |  |  | Não
NCR-ICN-ESC-12-0186-2020 | P0107517 | HP00002 | REPAIR | Repair the valve | REPAIR | This valve has be damaged due to bad alignment, to have a new O-ring kit it is necessary to raise an NCR MAT. | REWORK | A NCR MAT has to be raised and sentto level 3 to analyze if only new o'ring is sufficient and if all the valves needs to be checked by a specialist. It is necessary before changing the o'ring to inspect completely the valve including a dimensional check/measurement of all parts of the valve | Não
NCR-ICN-ESC-12-0286-2020 | P0194613 | KT03517R | REMOVE AND REWORK | Problems occurred in the valves (KT03517 and KT03518): - Orientation of switch box not correct (both sides); - Fixing on the support with holes oblong and support not correctly positioning (both sides). Solution of this issue: - Remove the valves KT03517 / KT03518, put the switch box in correct orientation and redo all inspection about these valves. | REWORK | -In accordance with level 2.1 -NCR-ICN-ESC-12-0244-2020 for valves KT01417 and KT01418 is in link with this NCR. -A NCR REGRESS will be raise to follow new inspections and tests. ( Patrick Daliguet) | REWORK | --> Remove valves KT03517 / KT03518 and put the switch box in correct orientation. --> Check well manoeuvre of the valves in both positions open and close. --> Redo all inspections about these valves, raise a NCR REGRESS. This operation must be mentionned in the valves tracability file. Nota : actions above mentionned do not impact tightness nor strength --> new pressure tests are not required. | Não
NCR-ICN-ESC-12-0286-2020 | P0194614 | KT03518R | REMOVE AND REWORK | Problems occurred in the valves (KT03517 and KT03518): - Orientation of switch box not correct (both sides); - Fixing on the support with holes oblong and support not correctly positioning (both sides). Solution of this issue: - Remove the valves KT03517 / KT03518, put the switch box in correct orientation and redo all inspection about these valves. | REWORK | -In accordance with level 2.1 -NCR-ICN-ESC-12-0244-2020 for valves KT01417 and KT01418 is in link with this NCR. -A NCR REGRESS will be raise to follow new inspections and tests. ( Patrick Daliguet) | REWORK | --> Remove valves KT03517 / KT03518 and put the switch box in correct orientation. --> Check well manoeuvre of the valves in both positions open and close. --> Redo all inspections about these valves, raise a NCR REGRESS. This operation must be mentionned in the valves tracability file. Nota : actions above mentionned do not impact tightness nor strength --> new pressure tests are not required. | Não
NCR-ICN-ESC-12-0291-2020 | P4123636 |  | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0369-2021 | P0153314 | KT01A54 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | 2 cases possible: 1)-it's possible to repair: repair the connector and check the good functionality 2)-not possible to repair and it will be necessary to change: NCR regress will be raise to redo all inspections and test (B11,B07, B02 ...) and NCR MAT to purchase a new one. |  |  | Sim | 91LT000D00006
NCR-ICN-ESC-12-0332-2021 | P4022827 |  | REWORK |  | REWORK | To correct the position of CA elements , and respect the alignment with lubber line, it´s necessary to build up all the holes. -Use a copper back support After welding carry out 100 VT, and 100% MT or DP. -Carry out a new drilling. in respect of the reference alignment and hight. in parallele due the dismount of the part of equipment P0117844, it will necessary to blast and paint the half ring (see SMB-002723) following the painting document BDMAT-BDM-00053491-A1 |  |  | Não
NCR-ICN-ESC-12-0429-2021 | P0151137 | AC41020 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | 6388773-MEGA-P-002
NCR-ICN-ESC-12-0429-2021 | P0154574 | AC42068 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418422-F3013
NCR-ICN-ESC-12-0429-2021 | P0154568 | AC42069 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418401-F3013
NCR-ICN-ESC-12-0429-2021 | P0154576 | AC42070 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418423-F3013
NCR-ICN-ESC-12-0429-2021 | P0154564 | AC42071 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP425211-F3013
NCR-ICN-ESC-12-0429-2021 | P0154566 | AC42072 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418404-F3013
NCR-ICN-ESC-12-0429-2021 | P0154570 | AC42073 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP424252-F3013
NCR-ICN-ESC-12-0429-2021 | P0154572 | AC42074 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP424248-F3013
NCR-ICN-ESC-12-0429-2021 | P0156017 | AC42085 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418387-F3013
NCR-ICN-ESC-12-0429-2021 | P0151937 | AC43055 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418416-F3013
NCR-ICN-ESC-12-0429-2021 | P0151763 | AC43058 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418418-F3013
NCR-ICN-ESC-12-0429-2021 | P0152060 | AC43060 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418419-F3013
NCR-ICN-ESC-12-0429-2021 | P0152088 | AC44028 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418394-F3013
NCR-ICN-ESC-12-0429-2021 | P0152097 | AC44032 | REWORK |  | REWORK | update and provide the missing informations |  |  | Sim | AP418392-F3013
NCR-ICN-ESC-12-0429-2021 | P0151724 | AC43051 | REWORK |  | REWORK | update and provide the missing informations |  |  | Não
NCR-ICN-ESC-12-0429-2021 | P0151728 | AC43053 | REWORK |  | REWORK | update and provide the missing informations |  |  | Não
NCR-ICN-ESC-12-0429-2021 | P0152020 | AC44046 | REWORK |  | REWORK | update and provide the missing informations |  |  | Não
NCR-ICN-ESC-12-0429-2021 | P0108976 | UE24400D | REWORK |  | REWORK | update and provide the missing informations |  |  | Não
NCR-ICN-ESC-12-0429-2021 | P0145859 | AG00013 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0151131 | AC41021 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0152022 | AC44047 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0152024 | AC44050 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0152059 | AC44048 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0116730 | KT03518 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0429-2021 | P0113044 | KT03517 | REWORK | [5 empty] | Não
NCR-ICN-ESC-12-0449-2021 | P0136396 | BQ00075 | AGREE WITH LEVEL 2.1 | It's needed to change de bolt stud 32VI220D00002 (M16X80) by 32VI220D00003 (M16X85). It's not needed the others fixing elements cause the assembly was just positioned without tight. | REWORK | In accordance with level 1.2 |  |  | Sim | 16
NCR-ICN-ESC-12-0449-2021 | P0137222 | BQ00086 | AGREE WITH LEVEL 2.1 | It's needed to change de bolt stud 32VI220D00002 (M16X80) by 32VI220D00003 (M16X85). It's not needed the others fixing elements cause the assembly was just positioned without tight. | REWORK | In accordance with level 1.2 |  |  | Sim | 16
NCR-ICN-ESC-12-0456-2021 | P0118606 | RM00001 | REWORK | The supplied screw does not meet the RM00001 equipment assembly process. To assemble the equipment, it is necessary to use a 15mm larger screw in length. It is suggested the screw that meets the correct length: 1. SCREW H M16X160X44 A4L-80 – CMD 32VI120D00318 – total: 11 unit. 2. SCREW H M16X180X44 A4L-80 – CMD 32VI120D00319 – total: 5 unit. References SMB-002465 and SMB-000500. | REWORK | TA NG propose to replace these screw by the following screws so: - SCREW HM16x160x44- A4L80 - CMD 32VI120D00318 - NGD 0930930261849. Available in the Batch: RM-SMB1-US07A-DB6/01_PARTE2 - SCREW HM16x180x44-A4L80 - CMD 32VI120D00319 - NGD 5305145376820. There are available in the Batch: RM-SMB1-US07A-DB2/01_PARTE2 Raise a NCR MAT to re-order and re completed the batches. |  |  | Não
NCR-ICN-ESC-12-0462-2021 | P0125624 | BB02506 | AGREE WITH LEVEL 2.1 | [5 empty] | Não
NCR-ICN-ESC-12-0462-2021 | P0124835 | BB02507 | AGREE WITH LEVEL 2.1 | [5 empty] | Não
NCR-ICN-UFEM-12-0546-2021 | N/A |  | REWORK | Rework. See comments and solution in attachment "2.1 ICN SOLUTION". Send to TA Patrick Daliguet to analysis. | REWORK | Agree with level 2.1, the work was done following annex enclosed. | REWORK | In accordance with rework done at the shipyard to allow right maneuver of the hatch AG00017 / balancing AG00037. Please proceed to a dimensional report of the parts and join it to the traceability file of the hatch and balancing. | Não
NCR-ICN-UFEM-12-0546-2021 | SC4-AG00037 |  | REWORK | Rework. See comments and solution in attachment "2.1 ICN SOLUTION". Send to TA Patrick Daliguet to analysis. | REWORK | Agree with level 2.1, the work was done following annex enclosed. | REWORK | In accordance with rework done at the shipyard to allow right maneuver of the hatch AG00017 / balancing AG00037. Please proceed to a dimensional report of the parts and join it to the traceability file of the hatch and balancing. | Não
NCR-ICN-ESC-12-0547-2021 | P4057932 |  | ACCEPT AS IT IS | ICN proposes that the NG accept as it is in view that for P4057932 we are 19% higher (62 mm instead of 52 mm) and for P4051911 we are 14% higher (126 mm instead of 110 mm).” | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0547-2021 | P4051911 |  | ACCEPT AS IT IS | ICN proposes that the NG accept as it is in view that for P4057932 we are 19% higher (62 mm instead of 52 mm) and for P4051911 we are 14% higher (126 mm instead of 110 mm).” | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0585-2021 | P0127959 | EJ02501 | REWORK | Repair paintwork and provide the outside of ventilation (fins) + filter, or replace with a new set. | REWORK | The CTE00758526 is a E01 inspection, it's not a control of shock sensor 1 - in what circumstance, did the shock sensor trigger? 2 - Has the follow-up form been completed? please put it as an attachment Wait for level 3 instruction |  |  | Não
NCR-ICN-ESC-12-0598-2021 | P0117366 | RC60021D | REWORK | Use the supplied connectors for the "SBR4" an "NCR-MAT" the same supply for the "SBR2" and a new supply for the "SBR4". |  |  |  |  | Não
NCR-ICN-ESC-12-0598-2021 | P0117427 | RC60012D | REWORK | Use the supplied connectors for the "SBR4" an "NCR-MAT" the same supply for the "SBR2" and a new supply for the "SBR4". |  |  |  |  | Não
NCR-ICN-ESC-12-0598-2021 | P0117423 | RC60011D | REWORK | Use the supplied connectors for the "SBR4" an "NCR-MAT" the same supply for the "SBR2" and a new supply for the "SBR4". |  |  |  |  | Não
NCR-ICN-ESC-12-0598-2021 | P0108896 | RH62621D | REWORK | Use the supplied connectors for the "SBR4" an "NCR-MAT" the same supply for the "SBR2" and a new supply for the "SBR4". |  |  |  |  | Não
NCR-ICN-ESC-12-0615-2021 | P0146676 | AG00066 | REWORK | For the assembly process of equipment 53B-AG00066 - P0146676 CMD 14VM000D00011 - NAV.BRIDGE LOWER TRUNK QUICK SHUT hatch, according to MAT424-0892. Supply a new part NGD 5975142425989 - SLEEVE TYPE CA (material -POLYCHLORPENE TYPE 31B6), Ref. MAT131-0018 and MAT131-0019. Open NCR MAT. | REWORK | Change the rubber by new ones from store. Raise NCR MAT to purchase a new ones. |  |  | Sim | 14VM000D00011
NCR-ICN-ESC-12-0624-2021 | P0119106 | RM00207 | REPAIR | Change seals |  |  |  |  | Não
NCR-ICN-ESC-12-0633-2021 | P0101583 | OO02500 | REWORK | Expert assessment level 2 will be required. |  |  |  |  | Sim
NCR-ICN-ESC-12-0633-2021 | P0106089 | ME03101 | REWORK | Expert assessment level 2 will be required. |  |  |  |  | Sim
NCR-ICN-ESC-12-0633-2021 | P0106087 | ME03102 | REWORK | Expert assessment level 2 will be required. |  |  |  |  | Sim
NCR-ICN-ESC-12-0644-2021 | P0115999 | DJ00004 | REWORK | Use the electrical connection base of these same equipment supplied for the "SBR4" and open an "NCR-MAT" for a new supply. | REWORK | Replace the motor of the DJ00004 valve. Study the possibility of repairing the electrical bases Open an NCR-MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0103312 | BE0900AE | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0103218 | BE0800AE | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102985 | BE0B00AC | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102983 | BE0B00AA | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102668 | BE0610CC | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102657 | BE0610BC | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0138889 | BE0B00AF | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102984 | BE0B00AB | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0103495 | BE0500AE | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0103494 | BE0500AD | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0674-2021 | P0102986 | BE0B00AE | REWORK | Use the domes of the luminaires supplied for the SBR4 and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0025-2019 | P4168094 |  | REWORK | the screw should be replaced with one larger than two threads. | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0122-2020 | P0101407 | OO02530 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0101409 | OO02531 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0101411 | OO02532 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0101410 | OO02533 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0101413 | OO02534 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0101583 | OO02500 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Sim
NCR-ICN-ESC-12-0122-2020 | P0145119 | BD02527 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Não
NCR-ICN-ESC-12-0122-2020 | P0145117 | BD02528 | REWORK | REWORK | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Não
NCR-ICN-ESC-12-0122-2020 | P0101414 | OO02536 | REWORK |  | REWORK | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors |  |  | Não
NCR-ICN-ESC-12-0171-2020 | P0101922 | BB01012 | ACCEPT AS IT IS | Send to level 2. | REWORK | BB01012 (CMD 19AS000D00006): - Ask Level 3 to create NGD for items 6.10 and 11. - Open an NCR-MAT to supply 2 items of each in RMS |  |  | Não
NCR-ICN-ESC-12-0171-2020 | P0156811 | BB01013 | ACCEPT AS IT IS | Send to level 2. | REWORK | BB01012 (CMD 19AS000D00006): - Update drawing from 13.5mm to 14mm (see drawing in Appendix 2) |  |  | Não
NCR-ICN-ESC-12-0200-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0246-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0287-2020 | P0153286 | KT01461 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153281 | KT01462 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153284 | KT01463 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153279 | KT01464 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153283 | KT01465 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153290 | KT01466 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153287 | KT01451 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153280 | KT01452 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153285 | KT01453 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0127042 | KT01454 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153282 | KT01455 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0287-2020 | P0153289 | KT01456 | REWORK | Send to level 2 | REWORK | The material on board is correctly mounting. The CMD on material is conform with the designation. The problem is between the functionnal mark and the CMD. For KT0145X the CMD necessary is 01PE00D00062 For KT0146X the CMD necessary is 01PE00D00063 It's possible to inverse on document SMB-000676 and SMB000677 | REWORK | Documents SMB-000676 and SMB-000677 will be updated, (batch 41). | Sim | NO CONFORM
NCR-ICN-ESC-12-0326-2021 | P0123239 | KT05286 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REMOVE AND REWORK | The socket has been damage due to a poor protection, it is for that it is not possible to connect it. So now it is necessary to raise a NCR MAT in order to replace this device by the same device to take on SBR 4 or 3, and to order a new socket to repare this one damaged. Record all the serial number between the Damaged valve and the new. |  |  | Não
NCR-ICN-ESC-12-0345-2021 | SP0009623 |  | REWORK | Add a section to the pipe. | REPAIR | The same issue was reported on SBR1 the solution will be the same On SBR1 NCR-ICN-ESC-11-0703-2019 the project should not been update but Job Order information should be read carefully by the production team Decision: REPAIR As per Job Order information, ICN designated this spool with adjustable length in its extremeties. Naval Group suggests to manufacture a new spool with more length of adjustment in its extremities. |  |  | Não
NCR-ICN-ESC-12-0388-2021 | P4151725 |  | ACCEPT AS IT IS | Send to level 2. |  |  |  |  | Não
NCR-ICN-ESC-12-0421-2021 | P4117185 |  | REMOVE AND REWORK | For AB35055: Before mounting the pipe DW50250Y1, it is necessary to check the status of the surface (Roughness). A specific inspection file has to be raised to be sure that the passage is in accordance with the requirements. For AB35013: It is necessary to dismount the pipe and the adaptator. The surface of the AB35013 ballast tank passage has to be machined in conformity with TDP IS requirements. For the others passage: To perform properly the painting, it is necessary to remove the adaptor which is tight in the ballast passage and to machine the passage in conformity with the TDP IS requirements. | REWORK | Rework as per ICN proposal. Open a NCR/Regress |  |  | Não
NCR-ICN-ESC-12-0452-2021 | P4170477 |  | REMOVE AND REWORK | Modify the Spool as defined in the attached FTG-8264-SBR2. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0452-2021 | P4170479 |  | REMOVE AND REWORK | Modify the Spool as defined in the attached FTG-8264-SBR2. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0461-2021 | P0116730 | KT03518 | REWORK | Pay 1 new unit of the NGD 5935144580825 and 5970997800444 to remounting the KT06488 connector that was damaged during a pre-test. | REWORK | Agree with proposal. The traceability folder should be updated with new swithches. | REWORK | In accordance with level 2.2 proposal. | Sim | 024
NCR-ICN-ESC-12-0472-2021 | B02KT03611 |  | REWORK | Scenario: During a pre-test (52.5 bar) on TLT1 (SBR2), to verify all flanges and finalize the Flooding and Draining Circuit TLT 1-3-5 installation, it was observed a leak on the body of the filling/draining valve "KT01011 / 18RT000D00200" of the TLT1. Solution: 1) Replace this valve "KT01011 / 18RT000D00200" by new one from SBR3 / SBR4; 2) Redo the B02 / B01 (B01_ KT03611 / B02_ KT03611 - adapted with the special tool inside the TLT1). |  |  |  |  | Não
NCR-ICN-ESC-12-0472-2021 | B01KT03611 |  | REWORK | Scenario: During a pre-test (52.5 bar) on TLT1 (SBR2), to verify all flanges and finalize the Flooding and Draining Circuit TLT 1-3-5 installation, it was observed a leak on the body of the filling/draining valve "KT01011 / 18RT000D00200" of the TLT1. Solution: 1) Replace this valve "KT01011 / 18RT000D00200" by new one from SBR3 / SBR4; 2) Redo the B02 / B01 (B01_ KT03611 / B02_ KT03611 - adapted with the special tool inside the TLT1). |  |  |  |  | Não
NCR-ICN-ESC-12-0506-2021 | N/A |  |  |  | REWORK | It is necessary to: cleaning , degreasing, Change the bolting damaged, brush, to remove the rust, and the dust, after that repaint and greasing, raise a NCR MAT to re-order the bolting. |  |  | Não
NCR-ICN-ESC-12-0540-2021 | P0115556 | DJ00002L | REMOVE AND REWORK | The actuator must be repaired or replaced with a new one. | REINSPECT THE ELEMENT | AUMA actuators are all inspected before shipment. Please specify the origin of the overvoltage. An assessment of the conditions of use must be carried out in order not to reproduce the same incident. Update 14/07/21: Due of a supply issue of the actuator DJ00002 during trials at workshop, found that the PCB SUPPLY is burned (varistance) picture attached OM 121319 to replace the valve by a new actuator 07.1 Open NCR MAT to buy a new PCB SUPPLY for AUMA 05.1 in order to repair the actuator and put back in warehouse. |  |  | Não
NCR-ICN-ESC-12-0581-2021 | P0120903 | ER00011 | REWORK | To connect the cable ER62514R in the forward part of the ER00011 it's needed dismounting temporary the spool ER50068X2-P4160794 and ER50067X2-P4160797, just. To connect the cable ER62515R in the forward part of the ER00012 it’s needed dismounting temporary the spool ER50070X3-P4160800, just. This problem happened because these spools were mounted before connecting these cables, so it's important to keep this matter to avoid rewords on SBR3 and 4 too. |  |  |  |  | Não
NCR-ICN-ESC-12-0581-2021 | P0120905 | ER00012 | REWORK | To connect the cable ER62514R in the forward part of the ER00011 it's needed dismounting temporary the spool ER50068X2-P4160794 and ER50067X2-P4160797, just. To connect the cable ER62515R in the forward part of the ER00012 it’s needed dismounting temporary the spool ER50070X3-P4160800, just. This problem happened because these spools were mounted before connecting these cables, so it's important to keep this matter to avoid rewords on SBR3 and 4 too. |  |  |  |  | Não
NCR-ICN-ESC-12-0579-2021 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0607-2021 | P0141082 | KO60513B | REWORK | Use the supplied complete connectors on the "SBR2" for another Submarine and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0607-2021 | P0141087 | KO60514B | REWORK | Use the supplied complete connectors on the "SBR2" for another Submarine and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0607-2021 | P0143624 | UW64554D | REWORK | Use the supplied complete connectors on the "SBR2" for another Submarine and open an "NCR-MAT" for a new supply. |  |  |  |  | Não
NCR-ICN-ESC-12-0622-2021 | P0101414 | OO02536 | REWORK | Provide a new connectors to continue the construction process. | REWORK | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  |  | Sim
NCR-ICN-ESC-12-0622-2021 | P0101411 | OO02532 | REWORK | Provide a new connectors to continue the construction process. | REWORK | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  |  | Sim
NCR-ICN-ESC-12-0622-2021 | P0101409 | OO02531 | REWORK | Provide a new connectors to continue the construction process. | REWORK | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  |  | Sim
NCR-ICN-ESC-12-0622-2021 | P0101410 | OO02533 | REWORK | Provide a new connectors to continue the construction process. | REWORK | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  |  | Sim
NCR-ICN-ESC-12-0622-2021 | P0113049 | DP02500 | REWORK | Provide a new connectors to continue the construction process. | REWORK | Provide a new connectors to continue the construction process Use an in-stock connector or make a local purchase Redo all tests and inspections |  |  | Sim
NCR-ICN-ESC-12-0631-2021 | P0155913 | FV00500 | REWORK | Perform the installation of new one equipment on board to attend the construction process of the SBR 2. As CMD 17FA000D00008 is tracked, authorization request to use 17FA000D00008_4007 - EV COOLING OF FV00500 SERIAL NUMBER: 14M001-401 from SBR4 in SBR2. | REWORK | Agree with level 1. ICN can use the material (NGD 9980000098471) from SBR4 |  |  | Sim | 17FA000D00008
NCR-ICN-ESC-12-0641-2021 | P0145848 | AG00016 | REWORK | According email historic and alignment report of balancing system AG00036 (NCR-ICN-ESC-12-0399-2021): REWORK. 1. On the Hinge Support (Rep. 26): Check the the flatness of the seating bearing surface e fix it using a hydraulic press. Perform a NDT 100% VT and 100% PT; 2. Measure again the coaxiality and procced according below if it is not conform: a) Machining the bearings according tolerances: • Side A: Ø50 the 2 sets of bearings at Ø50 0/+0,039; • Side B and C: Ø64 the 2 sets of bearings at Ø64 0/+0,046. b) Mark the positions of bearings to avoid mixing; c) Assembly the Bearing Caps (Rep. 06, 08 and 09) and tight the screws manually; Note: The ¼ of turning is impossible to apply. d) Check the clearance of 0,5 mm after tightening the bearing caps; e) Reaming the inner diameters Ø50H8 and Ø64H8 in the same axis. Coaxiality of 0,02 mm between 3 positions; f) Assembly the Hinge Axis (Rep.01) and Hinge Arm (Rep. 07) in the Hinge Support (Rep. 26) and control the arm movement. The movement should be without hard point and fluid. Send report final machining and coaxiality. 3. Seating onboard: rework the blue matching at 80% of the bearing surface (D55-02), reinstall the balancing system AG00036, take the measurements and machine a new shim (SBH.PLM.3D30.000166-F sheet F03) as required; 4. Check again the movement of complete set of Hatch AG00016 and Balancing System AG00036. |  |  |  |  | Sim | 01PE200D00028
NCR-ICN-ESC-12-0668-2021 | P0150994 | RF60040D | REWORK | Rework to fit the reference SMB. |  |  |  |  | Não
NCR-ICN-ESC-12-0685-2021 | P0125244 | GS02502 | REWORK | Rework. For 53B-GS02502 - P0125244 - OCULAR BOX equipment . Carry out the supply of a new right handle for the Ocular box - CMD 55PP000D00001. See ref. SBR-ETM-000GSM0001_page 62 and 63/1450, item 9 - A right handle. Take this one from SBR 3 or SBR 4. According to NCR-MAT-001373-2021 to supply a new one. This NCR is to treat of a new one delivery of new item for SBR2, the right handle part must be supplied for SBR3 or SBR4. | REWORK | Agree with proposal. Take care of the ocular box protection. A checking after mounting of all functionality will be done. |  |  | Não
NCR-ICN-ESC-12-0008-2019 | P0118828 | EJ00003 | MANUFACTURE | 1 - Change the position of the pumps. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0008-2019 | SMB-P0142323 |  | REWORK | 1 - Manufacture new nameplate for serial number 338 / 11-04 according to attached photo. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0020-2019 | SMB-P0129430 |  | NCR LEVEL 1 | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 18716
NCR-ICN-ESC-12-0047-2020 | N/A |  | AGREE WITH LEVEL 2.1 |  | REWORK | Naval Group confirms once again that this console must be replaced and that ICN can use that of the SBR3 or SBR4 while awaiting its replacement. Naval Group informs that the replacement of the BS02505 console is currently in progress and its arrival is imminent. For information, Naval Group has temporarily "repaired" the BIOS of the SBR2 console, but once again reminds you that it must be switched off correctly at each end of use so as not to lose the configuration. Finally, if this has not already been done, Naval Group reminds that ICN must open an NCR-MAT to formalize the replacement request. |  |  | Não
NCR-ICN-UFEM-12-0242-2018 | P0151127 | AC41019 | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | ACCEPT AS IT IS | Não
NCR-ICN-UFEM-12-0395-2019 | SC1-DP00156C-US-LOWER |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0466-2019 | P4175877 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0049-2020 | P0124026 | FH10106Q | REPAIR | Wait for NG orientation | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035479 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035503 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035483 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035538 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035485 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4180649 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0061-2020 | P4035490 |  | ACCEPT AS IT IS | ICN request evaluation to accept as it is. | ACCEPT AS IT IS | Accept as it is, to be validated by expert level 3 | ACCEPT AS IT IS |  | Não
NCR-ICN-ESC-12-0079-2020 | N/A | [7 empty] | Não
NCR-ICN-UFER-12-0139-2020 | N/A |  | ACCEPT AS IT IS | Accept as it is. Drill the Male Soft Patch holes using the holes in the female as a reference. |  |  |  |  | Não
NCR-ICN-ESC-12-0094-2020 | P4127221 |  | REMOVE AND REPAIR | ICN suggests applying the same decision made through NCR-ICN-ESC-11-0512-2019, FTG-7187. | REPAIR | Apply FTG-7187 |  |  | Não
NCR-ICN-ESC-12-0094-2020 | P0107649 | HP20001 | REMOVE AND REPAIR | ICN suggests applying the same decision made through NCR-ICN-ESC-11-0512-2019, FTG-7187. | REPAIR | Apply FTG-7187 |  |  | Não
NCR-ICN-ESC-12-0105-2020 | P0101409 | OO02531 | REMOVE AND REPAIR | A provisional repair has been made on the door (photos in attachment). NCR-MAT shall be opened to request a new door. | REMOVE AND REWORK | The door was removed to be transfered to SBR1 (first door damaged). NVG has to purchase a new door for SBR2 PLC OO02531 | REWORK | Please open a NCR MAT in order to purchase a new door for SBR2 PLC OO02531. | Sim
NCR-ICN-ESC-12-0113-2020 | N/A |  |  |  | REMOVE AND REWORK | remove the damaged hull bearing SBR2 for repair in work shop. define and order (NCRMAT)the spares to perform the repair. i suggest to mount in place of hull bearing SBR2 the hull bearing from SBR3 ( ensure the tracability) | REWORK | Rework according to SMB-TDP-PR6650333 and SMB-TDP-PR-6650334. | Não
NCR-ICN-ESC-12-0124-2020 | P0121806 | ES02500 | REWORK |  | REWORK | See FTG-8990 |  |  | Sim
NCR-ICN-ESC-12-0128-2020 | P0151763 | AC43058 | REWORK |  | REWORK | Dismount and remount in the good location with new gasket and lock washers. The new mounting will be followed by a new B06. |  |  | Sim | AP418418
NCR-ICN-ESC-12-0128-2020 | P0152060 | AC43060 | REWORK |  | REWORK | Dismount and remount in the good location with new gasket and lock washers. The new mounting will be followed by a new B06. |  |  | Sim | AP418419
NCR-ICN-ESC-12-0142-2020 | N/A |  |  |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0147-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0157-2020 | P0103230 | DA62512R | REWORK | Follow TA 2.2 guidelines. | REWORK | use the DA12512N (50DD500d00047) of the SBR4 define NGD of the base and the plug provide a new set for repair | REWORK | ok | Não
NCR-ICN-ESC-12-0157-2020 | P0104731 | DA12512N | REWORK | Follow TA 2.2 guidelines. | REWORK | use the DA12512N (50DD500d00047) of the SBR4 define NGD of the base and the plug provide a new set for repair | REWORK | ok | Não
NCR-ICN-ESC-12-0168-2020 | P4124534 |  | REMOVE AND REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0182-2020 | P0105108 | BC02550 | REWORK | Replace the power supply. | REWORK | Take on sbr4 in BC02550 the power supply U2 Open NCR MAT to replenish: MARTEK POWER 24VDC/230V 50Hz SUPPLY 600W Manufacturer Ref: ACR750 (B) BDM-00077872 |  |  | Sim
NCR-ICN-ESC-12-0197-2020 | P0116357 | KT22548 | MANUFACTURE | ICN authorization for the manufacture of the caps of KT22347 and KT22548 | REWORK | All informations are in the document MAT162-0390. |  |  | Não
NCR-ICN-ESC-12-0197-2020 | P0113127 | KT22347 | MANUFACTURE | ICN authorization for the manufacture of the caps of KT22347 and KT22548 | REWORK | All informations are in the document MAT162-0390. |  |  | Não
NCR-ICN-ESC-12-0208-2020 | P0104801 | MB00007 | SCRAP | Send to level 2. | REWORK | The SKF for SBR02 damaged has been control by photogrametry. The result will show if it is possible to be repaired. Open a NCR-MAT to decide what do if the damaged item. Actually use SKF SBR04 on the shaft SBR02 to finish the installation of the shaft line. As proposed in the mail (06/10/2020) jointed. (Charles Boucher). | REWORK | 1. Install on SBR2 shaft line the SKF coupling delivered for SBR4. 2. NAVAL GROUP will replenish a new SKF coupling for SBR4. 3. Open a NCR MAT to manage the damaged SKF coupling : scrap or repair in order to reput in stock as RGP. | Não
NCR-ICN-ESC-12-0218-2020 | P0104240 | BC02500 | REWORK | Replace the indicator | REWORK | Take on sbr 4 in BC02500 the NUMERICAL INDICATOR P5 (ENERDIS C.A 2150). Open NCR MAT to replenish it. |  |  | Sim
NCR-ICN-ESC-12-0232-2020 | P0145898 | AG00033 | REPAIR | Send to level 2. | REWORK | -This machining can't allow the good movement between the cover and hinge arm. -Dismount the hinge arm and finish the machining in conformity with the drawing. ( Patrick Daliguet) | REWORK | Rework according to plan MAT424-0871_G. This machining with the NCR reference must be identified in the panel's traceability file. Complete the NCR with the balancing serial number | Não
NCR-ICN-ESC-12-0311-2021 | P0117547 | KT66871D | REWORK | Provide a new cable (KT66871D) with a length of 6.5 m. | REWORK | Provide a new cable 11LS222D00016 with a length of 6.5 m. BO : kindly check and take into account the new length | REWORK | New length will be taken into account in next revision O of SBR PRODUCTION ROUTING FILE SMB-330521 | Não
NCR-ICN-ESC-12-0269-2020 | P0152023 | AC34050 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Não
NCR-ICN-ESC-12-0269-2020 | P0154567 | AC32069 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Não
NCR-ICN-ESC-12-0269-2020 | P0151126 | AC31019 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Não
NCR-ICN-ESC-12-0269-2020 | P4124223 |  | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Não
NCR-ICN-ESC-12-0269-2020 | P0151127 | AC41019 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Sim | 01PM100D00052
NCR-ICN-ESC-12-0269-2020 | P0154568 | AC42069 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Sim | 01PM200D00039
NCR-ICN-ESC-12-0269-2020 | P0152024 | AC44050 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -The dismounting of AC41019, AC42069 and AC44050, changing of gaskets and lock washers and mounting in the good orientation will be done after ceremony -To follow the new mounting with all inspections and tests a NCR REGRESS will be raise (Patrick Daliguet) | REWORK | In accordance with TA 2.2 | Sim | 01PM200D00003
NCR-ICN-ESC-12-0277-2020 | P4027863 |  | AGREE WITH LEVEL 2.1 |  | REPAIR | Taken into account the inclinaison ( 25 ° ) of the bottle EQ00101 on board, there is no longer any need for a dip tube inside this air bottle. | ACCEPT AS IT IS | Accept as is for the modified bottles SBR1 and SBR2 such as displayed by the AT to the level 2 of the NCR. In complement : bottles SBR3 and SBR4 will be modified before sending | Não
NCR-ICN-ESC-12-0284-2020 | P0120208 | EL02500 | REWORK | USE THE EL02500 EQUIPMENT LAMP (SBR4), IF APPROVED BY THE NAVAL GROUP. | REWORK | Take on SBR4 the light rep 50 of BDM-00060857 SIGNAL LAMP UNIT D22 LED BLUE 24V NGD: 6210144901880 Open NCR MAT to replenish it |  |  | Não
NCR-ICN-ESC-12-0304-2021 | P0124384 | FR22300 | REWORK | FOLLOW LEVEL 2 GUIDELINES. | REWORK | Check if NGD 0930930037510 connector available on SBR3 or 4. Open an NCR-MAT to supply a new connector |  |  | Não
NCR-ICN-ESC-12-0316-2021 | P0105174 | BB00031 | ACCEPT AS IT IS | The equipment has good physical and visual condition, must follow the next activities and inspection, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | BN10387301001
NCR-ICN-ESC-12-0334-2021 | P0139323 | EJ00211 | REPAIR | ICN request authorization to sandblast and paint according to tank schema. | REPAIR | Sandblast and paint the steel non return valve EJ00211 |  |  | Não
NCR-ICN-ESC-12-0341-2021 | N/A |  | REPAIR | Send to level 2. | REPAIR | For AC32060 and AC32061 accept as it is ( symetry of sleeve) AC32059 an dAC32065 MAchine a new sleeves AC 32062 ; AC32063 and AC32064 accept as it is , open a Pipe NCR to adapt the the spool to the wrong position of sleeves. |  |  | Não
NCR-ICN-ESC-12-0350-2021 | P4161492 |  | REWORK |  | REPAIR |  | REWORK | It is not up to the designer to modify the design and in particular by particularizing the definition file of a boat, to take into account an assembly anomaly. The Shipyard must correct its error and return to compliance with the definition, as recommended in the designer opinion: - Or by welding on board 2 spools, provided that it is technically possible to weld, to carry out the radio control and other NDT + PEH = 375 bar on board. - Otherwise go back to the configuration (==> dismantling) to allow nominal assembly of the spool. | Não
NCR-ICN-ESC-12-0362-2021 | P4021220 |  | REWORK |  | ACCEPT AS IT IS | To explain the misalignment, the seatings were positioned in relation to the pipes, the measurements outside tolerances are acceptable because the environment allows it |  |  | Não
NCR-ICN-ESC-12-0362-2021 | P4021221 |  | REWORK |  | ACCEPT AS IT IS | To explain the misalignment, the seatings were positioned in relation to the pipes, the measurements outside tolerances are acceptable because the environment allows it |  |  | Não
NCR-ICN-ESC-12-0362-2021 | P4021225 |  | REWORK |  | ACCEPT AS IT IS | To explain the misalignment, the seatings were positioned in relation to the pipes, the measurements outside tolerances are acceptable because the environment allows it |  |  | Não
NCR-ICN-ESC-12-0362-2021 | P4021321 |  | REWORK |  | ACCEPT AS IT IS | To explain the misalignment, the seatings were positioned in relation to the pipes, the measurements outside tolerances are acceptable because the environment allows it |  |  | Não
NCR-ICN-ESC-12-0372-2021 | P4021217 |  | REWORK |  | ACCEPT AS IT IS | Accepted as it is The seating was installed to be match with the spool, it´s why the coordinates are out of design. Can be accpeted like that no interference in this area. |  |  | Não
NCR-ICN-ESC-12-0372-2021 | P4021218 |  | REWORK |  | ACCEPT AS IT IS | Accepted as it is The seating was installed to be match with the spool, it´s why the coordinates are out of design. Can be accpeted like that no interference in this area. |  |  | Não
NCR-ICN-ESC-12-0372-2021 | P4021219 |  | REWORK |  | ACCEPT AS IT IS | Accepted as it is The seating was installed to be match with the spool, it´s why the coordinates are out of design. Can be accpeted like that no interference in this area. |  |  | Não
NCR-ICN-ESC-12-0372-2021 | P4021224 |  | REWORK |  | ACCEPT AS IT IS | Accepted as it is The seating was installed to be match with the spool, it´s why the coordinates are out of design. Can be accpeted like that no interference in this area. |  |  | Não
NCR-ICN-ESC-12-0387-2021 | P4017580 |  | REWORK |  | REPAIR | Cut the joint EL10004/EL998 and EL1004/1022 till the stepffener 1080. remove a 50mm part of EL998 and 1022 Adjust the hight of EL1004 measure and cut the news elements to complete the opening adjust and weld these news elements Carry out 100% VT and 100% MT of welds. |  |  | Não
NCR-ICN-ESC-12-0387-2021 | P4017749 |  | REWORK |  | REPAIR | Cut the joint EL10003/EL907 and EL1003/1005 till the stepffener 1081. remove a 50mm part of EL907 and 1005 Adjust the hight of EL1003 measure and cut the news elements to complete the opening adjust and weld these news elements Carry out 100% VT and 100% MT of welds. |  |  | Não
NCR-ICN-ESC-12-0415-2021 | P4172665 |  | MANUFACTURE |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0415-2021 | P0117731 | DV20014 | MANUFACTURE |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0415-2021 | P0107805 | DV00044 | MANUFACTURE |  | ACCEPT AS IT IS |  |  |  | Sim | 01PM300D00007
NCR-ICN-ESC-12-0428-2021 | P0105467 | DM03101 | REWORK | The plate must be replaced. | REMOVE AND REWORK | Replace the Pcb Control board with RMS stock. NGD:5998145794347 |  |  | Sim
NCR-ICN-ESC-12-0463-2021 | P0105343 | ME00001 | AGREE WITH LEVEL 2.1 |  | REPAIR |  | REWORK |  | Sim | n/a
NCR-ICN-ESC-12-0517-2021 | P0122998 | EV22021 | REPAIR |  | REWORK |  |  |  | Não
NCR-ICN-UFEM-12-0534-2019 | P4165275 |  | REPAIR | Use the same solution as the attached NCR-ICN-UFEM-11-630-2017 that was applied to SBR1. | REPAIR | REPAIR with the same solution in the FTG-6167 |  |  | Não
NCR-ICN-ESC-12-0028-2019 | P4175998 |  | NCR LEVEL 1 | Its not in accordance with SMB-200965_D item 9.2.1.2 Rule for the compression of the MN45 mounts. Rework | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0046-2020 | N/A |  | REPAIR | Repair the hole in the AF36006 from 36mm to 21mm as defined in SMB-104744. Wait for guidance from NG. |  |  |  |  | Não
NCR-ICN-UFEM-12-0221-2018 | P0149085 | AF35075 | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-UFEM-12-0367-2018 | P4029064 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0458-2019 | P4155637 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-UFEM-12-0500-2019 | P4161047 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0062-2020 | P0115998 | DJ00010 | REPAIR | NG provide another | REWORK | Take a DJ00010 available in stock Open an NCR-MAT to supply a new one Protect the valve to avoid a new breakage Check all the protection in the submarine |  |  | Não
NCR-ICN-ESC-12-0077-2020 | N/A | [5 empty] | REPAIR | 1 / acceptance by repair by remanufacturing the valve 2 / Replacing the valves with new ones when they arrive in Brazil BATCH SMB-RAW-DB394. | Não
NCR-ICN-ESC-12-0083-2020 | N/A |  |  |  | REPAIR | Rework some part of pilares (see annex) exchange the old one and correct the position. Carry out inspection required in IT21-02-10E. |  |  | Não
NCR-ICN-ESC-12-0093-2020 | P4107184 |  | SCRAP AND RE-MANUFACTURE | Manufacture a new tube according to the issued drawing. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0104-2020 | P0101413 | OO02534 | REPAIR |  | REWORK | Take module X37 and X38 in the OO02534 on SBR4 Open MAT to replenish them See drawing attached Module Phoenix contact MCR REPEATER POWER SUPPLIES Manufacturer reference 2864752 |  |  | Sim
NCR-ICN-ESC-12-0112-2020 | P0123065 | EV22018 | SCRAP | Please authorize replacement. | SCRAP | Need to take in stock a new one to proceed at the standard exchange. | REWORK | Agree with paragraph 2.2 : replacement of the flexible 18FH101D00617 by the 18FH101D00051 for SBR2. | Não
NCR-ICN-ESC-12-0123-2020 | P0121089 | EM02501 | REWORK |  | REWORK | Due of no RMS stock ,take on EM02501on sbr4 the item below: -BIPOLAR 2-POSITION FLIP SWITCH 3A SERIES 160UN01 WITH LOCK YELLOW TERMINATION 5930930151289 Open NCR MAT to replenish |  |  | Sim
NCR-ICN-ESC-12-0129-2020 | P4125592 |  | AGREE WITH LEVEL 2.1 | ICN requests authorization from NG to execute B01 and B02 in relation to BH00102 and BH00105 valves with the pipe installed. | ACCEPT AS IT IS | Exceptionally B01 and B02 can be carry out with pipe mounted It will be important to check the quantity of leak with difference of water quantity before and after the test inside the pump tank | REWORK | n accordance with level 2.2 proposal but the time for the pressure test has to be increased at minimum 15 min. David BERNEDE | Não
NCR-ICN-ESC-12-0140-2020 | P0132142 | UP02800 | ACCEPT AS IT IS | The missing cable is part of this product. | REWORK | The Launching Command Box UP02800 (P0132142) CMD: 11BR000D00021 was deliverred to SBR1 & SBR2 with its UP dummy Probes. The Dummy Probe of SBR1 was lost by ICN. Naval Group inquires to order and deliver a new UP dummy probe. Naval Group requests ICN to regulate the movement of mateial by editing a NCR MAT. | REWORK | Please create an NCR MAT for the replenishment of the material. | Não
NCR-ICN-ESC-12-0144-2020 | P0125624 | BB02506 | ACCEPT AS IT IS | Send to level 2. | REPAIR | Based on the annex 2 measurements, an analysis has been done following the aft battery connections in order to ensure a proper connection between the accumulators (SMB-000736). A repair proposal has been done on some identified seatings in order to respect as much as possible the tolerances of the batteries connectors. Annex”20200903-A150 - Etat avant reprise”: The cells to be reworked are in red background, and in orange background are highlighted the gap >1mm compared to the nominal high of each floors Upon rework done, new measurements have been taken and reported: Annex”20200908-A150 - Etat après reprise”. Based on these new measurements, the tolerance reported are within the connector tolerances. We would like to propose to accept as it is. | ACCEPT AS IT IS | Following the chocking rework and last measurements done, decision to Accept as is. | Não
NCR-ICN-ESC-12-0154-2020 | N/A |  |  |  | REWORK | Rework by surfacing |  |  | Não
NCR-ICN-ESC-12-0166-2020 | P0102154 | BB00040 | AGREE WITH LEVEL 2.1 | ICN acquisition analysis of NG | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0177-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0192-2020 | P0113529 | KT01111R | REWORK | NG, please check the item in question. | REWORK | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 |  |  | Não
NCR-ICN-ESC-12-0192-2020 | P0116261 | KT01112R | REWORK | NG, please check the item in question. | REWORK | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 |  |  | Não
NCR-ICN-ESC-12-0207-2020 | P0104606 | BH00106 | REMOVE AND REWORK | The damage valve need repair, raise a NCR-MAT, return it to warehouse and send to a supplier can make repair Halar. ICN is not qualified to repair Halar. | REPAIR |  | REPAIR | A sectioning recovery campaign will be implemented. They will not be treated individually. | Sim | 18RT010D00817-001-MICROMAZZA
NCR-ICN-ESC-12-0216-2020 | P0104733 | DA12510N | REWORK | Follow level 2.2 guidelines. | REWORK | Use the SBR4 connector provided for DA12510N Open an NCR-MAT to supply a new connector JUPITER FED F 10M T03-14 E123 |  |  | Não
NCR-ICN-ESC-12-0224-2020 | P0101411 | OO02532 | REMOVE AND REPAIR | NCRMAT shall be opened to request a new door. | REMOVE AND REWORK | Naval Group requests to replace the door of cabinet from SBR4 IPMS Equipment OO02532. ICN has to create a NCR-MAT |  |  | Sim
NCR-ICN-ESC-12-0239-2020 | P0152217 | AC30053 | REPAIR | Repair. The same defect was found e treated in NCR-ICN-UFEM-12-410-2019. Follow the steps below: 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. | REWORK | 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. |  |  | Não
NCR-ICN-ESC-12-0268-2020 | P0112500 | HE01202 | REWORK |  | ACCEPT AS IT IS | In accordance with level 1.1 ( Patrick Daliguet) | REWORK | Perform only B01,B02 HE01203 using the point at the end of line HE50120Y [Put a plug after the test put also plugs on each connections not mounted outside the pressure hull | Não
NCR-ICN-ESC-12-0274-2020 | P4158828 |  | REMOVE AND REWORK | Disassemble the FC00525 from the seating, and pipes connected to the seating, to perform A02 acoustic discretion inspection. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0281-2020 | P0104808 | MB00300 | ACCEPT AS IT IS | For analysis by Naval Group. | ACCEPT AS IT IS |  | ACCEPT AS IT IS | In accordance with level 2.2 position. | Sim | 18RT010D00474/XF32020
NCR-ICN-ESC-12-0281-2020 | P0104812 | MB00301 | ACCEPT AS IT IS |  | ACCEPT AS IT IS |  | ACCEPT AS IT IS | In accordance with level 2.2 position. | Não
NCR-ICN-ESC-12-0317-2021 | P0134354 | BM00032 | REWORK | Send to level 2 | REWORK | On B06 of BM00032: - all the tracability of nuts is not possible -Lock washers were bended more than one year after the last tightening (20/07/2020 - 30/01/2019) On BM00031: -Lock washers were bended more than one year after the last tightening (30/07/2020 - 22/01/2019) -F06 was done more than one year after the last tightening (24/07/2020) It's necessary to dismount and remount properly with inspections and tests the two valves A NCR regress will be raise and after B05 updated | REWORK | In accordance with level 2.2 proposal. It is not possible to know what could be happened between the dates of last tightening and the bending of tab washers. David BERNEDE | Sim | 012
NCR-ICN-ESC-12-0310-2021 | P4031090 |  | REWORK |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0330-2021 | P0131520 | MB00003 | REWORK | Send to level 2. | REWORK | Change the PELA SBR2 and replace it by the complete PELA of SBR4. NCR send to level 3 in order to inform NG BO about the utilisation of PELA SBR4 for the tracability. | REWORK | Change the PELA SBR2 and replace it by the complete PELA of SBR3 or SBR4. The PELA SBR2 has to be disassembled to replace the defective GUIDE BEARING (box item 33), with the new one once delivered, and then be mounted on board SBR3 or SBR4. The operations and tests to be carried out are described in document SBR-ETM-000MBM0004-STERNGLAND_B. For disassembly/reassembly operations, please also apply procedure STP-2338_A joined in annex. | Sim | 15PE000D00001
NCR-ICN-ESC-12-0340-2021 | P0146409 | FC00523 | ACCEPT AS IT IS | The equipment has good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | FC00523-3
NCR-ICN-ESC-12-0347-2021 | P0138893 | DA00002H | REMOVE AND REWORK | According to the description, the equipment data plate must be fixed in a visible place. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0359-2021 | P0108340 | DY02511 | AGREE WITH LEVEL 2.1 | Replace junction blocks | REMOVE AND REWORK | Take 2 new terminal blocks B1and B2 on DY02511 SBR3 Open NCR MAT to replenish them BDM-00059895: Rep 90 NGD:5940144372246 R: BJT23-8 / F: MAFELEC / |  |  | Sim
NCR-ICN-ESC-12-0364-2021 | P0120353 | EQ00043 | REWORK | • The design of the seating does not permit to use Lock Tab washer on the bottom (see details in SBH.2B30.SMD.006130_FL20); • The assembly drawing MAT424-0924 show a different seating profile that permit to install the Lock Tab washer. • Replace the Lock Tab washer by Nord-Lock washer NL10; • Apply torque of 50 Nm (dry condition) for screw M10 class 8.8 according BDM-00033368_A; • Update the hatch drawing and part list. | REWORK | With the profile of the support it's not possible to bend lock washers: -Replace lock washers (rep:6 of MAT424-1656) by steel Nord-Lock washers. -For the tightening with Nord-Lock washers the document applicable is the SMB-200963 ( in reference to the norme NF E 25-030-1 ). In this case with 8.8 steel it´s better to use grease (Jet Marine) for the mounting: the torque value in accordance with the SMB-200963 for M10 class 8.8 with grease is 37Nm. -A NCR MAT should be raise for the modification of nomenclature | REWORK | - Acceptance of Nord-Lock washers according to ISSP and designer recommendation. On the other hand, the tightening torque is different from that of NF E 25-030-1 (37Nm): tightening the NL requires a torque increased by 20%, configuration with lubrication, ie 45Nm. - ICN must formalize the situation concerning the mounting for the EQ00043 hatch on SBR1 -> waiting in BO for an NCR LVL3 | Sim | 01PE200D00038
NCR-ICN-ESC-12-0385-2021 | P0154568 | AC42069 | ACCEPT AS IT IS | The IM AC42069 is rotated 1 hole from the original position as shown on SBH.2D30.IMZ.006924 (F05) Since is a electric mobile part and here is no problem connecting the electric cable from inside the pressure hull, accept as it is | ACCEPT AS IT IS | No cable connection problem Accept as it is |  |  | Sim | 01PM200D00039-AP418401-F3013
NCR-ICN-ESC-12-0403-2021 | P4164490 |  | REMOVE AND REWORK | Redo de mounting using new gasket and washers following the procedure on SMB-200960 Open NCR-REGRESS to invalidate inspections B06, B01, B02 and do new inspections | REWORK | In accordance with level 1.2 Dismount and remount correctly Raise NCR REGRESS to redo inspections and tests | REWORK | In accordance with level 2.2 proposal. David BERNEDE | Sim
NCR-ICN-ESC-12-0424-2021 | P0129421 | DA00002 | ACCEPT AS IT IS | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 18830
NCR-ICN-ESC-12-0447-2021 | P0106087 | ME03102 | REWORK | Based on the answer given in NCR-1573, we would need to replace the Z1 source. | REMOVE AND REWORK | Replace Z1 component by a new one. Take it on SBR4. Please open NCR-MAT to reorder this part: EMC 3 phase filter SCHAFFNER FN 3258 H-16-44 BDM-00085914 |  |  | Sim
NCR-ICN-ESC-12-0509-2021 | P0149558 | DA00072 | NCR LEVEL 1 | The sensor must be replaced with a new one. | REMOVE AND REWORK | make a standard exchange of the DA10002N make ncr mat |  |  | Não
NCR-ICN-ESC-12-0156-2020 | P0131389 | DP00355 | ACCEPT AS IT IS | Accept as it is. The production team already performed the adjustment of the hole bushes and assembly the screws temporarily. It was not found any problem in the mounting. | ACCEPT AS IT IS | If you have already arrive to tight the bush on the coaming , accept as it is. |  |  | Não
NCR-ICN-ESC-12-0156-2020 | P0131390 | DP00356 | ACCEPT AS IT IS | Accept as it is. The production team already performed the adjustment of the hole bushes and assembly the screws temporarily. It was not found any problem in the mounting. | ACCEPT AS IT IS | If you have already arrive to tight the bush on the coaming , accept as it is. |  |  | Não
NCR-ICN-ESC-12-0153-2020 | N/A |  |  |  | REWORK | Rework, Due to the wrong forming and mounting, Naval-group/Ta proposes to rework some elements described in para1.2 |  |  | Não
NCR-ICN-ESC-12-0161-2020 | P0147304 | DP00292 | SCRAP | Proceed according 1.2. | REWORK | replace the seal rep 10 CMD 0930930292400 by the same. Open a NCR-MAT. |  |  | Não
NCR-ICN-ESC-12-0172-2020 | P0117405 | EG00102 | AGREE WITH LEVEL 2.1 |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 4-15-003
NCR-ICN-ESC-12-0187-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0201-2020 | P4123291 |  | REPAIR | NG, please analyze this problem | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0201-2020 | P4123301 |  | REPAIR | NG, please analyze this problem | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0201-2020 | P4123565 |  | REPAIR | NG, please analyze this problem | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0201-2020 | P4123516 |  | REPAIR | NG, please analyze this problem | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0201-2020 | P4164586 |  | REPAIR | NG, please analyze this problem | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0212-2020 | P0154557 | AC42042 | ACCEPT AS IT IS | The 116 mm stud is not appropriate for installing the AC42042, it is necessary to change to 126 mm to be accepted with at least two threads. | ACCEPT AS IT IS | The length of stud rods L=116 mm was replaced by L=126mm after the modification of thickness of lock washers (replace by new design for the lower side) | REWORK | The use of 126 mm is correct - accepted as it is David Bernede | Sim | 003 (CONTRACT NUMBER 6409900)
NCR-ICN-ESC-12-0221-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0235-2020 | P0101555 | OO02505 | REWORK | ICN kindly suggests to take the declared items from S-BR03 and mount on S-BR02 to continue the tests. NCR-MAT to be opened to request new item. | REMOVE AND REWORK | Naval Group request ICN to get the spare SSO screen from SBR3 IPMS equipments OO02500. ICN has to create a NCR-MAT |  |  | Não
NCR-ICN-ESC-12-0235-2020 | P0101410 | OO02533 | REWORK | ICN kindly suggests to take the declared items from S-BR03 and mount on S-BR02 to continue the tests. NCR-MAT to be opened to request new item. | REMOVE AND REWORK | Naval Group request ICN to get the spare thermal cut out from SBR3 IPMS equipments OO02533. ICN has to create a NCR-MAT |  |  | Sim
NCR-ICN-ESC-12-0261-2020 | P4152681 |  | AGREE WITH LEVEL 2.1 | NG, review the order in item 2.1 | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0272-2020 | P0131031 | KT03611 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 91AE000D00007
NCR-ICN-ESC-12-0272-2020 | P0126934 | KT03612 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 91AE000D00008
NCR-ICN-ESC-12-0272-2020 | P0131045 | KT03613 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 63GW000D00048
NCR-ICN-ESC-12-0272-2020 | P0126935 | KT03614 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 91AE000D00010
NCR-ICN-ESC-12-0272-2020 | P0131046 | KT03615 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 91AE000D00011
NCR-ICN-ESC-12-0272-2020 | P0126936 | KT03616 | ACCEPT AS IT IS | Accept as it is for ceremony. Send to level 2 to validate. | REWORK | -For the ceremony old lip seal were mounted on the external door -The B02 KT00251 to 256 were carried out and a vacuum will be done before ceremony to check the good watertightness. -To follow the new mounting with all inspections and tests before J06 a NCR REGRESS will be raise. (Patrick Daliguet) | REWORK | IN ACCORDANCE WITH 2.2 | Sim | 91AE000D00012
NCR-ICN-ESC-12-0278-2020 | P4160082 |  | REMOVE AND REPAIR | NG, please check the problem found. | OK - NOT MODIFIED | Keep as it is on board | REWORK | Rework of the pipe according to the bord constraints, acccording to approach provided in paragraph 2.2 and in line with what had to be done on SBR1. (SMB-TDP-PR-6779504 and SMB-TDP-PR-6779503) | Não
NCR-ICN-ESC-12-0278-2020 | P4172665 |  | REMOVE AND REPAIR |  | REMOVE AND REWORK | Use the wrong pipe as dummy | REWORK | Rework of the pipe according to the bord constraints, acccording to approach provided in paragraph 2.2 and in line with what had to be done on SBR1. (SMB-TDP-PR-6779504 and SMB-TDP-PR-6779503) | Não
NCR-ICN-ESC-12-0290-2020 | P0108667 | RF00008 | REMOVE AND REPAIR | Suggestion to change only the ball of the valve, since it is what is damaged. | REWORK | Take out the ball valve on SBR 4 or SBR 3 from the whare house, check theire ball Valve, If there are OK , in order to avoid to unmount all the valve ball assembly on the SBR 1, unmount ( With TA NG) only the ball assembly on SBR 4 or SBR 3 in this order, and change with this one of SBR 1. Raise an NCR MAT to replace the defective part. | REWORK | If the valve is not coçpletely dismouted it will be necessary to define and use a specific inspection file for mounting specific test will be also define to check the good fonctionality of the ball alve if it not possible to repair the situation the tool to perform B01 and B02 will be put in place for the ceremony of decembre 2020 D BERNEDE | Não
NCR-ICN-ESC-12-0315-2021 | P0118828 | EJ00003 | ACCEPT AS IT IS | The equipment has good physical and visual condition, must follow the next activities and inspection, but its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 338/11-04
NCR-ICN-ESC-12-0327-2021 | P0101413 | OO02534 | REWORK | Use o conector fornecido para o SBR4 e crie um "NCR-MAT". | REMOVE AND REWORK | Naval Group confirms the suggested action by ICN. Create a NCR-MAT to replace on SBR4 |  |  | Sim
NCR-ICN-ESC-12-0336-2021 | P0106089 | ME03101 | REPAIR |  | REPAIR | To allow starting of STW of ME system on SBR2, please take 2 busbars from SBR4 and install them on SBR2, with help of NVG TA Then, it will necessary to repair the 2 damaged capacity banks on SBR4 by replacing their busbar. Please open a NCR MAT to launch the repair of those parts. Then NVG will order new busbars. Upon delivery in brasil, NVG will organize the repair on SBR4 by Jeumont |  |  | Sim
NCR-ICN-ESC-12-0344-2021 | P0110267 | DT04200 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REPAIR | Cut the part of seating where the drilling are out of holes equipment, ajust and reweld at a good place. |  |  | Sim
NCR-ICN-ESC-12-0344-2021 | P0110268 | DT04300 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REPAIR | Cut the part of seating where the drilling are out of holes equipment, ajust and reweld at a good place. |  |  | Sim
NCR-ICN-ESC-12-0354-2021 | P0151146 | AC41018 | REWORK | Remove AC41018, remount according SMB-200960 using new gasket and new tab washers, redo inspection B06 and update B07 Open NCR-REGRESS to invalidate inspections B06 of A41018, B01 and B02 already done of the following pipes and isolating valves: DB50221Y1, DB50231Y1, DB50232Y1, DB50242Y1, DB00121, DB00101, DB00102, DB00122 | REWORK | In accordance with level 1.2 remove AC41018, remount according SMB-200960 using new gasket and new tab washers, redo inspection B06 and update B07 Open NCR-REGRESS to invalidate inspections B06 of A41018 and to redo pressure test: The link of pipes and mobile part will be verify by a S02_DBZ0001 (DB50221Y1, DB50231Y1, DB50232Y1, DB50242Y1) B05 will be updated | REWORK | Agree with paragraph 2.2, rework : Disassembly then reassembly of the moving part in accordance with SMB-200960. Change the seal during reassembly. Repeat the traceability and hull integrity inspections then record them in the traceability file. | Sim | 6321551-FB831-17/002
NCR-ICN-ESC-12-0363-2021 | P0134340 | BQ00018 | REWORK | Agree with 1.2. Replace the 18RO230D00135 by 18RO0230D00070. | REPAIR | Agree witl level 1.2. The dismounting of couplings is not possible: interference with support. -Change the CMD:18RO230F00260 (RUCH sqare coupling) and CMD:32FI301D00003 (shim) by 18RO0230D00070 -NCR MAT will be raise to modify the part list |  |  | Não
NCR-ICN-ESC-12-0363-2021 | P0134543 | BQ00017 | REWORK | Agree with 1.2. Replace the 18RO230D00135 by 18RO0230D00070. | REPAIR | Agree witl level 1.2. The dismounting of couplings is not possible: interference with support. -Change the CMD:18RO230F00260 (RUCH sqare coupling) and CMD:32FI301D00003 (shim) by 18RO0230D00070 -NCR MAT will be raise to modify the part list |  |  | Não
NCR-ICN-ESC-12-0390-2021 | N/A |  |  |  | REPAIR | Use theLoctite 5970 only to stick the GRP floor |  |  | Não
NCR-ICN-ESC-12-0390-2021 | COS-344782-001 | [7 empty] | Não
NCR-ICN-ESC-12-0394-2021 | P0106089 | ME03101 | REWORK | To change the screen. | REWORK | Found loose connection (white connector) on pcb. Picture attached in annex. |  |  | Sim
NCR-ICN-ESC-12-0408-2021 | P0104606 | BH00106 | REMOVE AND REWORK | Remove BH00106 to rework the holes on support P4027395, after done, remounte using procedure on SMB-200960 with new gasket and washers NCR-REGRESS will be raised to invalidate B01, B02, F06 and B06 of BH00106 Inspections F06, B01, B02, B06 and B07 must be redone | REWORK | In accordance with level 1.2 Dismount and remount correctly Raise NCR REGRESS to redo inspections and tests | REWORK | In accordance with proposal : correction of the seating and remounting following SMB-002930 inspections and SMB-200960 rules. David BERNEDE | Sim | 18RT020D0015-1001-ISSARTEL
NCR-ICN-ESC-12-0440-2021 | P0118608 | RM00003 | REMOVE AND REPAIR | During the assembly of the RADAR mast (53C-RM00003 - P0118608 – CMx 09EP000D00014 NAVIGATION RADAR MAST ASSEMBLY) on the SBR2 submarine, the mast antenna 53C-RD02504 - P0123648 CMx 62AB000D00049 RADAR ANTENNA MAST RESET DEVICE did not fit, checking the internal measurements it was identified that the internal diameter does not conform to the design drawing. The mast of the SBR4 was requested for possible assembly, before assembly the measurements were checked, then it was identified that the internal diameter is not in accordance with the design drawing. For this situation, it is suggested that the internal diameters are machined on the mast of SBR3 and SBR4. Machining the mast 53C-RM00003 internal diameter 162.00 mm, mounting area RADAR POD antenna. See annex 1. | REWORK | The two SBR3 and SBR4 radar antenna support mast 09EP000D00015 (RM00813) must be machined to the correct diameter according to the plan in the appendix (DIAMETER 162/0 + 1 and the depth 487/ 0+5). After machining of the machined part, a coat of gray JOTAMASTIQUE primer must be applied, according to reference documents SMB-002345 and SMB-002083. |  |  | Não
NCR-ICN-ESC-12-0492-2021 | P0105772 | ME11412M | REWORK | We need deliberation for another encoder. | REWORK | According to NCR-ICN-ESC-11-1165-2020, the encoders were taken from sbr2. Take the 2 encoders of SBR4 and remount them on SBR2. NCR-MAT-001397-2021 had been opened to refund the encoder damaged (encoder 2 of SBR1). No need new NCR MAT (encoder 1 of sbr1 + new encoder will be remounted together on SBR4). |  |  | Não
NCR-ICN-ESC-12-0539-2021 | P4168613 |  | AGREE WITH LEVEL 2.1 |  | ACCEPT AS IT IS |  | ACCEPT AS IT IS | This case has to be considered as an exception, not as a rule (David Bernerde). | Sim
NCR-ICN-ESC-12-0174-2020 | P0130198 | DP00162 | ACCEPT AS IT IS | Proceed according 1.2. Replace by items described in annex 1. | REWORK | ICN should open a NCR-MAT to replace all the items missing. In parallel Naval Group suggest to buy double or triple itens for spare. (Charles Boucher). |  |  | Não
NCR-ICN-ESC-12-0173-2020 | P0127385 | EQ00004 | REWORK |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 18DL100D00003
NCR-ICN-ESC-12-0205-2020 | P0116267 | KT01116R | REMOVE AND REWORK | Proceed according sheet nº 185. | REWORK | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 | REWORK | OK | Não
NCR-ICN-ESC-12-0205-2020 | P0116268 | KT01116 | REMOVE AND REWORK | Proceed according sheet nº 185. | REWORK | In accordance with declaration: - Raise a NCR regress - Dismounting valves - Mounting correctly valves with presentation of pipe for the correct orientation (new gasket) - Carry out pressure tests B01 and B02 and redo documents associated B11, B07 | REWORK | OK | Sim
NCR-ICN-ESC-12-0202-2020 | P0121806 | ES02500 | REWORK |  | REWORK | Replace the broken switch with a new one Open an NCR MAT to supply a new BIPOLAR 2-POSITION FLIP SWITCH NGD 5930930151289 |  |  | Sim
NCR-ICN-ESC-12-0215-2020 | P0131520 | MB00003 | SCRAP | 1) Replace the damaged parts from SBR 2 by SBR 4; 2) The traceability of the replaced parts of the both Stern Gland must be updated; Pay attention to register the correct serial number of the origin of equipment; For example : Rep 30 broken replaced per Rep 30 from Stern Gland which has traceability reference APXXXXXX. 3) Raise a NCR-MAT to delibery new parts. | REWORK | Naval Group suggest replace de broken item. Take from SBR4 and replace on SBR2. Take care with the traceability of the items. Add Naval Group suggest: 1) To changes all O-rings, items 29 and 35 of the MAT-422-0109; 2) Open a new NCR MAT to replanishment new items ( O-rings and Came )for SBR04. (Charles Boucher) | REWORK | In accordance with level 2.2 proposal. The traceability folder of both equipment concerned thhe one damaged and the one from which piece is taken from. 10/03/2021: 1) The displacement of the shaft line caused the spacers to break but may have damaged other parts. It is necessary to check with inspection report (visual, dimensional) with photos and inspection report the parts: - bangle Rep 7 - Ice Rep 5B - Carbon Rep 4B A visual check with photo is to be done for: - cam support Rep 30 - Glass holder Rep 5A - Carbon holder Rep 4A - Key Rep 8 - Key Rep 10 - Boitard Rep 33 Create a new NCR if any of these hardware is damaged 2) - Scrap of the 3 spacers damaged during the pressure tests. - Replacement of the 3 ice cams ref. 41 as well as their O-rings ref. 29 and 35, New items will be restocked (5331145330435-O-RING 41.50X2.65 20A8 CLASS A-N - Qty: 3 and 5331144145869-O-RING 20.00X2.65 20A8 A-N - Qty: 3) If taken by the time, possible sampling of the elements of SBR4, and order to be provided for SBR4 => Add the new compliance elements to the material tracking file. - Perform the pressure tests of the equipment The traceability aspect of parts is important and must be ensured. The reference of the NCR must be mentioned in the 2 traceability files (of the taking material - of the yielding material) | Sim | 15PE000D00001
NCR-ICN-ESC-12-0222-2020 | N/A |  |  |  | REWORK | Replace the BB00061 (12EP000D00014) broken by a new one available in stock Open an NCR MAT to supply a new one |  |  | Não
NCR-ICN-ESC-12-0238-2020 | P0122869 | EV00010H | REWORK | The compression dimensions are below the minimum recommended in SMB-200965_E. Naval Group TA evaluate a similar case in the SBR1 of the same equipment and make the necessary recommendations for 53B-EV00010S. | ACCEPT AS IT IS | The maximum out of tolerance is 2mm. As on SBR1 with NCR-ICN-ESC-11-330-2019 ( maximum out of tolerance: 4,5mm ) can be accept as it is. | REWORK | Accept as is and continuation of other inspections until SHIP11C, in the event of a deviation from SHIP11C, a new NCR must be issued. | Não
NCR-ICN-ESC-12-0263-2020 | P4165788 |  | AGREE WITH LEVEL 2.1 |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0263-2020 | P4165717 |  | AGREE WITH LEVEL 2.1 |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0271-2020 | P0102987 | BE0B00AD | REWORK | USE THE SBR4 LUMINAIRE, WITH THE APPROVAL OF THE NAVAL GROUP. | REWORK | Take on another boat, depending on available stock. Replace only the broken part (the globe) so that no REGRESS will be necessary, avoiding redo the ctrl E01 and STW. Send in lvl 3 to request the NGD of the globe in order to be able to launch an provisioning. Do NCR-MAT to replenish (Stephane Rideau) | REWORK | Scrap the damaged globe. Naval Group will send a new globe 0930930239565 and the seal 5330930177267. | Não
NCR-ICN-ESC-12-0271-2020 | P0138889 | BE0B00AF | REWORK | USE THE SBR4 LUMINAIRE, WITH THE APPROVAL OF THE NAVAL GROUP. | REWORK | Take on another boat, depending on available stock. Replace only the broken part (the globe) so that no REGRESS will be necessary, avoiding redo the ctrl E01 and STW. Send in lvl 3 to request the NGD of the globe in order to be able to launch an provisioning. Do NCR-MAT to replenish (Stephane Rideau) | REWORK | Scrap the damaged globe. Naval Group will send a new globe 0930930239565 and the seal 5330930177267. | Não
NCR-ICN-ESC-12-0271-2020 | P0102570 | BE0A00AC | REWORK | USE THE SBR4 LUMINAIRE, WITH THE APPROVAL OF THE NAVAL GROUP. | REWORK | Take on another boat, depending on available stock. Replace only the broken part (the globe) so that no REGRESS will be necessary, avoiding redo the ctrl E01 and STW. Send in lvl 3 to request the NGD of the globe in order to be able to launch an provisioning. Do NCR-MAT to replenish (Stephane Rideau) | REWORK | Scrap the damaged globe. Naval Group will send a new globe 0930930239565 and the seal 5330930177267. | Não
NCR-ICN-ESC-12-0280-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0294-2020 | P0101910 | BB00019 | SCRAP | It is necessary to change and open a NCR MAT for replenishment. | REMOVE AND REPAIR | Need to proceed to a standard exchange of the valve (take in stock or on SBR3 or SBR4). Need to create a NCR-MAT to order a coupling (item 3) following the SBR-ETM-00000M0001 folha 4134 to refund the stock. |  |  | Não
NCR-ICN-ESC-12-0307-2021 | P4021217 |  | REWORK |  | REWORK | Rework, The drilling of the seating were oblonded, so not in accord with the design. Remove the seatings remove the austenic trace carry out nital test , 100%VT, Open NCR/RO for each repair, annex a map defetc and dimension if the depht is less tan 3mm Carry out 100% VT , 100%MT. Re- install the seating at the good location If any defect depht is more than 3mm carry out 100% RT and 100%UT |  |  | Não
NCR-ICN-ESC-12-0307-2021 | P4021218 |  | REWORK |  | REWORK | Rework, The drilling of the seating were oblonded, so not in accord with the design. Remove the seatings remove the austenic trace carry out nital test , 100%VT, Open NCR/RO for each repair, annex a map defetc and dimension if the depht is less tan 3mm Carry out 100% VT , 100%MT. Re- install the seating at the good location If any defect depht is more than 3mm carry out 100% RT and 100%UT |  |  | Não
NCR-ICN-ESC-12-0307-2021 | P4021219 |  | REWORK |  | REWORK | Rework, The drilling of the seating were oblonded, so not in accord with the design. Remove the seatings remove the austenic trace carry out nital test , 100%VT, Open NCR/RO for each repair, annex a map defetc and dimension if the depht is less tan 3mm Carry out 100% VT , 100%MT. Re- install the seating at the good location If any defect depht is more than 3mm carry out 100% RT and 100%UT |  |  | Não
NCR-ICN-ESC-12-0396-2021 | P0127039 | FC00521 | REWORK | Send to level 2. | REMOVE AND REPAIR | make the standard exchange of the pieces damaged make NCR Mat |  |  | Sim | 17CA000D00077
NCR-ICN-ESC-12-0338-2021 | P4156549 |  | ACCEPT AS IT IS | The equipment has good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0348-2021 | P0104795 | MB00001 | REWORK | Follow 1.2. | REWORK | Agree with level 1. Any dust detect inside the thrust block during the buroscopy. Maintain all the holes of the thrust block close and protect the shaft part. |  |  | Não
NCR-ICN-ESC-12-0356-2021 | P0104733 | DA12510N | REMOVE AND REWORK | The internal part of the equipment must be replaced by another one. | REMOVE AND REWORK | Use RMS stock NGD:6680930201175 CMX:50DD500D00048 Open NCR MAT to replenish it |  |  | Não
NCR-ICN-ESC-12-0361-2021 | P0130282 | FC02520 | REMOVE AND REPAIR | Substituir material RMS |  | Due of the variator message incident "overvoltage bus dc ” It was identifed that the problem is that the thyristor does not close after the capacitors are preloaded Found that the “control board "must be replaced with a new one using RMS stock. NGD:5998145794347 Set the parameter according to SMB-345168 for FC02520. Open NCR MAT to replenish it. |  |  | Sim
NCR-ICN-ESC-12-0381-2021 | P0121682 | FH20203 | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0381-2021 | P0121680 | FH20201 | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0402-2021 | P4502664 |  | REWORK |  | ACCEPT AS IT IS |  | ACCEPT AS IT IS | Based on photos, the same problem exists on SBR1: why has ICN not create a NCR to SBR1? The pitch between the other clamps on the line is sufficient, acceptance as is without mounting the clamp P4502664: same for SBR3 and 4 at ICN to update their job order. | Não
NCR-ICN-ESC-12-0402-2021 | P4170154 |  | REWORK |  | ACCEPT AS IT IS |  | ACCEPT AS IT IS | Based on photos, the same problem exists on SBR1: why has ICN not create a NCR to SBR1? The pitch between the other clamps on the line is sufficient, acceptance as is without mounting the clamp P4502664: same for SBR3 and 4 at ICN to update their job order. | Não
NCR-ICN-ESC-12-0416-2021 | P0140161 | FQ00803 | REWORK | Send to level 2 | REWORK | Following decision of Diving Safety Engineer: The valve has to be dismounted and replaced by a new one. The polluted one has to be sent to the supplier to be reconditioned properly, the ball and pistons are probably damaged because the valve was maneuvered. Ali inspections previously done have to be cancelled and redone (mounting, pressure tests, traceability...). A NCR regress and NCR MAT will be raise. | REWORK | In accordance with ICN and Level 2.2 proposal. It is necessary to replace the valve by a new one and to send to the supplier the polluted one. David BERNEDE - ISSP | Sim | 18RT010D00581
NCR-ICN-ESC-12-0443-2021 | P0132224 | EW00001 | ACCEPT AS IT IS | N/A | REPAIR | The inferior neoprene gasket of the level indicator EW10002N is missing. Take a new-one in the stock (NGD: 5330143029900) to remount onboard. If no stock canibalize SBR3 or SBR4 and create a NCR-MAT to refund the stock. |  |  | Não
NCR-ICN-ESC-12-0443-2021 | P0126460 | EW10002N | REWORK | It is necessary to install a new level indicator sealing rubber EW10002N - 53B-P0126460 - 50MD500D00015 LEVEL INDICATOR FITTING ED 15MM | REPAIR | The inferior neoprene gasket of the level indicator EW10002N is missing. Take a new-one in the stock (NGD: 5330143029900) to remount onboard. If no stock canibalize SBR3 or SBR4 and create a NCR-MAT to refund the stock. |  |  | Não
NCR-ICN-ESC-12-0502-2021 | P4095984 |  | REWORK | Agree with 1.2. Weld using C27 inspection. | REPAIR | Create a new joint to have a good access. after adjustment weld the butt joint , carry out the inspections 100% VT and 100%MT if it 's correct can continue the fillet welding |  |  | Não
NCR-ICN-ESC-12-0550-2021 | P0106886 | GF22504R | REWORK | PROVIDE A NEW CABLE WITH THE LENGTH ACCORDING TO THE DESIGN. | REWORK | Use the 25 meter cable stocked at the ESC store under the ESC / E.02.05.D location or the one from the UFEM store under the 18C / H.05.26.A location. |  |  | Não
NCR-ICN-ESC-12-0185-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0195-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0209-2020 | P4164603 |  | REPAIR |  | REWORK | Due to the wrong fabrication of the seating , it was necessary to correct it before mounting on Board. Cut in 3 parts , build up and ajust in the good position. Carry out all the repairs following the IT21-02-10E rules and SMB-200853 |  |  | Não
NCR-ICN-ESC-12-0219-2020 | P4155477 |  | REWORK - UPDATE JOB ORDER | SUBMITTED FOR ANALYSIS AND REVIEW OF NAVAL GROUP TA | REWORK | The mounting is not in accordance with SMB-TCP-OR-6748378: 1 x MN45-110 1 x MN45-60 2 x MN45-85. Redo the mounting with the correct elasting mounts and redo the measurement. |  |  | Não
NCR-ICN-ESC-12-0233-2020 | P0115827 | KT05A42 | SCRAP AND RE-MANUFACTURE | Manufacture the shaft as per drawing attached. | REWORK | -In accordance with level 2.1 redo the axis with drawing enclosed in material: CuAl10Ni5Fe4 (Patrcik Daliguet) |  |  | Não
NCR-ICN-ESC-12-0256-2020 | P0101583 | OO02500 | REMOVE AND REPAIR | Forward to Naval Group to align repair actions or take from other Submarine. DS214 ( DIGITAL PANEL METER ICO 514VM [FAQ11 - AOIP] ) | REMOVE AND REWORK | After repaired the welds on DS214 Display naval group FO confirms that this display has a failure (error 0) on the analog Input wheb it is connected. Replace the Display DS214 from priority SBR4 else SBR3 product. Report on NCR the serial number of these products. |  |  | Sim
NCR-ICN-ESC-12-0270-2020 | P4168507 |  | REPAIR |  | REPAIR | Change the position of the welding piece as per shown on the isometric in anexure |  |  | Sim
NCR-ICN-ESC-12-0312-2021 | P0124217 | GV02501 | REWORK | NA | REWORK | Use the connector "D38999-26-W-G-75-BN (GV02501)" provided for the SBR4. Open a NCR MAT to supply a new one. |  |  | Não
NCR-ICN-ESC-12-0283-2020 | P0124217 | GV02501 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK - UPDATE JOB ORDER | Take out the cabinet , in order to see clearly the issue. clean with scrutiny with a vacuum cleaner all sockets, and close them with a metallic or plastic Caps. In the same time clean the arear and arrange the cables, change the plug broken. and protect the cabinet To perform that provide the following items: - Cotton, - Silicon grease, - WD 40, electrical contact cleanner spray - Vacuum cleaner, - Rags - Little metallic brush, as toothbrush... - plastic caps (see that with electrical Team). take pictures |  |  | Não
NCR-ICN-ESC-12-0306-2021 | P0155221 | EF62611F | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | see if the two connectors (NGD : 0930930098682 + 0930930273306 + 5975145548490 + 5975142632291) are available on another boat open an NCR-MAT to supply two new connectors |  |  | Não
NCR-ICN-ESC-12-0306-2021 | P0155220 | EF62610F | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | see if the two connectors (NGD : 0930930098682 + 0930930273306 + 5975145548490 + 5975142632291) are available on another boat open an NCR-MAT to supply two new connectors |  |  | Não
NCR-ICN-ESC-12-0324-2021 | SC2-PT1-MT |  | ACCEPT AS IT IS | Height can be adjusted during machining on board. Accept as it is. | ACCEPT AS IT IS | accept as it is H BOURGET |  |  | Não
NCR-ICN-ESC-12-0335-2021 | P0128192 | FC00524 | REMOVE AND REPAIR | Substituir componentes danificados. | REWORK | Dismount FC00524 and put it at the workshop for an expertise. Check the safety thermostat. If too much components are damaged ,take the unit of sbr4. Check in FC02524 that the relay K05 is not by-passed (terminal 2 and 5).BDM-00055058 Send to level 3 for analyse Update 30/06/2021: Taking into account expertise result, take the unit from SBR4 for remounting on SBR2. To open NCR MAT |  |  | Sim | N/A
NCR-ICN-ESC-12-0342-2021 | N/A |  |  |  | REWORK | Rework following the production orientation. |  |  | Não
NCR-ICN-ESC-12-0353-2021 | P0131081 | FC12560T | REMOVE AND REPAIR | Remover e substituir | REMOVE AND REWORK | CMX:50AM100D00017 Picture attached of damaged wire. Take new one on Sbr4. Open NCR MAT to replenish it. |  |  | Não
NCR-ICN-ESC-12-0360-2021 | P0131182 | KT00010 | REPAIR | Send to level 2. | REPAIR | Build up the drilling already done using E42 electrodes, grind to have a good profile Carry 100% VT and 100%MT. Carry out a new drilling 10mm aft. |  |  | Não
NCR-ICN-ESC-12-0377-2021 | P0119829 | EN00013F | REWORK | NA | REWORK | Replace the broken connector (NGD 5935144580825) with a new one. Open a regressed NCR to redo all the associated cable and equipment tests. |  |  | Não
NCR-ICN-ESC-12-0393-2021 | P0137156 | EV13502P | REPAIR |  | REWORK | Regarding the COS RIDA-07844, change the CMD of the sensor EV13502P (CMD 50DD200D00041 to CMD 50DD200D00042). Create a NCR regress to manage the inspection and test to redo. |  |  | Não
NCR-ICN-ESC-12-0405-2021 | P0106089 | ME03101 | REWORK | To change all the clamps in the power plates if the SBR-2. | REPAIR | In the beginning the 96 "non-conform" clamps were installed on SBR1 only. Due to the NCR-ICN-ESC-11-1248-2020 and NCR-ICN-ESC-11-1402-2021, all the clamps has been replaced by good ones on SBR1. Now, the non-conform clamps are either on SBR2, either on warehouse. For the non-conform clamps which are on SBR2, replaced them by clamps from Power plates in warehouse. Then collect the 96 non-conform clamps and send them to NVG France for modification. Open a NCR-MAT to follow the repair. No regression on SBR2 (Precom Jeumont not started yet) |  |  | Sim
NCR-ICN-ESC-12-0405-2021 | P0106087 | ME03102 | REWORK | To change all the clamps in the power plates of thte SBR-2. | REPAIR | In the beginning the 96 "non-conform" clamps were installed on SBR1 only. Due to the NCR-ICN-ESC-11-1248-2020 and NCR-ICN-ESC-11-1402-2021, all the clamps has been replaced by good ones on SBR1. Now, the non-conform clamps are either on SBR2, either on warehouse. For the non-conform clamps which are on SBR2, replaced them by clamps from Power plates in warehouse. Then collect the 96 non-conform clamps and send them to NVG France for modification. Open a NCR-MAT to follow the repair. No regression on SBR2 (Precom Jeumont not started yet) |  |  | Sim
NCR-ICN-ESC-12-0435-2021 | N/A |  |  |  | REWORK | Repair as per desciption of para.2.1 |  |  | Não
NCR-ICN-ESC-12-0477-2021 | P0106985 | DT14141T | REPAIR | A wire was added to solve the discontinuity issue on the printed circuit board. | REPAIR | Modification accepted as it is. Redo calibration at metrology workshop following SMB-002984 and put certificate inside NCR |  |  | Não
NCR-ICN-ESC-12-0477-2021 | P0106986 | DT14142T | REPAIR | A wire was added to solve the discontinuity issue on the printed circuit board. | REPAIR | Modification accepted as it is. Redo calibration at metrology workshop following SMB-002984 and put certificate inside NCR |  |  | Não
NCR-ICN-ESC-12-0531-2021 | P0131804 | FR00001 | ACCEPT AS IT IS | The equipment has a good physical and visual condition, must follow the next activities and inspection. But its operation should be checked during the STW. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim | 024/16-01
NCR-ICN-ESC-12-0184-2020 | N/A |  |  |  | REWORK | rework as per original design |  |  | Não
NCR-ICN-UFEM-12-0512-2019 | P4021531 |  | REWORK | Use 32VI110D00832 (SCREW H M16X80X80 CLASS 8.8) | REWORK | the screw H M16X60X60 CL8.8 FLZN mentioned are correct. Check the seating fabrication. |  |  | Não
NCR-ICN-ESC-12-0167-2020 | P4153109 |  | AGREE WITH LEVEL 2.1 |  | REWORK | OK |  |  | Não
NCR-ICN-ESC-12-0167-2020 | P4153110 |  | AGREE WITH LEVEL 2.1 |  | REWORK | OK |  |  | Não
NCR-ICN-ESC-12-0167-2020 | P4153113 |  | AGREE WITH LEVEL 2.1 |  | REWORK | OK |  |  | Não
NCR-ICN-ESC-12-0167-2020 | P4153115 |  | AGREE WITH LEVEL 2.1 |  | REWORK | OK |  |  | Não
NCR-ICN-ESC-12-0368-2021 | P0104738 | DA12515N | REWORK | USE THE CONNECTOR PROVIDED FOR THE DA12515N (SBR4) EQUIPMENT. OPEN "NCR-MAT" FOR NEW SUPPLY. | SCRAP | Replace the plug JUPITER (FEDF10MT03-14 E123) by a new one, Codigo: 11CI121D00020, NGD: 5935144069967. Take in stock or canibalize the SBR4 and create a NCR-MAT to refund the stock. | REWORK | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Não
NCR-ICN-UFEM-12-0433-2019 | BH2-EL1/EL3/EL4/EL7/EL8 |  | SCRAP | SCRAP | SCRAP | SCRAP | SCRAP | SCRAP | Não
NCR-ICN-ESC-12-0262-2020 | P4145049 |  | AGREE WITH LEVEL 2.1 |  | REWORK | It is not possible to respect the model ,lack of space for the clamping Study to be done by BO asap Send to level 3 | REPAIR | For SBR2 : Accept as is for the pipe clamp P4145050 mounting. For SBR1: As P4145049 & P4148243 SBR01 pipes were manufactured by ICN under Caderno: CC-200451-80510-11-001, please inform NAVAL GROUP Design Authority on what has be done for mounting the same pipe clamp. No NCR level 3 has been transmitted to NAVAL GROUP Design Authority. Repair action : Please note that the PTRH EN SMB-051113 will be updated to add the request to dismount the pipe clamp P4145050 before pressure and tightness test, in order to check there is no leakage. | Sim
NCR-ICN-ESC-12-0262-2020 | P4148243 |  | AGREE WITH LEVEL 2.1 |  | REWORK | It is not possible to respect the model ,lack of space for the clamping Study to be done by BO asap Send to level 3 | REPAIR | For SBR2 : Accept as is for the pipe clamp P4145050 mounting. For SBR1: As P4145049 & P4148243 SBR01 pipes were manufactured by ICN under Caderno: CC-200451-80510-11-001, please inform NAVAL GROUP Design Authority on what has be done for mounting the same pipe clamp. No NCR level 3 has been transmitted to NAVAL GROUP Design Authority. Repair action : Please note that the PTRH EN SMB-051113 will be updated to add the request to dismount the pipe clamp P4145050 before pressure and tightness test, in order to check there is no leakage. | Sim
NCR-ICN-ESC-12-0262-2020 | P4145050 |  | AGREE WITH LEVEL 2.1 |  | REWORK | It is not possible to respect the model ,lack of space for the clamping Study to be done by BO asap Send to level 3 | REPAIR | For SBR2 : Accept as is for the pipe clamp P4145050 mounting. For SBR1: As P4145049 & P4148243 SBR01 pipes were manufactured by ICN under Caderno: CC-200451-80510-11-001, please inform NAVAL GROUP Design Authority on what has be done for mounting the same pipe clamp. No NCR level 3 has been transmitted to NAVAL GROUP Design Authority. Repair action : Please note that the PTRH EN SMB-051113 will be updated to add the request to dismount the pipe clamp P4145050 before pressure and tightness test, in order to check there is no leakage. | Não
NCR-ICN-ESC-12-0118-2020 | P0116263 | KT01114 | REMOVE AND REWORK |  | REWORK |  |  |  | Sim | 32VI220D00001
NCR-ICN-ESC-12-0118-2020 | P4123601 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Sim
NCR-ICN-ESC-12-0545-2021 | N/A |  |  |  | AGREE WITH LEVEL 2.1 | Agreed to use the materials delivered for the HP Electric Compressors from S-BR 04, in order to allow performing the STW of DY subsystem on S-BR 02. To create NCR MAT for repositioning of the material for S-BR 04. |  |  | Não
NCR-ICN-UFEM-12-0392-2019 | P0129970 | FC00526 | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0245-2020 | P0130328 | FC20540 | AGREE WITH LEVEL 2.1 |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0245-2020 | P4152602 |  | AGREE WITH LEVEL 2.1 |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0098-2020 | N/A |  | ACCEPT AS IT IS | 1. There is an angle of 89°58’35.5” between the Machined Axis of FWD Hydroplane Holes and the Vertical Axis (see Machining Report - FL 3). Then, the Transmission Axis is not perpendicular for a tolerance of 90° ±1’ according SMB-200974. ACCEPT AS IT IS. 2. The Straightness and concentricity must be confirmed through piano wire inspection. 3. The Vertical Axis was shifted at Y = 0,35 mm to portside to follow the machined axis of AC34027 (see Machining Report – FL 4 and detail in FL 7). The distances C and D (for both sides) must be updated according new values after shifting of vertical axis: DP00356 • C = 203,47 • D = 814,72 DP00355 • C = 204,18 • D = 816,10 The ADJUSTING HALF-SHIM (2x Ref: 18) and THRUST WASHER (Ref: 26) will be machined accordingly. 4. The center diamenter was machined and the excentricity was corrected. Accept as it is. SEND TO LEVEL 2 ANALYSIS. |  |  |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100591 | AZ00073 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100593 | AZ00074 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100594 | AZ00075 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100595 | AZ00077 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100596 | AZ00076 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100597 | AZ00078 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100598 | AZ00079 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100599 | AZ00080 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100600 | AZ00081 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100601 | AZ00005 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100602 | AZ00014 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100603 | AZ00018 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100604 | AZ00015 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100605 | AZ00010 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100606 | AZ00019 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100607 | AZ00011 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100608 | AZ00016 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100609 | AZ00020 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100610 | AZ00004 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100611 | AZ00013 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100612 | AZ00017 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100615 | AZ00003 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100616 | AZ00012 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100617 | AZ00006 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100618 | AZ00007 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100619 | AZ00008 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100620 | AZ00009 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100621 | AZ00022 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100622 | AZ00026 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100623 | AZ00028 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100624 | AZ00023 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100625 | AZ00051 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100626 | AZ00024 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100628 | AZ00021 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100629 | AZ00029 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100630 | AZ00052 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100631 | AZ00025 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100632 | AZ00027 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100635 | AZ00002 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100637 | AZ00001 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100638 | AZ00064 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100639 | AZ00068 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100640 | AZ00066 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100641 | AZ00067 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100642 | AZ00204 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100643 | AZ00065 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100644 | AZ00205 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100646 | AZ00206 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100647 | AZ00059 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100648 | AZ00063 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100649 | AZ00061 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100650 | AZ00062 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100651 | AZ00208 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100652 | AZ00060 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100653 | AZ00207 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100654 | AZ00209 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100655 | AZ00056 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100656 | AZ00213 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100657 | AZ00211 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100658 | AZ00057 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100659 | AZ00212 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100660 | AZ00210 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100661 | AZ00214 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100662 | AZ00215 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100663 | AZ00053 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100664 | AZ00218 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100665 | AZ00216 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100666 | AZ00054 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100667 | AZ00217 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100668 | AZ00055 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100669 | AZ00219 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100670 | AZ00220 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100677 | AZ00030 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100678 | AZ00045 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100679 | AZ00229 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100680 | AZ00230 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100681 | AZ00031 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100682 | AZ00046 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100684 | AZ00231 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100685 | AZ00032 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100686 | AZ00048 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100687 | AZ00233 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100688 | AZ00234 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100689 | AZ00033 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100690 | AZ00049 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100691 | AZ00235 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100692 | AZ00263 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100693 | AZ00236 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100694 | AZ00034 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100695 | AZ00189 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100696 | AZ00237 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100697 | AZ00238 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100698 | AZ00035 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100699 | AZ00190 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100700 | AZ00239 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100701 | AZ00240 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100702 | AZ00036 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100703 | AZ00191 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100704 | AZ00241 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100705 | AZ00242 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100706 | AZ00037 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100707 | AZ00192 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100708 | AZ00243 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100709 | AZ00244 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100710 | AZ00038 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100711 | AZ00193 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100712 | AZ00245 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100714 | AZ00039 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100715 | AZ00195 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100717 | AZ00248 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100718 | AZ00040 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100719 | AZ00196 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100720 | AZ00249 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100721 | AZ00250 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100722 | AZ00041 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100723 | AZ00194 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100724 | AZ00251 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100725 | AZ00252 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100726 | AZ00042 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100727 | AZ00200 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100728 | AZ00253 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100729 | AZ00254 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100730 | AZ00043 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100731 | AZ00197 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100732 | AZ00255 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100734 | AZ00044 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100735 | AZ00199 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100736 | AZ00257 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100737 | AZ00258 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100738 | AZ00198 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100739 | AZ00224 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100740 | AZ00259 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100741 | AZ00260 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100743 | AZ00226 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100744 | AZ00261 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100745 | AZ00262 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100746 | AZ00227 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100747 | AZ00228 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100748 | AZ00232 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100750 | AZ00089 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100752 | AZ00096 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100753 | AZ00091 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100754 | AZ00098 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100755 | AZ00093 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100756 | AZ00100 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100757 | AZ00095 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100758 | AZ00102 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100759 | AZ00266 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100760 | AZ00267 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100761 | AZ00270 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100762 | AZ00272 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100763 | AZ00273 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100764 | AZ00274 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100765 | AZ00275 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100766 | AZ00276 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100768 | AZ00278 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100769 | AZ00279 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100770 | AZ00271 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100771 | AZ00090 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100772 | AZ00097 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100773 | AZ00092 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100774 | AZ00099 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100775 | AZ00094 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100776 | AZ00101 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100777 | AZ00264 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100778 | AZ00265 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100779 | AZ00268 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100780 | AZ00269 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100781 | AZ00103 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100782 | AZ00108 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100783 | AZ00104 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100784 | AZ00109 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100785 | AZ00105 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100786 | AZ00110 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100787 | AZ00106 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100788 | AZ00111 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100789 | AZ00107 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100790 | AZ00112 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100791 | AZ00280 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100792 | AZ00282 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100793 | AZ00283 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100794 | AZ00281 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100795 | AZ00125 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100797 | AZ00126 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100800 | AZ00170 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100802 | AZ00171 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100804 | AZ00083 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100806 | AZ00114 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100808 | AZ00116 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100810 | AZ00118 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100812 | AZ00120 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100817 | AZ00123 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100821 | AZ00119 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100824 | AZ00113 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100826 | AZ00115 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100828 | AZ00117 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100830 | AZ00084 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100831 | AZ00136 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100832 | AZ00086 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100833 | AZ00141 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100834 | AZ00088 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100835 | AZ00143 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100836 | AZ00128 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100837 | AZ00145 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100838 | AZ00146 | AGREE WITH LEVEL 2.1 | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100839 | AZ00130 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100840 | AZ00147 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100841 | AZ00148 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100842 | AZ00132 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100844 | AZ00133 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100846 | AZ00134 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100847 | AZ00176 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100848 | AZ00135 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100849 | AZ00131 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100850 | AZ00085 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100851 | AZ00140 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100852 | AZ00087 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100853 | AZ00142 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100854 | AZ00127 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100855 | AZ00144 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100856 | AZ00129 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100857 | AZ00137 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100860 | AZ00138 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100861 | AZ00172 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0100862 | AZ00173 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0103639 | AZ00047 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0103640 | AZ00221 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0147574 | AZ00070 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0147575 | AZ00071 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0147576 | AZ00069 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0147577 | AZ00072 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0147580 | AZ00082 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151673 | AZ00124 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151674 | AZ00139 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151675 | AZ00121 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151676 | AZ00122 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151677 | AZ00149 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151678 | AZ00150 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151679 | AZ00151 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151680 | AZ00174 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151681 | AZ00177 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151682 | AZ00178 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151683 | AZ00179 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151684 | AZ00180 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151685 | AZ00181 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151686 | AZ00182 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151687 | AZ00183 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151688 | AZ00184 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151689 | AZ00187 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151690 | AZ00186 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151691 | AZ00188 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0151692 | AZ00185 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157309 | AZ00332 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157311 | AZ00321 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157312 | AZ00322 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157313 | AZ00324 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157314 | AZ00325 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157316 | AZ00327 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157317 | AZ00328 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157318 | AZ00330 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157319 | AZ00331 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157320 | AZ00333 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157321 | AZ00334 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157322 | AZ00326 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157323 | AZ00329 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157324 | AZ00323 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157325 | AZ00320 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157326 | AZ00335 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157327 | AZ00336 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157328 | AZ00349 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157329 | AZ00338 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157330 | AZ00339 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157331 | AZ00341 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157333 | AZ00342 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157334 | AZ00344 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157335 | AZ00345 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157336 | AZ00347 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157337 | AZ00348 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157338 | AZ00350 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157339 | AZ00351 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157340 | AZ00343 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157341 | AZ00346 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157342 | AZ00340 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157343 | AZ00337 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157344 | AZ00352 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-UFEM-12-0541-2020 | P0157345 | AZ00353 | ACCEPT AS IT IS | This products received painted. Its not possible to inspect. | ACCEPT AS IT IS | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. |  |  | Não
NCR-ICN-ESC-12-0276-2020 | P4123633 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Sim
NCR-ICN-ESC-12-0276-2020 | P4021225 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Não
NCR-ICN-ESC-12-0276-2020 | P4021321 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Não
NCR-ICN-ESC-12-0276-2020 | P4021221 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Não
NCR-ICN-ESC-12-0276-2020 | P4021224 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Não
NCR-ICN-ESC-12-0276-2020 | P4021220 |  | REMOVE AND REPAIR |  | REWORK | -Rework the seating. -Remove the old one following SMB-20043 Re-install a new seating with the equipment or a mockup in accord with theorical dimension of the SMB |  |  | Não
NCR-ICN-ESC-12-0188-2020 | P0104798 | MB00004 | REWORK | The item was already replaced by SBR 3 that was available in workshop; Open a NCR-CQ for SBR 3 to use the item from SBR 4. Raise a NCR-MAT to supply new part or the drawing to manufacture for SBR 4. Remark: According certificate SMB-355803_FL86 (SBR 3), the material of Obturator (ref. 2) is S355NL. Available in ICN. | REWORK | 1- ICN could manufacture a new piece following NG drawings if raw material in ICN; 2- Order a new spare to NG; 3- Diving safety element ICN must open an NCR for all SBRs; 4- Naval Group Suggest to order spare items 3 and 5 of the drawing MTSI202200100EXP_B for all the submarines. (Charles Boucher) | REWORK | - Carry out a visual inspection of the bores that do not have a shutter for any signs of corrosion. If necessary remove them by grooming the surfaces. Renew the anti-corrosion protection by spraying a long-lasting protective coating (type Ardrox 3140 or equivalent) inside these shafts. - NCR to be created for SBR3 in order to declare the use of the SBR4 shutter on SBR3 - NCR to be created for SBR4 in order to decide whether or not to manufacture the shutter on site (See if NCR is needed to initiate the request for spare parts: seals and square brake) | Sim | 15LA000D00025
NCR-ICN-ESC-12-0096-2020 | P4163775 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4163773 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4142885 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4142886 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4140586 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4140585 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0096-2020 | P4140583 |  | MANUFACTURE |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0511-2021 | P0130037 | DU20076 | REMOVE AND REWORK |  | REPAIR |  | REMOVE AND REWORK | Considering the situation on board, the mounting has to be let as it is (David Bernede) | Não
NCR-ICN-ESC-12-0511-2021 | P0114488 | DU00001 | REMOVE AND REWORK |  | OK - NOT MODIFIED |  | REMOVE AND REWORK | Considering the situation on board, the mounting has to be let as it is (David Bernede) | Sim | 09AV200D00028
NCR-ICN-UFEM-12-0539-2020 | N/A |  | ACCEPT AS IT IS | Accept the machining as it is. See comments in document attached "2.1 ICN SOLUTION". |  |  |  |  | Não
NCR-ICN-ESC-12-0009-2019 | SMB-P0125441 |  | ACCEPT AS IT IS | The bolt and hole have the largest diameters, but their adjustments are within tolerance H7 / f6 (See annex01). Accept as is | ACCEPT AS IT IS | The gap betwwen holes and screws are minimum 0mm and maximum 0,03mm. Theoretical gap is 0,025/0,066. | REWORK | For the fitted screws n° 8 et 10, reduce the diameter in order to reach a minimum gap of 0,025 mm. See document FA255370 in annex. | Não
NCR-ICN-UFEM-12-0382-2018 | P0140145 | FQ00804 | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0243-2020 | P0130114 | DP00160 | SCRAP | Replace the items according CMD/NGD showed in annex. | REWORK | Change the damaged items to finish the correctly assembly in order to success of the pressure test. Open a NCT MAT to replanishment of the dameged items. ( Charles Boucher) |  |  | Não
NCR-ICN-ESC-12-0041-2020 | P0120883 | EM21002 | REWORK |  | ACCEPT AS IT IS | The storage limit date is 28/02/2018 and the date removal from storage is before. (14/07/2017) No problem for this swivel hose, the 8 years to use start the 14/07/2017. | ACCEPT AS IT IS | 1 / Keep on-board as they are the swivel hoses CMD 18LF100D00003. Consider that the equipment operational lifetime starts once the limit storage date has passed. 2 / Provide a precise statement of which swivel hoses are fitted on which boat for traceability and maintenance purposes. (non-respect of Naval Group's assignment requests) 3 / Adapt the maintenance schedule accordingly. (Ex : premature intervention on these swivel hoses while SRA) | Sim | x
NCR-ICN-ESC-12-0041-2020 | P0120028 | EN20015 | REWORK |  | ACCEPT AS IT IS | The storage limit date is 10/2017 and the date removal from storage is after. (20/02/2018) I propose for this swivel hose, the 8 years to use start the 10/2017 (storage limit date). | ACCEPT AS IT IS | 1 / Keep on-board as they are the swivel hoses CMD 18LF100D00003. Consider that the equipment operational lifetime starts once the limit storage date has passed. 2 / Provide a precise statement of which swivel hoses are fitted on which boat for traceability and maintenance purposes. (non-respect of Naval Group's assignment requests) 3 / Adapt the maintenance schedule accordingly. (Ex : premature intervention on these swivel hoses while SRA) | Sim | x
NCR-ICN-ESC-12-0181-2020 | P4140376 |  | REPAIR |  | REPAIR | Repair as per ICN proposal annexed |  |  | Não
NCR-ICN-ESC-12-0150-2020 | P0105469 | DM03151 | REPAIR | Repainting according parameters described in Appendix 1 and inspection template. If the color is diferent one entire lay can be applied. | REWORK | According to the paint specification SMB-002345, ICN must rework the painting with a RAL7038 |  |  | Não
NCR-ICN-ESC-12-0302-2020 | P4154678 |  | SCRAP AND RE-MANUFACTURE | Remanufatura dos itens conforme desenho anexo. | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0419-2021 | P4119159 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0419-2021 | P0105757 | DB00111 | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0163-2020 | P0140475 | DN00212R | REPAIR | Send to level 2. | REWORK | Not possible to repair at ICN but a supplier in Brazil have the capability. To allow the following of the repairing a NCR MAT have to be raise. | REWORK | NAVAL GROUP will globally take in charge all hull valves which have a damaged coating. These hull valves will be sent lot by lot to a dedicated supplier for rework. This topic will not be managed by RTE process. No NCR MAT required. | Não
NCR-ICN-ESC-12-0080-2020 | P4500363 |  | REMOVE AND REWORK | Follow the attached TAF | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0080-2020 | P4500364 |  | REMOVE AND REWORK | Follow the attached TAF. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0301-2020 | P0130119 | DP00159 | REWORK | Rework. Hydroplane Gear: • Dismounting the Hydroplane Blades completely, send to workshop and take new measurements; • Check the referential axis of the steering gear holes and transmission lines onboard by optical; • According results make new calculations and remachining the shims; • Check the cleaning of the coamings (holes) and pipes before installation (flow of the grease and control the quality); • Assembly back the Hydroplane blades, Stocks, Yokes and Tilting Arms; Note: Pay attention during torque applying with Superbolt Nut. Don’t use impact wrench, tight the nut by hand; • Check the clearances and flow of the grease after final mounting. Rudder Gear: • After finishing Hydroplane activities, an analyze must be made to verify if is necessary to dismounting the Rudder Gear completely as done in Hydroplane Gear or a minimum disassembly (for example, removing and machining only the shims). | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0301-2020 | P0130114 | DP00160 | REWORK | Rework. Hydroplane Gear: • Dismounting the Hydroplane Blades completely, send to workshop and take new measurements; • Check the referential axis of the steering gear holes and transmission lines onboard by optical; • According results make new calculations and remachining the shims; • Check the cleaning of the coamings (holes) and pipes before installation (flow of the grease and control the quality); • Assembly back the Hydroplane blades, Stocks, Yokes and Tilting Arms; Note: Pay attention during torque applying with Superbolt Nut. Don’t use impact wrench, tight the nut by hand; • Check the clearances and flow of the grease after final mounting. Rudder Gear: • After finishing Hydroplane activities, an analyze must be made to verify if is necessary to dismounting the Rudder Gear completely as done in Hydroplane Gear or a minimum disassembly (for example, removing and machining only the shims). | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0301-2020 | P0131101 | DP00259 | REWORK | Rework. Hydroplane Gear: • Dismounting the Hydroplane Blades completely, send to workshop and take new measurements; • Check the referential axis of the steering gear holes and transmission lines onboard by optical; • According results make new calculations and remachining the shims; • Check the cleaning of the coamings (holes) and pipes before installation (flow of the grease and control the quality); • Assembly back the Hydroplane blades, Stocks, Yokes and Tilting Arms; Note: Pay attention during torque applying with Superbolt Nut. Don’t use impact wrench, tight the nut by hand; • Check the clearances and flow of the grease after final mounting. Rudder Gear: • After finishing Hydroplane activities, an analyze must be made to verify if is necessary to dismounting the Rudder Gear completely as done in Hydroplane Gear or a minimum disassembly (for example, removing and machining only the shims). | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0301-2020 | P0131161 | DP00260 | REWORK | Rework. Hydroplane Gear: • Dismounting the Hydroplane Blades completely, send to workshop and take new measurements; • Check the referential axis of the steering gear holes and transmission lines onboard by optical; • According results make new calculations and remachining the shims; • Check the cleaning of the coamings (holes) and pipes before installation (flow of the grease and control the quality); • Assembly back the Hydroplane blades, Stocks, Yokes and Tilting Arms; Note: Pay attention during torque applying with Superbolt Nut. Don’t use impact wrench, tight the nut by hand; • Check the clearances and flow of the grease after final mounting. Rudder Gear: • After finishing Hydroplane activities, an analyze must be made to verify if is necessary to dismounting the Rudder Gear completely as done in Hydroplane Gear or a minimum disassembly (for example, removing and machining only the shims). | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0321-2021 | P0108340 | DY02511 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Following the NCR 1271 ,we took the "driver card" on sbr2 to repair the sbr1. In order to be able to start DY02511 on sbr2, we have to take the "driver card" on sbr3 No need to open NCR MAT because normally it has been done after NCR ESC 1271 |  |  | Sim
NCR-ICN-ESC-12-0146-2020 | N/A |  |  |  | REPAIR | Repair as per TA proposal. |  |  | Não
NCR-ICN-ESC-12-0296-2020 | P0110267 | DT04200 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Replace the existing screws with screws 32VI110D01871 "SLOTTED COUNTERSUNK FLAT HEAD SCREW WITH THREAD M6, NOMINAL LENGTH L = 20 AND PROPERTY CLASS 4.8" identical to SBR3 (see annex1) | REWORK | Replace the screws used (H head with washer) by FHC screws as provided in the definition file, (M6x20x20 CL4.8 - 32VI110D01871) is acceptable. | Sim
NCR-ICN-ESC-12-0029-2019 | SMB-P4125156 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125158 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125159 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125160 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125161 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125162 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4125163 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128131 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128146 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128178 |  |  | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128193 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128215 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128216 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128217 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4128218 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0029-2019 | SMB-P4144996 |  | REWORK | Replacing RUCH Fittings and Gaskets For: 18RO220D00054 (316L WELDING THREAD CONEC INSTRUM OD10.2) + 44JO304D00009 (O-RING, METAL 8X17,3X2,6) | REPAIR | REPAIR as per level 1 proposition, following previous revision of isometric drawing/part list. | REWORK | Agreement on the submitted proposal, the fittings provided for in the study are not suitable for the thread of the flexible pipes. Resumption of clean package with the right connections, a check will be made on the consistency of the flexible definition plan because a bad return of the sheet generated this study anomaly | Não
NCR-ICN-ESC-12-0314-2021 | P0110264 | DT04100 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | Replace the existing screws with screws 32VI110D01871 "SLOTTED COUNTERSUNK FLAT HEAD SCREW WITH THREAD M6, NOMINAL LENGTH L = 20 AND PROPERTY CLASS 4.8" identical to SBR3 (see annex1) | REWORK | Replace the screws used (H head with washer) by FHC screws as provided in the definition file, (M6x20x20 CL4.8 - 32VI110D01871) is acceptable. | Sim
NCR-ICN-ESC-12-0133-2020 | P0105126 | BC02660 | REWORK | To level 2. | REMOVE AND REWORK | Take on sbr4 Open NCR MAT to replenish: GMC INSTRUMENTS PROGRAMMABLE MULTIFUNCTIONAL TRANSMITTER SINEAX V604s Manufacturer Ref:168 329 BDM-00077875 |  |  | Não
NCR-ICN-UFEM-12-0515-2019 | P4176145-C-29324-13437-18RO110D00076 |  | REWORK | the spools P4176145 and P4156638 should both be tested with a pressure of 3.5 Bar which is the same test pressure as tube P4156638. | OK - NOT MODIFIED |  |  |  | Não
NCR-ICN-ESC-12-0260-2020 | P0101605 | OO24402 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | For the internal FLAT modules ASI type 4 integrated in the cabinet (FQ or IPMS) according with Document SMB-201629 (ASI MODULES DEFINITIONS) You don't need specific connector. For this case, apply the wiring described in BDM-00073622 To connect use rep 36 conductor quoted in this plan |  |  | Não
NCR-ICN-ESC-12-0260-2020 | P0101604 | OO24307 | REWORK | FOLLOW LEVEL 2.2 GUIDELINES. | REWORK | For the internal FLAT modules ASI type 4 integrated in the cabinet (FQ or IPMS) according with Document SMB-201629 (ASI MODULES DEFINITIONS) You don't need specific connector. For this case, apply the wiring described in BDM-00073622 To connect use rep 36 conductor quoted in this plan |  |  | Não
NCR-ICN-ESC-12-0135-2020 | P0101614 | OO24024 | REWORK |  | REMOVE AND REWORK | Remove the module from SBR2 and take the same reference from SBR3. |  |  | Não
NCR-ICN-ESC-12-0135-2020 | P0101607 | OO24208 | REWORK |  | REMOVE AND REWORK | Remove the module from SBR2 and take the same reference from SBR3. |  |  | Não
NCR-ICN-ESC-12-0318-2021 | N/A | [7 empty] | Não
NCR-ICN-UFEM-12-0498-2019 | P0124998 | EX00026 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | AGREE WITH 2.1 | Não
NCR-ICN-ESC-12-0275-2020 | P4019069 |  | REWORK |  | REWORK | Rework as per original, cut the seating, to ajust the hight if the gap if below 8mm build up the seating. if it´s more rework new elements After removing carry out a visual and nittal inspection of the hull, open an NCR/RO to build up the hull reinstall a seating. |  |  | Não
NCR-ICN-ESC-12-0189-2020 | P0131345 | DP00376 | ACCEPT AS IT IS | Accept as it is. Send to level 2 to validate. | ACCEPT AS IT IS | Less than 2 threads but more than 1,5 thread is visible. | ACCEPT AS IT IS | Accept as it is for SBR2. This problem was take in account by OM-114819. | Sim | 00045
NCR-ICN-ESC-12-0037-2020 | P0107353 | DT00201H | ACCEPT AS IT IS | Based on NCR-ICN-UFEM-12-469-2019 of SBR-1 with the same type of anomaly presented in SBR-2, we suggest accepting as is. | ACCEPT AS IT IS |  | REWORK | Agreement to accept assembly as is. The analysis of controls A04 (Control of suspension frequencies) then the upstream / downstream vibration measurements (SHIP11C) on these auxiliaries will enable us to decide on these studs. | Não
NCR-ICN-ESC-12-0037-2020 | P0107354 | DT00301H | ACCEPT AS IT IS | Based on NCR-ICN-UFEM-12-469-2019 of SBR-1 with the same type of anomaly presented in SBR-2, we suggest accepting as is. | ACCEPT AS IT IS |  | REWORK | Agreement to accept assembly as is. The analysis of controls A04 (Control of suspension frequencies) then the upstream / downstream vibration measurements (SHIP11C) on these auxiliaries will enable us to decide on these studs. | Não
NCR-ICN-ESC-12-0236-2020 | P0141690 | EL00006 | REWORK |  | REWORK | Raise NCR MAT to launch the manufacture of new one. Replace by temporary plug for ceremony | REWORK | The CMD is 18RO110D00822. In accordance with level 2.2 to raise an NCR MAT to manufacture a new one after confirmation that the equipment can´t be found. | Sim | 10RO110D00822
NCR-ICN-ESC-12-0183-2020 | P0138322 | BH00101V | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0183-2020 | P0138336 | BH00104R | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0183-2020 | P0138323 | BH00102V | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0183-2020 | P0138337 | BH00105R | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0183-2020 | P0138334 | BH00103R | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0183-2020 | P0138338 | BH00106R | REMOVE AND REWORK | Remove the valves, change the studs for the right length, change the washer and gasket for new and apply the entire Torque process again according to SMB-200960. | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-UFEM-12-0510-2019 | P4148809 |  | SCRAP AND RE-MANUFACTURE | The pipe must be remanufactured according to the model. | REPAIR | Repair solution proposed by ICN will be accepted as far as trade and proximity rules are complied. Spool manufactured must pass through all controls predicted for P4148809 |  |  | Não
NCR-ICN-ESC-12-0022-2019 | P4134339 |  | REWORK | The spool EJ50037J1 (P4134339) should be adjusted as per board. | REPAIR | job done on board , send to L3 for updating drawing acording to the attached annex |  |  | Não
NCR-ICN-ESC-12-0248-2020 | P4165717 |  | SCRAP AND RE-MANUFACTURE |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0248-2020 | P4165788 |  | SCRAP AND RE-MANUFACTURE |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Não
NCR-ICN-ESC-12-0248-2020 | P4123636 |  | SCRAP AND RE-MANUFACTURE |  | NCR LEVEL 1 | NCR LEVEL 1 |  |  | Sim
NCR-ICN-ESC-12-0248-2020 | P4154678 |  | SCRAP AND RE-MANUFACTURE |  | NCR LEVEL 1 |  |  |  | Não
NCR-ICN-ESC-12-0331-2021 | N/A |  |  |  | ACCEPT AS IT IS | In the SMB-002525 , only the Crude steel floor must be painted. On board the floor of A220 and A230 were painted. Accepted as it is. |  |  | Não
NCR-ICN-ESC-12-0074-2020 | P4153042 |  | REMOVE AND REPAIR | The project will not be changed, any modification must be dealt with directly at NCR. | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0074-2020 | P4153041 |  | REMOVE AND REPAIR |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0074-2020 | P4171221 |  | REMOVE AND REPAIR |  | ACCEPT AS IT IS |  |  |  | Não
NCR-ICN-ESC-12-0015-2019 | P0151846 | AC43009 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151137 | AC41020 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151115 | AC41017 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151127 | AC41019 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151131 | AC41021 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151146 | AC41018 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151223 | AC41015 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151172-B-29641-960-44JO230D00279 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0154463-B-28324-51829-32VI220D00151 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0154471-A-28141-51801-32VI220D00162 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0154439-A-27892-13189-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0154444-B-26471-12500-01PM100D00022 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REPAIR | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0156007-A-28425-1520-44JO230D00279 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0156010-A-28425-1513-44JO230D00276 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0154455-A-27892-13962-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0156023-A-27892-14963-44JO230D00241 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151533-A-26740-44222-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151536-A-26740-44205-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151551-A-26740-44189-32VI220D00162 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151554-A-26740-44278-32VI220D00162 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151566-A-26740-44168-32VI420D00043 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151814-A-26722-34160-32VI220D00170 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151877-A-28146-44323-44JO230D00276 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151884-A-26740-44236-44JO230D00245 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151890-A-26722-29152-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151894-A-26722-34168-44JO230D00245 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151930-A-26722-34177-44JO230D00245 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151934-A-26722-29143-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151940-A-26722-34187-32VI220D00170 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151943-A-26722-34195-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151948-A-26740-44254-44JO230D00072 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152073-B-27324-34150-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152167-A-26740-44308-32VI220D00170 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152168-A-26740-44294-44JO230D00227 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152759 | AC43064 | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152760-A-26722-34141-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151989-A-26743-7648-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0151997-A-26743-7674-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152006-A-26743-7689-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152027-A-26725-10399-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152029-A-26725-10408-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152033-A-26743-7706-32VI420D00031 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152039-A-26743-7727-44JO230D00245 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152052-A-26743-7739-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152070-A-26725-10418-44JO230D00228 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152071-A-23019-593-32VI220D00151 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152076-A-26743-7660-44JO230D00227 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0015-2019 | P0152081-A-23020-1228-44JO230D00243 |  | REMOVE AND REWORK | Run painting of mobile parts as described in DEI-200153-63120-12-002 | REMOVE AND REWORK | 1) Remove the mobile part. 2) Painting of the hull passage following SMB-002525. 3) Inspect before remounting the good status of mobile part and stud rods. 4) Mounting with a new gasket and new lock washers. 5) Redo all document of mounting and tracability. | REWORK | There is a misunderstanding. The SMB-002525 has to be used to paint the hull sleeves. Because it was not done before the mounting of mobile parts it is necessary to dismount them. | Não
NCR-ICN-ESC-12-0241-2020 | P0130056 | DP00163 | REWORK | Wait for NG orientation. | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0241-2020 | P0130994 | DP00264 | REWORK | Waiting for NG orientation. | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0241-2020 | P0130060 | DP00164 | REWORK | Waiting for NG orientation. | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0241-2020 | P0130995 | DP00263 | REWORK | Waiting for NG orientation. | REWORK | ok |  |  | Não
NCR-ICN-ESC-12-0066-2020 | P0101413 | OO02534 | REMOVE AND REWORK | ICN proposes to use the power supply from S-BR03 (cabinet OO02534). Forward to Naval Group to verify the proposal and check the progress of new material delivery regarding the NCR-MATs declared for S-BR01. | REWORK | Naval Group asks ICN to Pick up these two devices in the OO02534 cabinet of SBR3 |  |  | Sim
NCR-ICN-ESC-12-0442-2021 | P4167471 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0442-2021 | P4167473 |  | REMOVE AND REWORK |  | REWORK |  |  |  | Não
NCR-ICN-ESC-12-0175-2020 | P0104801 | MB00007 | MANUFACTURE | Manufacture or buy in SKF company the missing itens. Raise a NCR MAT to supply spare parts. | REWORK | Manufacture or buy new items in SKF company ( Charles Boucher) |  |  | Não
NCR-ICN-ESC-12-0134-2020 | P0122383 | FH02625 | REPAIR | Touch-up according parameters described in Appendix 1. | REPAIR | Repair as per comments of para 1.2. If the color is diferent one entire lay can be applied |  |  | Sim
NCR-ICN-ESC-12-0309-2021 | P0116850 | EF00380V | REMOVE AND REWORK | Assemble the EF00380 valve according to the project definition. | REWORK | Mount the valve according the drawing attached. | REWORK | SMB-000871 will be updated for inversion of the valve symbol with respect to the direction of the fluid. | Não
NCR-ICN-ESC-12-0223-2020 | P0101410 | OO02533 | REWORK | ICN suggests to remove the item from a cabinet in storeroom. | REMOVE AND REWORK | ICN used these lock for the door of OO02534 cabinet SBR1. | REWORK | Please take the lock of the door from the damaged OO02531 cabinet. | Sim
NCR-ICN-ESC-12-0259-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0059-2020 | P0103632 | BF02505 | REMOVE AND REWORK | Supply new | REWORK | Supply and replace by a new one : MAFELEC 22VC RED NGD 5930143490618 The breakage of the Mafelec shutter does not prevent the continuation of the tests and trials |  |  | Sim
NCR-ICN-ESC-12-0206-2020 | P0131520 | MB00003 | ACCEPT AS IT IS | Accept as it is. Send to level 2 and DA to validate the mounting. | REWORK | Find the cause of the problem, because is good for someones, add all the traceability of the stud in this NCR and rework if necessary respecting the rules (SMB-200960_H).Perform this job before to do the prssure test. ( Charles Boucher). | REWORK | In accordance with L2 proposal to check the traceability of the studs rods In addition at the other part of the stern gland there is some tab washers wich are nor adapted to the bolting D BERNEDE | Sim | AP398227
NCR-ICN-ESC-12-0024-2019 | P0118081 | RM12515P | REWORK |  | OK - NOT MODIFIED |  |  |  | Não
NCR-ICN-ESC-12-0073-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0257-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0257-2020 | P0105126 | BC02660 | REWORK | Replace voltmeter | REWORK | ICN needs to open an NCR MAT to replace the voltmeter + D1A-P4 of the BC02660 on the SBR2. On the other hand, Naval Group confirms that the voltmeter can be used as is while waiting for its replacement. |  |  | Não
NCR-ICN-ESC-12-0468-2021 | P4140406 |  | REWORK | Remounting the a new spool and scrapping the damaged one. | REWORK |  | REWORK | In accordance with level 2.2 proposal. David BERNEDE - ISSP | Não
NCR-ICN-ESC-12-0092-2020 | P4153841 |  | REMOVE AND REPAIR | Invert the connections due to lack of space to weld. | REMOVE AND REPAIR | Invert the connection male-female on the assembly of the spools P4153841 and P4153950 |  |  | Não
NCR-ICN-ESC-12-0092-2020 | P4153950 |  | REMOVE AND REPAIR | Invert the connections due to lack of space to weld. | REMOVE AND REPAIR | Invert the connection male-female on the assembly of the spools P4153841 and P4153950 |  |  | Não
NCR-ICN-ESC-12-0072-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0358-2021 | P0108718 | RF00026 | REMOVE AND REPAIR | install in SBR2 |  | The batch pertaining to RF system is arriving in June at Brazil |  |  | Não
NCR-ICN-ESC-12-0088-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0076-2020 | P0138656 | BH00001 | REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0076-2020 | P0138652 | BH00002 | REPAIR |  | REPAIR |  |  |  | Não
NCR-ICN-ESC-12-0069-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0295-2020 | P0140888 | EQ00027 | REMOVE AND REWORK |  | REWORK | EQ00027 CMD: 18RT210D00015 will be changed by a new one. NCR MAT will be raise to follow the repair of valve. NCR REGRESS will be raise to carry out new pressure tests and inspection (M05,B01,B02). | REWORK | In accordance with level 2.2 proposal. Add in the NCR regress the S02 test concerning the circuit. | Não
NCR-ICN-UFEM-12-0378-2018 | P4144983 |  | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | REPAIR | Não
NCR-ICN-ESC-12-0252-2020 | P0120784 | EM00007 | ACCEPT AS IT IS | Send to level 2. | REWORK | -Valves EM00007 and EM00008 were dismounted. -Gaskets and lock washers will be changed. A new purchase will be launch. -Stud rods can be reuse: there are in good status, the last tightening was in normal value and no hard point between stud and nuts -Raise a NCR REGRESS to redo inspections and test. (Patrick Daliguet) | REWORK | In accordance with L2.2 D BERNEDE | Sim | 18RT020D00018
NCR-ICN-ESC-12-0252-2020 | P0120300 | EM00008 | ACCEPT AS IT IS | Send to level 2. | REWORK | -Valves EM00007 and EM00008 were dismounted. -Gaskets and lock washers will be changed. A new purchase will be launch. -Stud rods can be reuse: there are in good status, the last tightening was in normal value and no hard point between stud and nuts -Raise a NCR REGRESS to redo inspections and test. (Patrick Daliguet) | REWORK | In accordance with L2.2 D BERNEDE | Sim | 18SC011D00097
NCR-ICN-ESC-12-0303-2020 | P0117415 | EG00202 | REINSPECT THE ELEMENT |  | REWORK | In accordance with level 1, NCR REGRESS will be raise with: -B07_EG00202 will be redone -B01_EG00202 and B02_EG00202 will be carry out (Pipe EG50202M disassembled). -M05 and S02_EGZ0001 will be carry out for pipe EG50202M -B05 will be updated | REWORK | In accordance with level 2.2. (David BERNEDE - ISSP) | Sim | 32VI220D00003
NCR-ICN-ESC-12-0160-2020 | P0113044 | KT03517 | REPAIR | Send to level 2. | REWORK | Raise a NCR MAT to follow the repairing of valve (indicating CMD and serial number). The repairing of Belzona can be carried out by ICN. For the remplacement on board 2 CMD can be use: -18RT010D00726 (Belzona) -18RT010D00834 (Halar) |  |  | Sim | 18RT010D00726
NCR-ICN-ESC-12-0160-2020 | P0116730 | KT03518 | REPAIR | Send to level 2. | REWORK | Raise a NCR MAT to follow the repairing of valve (indicating CMD and serial number). The repairing of Belzona can be carried out by ICN. For the remplacement on board 2 CMD can be use: -18RT010D00726 (Belzona) -18RT010D00834 (Halar) |  |  | Sim | 18RT010D00726
NCR-ICN-ESC-12-0333-2021 | P4151674 |  | REWORK |  | REWORK | Analysis :the seating was installed in wrong position. difference de 6mm Proposition: Correct the position in relation to the design. use the CTE annexed. Due to the small difference of position the new welding will touch the old one. No need to remove the austenitic. |  |  | Não
NCR-ICN-UFEM-12-0508-2019 | P0137397 | FQ00200 | REPAIR | Replace the screws CMD 32VI110D00800 (30mm lenght) for 32VI110D00802 (40mm lenght). | AGREE WITH LEVEL 2.1 | Change screws by new more long (40mm). Opening of NCR MAT to supply new screws and update documentation |  |  | Não
NCR-ICN-ESC-12-0193-2020 | P0152219 | AC30070 | REWORK | Rework the surface with appropriate tools, like NCR-ICN-UFEM-12-410-2019. Need to inspect thickness remain and planicity after the job. Respect the tolerance in MAT424-0776. | REPAIR | Map the defect , Clean by grinding and take the depth and map the defect . Carry out 100%VT and 100% DP Stop point to analyse with T.A. After analysis open the defect with a good profile (see WPS)Carry out 100%VT Build up using WPS 141/9-9/RPA2 Carry out 100%Vt and 100%DP Rework the manuel machining using a tool ( marble) |  |  | Não
NCR-ICN-ESC-12-0151-2020 | P0105249 | MB00312 | REPAIR | 1) For SBR 2, replace the Inflatable Seal from SBR 2 by SBR 4 (CMD 15PE000D00003 delivered in batch SMB4-MA16B-DB2). 2) For SBR 4, take the item from SBR 2 and proceed as below: • Remachining the Ø550 of the Inflatable Seal as less as possible until achieve a regular surface; • The minimum acceptable dimension is 549,80 ± 0,05 mm to obtain an extrusion gap less than 0,4 mm; • Perform a G06 dimensional inspection to register the machined diameter (issue CTEPROV); • If the measurement is in accordance, machining the AC30001 coaming according to the project (Ø550H7) respecting the PELA clearances; • If the measurement is not conform, scrap the equipment and raise a NCR-MAT for replacement; Note: The water tightness is achieved by static sealing and there is no risk for extrusion of the seal with a gap which remains smaller than 0.4 mm. See comments in "Annex 1 - 2.1 ICN SOLUTION-DECISION"; 3) Send to level 2, DA and Safety Diving especialist to analysis. | REWORK | Not agree with the proposed solution by ICN in 2.1. For SBR2 use the inflatable seal provided for SBR2. Using san d paper reduce the stripes on the external diameter. Install the inflatable seal and make the test at 20bar. If the rest is good accept as it is. ( Charles Boucher) |  |  | Não
NCR-ICN-ESC-12-0406-2021 | P0106089 | ME03101 | REWORK | It's missing the flow controllers in the CC1 and CC2. | REPAIR | 1) Take 2 flowmeter panels FC01-U1R2C1 from SBR4 and connect them on SBR2, 2) Open NCR-MAT to supply 2 flowmeter panels FC01-U1R2C1 for SBR4, 3) No regression on SBR2 (Jeumont precom still not done). |  |  | Sim
NCR-ICN-ESC-12-0406-2021 | P0106087 | ME03102 | REWORK | It's missing the flow controllers in the CC1 and CC2. | REPAIR | 1) Take 2 flowmeter panels FC01-U1R2C1 from SBR4 and connect them on SBR2, 2) Open NCR-MAT to supply 2 flowmeter panels FC01-U1R2C1 for SBR4, 3) No regression on SBR2 (Jeumont precom still not done). |  |  | Sim
NCR-ICN-ESC-12-0010-2019 | P0104799 | MB00005 | REWORK | 1) Replace the Aft Immersed Bush (MB00005 - P0104799 - 14CO100D00003) from SBR 2 by SBR 4 (available in warehouse) and machine the external diameter respecting the clearance of 0/+0,04 mm according onboard machined dimensions, see Annex 1 (inspection sheet CTE00687337.2). 2) For the upward offset of 3 mm in the inner diameter, the operation must be following by TA Naval Group, ICN engineer and CQ Inspector to validate and authorize the machining. All operations must be done according documents MTSI205100100EXP_A and TAF-TA-2017-0822. | ACCEPT AS IT IS | Agree with the proposed solution 1 Continue the installation of the shaft-line with this bearing , in thies conditions 2 Wait of the confirmation by NG Design to accept as it is. The feedback on this material permite to accept as it is. | REWORK | REWORK : machine a new internal bush. Internal bush NGD 0930930013869 (quantity 2) have been delivered to Itaguai on 14/04/2020 through batch SMB-RMS-CUR-DB35/01. | Não
NCR-ICN-ESC-12-0225-2020 | P0152216 | AC30052 | REPAIR | Repair. The same defect was found e treated in NCR-ICN-UFEM-12-410-2019. Follow the steps below: 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-UFEM-12-410-2019. | REWORK | Rework Agree with para.2.1. Rework as per description stop point with Naval-group/TA |  |  | Não
NCR-ICN-ESC-12-0319-2021 | P0141011 | GN02563 | REWORK | Apply the connector provided for the SBR4 and open the "NCR-MAT" for a new supply. | REWORK | NG does not authorize taking on another submarine. Spare available with production team. The connector is already repaired by the production team. |  |  | Não
NCR-ICN-UFEM-12-0106-2018 | P4503089 |  | REWORK | REWORK | REWORK | REWORK | REWORK | REWORK | Não
NCR-ICN-ESC-12-0426-2021 | P4161492 |  | SCRAP AND RE-MANUFACTURE | For analysis by Naval Group. | SCRAP AND RE-MANUFACTURE |  |  |  | Não
NCR-ICN-ESC-12-0214-2020 | P0151979 | AC44031 | REWORK | Send to level 2. | REWORK | En accordance with level 2.1 but I added the drawing to use for the manufacture (EX lock washer.pdf). | REWORK | In accordance with levels 1.2 and 2.2 proposal. | Sim | 01PM000D00022
NCR-ICN-ESC-12-0300-2020 | P0102195 | BB00700 | REMOVE AND REPAIR | It is necessary remove the pipe to repair. To perform this it also necessary remove the battery connection BB22511 to access the pipe. | REPAIR | Agree with proposed solution above in 2.1, but after having located and repaired the leakage in workshop, carry out a pressure test on the PVC element before remount the pipe on board. ( Alain Lamy) |  |  | Não
NCR-ICN-ESC-12-0162-2020 | P0106322 | DN00112 | REPAIR | Send to level 2. | REWORK | Not possible to repair at ICN but a supplier in Brazil have the capability. To allow the following of the repairing a NCR MAT have to be raise. | REWORK | NAVAL GROUP will globally take in charge all hull valves which have a damaged coating. These hull valves will be sent lot by lot to a dedicated supplier for rework. This topic will not be managed by RTE process. No NCR MAT required. | Sim | 18RT010D00808
NCR-ICN-ESC-12-0162-2020 | P0140473 | DN00112R | REPAIR | Send to level 2. | REWORK | Not possible to repair at ICN but a supplier in Brazil have the capability. To allow the following of the repairing a NCR MAT have to be raise. | REWORK | NAVAL GROUP will globally take in charge all hull valves which have a damaged coating. These hull valves will be sent lot by lot to a dedicated supplier for rework. This topic will not be managed by RTE process. No NCR MAT required. | Não
NCR-ICN-ESC-12-0244-2020 | P0116276 | KT01418 | REWORK | Rework. Replace the gasket and check the good condition and cleanliness; Check the condition of the bearing surfaces; Check the integrity of the studs and nuts; Replace the lock tab washer and install the valve according SMB-200960. | REWORK | Valves were not correctly mounted: -Switch box not in good orientation and support are not in line with the valves. -Dismount completely, cut and replace support at the good location. -Mount the switch box in the good orientation. -Mount valves and redo all inspections ( Patrick Daliguet) | REWORK | in accordance with L2,1 proposal raise a NCR REGRESS if any inspection was done before this dismounting redo all inspections of mouting, testing traceability D BERNEDE | Sim | 18RT000D00196
NCR-ICN-ESC-12-0244-2020 | P0111097 | KT01417 | REWORK | Rework. Replace the gasket and check the good condition and cleanliness; Check the condtion of the bearing surfaces; Check the integrity of the studs and nuts; Replace the lock tab washer and install the valve according SMB-200960. | REWORK | Valves were not correctly mounted: -Switch box not in good orientation and support are not in line with the valves. -Dismount completely, cut and replace support at the good location. -Mount the switch box in the good orientation. -Mount valves and redo all inspections ( Patrick Daliguet) | REWORK | in accordance with L2,1 proposal raise a NCR REGRESS if any inspection was done before this dismounting redo all inspections of mouting, testing traceability D BERNEDE | Sim | 18RT000D00196
NCR-ICN-ESC-12-0131-2020 | P0104733 | DA12510N | REPAIR | Send to level 2. | REPAIR | See FTG-8992 |  |  | Não
NCR-ICN-ESC-12-0097-2020 | P0109304 | DY01031 | REPAIR | Forward to Naval Group to provide the necessary material in order to repair and mount on S-BR02. | REPAIR | ICN to repair in workshop the both valves DY01031 and DY01032, needs to create a spare part request to take in the RMS the items below (rep 4 and 5 of the SBR-ETM-00000M0001, page: 3849): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS If the RMS stock is not available, need to replenish with a safety stock (the consumption of these kinds of O-RING is very common. I suggest a replenishment threshold of 50 units). |  |  | Não
NCR-ICN-ESC-12-0097-2020 | P0109305 | DY01032 | REPAIR | Forward to Naval Group to provide the necessary material in order to repair and mount on S-BR02. | REPAIR | ICN to repair in workshop the both valves DY01031 and DY01032, needs to create a spare part request to take in the RMS the items below (rep 4 and 5 of the SBR-ETM-00000M0001, page: 3849): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS If the RMS stock is not available, need to replenish with a safety stock (the consumption of these kinds of O-RING is very common. I suggest a replenishment threshold of 50 units). |  |  | Não
NCR-ICN-ESC-12-0097-2020 | P0109307 | DY02033 | REWORK | Waiting to repair the valve DY01031 or DY01032 from S-BR01 and mount it on S-BR02. | REPAIR | ICN to repair in workshop the both valves DY01031 and DY01032, needs to create a spare part request to take in the RMS the items below (rep 4 and 5 of the SBR-ETM-00000M0001, page: 3849): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS If the RMS stock is not available, need to replenish with a safety stock (the consumption of these kinds of O-RING is very common. I suggest a replenishment threshold of 50 units). |  |  | Não
NCR-ICN-ESC-12-0097-2020 | P0109308 | DY02034 | REWORK | Waiting to repair the valve DY01031 or DY01032 from S-BR01 and mount it on S-BR02. | REPAIR | ICN to repair in workshop the both valves DY01031 and DY01032, needs to create a spare part request to take in the RMS the items below (rep 4 and 5 of the SBR-ETM-00000M0001, page: 3849): O-RING 37,30 x 3,60 20A8 GN (CMD: 44JO110D00018) - 6 UNITS O-RING 18,40 x 2,70 20A8 GN (CMD: 44JO110D00309) - 8 UNITS If the RMS stock is not available, need to replenish with a safety stock (the consumption of these kinds of O-RING is very common. I suggest a replenishment threshold of 50 units). |  |  | Não
NCR-ICN-ESC-12-0050-2020 | P4004511 |  | REWORK |  | REWORK | -Open a cavity to remove the defetc and to have a good shape with ''spoon'' on each side ( as per WPS). -Carry out 100% VT and 100% DP. - if the depth is less than 2mm,Build up using WPS 141/9-6/5RP.A1. - if the depth is more than 2mm, stop point. -The welder must be qualified as per SMB-030502-B para.15.4 -Carry out 100%VT and 100% DP. -smooth grinding with sand paper and JIG ( anel) to ajust the good shape. -Carry out flatness inspection on the coaming face | REWORK | -If the depth is less than 2mm build up using WPS 141 / 9-9 / 6/RP.A1 according to SMB-200046. -The welder must be qualified as per SMB-030502-B para.15.4 -Carry out 100%VT and 100% DP. - Smooth grinding with sand paper and JIG ( anel) to ajust the good shape. - Carry out flatness inspection on the coaming face - If the depth is more than 2mm, stop point and open a new NCR to send to level 3. | Não
NCR-ICN-ESC-12-0251-2020 | P0106459 | DN00311R | ACCEPT AS IT IS | Accept as it is. | REWORK | a visual control have to be done B001 and B02 pressure tests will be done after remounting if the mounting is conform and pressure tests without leaks, it is possible to accept as it is DALIGUET P |  |  | Não
NCR-ICN-ESC-12-0251-2020 | P0140476 | DN00312R | ACCEPT AS IT IS | Accept as it is. | REWORK | a visual control have to be done B001 and B02 pressure tests will be done after remounting if the mounting is conform and pressure tests without leaks, it is possible to accept as it is DALIGUET P |  |  | Não
NCR-ICN-ESC-12-0114-2020 | P0121233 | EM02500 | REWORK |  | REWORK | Due of no RMS stock ,take on EM02500on sbr4 the items below: -BIPOLAR 2-POSITION FLIP SWITCH 3A SERIES 160UN01 WITH LOCK YELLOW TERMINATION Rep 65>>>5930930151289 -INDICATOR LAMP SERIES 330B WITH RED LENS WITHOUT BULB Rep67>>>6210930150643 Open NCR MAT to replenish |  |  | Sim
NCR-ICN-ESC-12-0137-2020 | N/A |  | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0137-2020 | P0131031 | KT03611 | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0137-2020 | P0131046 | KT03615 | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0137-2020 | P0131045 | KT03613 | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0137-2020 | P0126936 | KT03616 | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0137-2020 | P0126934 | KT03612 | REWORK | TLT 1 and 2: The depth is enough. Accept as it is. TLT 3, 5 and 6: • Manufacture a punch mark with Ø4 mm and counter mark the adaptor Rep. M40; • Remove the adaptor and drill the hole Ø4 mm; • Assembly the adaptor and check the correct position of the hole Ø4 mm. | REWORK | TLT1: the depth is enough to allow the correct greasing, accept as it is. TLT2: after checking, the depth is enough to allow the correct greasing, accept as it is. TLT3: replace the adaptor by a new one, position, mark and drill at the correct location. TLT5: replace the adaptor by a new one, position, mark and drill at the correct location. TLT6: replace the adaptor by a new one, position, mark and drill at the correct location. | REWORK | In accordance with level 2.2 proposal. Put the reference of the NCR in the traceability folder of TLT 3,5,6 | Não
NCR-ICN-ESC-12-0237-2020 | P4154682 |  | REPAIR |  | REWORK | Rework After remotion carry out a nittal attack to remove the austenitic welding. Open an NCR/RO to build up the planking. Ajust the position of the seating in accord with P4164603. |  |  | Não
NCR-ICN-ESC-12-0237-2020 | P4154667 |  | REPAIR |  | REWORK | Rework After remotion carry out a nittal attack to remove the austenitic welding. Open an NCR/RO to build up the planking. Ajust the position of the seating in accord with P4164603. |  |  | Não
NCR-ICN-ESC-12-0237-2020 | P4154689 |  | REPAIR |  | REWORK | Rework After remotion carry out a nittal attack to remove the austenitic welding. Open an NCR/RO to build up the planking. Ajust the position of the seating in accord with P4164603. |  |  | Não
NCR-ICN-ESC-12-0100-2020 | N/A | [7 empty] | Não
NCR-ICN-ESC-12-0100-2020 | N/A | [7 empty] | Não