## Sheet1
| Número NCR | Status | Tempo de Tramitação | Tempo de Tramitação Mais Recente | Descrição | Deliberação N1 | Deliberação N2 | Deliberação N3 | CHANGE | OLD
0 | NCR-ICN-UFEM-13-0080-2019 | Closed | 133 Dias | 0 dias | The seating P4148568 was welded according to the drawing, but during installation of EG2C tank, it was necessary to remove the seating because there was an interference for adjust it. | Remove the seating using annex 1. Install again using SBH and CTE´s annexed. OBS: 1.2 proposed to don´t use nittal atack if its possible. | REWORK Remove and Rework as per original | - | FALSE
1 | NCR-ICN-UFEM-13-0081-2019 | Closed | 485 Dias | 0 dias | The seating P4116043 was not welded with dimensions according to the drawing. The installation coordinates are in Annex 1. | Remove the seating according to Annesx 2. Install again using SBH.1A10.SAD.003287_E, C23 and G02 annexed. | Rework Rework as per original | - | FALSE
2 | NCR-ICN-UFEM-13-0082-2019 | Closed | 106 Dias | 0 dias | The seatings P4150817 and P4150818 were not welded with dimensions according to the drawing SBH.1A20.SAD.004676_D. See annex 1 with installation coordinates. | Remove both seatings using Annex 1 and install them again using SBH.2A20.SAD.004676_D, C23 and G02 annexed. | Rework Remose using annex 1 and re-install a new seatings in the good place | - | FALSE
3 | NCR-ICN-UFEM-13-0083-2019 | Closed | 74 Dias | 0 dias | The seatings P4156321, P4156322, P4156323 and P4156324 were welded with dimensions according to the drawing SBH.2A20.SAD.004722_D as shown in annex 1. During manufacturing of the pieces, the dimension "A" shown in annex 2 (SBH.2A20.SMD.005028_c) was not respected , being used 40mm. During fitting of the seatings, it has not been checked and now there are some interferences for install the pipes. | Remove the seating using Annex 3. Adjust them using SBH.2A20.SMD.005028_C. Install again using SBH.2A20.SAD.004722_C, C23 and G02 annexed. OBS: NG to check the possibility of not use nittal atack. | rework. Because the seating will be install in the same place, the nital attack inspection is not required. | - | FALSE
4 | NCR-ICN-ESC-13-0001-2019 | CEDOC Closure | 928 Dias | 522 dias | During the assembly and welding process of the S3 / S4 junction, it was verified that SMB-200016_H activities 555 and 595 were not performed. 53C - JUNCTION SECTIONS S3 / S4 | Junction was approved in all inspections. ICN must send the information for DA or TA prior all joining of section. Accept as it is. | Accepted as it is, Non confirmity discovered during DA inspection. Must be sent to level 3 | Follow decision 3.2 in annex | FALSE
5 | NCR-ICN-UFEM-13-0084-2019 | Closed | 92 Dias | 0 dias | During pre-machining of Pintle Solid Part (53C-SC1-APGV00546-4-US) of the Upper Rudder Blade of the SBR3, the milling machine touch the piece during a wrong movement of the tool and it has been damaged. See annex 1. | Proceed according to 1.2. Grinding the weld and perform Non Destructive Test (NDT) after welding procedure. | Rework. Carry out a grinding with a good profile, with spoon at the end. Visual inspection Build up with TIG process following o SMB-200045. Grind to redo a good shape. After 72 hrs carry out all the NDTs requered in IT21-02-10-E | - | FALSE
6 | NCR-ICN-UFEM-13-0085-2019 | Closed | 51 Dias | 0 dias | After adjustments of the AI-EL009 and AI-EL010 elements, it was verified that they got smaller 8mm at one of their ends, attached details. | Rework according to item 1.2 | Repair | - | FALSE
7 | NCR-ICN-UFEM-13-0086-2019 | CEDOC Closure | 923 Dias | 433 dias | Improvement in pipe assembly after the cradle shipped in Section 3, since clamp P4133168 is not weldable, and pipes P4133166 and P4133167 have difficulty installing the straub joint. | reworking the tubes by welding the flanges, and the clamp's modified positioning using the same type of clamp. | Decision: REPAIR NVG agrees with repair solution performed by ICN. | - | FALSE
8 | NCR-ICN-UFEM-13-0087-2019 | Closed | 67 Dias | 0 dias | During marking of the reference lines for accommodation integration, some minor dimensions were identified in the structure in relation to the dimensions in the drawings SMB-104701 (OS-LGT-EL791, OS-LGT-EL608, OS-LGT-EL682, OS-LGT-EL678 and OS-LGT-EL676) and SMB-104708 (OS-LGT-EL845, OS-LGT-EL761, OS-LGT-EL763 and OS-LGT-EL765). The difference from the real to the project is 10mm. | Rework according to item 1.2 | REPAIR Repair as per para. 1.2 | - | FALSE
9 | NCR-ICN-UFEM-13-0088-2019 | Closed | 194 Dias | 0 dias | The seating P4136441 was not welded with dimensions according to the drawing SBH.2A21.SAD.004849_D. See annex 1. | Remove the seating using Annex 1. Install again using C23, C24M, G02 and sbh.2a21.sad.004849_D annexed. | Rework as per original | - | FALSE
10 | NCR-ICN-UFEM-13-0089-2019 | Closed | 94 Dias | 0 dias | The seating P4156205 was not welded with dimensions according to the drawing SBH.2A21.SAD.004736_C. See annex 1. | Remove the seating using Annex 1. Install again using C23, G02 and SBH.2A20.SAD.004736_C annexed. | Rework as per original, using annex 1 for removing | - | FALSE
11 | NCR-ICN-UFEM-13-0090-2019 | Closed | 193 Dias | 0 dias | The seating P4146969 and P4141307 were not welded with dimensions according to the assembly drawing . See annex 1 and annex 2. | Rework according to item 1.2 | Rework as per original. Annex all the inspection requered when ICN removes a seating with austenitic welding. | - | FALSE
12 | NCR-ICN-UFEM-13-0091-2019 | Closed | 54 Dias | 0 dias | During the inspection of the alignment of the 1st section 1, it was detected that the distance between the C15 - C28 structures is at odds with the design tolerance of - 2 mm | Accept as it is. The references for the instalation of hydroplane bushes will be frame C12 and reference frame C15 for rudder bushes. | Accepted as it is | - | FALSE
13 | NCR-ICN-ESC-13-0002-2019 | CEDOC Closure | 910 Dias | 448 dias | the pipe P4171974 with the current conformation is not connecting with the TE P0125204 and the TE P0125203. | the pipe P4171974 shall be remanufactured according to isometrico with an annexed amendment. | Agree with the FTG7979. And after analyse of the GIR , there is an impact on the arrangment. So REWORK | - | FALSE
14 | NCR-ICN-UFEM-13-0092-2019 | Closed | 118 Dias | 0 dias | During inspection of the hull penetration machining AC300060, anomaly was detected in the thread of hole No. 2 and in the depth of holes No. 28 and 30 as specified in Annex 01 of CTE00597763.3. | Accept as it is. See comments in Annex 2. | Accepted as it is | - | FALSE
15 | NCR-ICN-UFEM-13-0093-2019 | Closed | 44 Dias | 0 dias | IN THE DIMENSIONAL INSPECTION TYPE D63-2 WAS DETECTED SOME DIMENTIONS OUT OF THE TOLERANCE. CTE00635729.2 | 1. Cut the new elements 53C-BA1-EL048 and 53C-BA1-EL057 in the plasma machine according to the annex (pages 3 and 4); 2. Grind the fillet welds of the elements 53C-BA1-EL048/EL046, 53C-BA1-EL057/EL051, 53C-BA1-EL057/EL388, 53C-BA1-EL057/EL387, 53C-BA1-EL048/EL388 e 53C-BA1-EL048/EL386; 3. Oxicutting the elements 53C-BA1-EL048 and 53C-BA1-EL057 on board according with the measures of the new ones; 4. Grinding the bevels according to: REP 2 (butt welds) 5. Welding according to: REP 2 (butt welds) and REP 40 (fillet welds); 6. Grinding; 7. NDT inspections (Class 2/2: BW - VT-100%, RT/UT – 30%, FW -VT-100%, MT/PT – 30% ) | Repair as per annex | - | FALSE
16 | NCR-ICN-UFEM-13-0094-2019 | Closed | 41 Dias | 0 dias | The weld passage on CI14-EL037/CI14-EL035 and CI12-EL004/CI12-EL010 was opened larger than the project requested. ICN production team suggest to replace the material taken with RAP 51. See annex. | Close the limber hole done with a round bar and do a new one with REP 51. Use C24 annexed to inspect 100% VT and 100% MT or PT . | Repair Close the limber with half round bar like described in IT21-02-10E para.11.5 | - | FALSE
17 | NCR-ICN-ESC-13-0003-2019 | Closed | 71 Dias | 0 dias | During the propeller assembly process (P0104798) along the Shaft Line, an incompatibility was detected between the SKF hydraulic nut and the shaft line. It is important to emphasize that this situation prevented the safe continuation of the assembly activities of the SBR-1 propulsion system. The contact test was performed between the threads of the hydraulic nut and the threads of the propeller shaft line, showing that only 3 of the 9 points are in contact between the two elements. | Follow to level 2 analysis. | On the shaft line SBR3, the hydraulic nut has been installed after machining and using a special tooL The shaft line can ce install on board as it is. For information , the threated part of the shaft line SBR1 has been also grunded and the hydraulic nut can be also install without any difficulties. | - | FALSE
18 | NCR-ICN-UFEM-13-0095-2019 | Closed | 100 Dias | 0 dias | The lower seatings (SU01 to SU18) were welded and the detail of the bevels was not respected. See annex 1. | Remove the weld, rework the bevel as per original and redo the inspections (100%VT and 20% MT or PT) | Rework | - | FALSE
19 | NCR-ICN-UFEM-13-0096-2019 | Closed | 28 Dias | 0 dias | During the assembly of the longitudinal Bulkhead with the EL 067 with the Coaming AC 30001 with EL069 the Metalworker were positioning the Therfane in the wrong reference and do the trace. After that were the metalworker cut the plate less them the measurement in the radius area in the bolls element’s EL 076 and EL069. The results can be seen in the attached photo nr. 1 and picture nr. 2. | ICN production team proposes to take out the elements on EL 067 and EL 069 and perform the buttering to 12 mm in the region what was cut as per the picture nr. 1 and table S-11-20 from IT 21 02 10 E – E. Only basic type E42 electrodes are used. The parameters specified by the suppliers are to be used. After finishing the weld, apply the procedure of the grinding and do the inspections. | Rework , build up like described in annex | - | FALSE
20 | NCR-ICN-UFEM-13-0097-2019 | Closed | 78 Dias | 0 dias | During check of verticality and horizontality of S2A section before machining the female soft patch, it was found that some measures are not in accordance with the design tolerance. See attachements: D36G-CTEPROV207741 D36F_CTEPROV207742 D69_CTEPROV20776244 | After analyzing the attached CTEs, proceed as per item 1.2. | Accepted as it is . The deviation of verticality will corrected during the next junction. | - | FALSE
21 | NCR-ICN-UFEM-13-0098-2019 | CEDOC Closure | 863 Dias | 474 dias | The element AB35006 has been installed in incorrect position, on the position of element AB35014. | Remove and position the parts correctly. There is no possibility of keeping the passage piece in the wrong position. | Rework Rework as pér original , following SMB-104807-E | - | FALSE
22 | NCR-ICN-UFEM-13-0099-2019 | CEDOC Closure | 859 Dias | 433 dias | The seatings P4156180, P4156297, P4146620 and P4031671 were not welded with dimensions according to the assembly drawing and measures used on board are attached. ICN production team has verified these mistakes in July. P4156180 - Annex 1; P4156297 - Annex 2; P4146620 - Annex 3; P4031671 - Annex 4. | Remove and install again all the seatings using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. | Rework as per original. to remove the support use annex 1 | - | FALSE
23 | NCR-ICN-UFEM-13-0100-2019 | CEDOC Closure | 859 Dias | 573 dias | During traceability inspection of the passage AC30050, it was checked that the passage fitted in the SBR3 belongs to the SBR4. Serial Number: 53D HB023-001 | Accept as it is. Aneex all the documents to close the NCR. | Accepted as it is Annex all the documents to close this NCR | - | FALSE
24 | NCR-ICN-UFEM-13-0101-2019 | Closed | 128 Dias | 0 dias | During dimensional inspection for pre installation, it was checked that the upper rudder fin stabilizer is with warped, 23 mm out of the measure ( 53C-AD-EL-118, 53C-AD-EL193 ) | Proceed as 1.2 described doing 100% VT, RT and PT or MT. Use C21 and G01 annexed. | Repair, Create a new joints following the IT21-02-10-E request. | - | FALSE
25 | NCR-ICN-UFEM-13-0116-2019 | Closed | 16 Dias | 0 dias | During the dimensional inspection (G01) in the 4 eyebolts of the DSRV platform, it was detected dimensions out of the tolerance. Radius designed: 21mm / Radius measured: 11mm Length designed: 450mm / Radius measured: 430mm | The lifting can be done correctly. Accept as it is. See NCR-ICN-UFEM-12-289-2018 | NCR LEVEL 1 | - | FALSE
26 | NCR-ICN-UFEM-13-0115-2019 | CEDOC Closure | 800 Dias | 643 dias | During assembly, it has been verified that some measures are in disagree with the project, as indicated in the drawing SMB-104831 in annex. | Accept as it is. Validate during strength test. | Scrap and rework a new one ( already going on ) | - | FALSE
27 | NCR-ICN-UFEM-13-0102-2019 | Closed/Unfounded | 22 Dias | 0 dias | During pre-installation of aft trim tank, contaminated oil tank and reserve lubrication oil tank, there was a lack of material in the longitudinal bulkheads of the tank (EL-119 and EL-118). See Annex 1 for the missing size for onboard tank adjustment. | Rework according annex 3. | - | - | FALSE
28 | NCR-ICN-UFEM-13-0109-2019 | CEDOC Closure | 813 Dias | 168 dias | During dimensional inspection of assembly after welding the elements (EP1, EP2, EP3, EP4) in the Battery Room aft, Section 2A SBR3. Measures outside the specifications were detected according to CTE00616201-2 and ANNEX A. In Sub-request 1, the previous positioning inspection was approved in CTE00616201-1 (in Annex), using reference documents: SMB-600317 (F19, F29) mentioned in work instruction IT-319098-22310-13-001 TASK : 10,500. According to the class B tolerance table (SMB-02288), ANNEX A of IT-319098-22310-13-001: For measurements:> 315 ≤ 1000 (± 3 mm) For measurements:> 1000 ≤ 2000 (± 4 mm) For measurements:> 2000 ≤ 4000 (± 6 mm) | As we can see in the CTE CTE00616201_2 annexed the distance that is over the limit is from the forward pillars and EG3-CL53. We suggest this distances can be ajusted with the shims used for the batteries. | Rework as per original Naval-group reminds that the acceptance criteria is the dimension with tolerance of drawing SMB . If the SMB dont give this tolerance a SMB-002288 must be apply. For this task the drawing to be followed are SMB-104624 ; SMB-600317. | - | FALSE
29 | NCR-ICN-UFEM-13-0103-2019 | CEDOC Closure | 846 Dias | 573 dias | During installation of the E4B/C tank, a manufacturing error in deck structure was verified (forward, port), this structural problem was solved by NCR-ICN-UFEM-13-064/2019. To adjust the tank, it was necessary to reduce the port height by 11mm, which caused the 2M line to be out of tolerance, impacting the passages pieces (AF35325, AF32102, AF35326, AF35125, AF35155, AF35328, AF35323, AF35319, AF35346, AF35126, AF35331, AF35159, AF35313, AF35312, AF35178, AF35324, AF35166, AF35165, AF35347, AF35169, AF35322, AF35330, AF35118, AF35124, AF35093, AF35117, AF35343, AF35388, AF35344, AF35160, AF35345, AF35350, AF35092,AF35320, AF35351, AF35161, AF35329, AF35327, AF35321 and AF35115) that were already installed. | ICN production team proposes to accept as it is. | Accepted as it is Correct the pipes if necessary | - | FALSE
30 | NCR-ICN-UFEM-13-0104-2019 | Closed/Unfounded | 55 Dias | 0 dias | During the manufacturing process of the horizontal rudder fixed fin, there was a deformation in the block after its welding in the plating, being in the longitudinal direction with an inclination of its axis 16 mm upwards. See attachments. | - | - | - | FALSE
31 | NCR-ICN-UFEM-13-0105-2019 | CEDOC Closure | 835 Dias | 522 dias | After checking in the maintenance of Scorpene class submarines that mobile parts were not painted, he found that without painting the mobile parts suffered a severe corrosion thus impairing their service life. In this case, all SBR3 mobile parts must be painted to prevent future corrosion. Industrial Markers: AC43037, AC43059, AC43062, AC43014, AC43015, AC43028, AC43033, AC43052, AC43056, AC43057, AC43064, AC43065, AC42039, AC42036, AC42016, AC44045, AC44044 and AC44049. | Remove all mobile parts of SBR3, check the list in Annex 01, discard gasket and washers, check stud bolts and replace if necessary. Send the mobile part for painting. Install new gasket and washers and re-apply the entire torque process per SMB-200960. Redo B06, B07 and paint inspections. Flow correction. This NCR is level 2. Inspections performed and attached to this NCR. | Accept as it is the moving parts in stainless steel must be painted according to SMB-002525. Anadvice illustrates this point in TAF-TA-2019-1041. No link to the maintenance document. | - | FALSE
32 | NCR-ICN-UFEM-13-0106-2019 | CEDOC Closure | 827 Dias | 432 dias | During August, the following seatings anomalies were identified: P4112297, P4112298, P4112299 and P4112300 – ANNEX 1 - Seatings were installed misplaced. ICN production team proposes to remove and install according to the drawing. P4029540 – ANNEX 2 - Seating was installed misplaced. ICN production team proposes to remove and install according to the drawing. P4163744 – ANNEX 3 - Seating was welded aft the frame. ICN production team proposes to remove and install according to the drawing. P4027719 – ANNEX 4 - Seating is already welded and does not allow the DP pipe lines between Frames 84 and 85 to be installed. It is impossible to weld the pipes on board due to the difficult access/position and with the seating welded, the pipes cannot be welded in the workshop and installed afterwards because of their size and geometry. ICN production team proposes to remove both parts of seating P4027719, weld all pipes in the workshop and after installing all pipes, reinstall the seating. P4177984, P4177985, P4161607, P4161608, P4161678, P4161679, P4161680 and P4161681 – Seatings have been welded according to the assembly drawing, but are interfering the installation of soft patch machining equipment. It was a work sequencing error.ICN production team proposes to remove the seatings (without nital attack) and install again after machining. | Remove and install again all the seatings using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. | rework as per original. | - | FALSE
33 | NCR-ICN-UFEM-13-0107-2019 | PROD 6.1 | 824 Dias | 302 dias | After check NCR-MAT-000422-2018, ICN decided check the surface of the hole of drain valve curve in TLT 5 SBR3 and found some damage, see ANNEX01. | Perform the repair according to NCR-ICN-UFEM-11-462-2016 (See annex) | 1) take dimensions on the elbow and bore of TLT ( 135g6 / 135H7 ) If it's possible, smooth the surface and remove the defect on the O-ring surface. 2) If necessary to repair by welding it's possible to use information inside NCR-ICN-UFEM-11-462/2016 | Agree with paragraph 2.2, repair by using informations from NCR-ICN-UFEM-11-462/2016. | FALSE
34 | NCR-ICN-UFEM-13-0108-2019 | CEDOC Closure | 817 Dias | 431 dias | “Durante a montagem das aletas horizontais fixas dos lemes do SBR3, o posicionamento inicial, seguindo as linhas de referência no seu ponto teórico, ficou fora de suas tolerâncias. Após novos ajustes, considerando o posicionamento correto do leme, chegamos a uma nova configuração respeitando todas as tolerâncias, mas que empregaria shims. Após a aplicação, o local com maior gap recebeu 4 mm de shims, também dentro do permitido pela documentação. Pedimos autorização da NG para prosseguir com a solda nessa configuração, utilizando shims.” “During assembly of rudder fin stabilizers of SBR3 following the reference lines in their theoretical position, the final positioning was out of tolerance. After new positioning, assuming a new configuration with the fins in their correct positioning, all tolerances were conform, but requiring the use of shims. After installing them, the worst gap received a 4 mm shim, also allowed by SMBs and ITs. We ask NG to allow welding in this configuration, using shims.” | We ask NG to allow welding in this configuration, using shims. | REPAIR NG received the QC inspection report. the measured gap was 6.5mm. in order to avoid deformations related to an over-calibration of the welding groove if this welding had been done with a shim, NG makes it possible to buld-up the elements and to adjust them before welding. Residual differences should be taken into account when making gudgeons. A position inspection report after welding of both dive fins will be required to close this NCR. An ICN action plan will have to be opened to know the origin of the defect and why it has not been discovered before. | - | FALSE
35 | NCR-ICN-UFEM-13-0113-2019 | CEDOC Closure | 805 Dias | 474 dias | Clamp P4167386 is not possible to perform interference bolting of frame P4165814. | Because of the revision of the seating P4165814 on the document (SBH.2B30.SAD.006032_B.pdf to SBH.2B30.SAD.006032_C.pdf ) (Anexo 1 and Anexo 2), there is no access to torque the screws of the clamp P4167386 as attachment ( Anexo 3 and Anexo 4). Analyzing the equipment that will go in these seatings, wich are a sink and a cabinet (P0131023 and P0142434) (Anexo 5), ICN proposes to cut the support P4165814 according to the attached document (Anexo 6). | Repair, Cut a part of P4165814 in front of P4167386 with a radius of 20mm | - | FALSE
36 | NCR-ICN-UFEM-13-0110-2019 | CEDOC Closure | 810 Dias | 596 dias | The P4156637 clamp screw is interfering with the P4156671 tube, the distance between the clamp and the tube is 8.5mm, and the screw head is 10mm. | Seating P4156662 and P4156661 should have their elevation changed by 12 mm, which will increase the spacing to 20 mm, allowing bolting of the P4156636 and P4156637 clamps. | Decision: REPAIR Repair solution proposed by ICN will be accepted. Trade and proximity rules must be checked. | - | FALSE
37 | NCR-ICN-UFEM-13-0111-2019 | CEDOC Closure | 806 Dias | 448 dias | P4168715 tube is of different coordinates than SBH.2B10.TUY.006213, which is outside the clamp coordinates and interfering with carbon steel tube P4168733. | The pipe P4168715 should be reworked according to the attached sketch, which will conform to SBH.2B10.TUY.006213 and in the clamp coordinates and without interference with the carbon steel pipe P4168733. | Repair | - | FALSE
38 | NCR-ICN-UFEM-13-0112-2019 | Closed/Unfounded | 15 Dias | 0 dias | During the machining process of the hull (53C-SC2A-TR3-BO3)for installation a slleve part AC 32072 it was detected that the machine lock was not performed correctly and therefore caused a tool to enter the hull. | 1)Cleaning by grinding the area affected; 2)Surfacing by TIG according 141/3B-3B/30/RCA3; 3)Cleaning by grinding with a good profile; 4) Wait 72h after the end of the weld for perform NDT; 5)Perform NDT VT 100%; PT 100% ( IT 21-02-10E E). | - | - | FALSE
39 | NCR-ICN-UFEM-13-0114-2019 | Closed | 75 Dias | 0 dias | During the final inspection of the male Soft Patch it was detected that there is a problem with the flat bar positioning. Theoretical dimension in relation to the reference plane : 425 mm. Measured dimension in relation to the reference plane: Fwd = 433 mm / Aft = 429 mm. | Follow to level 2 decision. | Remove the flat bar carefuly.( grinding) Carry out 100VT and 100MT Rework a new flat bar Install and weld a new flat bar using SMB-104057 Continue the fabrication process | - | FALSE
40 | NCR-ICN-UFEM-13-0117-2019 | CEDOC Closure | 799 Dias | 433 dias | The RP P0150970 was 42mm smaller for closing with between the P4114362 tube and the P0120304 valve. | Add a 42mm nipple on P0150970 between the reduction and the curve. This piece has no bends and reduction tube only. Y-piece size measures 302mm without nipple and with nipple will measure 344mm as per design. | apply the following PR: SMB-TDP-PR-5915043 SMB-TDP-PR-5915044 SMB-TDP-PR-5950000 SMB-TDP-PR-5950001 SMB-TDP-PR-5950002 SMB-TDP-PR-5950003 SMB-TDP-PR-5950004 SMB-TDP-PR-5950005 SMB-TDP-PR-5950006 SMB-TDP-PR-5953186 SMB-TDP-PR-6024981 SMB-TDP-PR-6024982 SMB-TDP-PR-6024983 | - | FALSE
41 | NCR-ICN-UFEM-13-0118-2019 | CEDOC Closure | 796 Dias | 537 dias | During September, the following seatings anomalies were identified: P4024099 and P4153253 - The seatings were misplaced and welded according to annex. P4145783 - The seating was installed in accordance with SBH.2A21.SAD.004423_E, but now the correct revision is SBH.2A21.SAD.004423_F. | Remove and install again all the seatings using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. | rework as per original. | - | FALSE
42 | NCR-ICN-UFEM-13-0119-2019 | CEDOC Closure | 791 Dias | 475 dias | Spool P4134229 according to X coordinate is in front of flange bolt 18RO110D00078 spool P4133353 preventing mounting and torque. | Decrease the length of the P4134230 tube by 15mm, which couples to the P4134229 tube. Move the P4134600 tube lobe mouth 48mm forward. | Repair | - | FALSE
43 | NCR-ICN-UFEM-13-0120-2019 | PROD 6.1 | 790 Dias | 326 dias | The P4116987 SBR3 tube does not connect to the AB35013 through piece because it has been installed with 45mm offset from its position. | P4116987 SBR3 tube should be manufactured as template. | Decision: REPAIR Spools P4116987, P4117160, P4116986 must be remanufactured and new isometrics must be presented. All inspections predicted must be performed to these spools and evidences must be provided. Spool P4117007 does not need to be remanufactured, but only moved as well as the TE P0109069. Clamp P4117001 must be repositioned as well as its seating. | - | FALSE
44 | NCR-ICN-UFEM-13-0121-2019 | CEDOC Closure | 785 Dias | 433 dias | The seatings P4122266, P4122265, P4122171, P4122169 and P4122170 wich are welded for housings of the buchings of portside and standborad interferes with the machining machine. In order to enable this machining, the seatings are provisionally made and the parts that make contact with the housings are cut and welded to the housing of the bushings. Immediately after the machining make the final assembly of the seatings, not needing to weld more in the machined housings. ICN request the creation of new welding joints and required CTEs. | We had the similar solution for the NCR-ICN-UFEM-12-207-2018 (attached) Remove these elements from the suport and weld in the rudder holes before machining. After machining, install the remaining fo the seatings. | NCR LEVEL 1 | - | FALSE
45 | NCR-ICN-UFEM-13-0122-2019 | Closed | 53 Dias | 0 dias | During grinding and adjustment to install the plane fin stabilizers, more material than necessary was removed. Se annex 1. | Do the surfacing accordint to IT-21-02-10E_E (page 66) | NCR LEVEL 1 | - | FALSE
46 | NCR-ICN-UFEM-13-0123-2019 | CEDOC Closure | 777 Dias | 658 dias | This MAT456-0026 _EXP / A component (trim) was received from NG to be applied to the upper rudder stabilizer, but during mounting on board it was found to be shorter in length (525 mm / 595 real design mm) missing 30 mm, preventing proper installation ”. For both SBR 3 and SBR 4. | Following according to 1.2 | Agree with the repair proposed. Annex the analysis of the problem with the dimensional inspection before and after repair. | - | FALSE
47 | NCR-ICN-ESC-13-0008-2020 | CEDOC Closure/Unfounded | 575 Dias | 537 dias | “GV22501D, GV22502D and GV22503D” cables (cable fitted) have a length shorter than the length required to service the installation. | Supplier delivery | See NCR-ICN-ESC-11-0705-2019 | - | FALSE
48 | NCR-ICN-UFEM-13-0124-2019 | Closed | 48 Dias | 0 dias | During the final inspections following the manufacture of the male Soft Patch, deviations were found in disagreement with the design tolerance. 1) Deflection .(See D82-43_CTE00846296) 2) Longitudinal and transverse dimension. (See D82-44_CCTE00846297 and D82-45_CTE00846298) 3) Elevation of seating connecting iron .(See D82-53_CTE00846306) | We had similar problems in the NCR's: NCR-ICN-UFEM-12-196-2018, NCR-ICN-UFEM-12-197-2018 and NCR-ICN-UFEM-12-239-2018. Accept as it is D82-53_CTE0084306 The iron beam is used to machine the soft patch. It will be removed later. D82-43_CTE00846296 This deviation will be resolved during machining D82-44_CTE00846297 and D82-35_CTE00846298 The machining of the male will be update | NCR LEVEL 1 | - | FALSE
49 | NCR-ICN-UFEM-13-0125-2019 | CEDOC Closure | 775 Dias | 433 dias | During mounting on board was detected that the diameter of the passagem piece AF31558 and the spool P4165275 are incompatable | Use the same solution as the attached NCR-ICN-UFEM-11-630-2017 that was applied to SBR1. apply to SBR3 and SBR4. | apply the same solution as the SBR1 /SBR2 , follow the FTG -7927 | - | FALSE
50 | NCR-ICN-UFEM-13-0126-2019 | CEDOC Closure | 774 Dias | 658 dias | During the adjustment and grinding of the upper rudder fin stabilizer, more material than necessary was removed. In order to solve this problem, NCR-ICN-UFEM-13-0122-2019 was opened and the surfacing was proposed to solve this problem. After made the surfacing, the QC inspection was performed and NOT CONFORM according to CTE C24-NCR-ICN-13-0122 / 2019-1 and CTE C24-NCR-ICN-13-0122 / 2019-2. | Since the surfacing has been disapproved by the QC, we propose the solution of using an insert plate for caves 16 and 17 according to Annex 1. Install a 20 mm thick insert plate, welded with rep 10 according to SMB-001386, in accordance with IT21-02-10E_E (§ 6.2.2.2.3 and § 6.5) proximity between welds for a class 2/2 (d> = 100mm). Repair inspections will be based on IT21-02-10E_E (C-10-6) for a butt weld of a class 2/2 structure. (100% VT, 100% RT / UT). | Repair, Weld 2 insert part as described in the annex. Perform 100% VT 100% RT and 100%MT. | - | FALSE
51 | NCR-ICN-UFEM-13-0127-2019 | DA 3.2 | 764 Dias | 739 dias | The EX system on the ceiling of the S4 has minimess sampling very close to the ceiling, so it impairs the collection of samples at these points. | NG will define | Level 3 | - | FALSE
52 | NCR-ICN-UFEM-13-0128-2019 | PROD 6.1 | 763 Dias | 412 dias | Clamp P4134612 not enough space for bolting, interferes with cradle beam. | Clamp P4134612 should be rotated 90º and place a reinforcement for clamp welding on seating P4031069. | SEE FTG-7926 | - | FALSE
53 | NCR-ICN-UFEM-13-0129-2019 | Closed | 328 Dias | 0 dias | During October, ICN production team identified the following seatings anomalies: P4059541 (AL00231) – It was mistakenly positioned and it is avoiding pipes installation. See annex 1. P4149822 – It was 100mm misplaced on hull. See annex 2. P4145671, P4148575, P4148576, P4148577 and P4149051 – It were welded according to the assembly drawing but must be removed to finish the welding complement of frame 43. See annex 3. P4023967 and P4023934 – It were Installed on inverted position. The reference point was interpreted on the opposite corner of the angle bar. See annex 4. | Remove and install again all the seatings using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. | Rework, Rework as per original | - | FALSE
54 | NCR-ICN-UFEM-13-0130-2019 | CEDOC Closure | 743 Dias | 685 dias | During the inspection of the upper rudder stabilizer positioning, a deviation in the structure was detected as mentioned in Annex 01 of CTE00647082. | - Grind the weld of the elements 53C-AD-EL208/BA2-EL001, 53C-AD-EL243/BA2-EL001, 53C-AD-EL190/BA2-EL001 - Do the rectification - Re-weld the elements - Do the inspections (C22 and G02) | Rework carry out rectification and reweld | - | FALSE
55 | NCR-ICN-UFEM-13-0131-2019 | CEDOC Closure | 740 Dias | 433 dias | Tube P4134723 is not connecting with equipment EJ00194. | Tube P4134723 shall be modified as per attached template for closing with equipment. | After verification of the position of the water baloon P0147321, this one is not at the good place . It's less dificult to modify the spool P4134723 than the seating of the pipe. The GIR made an analyse and not any impact in the area . So the solution is to modify the spool P4134723 : REPAIR | - | FALSE
56 | NCR-ICN-UFEM-13-0132-2019 | CEDOC Closure | 738 Dias | 433 dias | During the inspection of the upper vertical rudder deviations were found according to attached CTEs. | NCR Level 1. Accept the machining as it is. See comments in document "2.1 ICN SOLUTION". | NCR LEVEL 1 | - | FALSE
57 | NCR-ICN-UFEM-13-0133-2019 | CEDOC Closure | 733 Dias | 433 dias | During November, ICN production team identified the following seatings anomalies: P4024494 - The seating was 270mm misplaced on hull. See annex 1. P4149828 – The seating was 100mm misplaced on hull. See annex 2. P4024638 – The seating was 20mm misplaced on hull. See annex 3. P4147537 and P4147824 – The seatings were +14mm misplaced on hull. See annex 4. P4172760 - The seating was welded according to the drawing SBH.4C20.SAD.005221_C, not in accordance with SMB-TDP-PR-5707070, preventing pipe installation. See NCR-ICN-UFEM-12-218/2018 attached and annex 5. | Remove and install again all the seatings using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. | Rework, Replace All the seatings as per original, carry out 100%VT and 100% PT inspection on the welding | - | FALSE
58 | NCR-ICN-UFEM-13-0138-2019 | CEDOC Closure | 721 Dias | 271 dias | There is no shock sensor on the equipment. According to SMB-322444_E (PHST) there should be one shock sensor on UA04000. | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
59 | NCR-ICN-UFEM-13-0136-2019 | CEDOC Closure | 727 Dias | 677 dias | The seating P4122511 (which was welded according to the drawing) is making difficult the meeting between the spool P4120692 and P0107843 to close the pipe line, as shown in annex 1. In order to solve the problem, ICN production team removed the seating and installed it 15mm higther, as shown in annex 2, with the new coordinate it it possible to close the pipe line. | We propose to accept the seating 15mm higher. We believe that it doesn´t make any interference in other jobs. | Accepted as it is Annex a copy of welding inspection seating. | - | FALSE
60 | NCR-ICN-UFEM-13-0134-2019 | CEDOC Closure/Unfounded | 728 Dias | 690 dias | System HG's HG02511 and HG02512 sockets located in SBR1 compartment C-200 are with positions exchanged respectively with HG02521 and HG02510 sockets on the models, as shown in the annex. In this way, operators of the HG circuit torpedo firing network are in positions exchanged with operators of the internal service network which makes it difficult to drive the SBR. | Please change the project for all SBR. Naval Group please check it. | - | - | FALSE
61 | NCR-ICN-UFEM-13-0135-2019 | Closed | 0 Dias | 0 dias | During dimensional inspection of skin shape at the joining area of Forward Framework and Ballast Tank 4 it was detected 2 points out of the tolerance according to CTE00780388 attached (annex 1). | This NCR is similar to NCR-ICN-UFEM-11-174-2015. Since the value of the deviation in point 3 and 6 is similar to the final that was accepted in sbr1. We propose to accept as it is. | NCR LEVEL 1 | - | FALSE
62 | NCR-ICN-UFEM-13-0137-2019 | CEDOC Closure | 726 Dias | 537 dias | The equipment EG01204 (CMD: 18FL000D00300) was received in production missing elements 3 and 10 that should have been assembled on it, according to MAT865-0014 (Sheets 11 and 12). Attached are images of how the SBR3 equipment came and how it should come (SBR2 equipment photo). | For item 3, can use the CMD 9980000026218 - SEAL CUTTING 100X146X2 - 130X7X8 or the CMD 44JO230D00272 - GASKET SHEET FIBERS/NBR 1000X1000X2 to manufacture the gasket according the dimensions in MAT865-0014 FL12. For item 10, manufacture using the CMD 9980000049203 - GLASS FABRIC VERRANNE 205 G/M2 1200MM. | agree with the solution propsed by ICN if not raw material here in the ship yard order it. | - | FALSE
63 | NCR-ICN-UFEM-13-0139-2019 | Closed/Unfounded | 230 Dias | 0 dias | The AF35148 has been installed 13º aft and the design must be turned 13º ahead. | The AF35148 must be accepted as installed, because after the siphon is installed, the coordinates will be according to the project, turning 13º forwards, causing no deviation in the project. | ACCEPT AS IT IS | - | FALSE
64 | NCR-ICN-UFEM-13-0140-2020 | Closed | 700 Dias | 0 dias | During the inspection of the final machining of the Soft Patch Femea Fwd and Aft faces, it was found that the longitudinal dimension is in disagreement with the theoretical dimension calculated by the design according to D57-07_CTE00909455. Note: A prior inspection was performed before removing the machining machine and the angles were in accordance with tolerance, after removal of the machine the angle was in disagreement with the design tolerance. See annex (Inspection before removing the machining machine). | Accept as it is. | accept as it is but modify the forward opening for the machiningof he male sotf patch, See annex They will be enough thickness of the forward face of the male 44,85<e<49,51 C BOUCHER | Accept as it is in accordance with the remark indicated at the 2,2 by FO. Futhermore, NG reminds ICN that the machining of the upper edges of the female soft patch has to be done before the first presentation of the male soft patch (see phase 150 of SMB-200977 and the prerequisite of the SMB-314163_D §5,4,1 Soft Patches assembly and inspections procedure. This machining done at the right time would avoid the problem on SBR2 concerning the situation of the edges. | FALSE
65 | NCR-ICN-UFEM-13-0144-2020 | CEDOC Closure | 681 Dias | 307 dias | Foi verificado no ensaio de tração longitudinal da amostra IPS-53C-SC2-TR5-CO45-SE2/SE3 que o valor encontrado no alongamento não está de acordo com os cretérios de aceitação especificados na SMB-200031_B. Ver relatório ICN-330/18. It was verified in the longitudinal traction test of the sample IPS-53C-SC2-TR5-CO45-SE2 / SE3 that the value found in the elongation does not comply with the acceptance criteria specified in SMB-200031_B. See report ICN-330/18. | Follow to 2.2 decision. | To be send to level 3 for decision ICN must annex a complete analysis. | Accept as it is. The defect on the specimen is a fallen part. A vigilance call be made to the NUCLEP control service, which was unable to detect the indication. | FALSE
66 | NCR-ICN-UFEM-13-0141-2020 | CEDOC Closure | 692 Dias | 573 dias | ICN production team has identified that the 11TE170D00063 cable gland is not in accordance with MAT697-0034. After check, it was observed that the piece size meets the need for installation and the production team would like to have permission to use it. Attached are the drawing and photographic record for comparison. | Wait for NG orientation | The CMD provided does not correspond to the BDM-00084474 Use the CMD provide | - | FALSE
67 | NCR-ICN-UFEM-13-0142-2020 | CEDOC Closure | 687 Dias | 677 dias | During the machining inspections of the rudder BE SBR3 at the supplier some non-conformities were verified according to annex 1 CTE00959825.3 / CTE00959826.2 / CTE00959825.1 / CTE959826.3 | Accept as it is. NCR level 1. See comments in annex "2.1 ICN SOLUTION". | NCR LEVEL 1 | - | FALSE
68 | NCR-ICN-UFEM-13-0143-2020 | CEDOC Closure | 686 Dias | 658 dias | During fitting of BT22503, BT22505 and BT22612 equipment on board, it was verified that the fastening elements (CMD 32VI110D01973 - CHC SCREW M6X16 CL8-8) were less than the required lenght. | Replace the screw CMD 32VI110D01973 by 32VI120D00358. | NCR LEVEL 1 | - | FALSE
69 | NCR-ICN-UFEM-13-0145-2020 | CEDOC Closure | 677 Dias | 433 dias | During the machining inspections of the rudder BB SBR3 at the supplier some non-conformities were verified according to annex 1 CTE00959818.1 / CTE00959820.1 / CTE00959818.3 / CTE00959820.2 | Accept as it is. NCR level 1. See comments in annex "2.1 ICN SOLUTION". | NCR LEVEL 1 | - | FALSE
70 | NCR-ICN-UFEM-13-0148-2020 | CEDOC Closure | 671 Dias | 433 dias | During the machining inspections of the SBR3 lower rudder at the supplier, some non-conformities were verified according to annex 1 CTE00962799-2 / CTE00962803-1 / CTE00962800 | Accept as it is. NCR level 1. See comments in annex "2.1 ICN SOLUTION". | NCR LEVEL 1 | - | FALSE
71 | NCR-ICN-UFEM-13-0147-2020 | CEDOC Closure | 673 Dias | 474 dias | The element (53C-SC2B-OS-LGT-EL137-PLATE) was welded before ducts P4163928 and P4163928 installation. During duct adjustment, it was verified that the there are interference to bring the duct closer to its original location. The seatings P4502886, P4502887 and P4502888 were installed according to the assembly drawing, but ICN production team would like to know if it is possible to cut some elements (as shown in annex) to install the duct line, because the space has been reduced. | Cut seating P4502886, P4502887 and P4502888 as the annex and weld again after install the ducts with C24 annexed. | NCR LEVEL 1 | - | FALSE
72 | NCR-ICN-UFEM-13-0146-2020 | CEDOC Closure | 673 Dias | 446 dias | During January, ICN production team identified the following seatings anomalies: P4024386 - Annex 1 - The seating was misplaced on coaming AC30103. See attached the real dimensions found on board. P4145767 - Annex 2 and annex 3 - During adjustment of the EF00029 (30 LITRES CO2 BOTTLE), it was verified that the lower element of seating should be higher and have been welded after adjusting the equipment. In addition to this problem, the lower piece must be removed to avoid interfering with boarding the bulkhead 40. | Remove and install again all the seating P4024386 using Annex 1 to remove them and C23 and G02 annexed to inspect the new mounting. For the seating P4145767 remove the lower part and install according to the equipment, use CTE´s annexed to inspect. | Rework, Carry out all the inspection in annex. | - | FALSE
73 | NCR-ICN-UFEM-13-0149-2020 | CEDOC Closure/Unfounded | 648 Dias | 644 dias | During the assembly onboard of the element 53D-CI01-EL035 of the Compensating and Regulating tanks with the marginal plates 53D-CI14-EL001/EL005/EL009/EL013/EL017, ICN Production team has verified that was a reduction in the welding region, as shown on the annex 1. | - | - | - | FALSE
74 | NCR-ICN-UFEM-13-0150-2020 | CEDOC Closure | 646 Dias | 446 dias | According to answer 2.2 and 3.2 of NCR-ICN-UFEM-12-141/2018 given by the TA of NG, we used the DT pump of SBR3 in SBR2 and we would have to send those of SBR2 to France. | The DT pumps that we have on the warehouse to install on the SBR3 are damaged, presents oil leakage detected on the leak test conform NCR-ICN-UFEM-12-141/2018. Install the SBR4 pumps on the SBR3 respecting the serial numbers. | It’s possible to take from SBR4 but it’s necessary to respect this order: DT00101 P0107213 4320930213629-0011 DT00201 P0107214 4320930213629-0010 DT00301 P0107215 4320930213629-0012 It's very important to send defective pumps of SBR2 in France to repair these and allow their availlibility on SBR4 | - | FALSE
75 | NCR-ICN-UFEM-13-0020-2018 | CEDOC Closure | 1199 Dias | 266 dias | 1.1. Após remarcação das referências da cupola, conforme as NCR-ICN-UFEM-13-004/2017 e NCR-ICN-UFEM-13-005/2017, foi verificado o deslocamento do centro da coaming AC30052 em 11,40mm à ré e da coaming AC30051 em 16,14mm à ré da referência CO82. A | ICN propõe soldar a cupola deslocada em 3mm para vante em relação a referência do casco (atendendo ao requisito da IT21-02-10 C-6-9), fazendo com que as coamings fiquem desalinhadas 8,4mm à ré (AC30052) e 13,14mm à ré (AC30051). Para a AC30052 não há impa | NG/TA CONFIRMS THE DEFECT. NG/TA PROPOSES TO USE SBR4 CUPOLA TO FIT ON SBR3. FOR THIS ONE, REMOVE AND SCRAP ALL THE FRAMES. RE-INSTALL NEW FRAMES TO ALIGN WITH S3. | (VER DELIBERAÇÃO NO ARQUIVO DIGITAL DA NCR). | FALSE
76 | NCR-ICN-UFEM-13-0027-2018 | Closed | 500 Dias | 0 dias | There is not enough space to connect the spool P4108535 with spool P4108536. | MANUFACTURE THE SPOOLS AS ATTACHED. DECISION: APPLICATION VALIDATES FOR SBR 03. | MODIFY THE PIPES P4108535 AND P4108536 AS PER ISOMETRICS ATTACHED. | - | FALSE
77 | NCR-ICN-UFEM-13-0050-2019 | CEDOC Closure | 1044 Dias | 433 dias | During dimensional inspection of positioning and assembly of the EPM base, it was detected some measurements out of the specified in the design (see attached drawing SMB - 600307 Rev. A). The deviations found are misalignment between the base and the fra | WE PROPOSE TO ACCEPT AS IT IS. CONSIDERING TAF-TA-2017-818 AND THE CORRECT POSITION OF THE BRACKETS ME00001C-EL002, EL004, EL006, EL008, EL003, EL005 AND EL007. | After analysis ar corod NG/TA proposes to ajust the oft park of the support cefore welding (1539-1545) also carry REP 25 all around the part in touch with forue. | - | FALSE
78 | NCR-ICN-UFEM-13-0063-2019 | Closed | 312 Dias | 0 dias | The SBH.3D30.1MZ.006656_A, show the position of the connections and your numbers, but the positions of the mobile parts was marked according the axis "z" of the equipment, conform annex 1 (highlighted in red colou r). Marking other than the reference doc | Rework the marking according to SBH.3D30.IMZ.006656. Repair can be done on board. Not use punching for realise marking. Repair. | AGREE WITH PROPOSED SOLUTION. | - | FALSE
79 | NCR-ICN-UFEM-13-0076-2019 | Closed | 273 Dias | 0 dias | The elements 53C-BA2- EL-170 and 53C-BA2-EL-169, came with the holes cut in the final diameter (0500mm and 0582), making machining impossibe and not being able to install AB35039 and AB35040 coamings. | REWORK FOLLOWING THE DESCRIPTION IN THE DOCUMENT ANNEXED (SEE ANNEX 1). TO BE FORWARDER TO EXPERT LEVEL 2. | IN RELATION OF 3D INSPECTION, NG /TA, PROPOSES TO ACCEPT AS IT IS. A NEW ANALYSIS MUST BE DONE AFTER THE COMPLETE FIRST ALIGNMENT. | - | FALSE
80 | NCR-ICN-UFEM-13-0151-2020 | CQ 7.1 | 641 Dias | 408 dias | During the assembly of the grp panels on the S1 of the SBR3, there was an error on the filling and the mapping of the CTE00777169 of temporary fasteners. | - Do the mapping of the temporary fastener correctly - Fill the CTE00777169 correctly - Perform the application of "Nital" (if still have any austenitic material is allowed grinding and redo the NDT´s, perform measure if the thickness of the hull, if necessary surfacing) - Perform the inspection 100%VT and 100% MT/PT - Send this NCR to level 3 according to the Hull inspection campaign | Rework Rework following the point 1.2 comments. this defect was detected during Specialist engeneer inspection. To be forwarded to level 3. | Acceptance as is, subject to CND compliance during the removal of these temporary fasteners and the result of the NITAL attack on the presence or absence of residual austenitic during removal. Please ICN, inform paragraph 6 accordingly. | FALSE
81 | NCR-ICN-UFEM-13-0152-2020 | Comissionamento 5.1 | 639 Dias | 210 dias | During an inspection at SBR03 it was identified that the KE accumulators were not "keeping up" the pressure. See attached reports... | Please, send this NCR to the Naval Group Specialist Paul Fosse or Herve de Backer. | Apply the TAF-TA-2021-1211, and perform that under witness of TA NG. | - | FALSE
82 | NCR-ICN-UFEM-13-0154-2020 | CEDOC Closure | 635 Dias | 168 dias | During visual global audit of the Naval Group, it has been verified in the reconstitution of the AV ballast structures that was not in conformity the following items: - Methodology for ensure the traceability and removed the temporary fasteners is not according to SMB-200042; - Removed by hammer without traceability (no red marks); - Removed by grinding with damage the parent metal ➔ Severe! Surfacing repairs (HRO's); - Management of shimming area for fillet welds without shims even the welding gap in cold condition is more than 1 mm, not conform according to the Hull Technical lnstruction IT 21.02.10 E; - Tack-welding not correctly realized, cold cracking. | the AV ballast structures that was not in conformity the following items: 1 - Methodology for ensure the traceability and removed the temporary fasteners is not according to SMB-200042; 2 - Removed by hammer without traceability (no red marks); 3 - Removed by grinding with damage the parent metal ➔ Severe! Surfacing repairs (HRO's); 4 - Management of shimming area for fillet welds without shims even the welding gap in cold condition is more than 1 mm, not conform according to the Hull Technical lnstruction IT 21.02.10 E; 4 - Tack-welding not correctly realized, cold cracking. | Non conformity detected by Hull structure engeneer specialist , must be sent to level 3 | Rework by creation of HRO's by ICN. And in complementary action, an 8D of this recurring problem is requested. | FALSE
83 | NCR-ICN-UFEM-13-0153-2020 | CEDOC Closure | 636 Dias | 537 dias | During machining process of the AC30001 a calculation mistake in the X axis was detected. That was due to a misinterpretation by mechanical team of the after pre-machining optical report. According to original calculation made during the 2nd alignment registered on CTEPROV32781601, the Forward face of the coaming was supposed to be machined 5,07mm. A pre-machining was made to make sure the diameters and faces are perfectly round and flat and the optical measures taken could be more precise. Unfortunately after the pre-machining the new report was misinterpreted and the actual value removed at this point was 7,58mm on the forward face. The machining was stopped so the next steps can be thoroughly analysed. | The machining of the coaming AC30001 was stopped so the next steps can be thoroughly analysed. | Agree with ICN analysis accept as it is, and aslo with solution 1 , finish the machining since the stainless thickness wil respected send to L3 for validation | Acceptance of this machining phase, for further machining with the following requirements: - held imperative of the two dimensions 115 mm and 673.1 mm defined on the drawing SMB-104029. -It is absolutely necessary to keep a thickness of stainless steel addition greater than 5 mm. New NCR to open in case of non-compliance with one of these 2 imperatives. | FALSE
84 | NCR-ICN-UFEM-13-0155-2020 | CEDOC Closure | 634 Dias | 495 dias | The valves KT02111, KT02113, and KT02115 are with the holes in accordance with the seating P4021210, but the pipes did not match the valves. When production team checked the seating positioning, it was found that the 3 upper pices was misplaced on hull .See annex 1 with the coordinates found on board. | Repair according to 1.2 | Rework After inspection on board, it's appear that it is not possible to cut partially the valves support to correct the problem. The alignment will be out of tolerance. Naval-group/TA propose to remove all the support , use SBR3 support . Manufacture a mock up of valves to install the new support. Rework as per original | - | FALSE
85 | NCR-ICN-ESC-13-0004-2020 | PCP 6.1 PEND MATERIAL | 632 Dias | 292 dias | After the test performed on the FR12503 SBR3 panel (serial number 20160447) it was identified that the memory card is damaged. You will need to perform the exchange. | - | -Cabinet sbr3 20160447:damaged flash card need to buy a new one from AP2E. -Cabinet sbr4 20160448:functional flash card cloned from 445 because loss of internal program. -To forward in level 3 -Panel sbr3 20160447: cartão flash danificado, precisa comprar um novo da AP2E. -Panel sbr4 20160448: cartão flash funcional clonado de 445 devido à perda de programa interno. -Para avançar no nível 3 | - Send back the units 50AM906D00030 (FR12503) to the supplier in order to repair and upgrade, according to RTE 2020-04-037. - The "Outer membrane filter" (Manufacturer Ref. 056-015 in BDM-00087885_A and item 128 in BDM-00078282_A, NGD 4240145776236 "0.1 MICRON MEMBRANE FILTER") have to be replaced at a monthly frequency. Maintenance policy, maintenance tasks and supplier documentation to be updated. - Delivery of filters for SBR1-2-3-4 under following RMS : SMB-RMS-CUR-DB19/02 / NGD 4130145776229 / FAN FILTER / qty 25 SMB-RMS-CUR-DB19/02 / NGD 4240145776238 / FILTER 2 MICRONS / qty 3 SMB-RMS-CUR-DB26/01 / NGD 4240145776236 / 0.1 MICRON MEMBRANE FILTER / qty 5 SMB-RMS-PREV-DB9 / NGD 4240145776225 / MAINTENANCE KIT FILTERS 1 YEAR / qty 4 (Manufacturer Ref. 153-008 in BDM-00087885_A, including 10 outer membrane filters) | FALSE
86 | NCR-ICN-ESC-13-0005-2020 | CEDOC Closure/Unfounded | 630 Dias | 428 dias | All scape suit (MK11) EQ00234 until EQ00243 are installed in the B310 Accommodation alleyway (middle area) obstructing the passage. The supports must be modified from places. | - | - | - | FALSE
87 | NCR-ICN-UFEM-13-0156-2020 | PCP 6.1 PEND MATERIAL | 630 Dias | 488 dias | The DA02000 equipment was installed without connectors. Waiting for arrival of new connectors to service the NCR-MAT-000463-2019. | The equipment DA02000 is necessary to auxiliary cradle embarkation, because of that the equipment will be install without the connections. The connections can be install onboard after the auxiliary cradle embarkation. | Waiting for NCR-QMAT-000463-2019. Waiting for BO instruction. | - | FALSE
88 | NCR-ICN-UFEM-13-0157-2020 | CQ 7.1 | 600 Dias | 99 dias | The equipments KO02550 and KO02540 (CMD 62ER000D00181) were installed with some components pending (Joysticks / Sealing Rubber and Locks / Audio Balance Knob). See the following NCRs: NCR-ICN-ESC-11-0338-2019 NCR-ICN-ESC-11-0494-2019 NCR-ICN-ESC-11-0495-2019 NCR-ICN-ESC-11-0493-2019 NCR-ICN-ESC-11-0589-2019 NCR-ICN-ESC-11-0698-2019 NCR-ICN-UFEM-12-0524-2019 NCR-MAT-000641-2019. | Waiting for NG's answer | As propose by ICN, please 1/ treated damaged items as an accessory for the console by using the part number and the serial number of each damaged items in your database 2/ release the main equipment (MFCC) 3/ keep in stock only the damaged items Be care full in the following up of the next damaged items : - missing NCR MAT for 2 joysticks seen in NCR-ICN-ESC-11-1373-2021 - missing NCR CQ and MAT for joystick zith the serial number : 1 699 801 206 and 1 958 941 514 - LLC is under investigations NCR-ICN-ESC-11-1494-2021 - VDU is under investigations NCR-ICN-ESC-11-1290-2020 A clear overview and photo of the damaged items will be appreciated | - | FALSE
89 | NCR-ICN-ESC-13-0006-2020 | CEDOC Closure | 611 Dias | 596 dias | "According to COS-200631, ICN manufactured the GRP SHIM FOR PORTSIDE FLANK ARRAY elements for SBR3. This element requires inspections of type "PC07 - Destructive testing by ignition loss". The test was carried out at Alltec, wiith inspection CTE00803771, and it failed because it had a void higher than that defined by the standard procedure, which defines as a limit the element having a maximum of 3% void. In the piece, void of 3.73% was found" | As discussed with TA, accept as it is. | Accepted as it is. The pourcentage above the tolerance is acceptable | - | FALSE
90 | NCR-ICN-UFEM-13-0158-2020 | CEDOC Closure | 594 Dias | 573 dias | During the assembly of the of the Portside Stern Hydroplane Blade Metal Part (ID01 – SBR 3) in the PREMIX application mold in ALLTEC, excessive clearance was identified between parts as shown in the annex “REL-ID01C-PC03-C020-C030”. It has been happened due to the dimensions of the metal part are not in accordance with the design (see SMB-600536 and annex 1). | Send to TA Hugues Bourget. | Accepted as it is. The defect is not signifient and can be accepted as it is. The continuity of the shape will not be affected. ALLTEC must be carry out the work following the SMB-327593-D. specially task 030. Naval-group/TA don´t think that some shims are necessary. Let the premix flow in the mould. | - | FALSE
91 | NCR-ICN-UFEM-13-0159-2020 | PROD 6.1 | 588 Dias | 386 dias | During machining of parallel keyway of the Portside Bow Hydroplane Blade (APGV00491-2-2 – CMD 21SA000D00011) of the SBR3, the milling machine touch the cone during a wrong movement of the tool and it has been damaged. See annex 1. | Carry out smoothing in the damaged area until to achieve a good profile (without edges). Perform a NDT Visual inspection. | Smooth (scratch area) surface with some paper and accept as it is (Charles Boucher) | Smooth the defect area with sandpaper. The grease or the paint will delay the corrosion. In view of the attached photographic report, another problem is detected : the bearing is insufficient, according to SMB-341082 and inspection sheet D96-01, the minimum bearing must be 70% minimum evenly distributed over the entire of the cone. However according to the photograph this is not the case. Please create a new NCR to send to level 3 for this problem. | FALSE
92 | NCR-ICN-ESC-13-0007-2020 | CEDOC Closure | 588 Dias | 495 dias | The passage AF35092 was deleted from Project, however in ICN control for SBR2 the piece is a 100% installed (welded and inspected). ICN request NG a repair procedure to correct the deviation. | Do the same as NCR-ICN-ESC-12-0053-2020. | Repair, Close with an circular insert plate. with REP2 bevel. Weld it using SMB-200853. Carry out welding inspections requered. Take care of the cut. to respect the para C-6-23 of IT21-02-10-E the center of the repair will be different that the center of the passage. | - | FALSE
93 | NCR-ICN-UFEM-13-0160-2020 | CEDOC Closure | 578 Dias | 447 dias | During the fitting of the relative pressure transmitter (DT14330P/P0106998), it was noticed that there is a misalignment with the seating P4031048 according to the attached photos. | - cut the element 083/084 of the element 082 of the seating P4031048 - remanufacture the element 083/084 with 200 mm of length (NCR – P4031048) - weld the element 083/084 with the element 082 - carry out inspections | remove the element 83 and 84 and adjust with new dimensions, carry out of inspections | - | FALSE
94 | NCR-ICN-UFEM-13-0161-2020 | CEDOC Closure | 573 Dias | 433 dias | During the positioning of the metallic part of the Lower Vertical Rudder Blade – SBR 3 (APGV00514 -ID03) in the PREMIX lower mold (inspection C120 of SMB-327597) in ALLTEC, it was identified that the axis of the cone/keyway does not match with the center of the mold (see annex 1 - figure 3). After dimensional inspection, a position deviation was found between the center of the cone (stock side) and the center of the Blade Solid Part according to the report attached (see Annex 1 - figures 4 and 5” and Annex 2). This failure occurred because the machining operator did not follow the reference lines marked on the piece. | Send to TA Hugues Bourget. | Rework, There is too much uncertainty to continue work on the stabilizer. ICN must ensure that the axes are traced correctly, provide a full dimensional report. at the end if the part is acceptable ICN will have to make sure that the solid part is inserted in its correct position in the mold. | - | FALSE
95 | NCR-ICN-UFEM-13-0162-2020 | CEDOC Closure | 573 Dias | 474 dias | The element AB35006 has been installed in incorrect position, on the position of element AB35014. Following the response from NCR-ICN-UFEM-13-0098-2019, the piece was removed, but now the diameter of the hole that was 255 mm is 275 mm. | Follow the Annex - NCR-ICN-UFEM-13-0162-2020 - Welding the passage piece AB35014 on a backing strip (steel slat) following gap 3 (SMB-001386_F e SMB-200045_B); - The inspections should be made according to CTE (100% VT, 30% RT/UT): 53C-CTE00779609 | Rework, Agree with the proposalin para 2.1. Because of this repair is in relation with the Ballast tank, Naval-group /TA ask 100% of RT. | - | FALSE
96 | NCR-ICN-UFEM-13-0163-2020 | CEDOC Closure | 560 Dias | 433 dias | The Copper-Nickel pipe of OD73x3,40 (18LT100D00210) is out of stock, without delivery forecast and it is necessary to manufacture the product P4114228 (EM50016M1) for the embarkation of the SBR3 aft auxiliary cradle (AM00001). | - In view of the lack of material, the absence of supply forecast and the imminent embarkation of the aft auxiliary cradle (AM00001), ICN proposes that for SBR3 on the section highlighted below, we use 2 Copper-Nickel 2D Bends according to the isometric revision B (SBR3.SBH2A10.ISO.01.P4114228), even if not according to the distance between welds specified in IT33-04-13E_H for the bend with 8.8°. (2e+20mm = 26,8 mm > 17 mm) (see annex NCR-ICN-UFEM-13-0163-2020 | Due to lack of material cupro-Nickel tube Ø73x3,40 and to avoid a postpone the embarkation of the aft auxilary cradle, elbows 18LT300D00049 can be used for the manufacturing of this pipe. Nevertheless, to respect the minimum distance between two welds specially for the small radius (8,8 degrees) the angle of the other elbows can be adjusting ( by machining) in order to increase the length of the smaller elbows. | - | FALSE
97 | NCR-ICN-UFEM-13-0164-2020 | DA 3.2 | 558 Dias | 497 dias | During NG auditory mission, it was verified that the visual inspection after welding is in accordance with the qualification of the welder, traceability of welding consumables, technical documentation and dimensional inspection of flush grinding operation on butt-welded joint. However, the traceability inspection was not performed correctly, because the hull reference on technical documentation (welding file) and the structure were not correct and were still allocated to SBR3, while this structure was normally allocated to SBR4. There is no reference from NCR to address this change in allocation. 53C-SC2-SP1-RE1-B01/CA2 - Sewage Tank | This NCR is a consequence of the reply of the NCR-ICN-UFEM-12-352-2018 - Mark correctly the traceability of the product in all SBR's - Correct the traceability documentation NG Mission - Send to Level 3 (Fabien Bris) | Rework the tracability corectly To be forwarded to level 3 for infirmation | - | FALSE
98 | NCR-ICN-ESC-13-0009-2020 | DA 3.2 | 557 Dias | 513 dias | When transporting the BQ00014 (SN: 4820930181644-0008) destined to the SBR3 for installation in the SBR1, it rolled over the truck body hitting against the side protection. As directed, the valve should be blocked and sent for analysis by a specialist. | Send the equipments back to France to make a technical analysis by the NAVAL GROUP/manufacturer and check for possible repair or replacement. | The equipment will be sent back to the manufacturer for analysis and repair if it's possible or launch a new supply. OPen A Ncr mat IF REQUIRED | - | FALSE
99 | NCR-ICN-UFEM-13-0165-2020 | CEDOC Closure | 553 Dias | 433 dias | The NCR-ICN-ESC-11-0806-2020 was opened because the EV00100 equipment had a heating problem. The FTG-E626 presents a repair solution proposed to support the valve thermostatic actuator. This solution has been created based on the fixation of ES00024 and proposes a modification on seating P4031069 (item 16) as shown in annex. | Do the same procedure as NCR-ICN-ESC-11-0806-2020. | NCR LEVEL 1 | - | FALSE
100 | NCR-ICN-UFEM-13-0166-2020 | PROD 6.1 | 553 Dias | 320 dias | The NCR-ICN-ESC-11-0887-2020 was opened because all scape suit (MK11) EQ00234 until EQ00243 are installed in the B310 Accommodation alleyway (middle area) obstructing the passage, so, the supports must be modified from places. The FTG-8399 presents the new arrangement in B302, with 3 modified seatings (P4180263, P4180262 and P4180259). | Do the same procedure as NCR-ICN-ESC-11-0887-2020. | NCR LEVEL 1 | - | FALSE
101 | NCR-ICN-UFEM-13-0167-2020 | CEDOC Closure | 547 Dias | 503 dias | Foi verificado na fabricação dos: 1) GREASING PIPE Ø8X1(item 49, MAT424- 1864_C – Part List). Ref. Manufacturing Dwg : MAT424-0743_I (fl. 35/36); 2) GREASING PIPE Ø8X1(item 50, MAT424- 1864_C – Part List). Ref. Manufacturing Dwg : MAT424-0743_I (fl. 37/38), que os mesmos não estão de acordo com o projeto, ver CTEPROV33072409 anexo. As dimensões foram ajustadas a bordo. It was verified in the manufacture of: 1) GREASING PIPE Ø8X1 (item 49, MAT424- 1864_C - Part List). Ref. Manufacturing Dwg: MAT424-0743_I (page 35/36); 2) GREASING PIPE Ø8X1 (item 50, MAT424- 1864_C - Part List). Ref. Manufacturing Dwg: MAT424-0743_I (page 37/38), that they are not in accordance with the project, see attached CTEPROV33072409. The dimensions were adjusted on board. | Accept as it is. The dimensions were adjusted to fit on board. | The said pipes have been adjusted on board, so we can keep as it is (accept as it is) | - | FALSE
102 | NCR-ICN-UFEM-13-0169-2020 | CEDOC Closure | 547 Dias | 475 dias | The accumulator DT00203 with serial number AB15/0706 was taken on board for positioning and adjustment of the support. After the adjustment, the accumulator was taken for painting, in the painting workshop oil leakage was detected in item 4 (Valve U6 M50 x 1.5mm) of the attached Annex 1. It was found that item 4 and item 5 (Groove Nut M50 x 1.5mm) were loose, generating oil leakage. | When releasing items 4 and 5, the o-ring (item 22) may have moved out of position, or worse, damage to the o-ring has occurred. It is necessary to inspect the interior of the accumulator and check for possible damage inside. | It's necessary to inspect the bladder and the water tightness of mounting of coupling with O-ring. The accumulator will be send to France for carry out this task and a NCR mat will be raise to follow this. The accumulator DT00103 can be replace by one of SBR4 or by DT00105 (P011191) of SBR3 more accessible. Open a NCR MAT if needed | - | FALSE
103 | NCR-ICN-UFEM-13-0168-2020 | CEDOC Closure | 547 Dias | 495 dias | The seating P4024309 was installed on inverted position. The reference point was interpreted on the opposite corner of the angle bar. See annex 1. | Remove the seating and install againdo usingo SBH.4C20.SAD.004010_D annexed. Use C23 and G02 to inspect. | Rework as per original. After remove the support cary out all the inspection. Open a new NCR if the tickness is below the tolerance | - | FALSE
104 | NCR-ICN-UFEM-13-0170-2020 | CEDOC Closure/Unfounded | 546 Dias | 520 dias | ICN request to Naval Group for use 8040992564172 SEALANT GLUE FOR VERSATILE USE SIKAFLEX at lead ballast tank in S2A. The Project material is 9980000028742 MOMENTIVE ADHESIVE RTV 210A / RTV 229B 250 ML but it expired at ICN. | As material is 9980000028742 MOMENTIVE ADHESIVE RTV 210A / RTV 229B 250 ML is expired, use 8040992564172 SEALANT GLUE FOR VERSATILE USE SIKAFLEX | - | - | FALSE
105 | NCR-ICN-UFEM-13-0171-2020 | CEDOC Closure | 540 Dias | 274 dias | The panel OO02536 was tilted during embarkation. The two tilt sensors were triggered. No shock sensors were triggered. | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
106 | NCR-ICN-UFEM-13-0174-2020 | CEDOC Closure | 531 Dias | 250 dias | It was not found shock and tilt sensors glued on GN02551. | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
107 | NCR-ICN-UFEM-13-0172-2020 | CEDOC Closure | 531 Dias | 433 dias | During the dimensional inspection D95-32 (Check the condition and flatness of the attack periscope first stage sun gear) and D95-33 (Check the verticality and centering of the axis with respect to the attack periscope coaming) the following problems were detected: 1) The surface is not flat. (See CTE00917216 and Annex 01) 2) The face plane of the EL340 is not level. (See CTE00917216 and Annex 01) 3) The coaming bottom (EL340 of the tank) is decentralized in relation to the coaming top (AC30060). (See CTE00917217 and Annex 01) | Remove the element CI16-EL514 element (with the CI16-EL340-PLATE, CI16-ELAF31028 and CI16-ELAF31019 elements) and remanufacture a new one, respecting the distance rules between welds (50 mm). VT: 100%, RT or UT: 100% and MT or PT 100% (See aneex NCR-ICN-UFEM-13-0172-2020.pdf) | Repair Repair as per annex. | - | FALSE
108 | NCR-ICN-UFEM-13-0173-2020 | CEDOC Closure | 531 Dias | 431 dias | The spool P4167336, P4167335, P4128937, P4167337, P4140867, P4128933 and P4167338 are interfering with the “X” coordinate with the rib of the P0133575 diesel generator. | The spool P4167336, P4167335, P4128937, P4167337, P4140867, P4128933 and P4167338 have been modified in the “X” coordinate for the deviation of the rib of the P0133575 diesel generator. | REPAIR Following the FTG-8902 | - | FALSE
109 | NCR-ICN-UFEM-13-0175-2020 | CEDOC Closure | 530 Dias | 271 dias | There is no shock sensor on the equipment. According to SMB-322444_E (PHST) there should be one shock sensor on UA05000. Two tilt sensors glued on the equipment. | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
110 | NCR-ICN-UFEM-13-0176-2020 | CEDOC Closure | 529 Dias | 448 dias | The seatings below were welded incorrectly. P4024918 - It was welded on inverted position, don't reaching the piping line, but the installation dimensions are correct. See annex. P4024383 - It was welded misplaced on TLT coaming (- 30mm down). | The proposal from production team is "Remove the seating P4024918 (without perform nital attack) and reinstall a new piece as shown in annex 1 (page 4) in the same place. About P4024383, it is proposed to remove the seating and reinstall according to the drawing". We don´t see any problem follow this proposal if there is material of this new type of profile that want to be used. See CTE´s and drawning annexed by us to do the inspections. | TA is agree with ICN proposal ,carry out of inspections | - | FALSE
111 | NCR-ICN-UFEM-13-0178-2020 | CEDOC Closure | 526 Dias | 475 dias | During the inspection D62-C-05 (Inspection of drilling of the stern gland coaming flange) deviations were detected in disagreement with the tolerance.(See attached CTE00917399) | Accept as it is. Atention during assembly of the studs. At least two threads must be left to protrude from the nuts. | No impact of the instalation of the stern-gland. Accept as it is. (Charles Boucher) | - | FALSE
112 | NCR-ICN-UFEM-13-0177-2020 | PROD 6.1 | 527 Dias | 179 dias | The P4151881 and P4167339 tubes had to have their connections reversed with the interconnection tube, as they have interference and it is not possible to thread the connectors. | Changing the connectors between the P4151881 and P4128923 tubes and Changing the connectors between the P4167339 and P4128929 tubes. | See FTG-8849 | - | FALSE
113 | NCR-ICN-UFEM-13-0179-2020 | CEDOC Closure | 518 Dias | 433 dias | During the final inspection of the machining of the DP's of the vertical rudder, it was detected that the diameter Ø350H9 of DP00155 or Ø280H9 of DP00156 are at variance with the tolerance. | Accept as it is. The diameter of the seal boxes will be updated according the machining diameter of the coaming. | NCR LEVEL 1 | - | FALSE
114 | NCR-ICN-UFEM-13-0180-2020 | CEDOC Closure | 512 Dias | 428 dias | During the dimensional inspection of the holes in the base of the EPM, deviations were detected in disagreement with the tolerance of the ISO 2768_C standard. See annex D58-2_CTE00952909 and G06_CTE00952936. | Accept as it is. | For the spot facing diameter 82 mm accept as it is. For the threated hole M16 rework. ( Charles Boucher) | - | FALSE
115 | NCR-ICN-UFEM-13-0181-2020 | CEDOC Closure | 512 Dias | 475 dias | the isometric P4128907 is interfering with the structure of the floor base. | the isometric P4128907 should have its degree changed to solve the interference problem, according to the attached isometric | See FTG-8848 | - | FALSE
116 | NCR-ICN-UFEM-13-0182-2020 | CEDOC Closure/Unfounded | 508 Dias | 428 dias | The seating P4024918 was welded according to design coordinates, but the piece was inverted, not meeting the correct distance to the piping line, as shown in annex 1. | The proposal from production team is "Remove the seating P4024918 (without perform nital attack) and reinstall a new piece as shown in annex 1 in the same place. We don´t see any problem follow this proposal. See CTE´s and drawning annexed by us to do the inspections. | - | - | FALSE
117 | NCR-ICN-UFEM-13-0183-2020 | CQ 7.1 | 504 Dias | 278 dias | One tooth of the internal door (KT00352 – Serial Number - 1700013) of the WLT2 was damaged (ANNEX 1). This damage was not identified when dismantling the WLT2. | Wait for NG's decision | Smooth the scuffing on each teeth with sandpaper. After mounting on board it's necessary to let the surface clean and grease. | - | FALSE
118 | NCR-ICN-UFEM-13-0184-2020 | CEDOC Closure | 498 Dias | 448 dias | During inspection D59-03 (CTE00954298), a deviation that was not in accordance with the tolerance was detected , as shown in the annex. Produto: 53C-SC2-BR2 (male soft patch) | Accept as it is. Send to NG Design Authority to validate. | According all the report given (in annex) for the adjustments. All the inspections are in the criteria except one corner gap. Accept as ii is. Send to level 3 | The two deviations concern 2 clearances measured at 1,2 mm and 1,45 mm for a maximum value of 1 mm. Both located in the upper and lower part of the corner Aft-Port. The other criteria, altitude, blue matching and thickness are obtained. A rework to obtain the right clearance could result in a loss of the other criteria. Decision to accept as it is. | FALSE
119 | NCR-ICN-UFEM-13-0185-2020 | CEDOC Closure | 496 Dias | 426 dias | The P4134328 tube, according to its conformation, it is not possible to install a cradle shipped on board without having space to remove the exchangers. | NCR-ICN-UFEM-12-306 / 2018 SBR2 reference. cut the tube and add ruch connections and make a fixation in place, adding a seating and clamp (OD36). Screw to the clamp. SCREW, H M8 25x25 CL 8.8 32VI110D00787 NUT, H M8 CL 8 32VI310D00058 NORLOCK M8 32VI410D00074 and fittings for the pipe CUAL RBS24 ° STRAIGH UNION OD36 1 ea 18RO230D00087 CUAL RBS24 ° UNION NUT OD36 1 ea 18RO230D00101 CUAL RBS24 ° CRIMPING RING OD36 1 ea 18RO230D00108 CUAL RBS24 ° UNION NUT OD36 1 ea 18RO230D00101 CUAL RBS24 ° CRIMPING RING OD36 1 ea 18RO230D00108 | Follow FTG-8847 | - | FALSE
120 | NCR-ICN-UFEM-13-0186-2020 | CEDOC Closure | 489 Dias | 326 dias | The tube P4124839 was manufactured on 02/07/2020 and because of the conformation it will not be possible to install the tube, since the cradle shipped on board section 3 and to several interfaces that cannot be disassembled. | disconnect everything and add connections for the junction. Necessary connections. 18RO230D00566 18RO230D00577 44JO312D00002 18RO230D00587 | See FTG-8850 | - | FALSE
121 | NCR-ICN-UFEM-13-0187-2020 | CEDOC Closure | 489 Dias | 428 dias | The product P0120028 (CMD 18LF100D00003 tracked), has an expiration date and it is provided with different configuration/directions, being determined by the product/positioning. The parts reserved for SBR3 have the same direction, however for the product P0120028 we need the opposite direction. To meet the need for SBR3, we need one of the SBR4 equipment to be released in the desired direction. Note: It was necessary to pay 1 unit of SBR3 to remedy a loss problem occurred in SBR1. There is 1 unit of this material (referring to SBR1) in the warehouse that is out of date, being treated in NCR-MAT-000921-2020. | Use the one of the SBR4 with the desired direction on the SBR3 | NCR LEVEL 1 | - | FALSE
122 | NCR-ICN-UFEM-13-0188-2020 | CEDOC Closure | 483 Dias | 428 dias | After execution of NCR-ICN-ESC-11-1012-2020 and NCR-ICN-ESC-12-0098-2020 and discussion with TA Charles Boucher (see e-mail attached), the lubrication groove (center diameter) of all bushes of DP system (stern steering gear and bow hydroplane) must be machined to avoid any problem of lubrication after final assembly. See reports attached for SBR 2 and SBR 3. | Machining 0,5 mm (radius) or as less as possible to achieve values bigger than the theoretical gap (7,5 mm): • The coaming first in priority; • The bush after if for the coaming it’s too late, but take care because on this diameter there is the traceability; • Record the traceability and after machining, stamp back. | Agree with the proposed solution, the thickness of the grooves should be respected between the bush and the sleeve. Machining the bush if necessary. ( Charles Boucher) | - | FALSE
123 | NCR-ICN-UFEM-13-0189-2020 | CEDOC Closure | 482 Dias | 448 dias | The seating P4149823 was welded in disagreement with the coordinates of the drawing, as shown in annex 1, interfering with the piping line. The problem occurred because the view does not show the angular degree of seating installation and the optical reference was not respected. | Remove the seating and install again. The problem of the angle can be solved using the SBH for manufacturing the seating. Use the drawnings and CTE´s annexed to install the seating again. | carry out of inspection. | - | FALSE
124 | NCR-ICN-UFEM-13-0190-2020 | CEDOC Closure | 482 Dias | 428 dias | the P4169114 tube has a 30mm nipple that, together with the reduction part od25 / 27 (18RO000D00533), is different from the isometric coordinates. | the P4169114 tube must have the 30mm nipple removed and the reduction part od25 / 27 (18RO000D00533) must be directly welded to the P4168726 tube so that the coordinate is according to the project. | Agree with the ICN decision | - | FALSE
125 | NCR-ICN-UFEM-13-0192-2020 | DA 3.2 | 480 Dias | 413 dias | As occurred in NCR-ICN-ESC-12-0122-2020, the fiber optic connector provided on the equipment’s OO02530, OO02531, OO02532, OO02533, OO02534, OO02500, BD02527, BD02528 is not compatible for cables CMD 11LS215D00012 that are provided on project. | Wait for NG orientation | The connectors supplied with the materials are not compatible with 11LS215D00012 fibers. The crimping ring does not allow the installation of the kevlar braid for mechanical holding. Locally supplied connectors allow this. See annex Awaiting decision BO 1-accept as is 2-rework after receiving the correct connectors | - | FALSE
126 | NCR-ICN-UFEM-13-0191-2020 | CEDOC Closure | 481 Dias | 327 dias | due to the scheduling date for the production of the PR-6631070 modification, the location is without access, since the auxiliary cradle is installed on board the SBR-3 and it is not possible to remove or move it for access. | PR-6631070 modifies P4121068 and cancels P0154914 (TE), the coordinates have not been modified, as it is not possible to remove P0154914 and modify P4121068 due to lack of access, make a long plug of the same material for the pipe sealing. it will only be used for the SBR-3. | -Keep the initial configuration without applying the PR-6631070. -Assembly of the valve SART P0122107 valve with the probe. -Do not manufacture a plug and not install a plug. -REWORK | - | FALSE
127 | NCR-ICN-UFEM-13-0193-2020 | CEDOC Closure | 470 Dias | 418 dias | Anodes 1Z, 2Z and 4Z have CP1 inspection for painting with epoxy paint on the face of the anode in contact with the hull according to SMB-002081. However, the anodes received by ICN have already been painted from the manufacturer, and it is not possible to carry out the inspection by ICN. | This products received painted. Its not possible to inspect. Attached are receipt documents received by ICN without painting certificates and other documents, see NCR-MAT-00585-2019. | Accepted as it is accepted as it is. the inspection sheets can be filled in with a comment '' N.A. inspections already done by the supplier '' he acceptance inspections of this equipment must state that the anodes have been delivered painted. | - | FALSE
128 | NCR-ICN-UFEM-13-0194-2020 | CEDOC Closure | 468 Dias | 168 dias | The thickness of lock washer (MAT424-1881_Ref: 57 / MAT424-0690_FL13) is 1,5mm and impossible to bend, it’s necessary to replace by thickness 1mm. IM: AG00016. | Accept the modification as it is. The new lock washer was mounted and bended correctly. | The thickness of lock washer (MAT424-1881_Ref: 57 / MAT424-0690_FL13) is 1,5mm. With this tickness it's impossible to bend correctly without damage of others parts. The remplacement by thickness 1mm was decided with same material (X6CrNiTi18-10) and gave satisfaction. A modification of definition file will be done. | In agreement for evolution from 1.5 mm to 1 mm The definition file will be updated. Put a copy of the material report by indicating manually the reference of the part mark Rep 57 and place this copy in the traceability file of the traceability number panel AP425461 | FALSE
129 | NCR-ICN-UFEM-13-0195-2020 | CEDOC Closure | 467 Dias | 448 dias | During the inspection D36K-2 (Inspection of the end frame clerances) deviations were detected in disagreement with the design tolerance. (See attached CTE00915065) | Level the sections and adjust the Gap to weld. If the gap is out of tolerance open a new NCR to treat. Accept as it is. | Accepted as it is The deviation will be resolved by grinding during the junction | - | FALSE
130 | NCR-ICN-UFEM-13-0196-2020 | CEDOC Closure | 464 Dias | 418 dias | After reworking the provision of the solution proposed in item 2.2 of NCR-ICN-UFEM-13-0172-2020, deviation was detected in disagreement with the project in inspections G01_NCR-ICN-UFEM-13-0172-2020-1 and D95-33_NCR -ICN-UFEM-13-0172-2020. | Accept as it is. The deviation of 10 mm on the Z axis will be compensated with the chockfast. | Accepted as it is The structure ICN team must analyse and annex this analyse to the NCR and inform Mechanical team. | - | FALSE
131 | NCR-ICN-UFEM-13-0197-2020 | CEDOC Closure | 463 Dias | 428 dias | The seating P4024010 was welded with correct dimensions on board, but it was on inverted position. The longest part of angle bar was welded on coaming and the shorter for piping line (which has an interference). | Rework and install the seating in the right position using CTE´s annexed. PS: Production asked to not perform nittal attack. | Rework, Agree with para. 1.2, carry out inspections as per original | - | FALSE
132 | NCR-ICN-UFEM-13-0198-2020 | CEDOC Closure | 462 Dias | 448 dias | During the inspection D36B-1 (Joint cold clearance) before the junction of sections S4 / S3 + S2B, deviation was detected in disagreement with the project. See D36B-1_CTE00915060 | Accept as it is. We had similar problem on NCR-ICN-UFEM-12-032-2016. Perform the joint hot clearence inspection (D36C - JOINT CONDITION HOT INSPECTION (CTC00915056)) and annex the CTE's on this NCR. | NCR LEVEL 1 | - | FALSE
133 | NCR-ICN-UFEM-13-0199-2020 | Tratamento 6.1 (FS) | 461 Dias | 284 dias | During execution of NCR-ICN-ESC-11-0711-2019 (shaft line alignment), some items of system MB from SBR 3 were used in SBR 1. ICN request to use the parts from SBR 4 to be applied in SBR 3 (see remarks in Annex 1). IM: MB00001 MB00003 MB00005 MB00007 MB00312 | Replace all parts missing of SBR 3 by SBR 4 according delivery batchs showed in annex 1. Open a NCR-MAT to supply new items for SBR 4. | I agree with the proposal. ICN should open a NCR MAT to replace the material for SBR04. In parallel Naval Group suggest to buy double or triple itens for spare. ( Charles Boucher). | - | FALSE
134 | NCR-ICN-UFEM-13-0200-2020 | CEDOC Closure | 454 Dias | 324 dias | Tube P4134714 is interfering with tube P4125690. | P4134714 - P4134718 tubes should be changed according to the attached template to remove the interference from the P4125690 tube, being necessary to carry out the LP and TH tests, as well as filling the CTE. | -Agree with the ICN proposal : N1 -Repair for the SBR 3 | - | FALSE
135 | NCR-ICN-UFEM-13-0201-2020 | CEDOC Closure | 449 Dias | 271 dias | It was not found tilt sensors glued on RH02531. | The equipment has a good physical and visual condition , must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
136 | NCR-ICN-UFEM-13-0202-2020 | CEDOC Closure/Unfounded | 448 Dias | 428 dias | The P4172750 tube (OD 76.1 x 2.9) cannot be installed because the electrical cables, equipment and tubes that are in the same region that are below this tube have already been installed. | The P4172750 tube (OD 76.1 x 2.9) cannot be installed because the electrical cables, equipment and tubes that are in the same region that are below this tube have already been installed. CMD 18RO200D00018 | - | - | FALSE
137 | NCR-ICN-UFEM-13-0212-2020 | CEDOC Closure | 420 Dias | 250 dias | During the inspection of the Rudder hole drilling of DP00155, DP00156, DP00255 and DP00256, deviations were detected in disagreement with the design tolerance. See attachments: D63-11_CTE00895167 / 1 (DP00155) D63-11_CTE00895167 / 2 (DP00156) D63-11_CTE00895167 / 3 (DP00256) D63-11_CTE00895167 / 4 (DP00255) | The dimensions of the hole and threaded depth is bigger than theoretical and this it will not affect in the mounting of the bushes.. It can be accept as it is. The condition of the threads permit a good mounting. | If the condition of the threads permit a good mounting, accept as it is. ( Charles Boucher) | Accept as it is. The inspection must be able to decide on a good mounting. | FALSE
138 | NCR-ICN-UFEM-13-0213-2020 | CEDOC Closure | 420 Dias | 398 dias | During the inspection of the M24 threaded holes on the aft face of the Bracket tube machining MB00005C, a problem was detected in the thread of hole No. 2. See attached D62-D-03_CTE00687337-5. | Accept as it is. The aft immersed bush was already installed and the screws was tightened in accordance with the torque requested. | NCR LEVEL 1 | - | FALSE
139 | NCR-ICN-UFEM-13-0214-2020 | PROD 6.1 | 420 Dias | 173 dias | During the dimensional inspections of the machining of the penetration of the transmission axis of the steering and diving rudders, deviations were detected in disagreement with the design tolerance. See Attachments: D51-3_CTE00898245-1 D51-3_CTE00898245-2 D51-3_CTE00898245-3 G06_CTEPROV34514519 G06_CTEPROV34514521 G06_CTEPROV34514525 | Accept as it is. See comments in "2.1 ICN SOLUTION". | The solution in annex is ok for me. Send to level 3 to inform of the situation. | AC31009 (CTE00898245-3) - MAT214-1714_C => Accept as it is of non-conforming dimensions + continue machining the shoulder on the limiter side 5-> 15mm AC31008 (CTE00898245-1) - MAT214-1716_C Ra NC =>Rework - Soften by surfacing with sandpaper non-compliant rating. 2674 ± 1 / C15 => Accept as it is - Deviation compensated by compensating shimming AB35039 (CTE00898245-2) - MAT214-1712_C Ra NC => Rework - Soften by surfacing with sandpaper and particular attention to the level of the joint surfaces AB35039 (CTEPROV34514521) / AC31008 (CTEPROV34514519) / AB35040 (CTEPROV34514525) => Accept as it is - Internal threads ok and drilling carried out during the assembly phase. | FALSE
140 | NCR-ICN-UFEM-13-0203-2020 | Closed | 442 Dias | 0 dias | During circularity monitoring measurements of section 2A frame 32 (53C-SC2-TR3-CO32), it was detected that it is out of tolerance for the current design phase (¦F¦≤2.〖10〗^(-3).R (2nd phase)). | Follow 1.2 | Rework Before junction, put a kill block bellow the section in the aft part of section 2A to support the weigth. Put an horizontal e-beam between the electric platerform supports and push it. Chek the circularity and verticallity. If the measurment are in the tolerance the junction can be start. For the Electric plateform , follow the TA mechanical advise annexed . | - | FALSE
141 | NCR-ICN-UFEM-13-0204-2020 | CEDOC Closure | 441 Dias | 149 dias | During MS02 inspection on EQ00057S (P4164269) the lack of lock washer ND 8 was checked. | REWORK ACCORDING TO DE-000000-80500-13-022_A AND MATERIAL LIST | NCR LEVEL 1 | - | FALSE
142 | NCR-ICN-UFEM-13-0205-2020 | CEDOC Closure | 440 Dias | 428 dias | During the inspection of the machining of the AFT Bracket Tube, deviation was detected in disagreement with the design tolerance, with also lack of information regarding the tolerance specified in CTE, IT and MTSI200F03546_D. | Accept as it is. The aft immersed bush will be machined accordingly respecting the tolerances 0/+0,04 mm. See BDM-00075285_C. | NCR LEVEL 1 | - | FALSE
143 | NCR-ICN-UFEM-13-0206-2020 | CEDOC Closure | 436 Dias | 420 dias | During the dimensional inspection D06 (Joining frame space and adjacent frame space deflection inspection) and D36F (Verticality of sub-sections ends or junction ends) deviation was detected in disagreement with the design tolerance. (See D06-CTE00915082 and D36F-CTE00915083) | Accept as it is | Accepted as it is the inspection D36-F will be corrected with the next junction the inspection D37 (D 06) is inside the tolerance , Mj -Mj/100 + 5mm)<Mjmeasured j <Mj/100) | - | FALSE
144 | NCR-ICN-UFEM-13-0207-2020 | CEDOC Closure | 433 Dias | 414 dias | The seatings P4112297, P4112298, P4112299 and P4112300 were not welded according to design, as described in NCR-ICN-UFEM-13-0106-2019. See appendix G02 for the failed supports and their actual dimensions found on board. | We propose to accept as it is. The pipes are already installed. | After Naval-group analysis and inspection ( TA piping and TA structure) it will be decided to accept as it is | - | FALSE
145 | NCR-ICN-UFEM-13-0208-2020 | PROD 6.1 | 429 Dias | 386 dias | During MS01 inspection on BK02500S the resilient mount compression was checked out of tolerance in disagreement with SMB-200965_E. See attached CTE00976182 sheet 3. | Rework according to the tolerances specified in SMB-200965. See CTE00976182 annex. | NCR LEVEL 1 | - | FALSE
146 | NCR-ICN-UFEM-13-0219-2020 | CEDOC Closure | 405 Dias | 250 dias | During the inspection of the machining of the solid blocks of the forward rudder (Port and starboard) , deviations were detected in disagreement with the project. NOTE: Inspections of the caliber CAL-107 and inspections that use the caliber were not carried out because the caliber is located in the company subcontracted by ICN to machine the cones. See attachments: G06_CTE00933385-1, G06_CTE00933385-2, G06_CTE00933385-5, G06_CTE00933385-6, D52- 20_CTE00933383-1, D52-20_CTE00933383-2, D52-21_CTEPROV34399403 and D52-21_CTEPROV34399404 | Accept the machining as it is. See comments in document attached "2.1 ICN SOLUTION". | The control tools (caliber) normally used to control the cone are sent to ICN by the supplier The inspection was perform after by ICN, All the inspection sheet have been complete if no deviation during these inspection Accept as it is. Charles Boucher | - | FALSE
147 | NCR-ICN-UFEM-13-0218-2020 | CEDOC Closure | 410 Dias | 250 dias | During the inspection of the positioning of the Trust Block, it was detected that the distance from the face ahead of the Trust Block to the first hole Ø50mm in diameter from the EPM base, is different from that specified in the project. See D85-2_CTEPROV31970547 / 1 | Accept as it is. The distance between FWD Face of Thrust Block and the first hole Ø50mm of EPM seating is out of tolerance because the holes Ø50mm of EPM seating were machined following the position of the holes on the EPM body. According the drawing SMB-345242, the reference of AFT face of EPM is 3360 ± 1mm + 302,5 ±0,5mm. | Agree with N1. The position of the holes are adjust according the reality of the engine. | - | FALSE
148 | NCR-ICN-UFEM-13-0210-2020 | CEDOC Closure | 427 Dias | 271 dias | In this equipment, only 1 tilt sensor and 1 shock sensor (15G) were found glued to the BK02501. According to SMB-322414_E (PHT), there should be two shock sensors (10G and 15G) and two tilt sensors glued to the equipment. Acceptance criteria for inspection A06: SMB-204559_C. | The equipment has a good physical and visual condition, must follow the next activities and inspections. But its operation hould be checked during the STW. | NCR LEVEL 1 | - | FALSE
149 | NCR-ICN-UFEM-13-0209-2020 | CEDOC Closure | 427 Dias | 271 dias | In this equipment, only 1 shock sensor (15G) and 2 tilt sensors were found glued to the BK02500. According to SMB-322414_E (PHT), there should be two shock sensors (10G and 15G) and two tilt sensors glued to the equipment. Acceptance criteria for inspection A06: SMB-204559_C. | The equipment has a good physical and visual condition, must follow the next activities and inspections. But its operation hould be checked during the STW. | NCR LEVEL 1 | - | FALSE
150 | NCR-ICN-UFEM-13-0211-2020 | PROD 6.1 | 424 Dias | 383 dias | The seating P4018991 was not welded with dimensions according to the assembly drawing. See annex 1 that show the real dimension of the seating for harnesses in access trunk. | Remove the seating using annex 2. Install again using the drawning and CTE´s annexed. | Rework, Rework as per original. Use annex 2 for removing. after inspection open an NCR/RO If necessary | - | FALSE
151 | NCR-ICN-UFEM-13-0215-2020 | CEDOC Closure | 420 Dias | 407 dias | The passage piece AB35007 (18RO000D00039) was installed in the inverted position, with aft face facing forward. See G03 attached. | We had similar problem on NCR-ICN-UFEM-13-0162-2020 Reword according to Annex 1 Re-do the G03 and C22 CTE (100% VT and 30% MT/PT) | NCR LEVEL 1 | - | FALSE
152 | NCR-ICN-UFEM-13-0216-2020 | CEDOC Closure | 417 Dias | 412 dias | Due to the differences in the conformation of tube P4120784 regarding the isometric, it was necessary to as-built it in the best coordinates, as attached. | The pipe curve P4120784 of 90.5º is 88.5º, it does not conform to IT-33-04-13 H the tolerance in the degree of curvature and +/- 1º, repair the curve, install on board and check if the coordinate that connects with the hose is according to the project, as we may have problems with the correct installation of the hose. | The difference in the curve of the spool P4120784 has no impact on the enviromnent and then, can be accepted as it is. Only the position of the seating has to be adjusted (as shown sheet 9/9 of annex 1) to the routing of the pipe. This modification is to be applied on SBR3 only. | - | FALSE
153 | NCR-ICN-UFEM-13-0217-2020 | CEDOC Closure | 412 Dias | 271 dias | In this equipment, only 2 shock sensors (10G and 15G) were found glued to the EJ00001. There were no tilt sensors (two) glued to the equipment, according to SMB-322409_C (PHST). Acceptance criteria for inspection A06: SMB-204559_C. | The equipment has a good physical and visual condition. Must follow the next activities and inspections. But its operations should be checked during the STW. | NCR LEVEL 1 | - | FALSE
154 | NCR-ICN-ESC-13-0010-2020 | CEDOC Closure | 410 Dias | 162 dias | The mobile part AF35350 (MAT169-0199) is not compatible with drilling the DA12510N tank level (BDM-00036934). | Proceed according document FTG-8992. | REPAIR Repair as per FTG Carry out a depth drilling inspection . | - | FALSE
155 | NCR-ICN-ESC-13-0011-2020 | Tratamento 6.1 (FS) | 404 Dias | 278 dias | The movement of the base "SUPPORT FOR WATERPROOF PRESSURE RESISTANT BEARING REPEATER" (GN02560) is very heavy and can cause damage due to the weight in the "WATERPROOF PRESSURE RESISTANT BEARING REPEATER" (GN02545). ICN request some mechanical modification in GN02560. | Send to level 2. | The mechanical modification of GN02560 will be done regarding the OM 118496, as soon as the modification kit will be received. | - | FALSE
156 | NCR-ICN-ESC-13-0012-2020 | PCP 6.1 PEND MATERIAL | 398 Dias | 253 dias | MN03-260 wedges, purchased in Brazil by the nationalization contract, are showing breakage after the application of 923Nm torque. We believe there is a manufacturing error in the shoes. | Replace all elastic mount by new ones with a different lot. Send to NG analysis. | After analyse the back office the damage of the rubber was due to didn't use of special tool to immobilize buffer ring during the tightening. see the document in annex (extract of SMB-200949). | - | FALSE
157 | NCR-ICN-UFEM-13-0220-2020 | DA 3.2 | 404 Dias | 272 dias | “During the resistance test of the shaft line tube S04 - CTE00929608 - 53C-SC1-CR-BA12-TLA-MT, pressure was monitored by the manometer and visual inspection on the element according to the attached CTE, but the measuring of deformation have not been carried out due to the tube surface being cylindrical and besides that the CTE don’t have a drawing attached with the reference point to be measure. Navy requested the opening of NCR, in view of the impossibility of gauging the measures and deformation assessment under the acceptance criterion provided for in SMB-051242_D in inspection S04 for element 53C-SC1-CR-BA12-TLA-MT so that it can be reassessed the procedure for carrying out the stress test for this structure (see attached email).” | follow for analysis of level 2. | Send to level 3 in order to analyze the possibility of changement asked by the navy. See email in annex. | - | FALSE
158 | NCR-ICN-UFEM-13-0221-2020 | CEDOC Closure/Unfounded | 398 Dias | 398 dias | The upper DSRV (53D-SC2-PF-SUP-1) platform underwent rectification activities after all non-destructive tests were performed. According to IT-21-10E - C- 9-9: "Non-destructive tests of welded joints on rectified structures must be conducted or repeated after the last rectification operation (if the initial volume check includes an X-ray inspection and an ultrasonic inspection, only the ultrasonic inspection is repeated). "It is necessary to repeat tests after last rectification on 53D-SC2-PT1-PF-SUP-1. See attached photos. | NCR asked by MB. Perform missed NDT inspections. | - | - | FALSE
159 | NCR-ICN-UFEM-13-0222-2020 | CEDOC Closure | 397 Dias | 323 dias | Due a problem in the power generator during machining of the Male Soft Patch Exhaust Sleeve AC32025, the tool of milling machine touch the piece and it made a defect in the INCONEL coating surface | Accept as it is. There is not sealing contact in the damaged surface due a gap between flanges. See drawing in annex 3. Send to level 2 analyze the remaining INCONEL coating. | Accepted as it is | Acceptable defect with respect to hull integrity. | FALSE
160 | NCR-ICN-ESC-13-0013-2020 | Closed | 26 Dias | 0 dias | During the inspection of junction sections S2A/S2B was detected that some measures are out of tolerance according to CTE00862867_D36A_2, CTE00862873_D69 and CTE00862851D36K_2 attached. | Proceed with the junction. After adjust the gap for junction, open a new ncr if necessary. | Accept as it is Regarding D36A-2 and D69, the verticality deviation is 3mm--> accepted as it is . Regarding the D36K-2 end frame clearance inspection, the lnght to be found is : TR8A 154-2,5= 151,5 the average difference is +5,5 TR8B 426-12-2,5= 411,5 the average difference is -5,5mm Naval-group/TA proposal is accept as it is. | - | FALSE
161 | NCR-ICN-UFEM-13-0223-2020 | CEDOC Closure | 384 Dias | 271 dias | According to SMB-322405_D (PHST) two shock sensors (10G and 15G) should be glued to the DJ00043. There were no shock sensors glued to the equipment. Acceptance criteria for inspection A06: SMB-204559_C. | The equipment has good physical and visual condition, must follow the next activities and inspections, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
162 | NCR-ICN-UFEM-13-0224-2020 | ICN 1.1/1.2 | 378 Dias | 197 dias | The Bolted Hatch of Ballast Tank nº 2 - AE00002 (portside) initially intended to be used on SBR 4 was incorrectly installed in starboard in place of AE00003. Products: AE00002 (P4062580 – CMD 01PE200D00043) – Port Side AE00003 (P4064132 – CMD 01PE200D00044) – Starboard | Accept as it is There are two hatchs. For the portside (AE00002) and for the Starboard (AE00003) and this two hatchs are differently. On the SBR3, for mistake, the Production team installed on both sides (portside and starboard) the hatch AE00002 (MAT451-0044), this hatch is smaller. So, only for the SBR3, we suggest to accept with the both sides wiht only the hatch AE00002. For SBR4 we opened two new NCR's. | - | - | FALSE
163 | NCR-ICN-ESC-13-0014-2021 | PCP 6.1 PEND MATERIAL | 330 Dias | 196 dias | The DN10103P manometer has a broken capillary. It is necessary to replace it with another similar manometer. | It is necessary to replace it with another similar manometer. | Replace the complete manometer DN10103P (50MD200D00041) onboard of the SBR3 by a new one from the stock. Create a NCR MAT to buy a new flexible capillary (5m), repair and recalibrate the manometer (F5694 PVP110025-0 A 60M) to refund the stock. | - | FALSE
164 | NCR-ICN-UFEM-13-0225-2021 | PROD 6.1 | 329 Dias | 301 dias | To correct a flatness problem on the DSRV upper platform, the structure was placed at a height that allows post-weld machining, according to NCR-ICN-UFEM-12-0292-2018, however this solution was not enough and there was the need to open the NCR-ICN-ESC-12-0210-2020 to use the SBR3 DSRV in the SBR2. In addition, NCR-ICN-ESC-12-0187-2020 and NCR-ICN-ESC-12-0240-2020 were also opened to butter the elements shown in annex 1 and annex 2. Thus, the production team requests analysis from the Naval Group to use SBR2 DSRV in SBR3 and remake the related templates. | - change the upper plate - leave the upper plate with 30mm until the weld with the bottom part - do the machining onboard | NCR-ICN-UFEM-0292-2018 was opened to relate a non-conformity of flatness of the upper platform. We can see from the report that the thickness was already very close to 25mm (final thickness) before welding on the bottom. So to try to solve this problem of the upper platform, we tried to place the platform at a sufficient height and thus to be able to machine after welding, the NCR-ICN-ESC-0187-2020 and NCR-ICN-ESC-0240-2020 were opened to build up the cylinder and the steffeners. The attempt was not enough and another NCR was opened. The answer on NCR-ICN-ESC-0210-2020 propose to use the SBR3 platform. Change all the tracability in accord with the SM Change the upper plate of the plate forme Oxycut each part carefully grinf in respect of the thickness Carry out 100VT, 100%MT Carry out flatness inspection. Build up when is necessary ( to do this build-up open anNCR/RO for each part after rectification , carry out 100VT, 100% mt, and 100% UT. install a new plate, follow the original process and inspections in accord. Take care of alignnment axis | - | FALSE
165 | NCR-ICN-ESC-13-0016-2021 | CEDOC Closure | 322 Dias | 168 dias | Traceability problems after EJ00007 (CMD12PC000D00017) pump embarkation: 1) This pump is without one identification plate, see photo attached (Annex 1); 2) This equipment was traced by serial number of the electric motor and corresponds to the CMD12GH000D00005 IM EJ00003, hydrophore group (electric pump+balloon),see photo attached (Annex 2). | Remove on-board equipment CMD-12GH000D00005 and replace with CMD-12PC000D00017 equipment that starts with serial number 087/13-xx. | NCR LEVEL 1 | - | FALSE
166 | NCR-ICN-ESC-13-0015-2021 | ICN 1.1/1.2 | 327 Dias | 71 dias | In fresh water tanks, the decoupled ring is larger than the clamp used for tubes smaller than OD48,3. | according to SMB-323201 the tubes of the fresh water tank must for diameters smaller than OD48,3 use an uncoupled ring. apply according to SMB. | - | - | FALSE
167 | NCR-ICN-ESC-13-0017-2021 | CEDOC Closure | 322 Dias | 271 dias | In this equipment, only one shock sensor (10G) was found glued to the EJ00003. According to SMB-322408_F (PHST), there should be two shock sensors (10G and 15G) and two tilt sensors glued to the equipment. Acceptance criteria for inspection A06: SMB-204559_C. | The equipment has good physical and visual condition, must follow the next activities and inspection, but its operation should be checked during the STW. | NCR LEVEL 1 | - | FALSE
168 | NCR-ICN-ESC-13-0018-2021 | PROD 6.1 | 305 Dias | 268 dias | During the dimensional inspection after welding the elements RE16, RE17, RE18 and RE19, deviation was detected in disagreement with the tolerance of the drawing SMB-200121_D. (See Annex 01 and Annex 02) | Accept as it is To fix the error on the installation of the vertical stiffeners , adjust the stoppers and the separating strips and plates (according to SMB-332707_B), since the main measures of TAF-TA-2018-0870 are being respected. Please see annex NCR-ICN-ESC-13-0018-2021.pdf. | Analysis, The annex 2 shows that some measure of tanks are out of tolerance and the verticality of the bulkheads also. Naval-group reminds that these defects should be discover during the mounting. However no NCR were open. Annex 1 shows some defects of the stiffeners position , the average defects is 7mm in reference of C89 ( SMB-600112) and in transversal the average defetcs is 2mm. The verticality is respected. REWORK Naval-group/TA proposes to rectify the planeity of stiffeners , ( by heating process or pneumatic hammer) and propose to apply o TAF-TA-2018-0870 to correct another deviation. | - | FALSE
169 | NCR-ICN-ESC-13-0019-2021 | TA 2.2 Specialist | 301 Dias | 67 dias | During the inspection of the positioning of stowage racks of the 53C-KE01000 53C-P0128188 - CMD 19AM000D00140 - HANDLING AND STOWRAGE SYSTEM, module with respect to the TLT axes, deviation was detected in disagreement with the tolerance in the measurement of the gaps between the axes of in TLTs 3, 5 and 6 with stowage racks. (See Annex 1, 2 and 3) | After mounting and aligning the 53C-KE01000 53C-P0128188 - CMD 19AM000D00140 - HANDLING AND STOWRAGE SYSTEM module, the alignment was checked. According to dimensional: For weapons guide slides TLT 1, 2, 3, and 4, the position of the racks, accept as it is. For weapons guide slides TLT 5 and 6, the rack must be adjusted. | - | - | FALSE
170 | NCR-ICN-ESC-13-0020-2021 | CQ 7.1 | 286 Dias | 90 dias | According NCR-ICN-ESC-12-0188-2020, the item 2 (obturator) of Propeller Shat (MB00004) from SBR 3 was used in SBR 2. ICN request to use the piece from SBR 4 to be applied in SBR 3. | Take the piece of SBR 4 and install in propeller shaft of SBR 3. The NCR-MAT-001404-2021 was opened to supply or manufacture a new part. | Agree with level 1. ICN need to follow the answer level 3 of NCR-ICN-ESC-12-0188-220 to asssembly this obturator. The NCR-MAT-001405-2021 is already open in order to supply or manufactur the missing material. This NCR need to be forward in level 3 to inform NG BO for the tracability. | Agreement for using obturator from SBR4 on SBR3. Also perform the following operations (already mentioned in NCR-ICN-ESC-12-0188-2020 which covered the use of the obturator from SBR3 on SBR2): 1. Carry out a visual inspect of the bores for any signs of corrosion. If necessary, remove them by belt finishing the surfaces. 2. Renew the anti-corrosion protection by spraying a long-lasting protective coating (type Ardrox 3140 or equivalent) on the inside of these shafts. 3. Temporarily close the SBR4 shaft (while waiting for a new part to be produced) and regularly renew the anti-corrosion protection mentioned in the previous point if the tightness of the device is not guaranteed. | FALSE
171 | NCR-ICN-ESC-13-0021-2021 | PROD 6.1 | 274 Dias | 257 dias | Duct P4159901 with the wrong manufacture. Openings and the grade of the duct were made on the opposite side. | Remanufacture according to project. | Remanufacture according to the project. | - | FALSE
172 | NCR-ICN-ESC-13-0022-2021 | CQ 7.1 | 268 Dias | 257 dias | In the C100 compartment of the SBR3, it is necessary to apply RTV210 (01RA300D00022) according to SMB-323114. The RTV is expired, with its petrified catalyst, which prevents the material from curing. ICN requests the replacement of this material by LOCTITE 5970 ALCOXY SILICONE ADHESIVE CARTRIDGE (01RA300D00004). | Please TA analisys to replacement of this material by LOCTITE 5970 ALCOXY SILICONE ADHESIVE CARTRIDGE (01RA300D00004). | REPAIR In this case only, apply a ADEKIT5970 01RA300D00004 | - | FALSE
173 | NCR-ICN-ESC-13-0023-2021 | CEDOC Closure | 267 Dias | 214 dias | During the inspection of flatness and alignment after welding the upper structure of the sail, deviations were detected that were not in accordance with the design tolerance. | Wait for NG orientation. | The flatness inspection must be done during fabrication process ICN no detected the defect at this time !!!!! ICN must annex the inspection fabrication file. Accepted as it is . if any interference appear during mat integration oepn a new NCR | - | FALSE
174 | NCR-ICN-ESC-13-0024-2021 | CEDOC Closure/Unfounded | 267 Dias | 246 dias | The absence of acrylic AQ00908 and AQ00909 (BB and BE) was observed after the return of Submarino Riachuelo from exit 10. Check with a Naval Group, for a solution to prevent the loss of acrylics. Open a NCR MAT to have a new supply. | Wait for Naval Group decision. | - | - | FALSE
175 | NCR-ICN-ESC-13-0025-2021 | ICN 1.1/1.2 | 263 Dias | 218 dias | During the inspection of the forward positioning of the Seatings of the batteries, deviations were detected in some dimensions in disagreement with the tolerance specified in the drawing SBH.PLM.4C10.000996_C. See annex 01 | It was requested to Accept As It is for the seating BB02507C. | - | - | FALSE
176 | NCR-ICN-ESC-13-0026-2021 | PROD 6.1 | 261 Dias | 226 dias | During the dimensional inspection of the rudder axis marking made by the optical department, deviation in the position of the AC34027 sleeve was detected, as shown in Appendix 3 attached to CTE00917348. The alignment of the plates was performed using as reference the actual position of the AC34027 sleeve and the plates in accordance with the procedure SMB-200955_B. -See attached D45-1_CTE00917348 | Accept as it is. Use the axis (x, y) of sleeve AC34027. The reference for positioning of Bow Hydroplane Gear and Rudder Holes (DP00355 and DP00356) will be the center of sleeve AC34027. | Agree with decision N1 Use the center of sleeve AC34027 like reference. | - | FALSE
177 | NCR-ICN-ESC-13-0027-2021 | TA 2.2 GIR | 258 Dias | 2 dias | The BX00001 equipment was damaged on board. | The 53C-BX00001 equipment was damaged on board during construction process. The screw fixation is fragile and easy to break, not shock resistant. ICN suggests adapting the seat. Make a new seat to adapt the mounting of the equipment so that it is more impact resistant. See annex 1. | - | - | FALSE
178 | NCR-ICN-ESC-13-0056-2021 | PCP 6.1 | 194 Dias | 70 dias | The spools P4108415, P4108416 and P4108414 identified in AFT HORIZONTAL PORTSIDE (D111), STARBOARD (D112), LOWER (D120) AND UPPER (D200) VERTICAL HELMS, has E5 painting scheme, however it is located in the outer area of the hull, application of the A1 scheme | Apply painting on pipe as per SMB-002345. Painting details/range is mentioned in isometric drawing and SMB-360002. If isometric drawing are not coherent, follow details which are mentioned in SMB-360002. | REWORK Apply the correct sheme as per SMB-002345 | - | FALSE
179 | NCR-ICN-ESC-13-0028-2021 | PCP 6.1 PEND MATERIAL | 256 Dias | 231 dias | In the solid ballast board and closing tank solid ballast in section 2A (A130, A150, A220 and A230), for activity to preparation of the surface of the plating for application of the adhesive in lead ballast box, it is necessary to apply LOCTITE 5366 (01RA300D00012) according to SMB-324572. This material is not available in the warehouse. ICN requests the replacement of this material with the LOCTITE 5970 ALCOXY SILICONE ADHESIVE CARTRIDGE (01RA300D00004). | Please TA-NG analyze the possibility of Loctite 5970 ALCOXY SILICONE ADHESIVE CARTRIDGE to be used for this purpose, according description in datasheet (attached) in compliance with the tests performed in RCQ-UFEM-0242-2021. | repair Apply a loctite 5970. Open an NCR /MAT with the quantity used to receive a new supply | - | FALSE
180 | NCR-ICN-ESC-13-0029-2021 | PROD 6.1 | 256 Dias | 208 dias | As attached, it was asked which material of FA00123 requires the material to be STAINLESS according to MAT823-0021_EXP_A and SMB-335202_C but ICN received a mixture of material (STAINLESS and galvanized), see attachment. Please clarify which material to use for each SBR. | Please clarify which material to use for each SBR. | The equipment FA00123 must be manufactured in Stainless steel as specified in document MAT823-0021_EXP_A and SMB-335202_C . Qty 5 siphons has already been supplied by Naval-Group, some in stainless steel and some in steel. ICN is requested to fit on SBR1 to SBR4 the said siphons CMD 27MP000D0008 / FA00123 manufactured in Stainless steel and raised a NCR-MAT regarding the quantity of wrong supplied. | - | FALSE
181 | NCR-ICN-ESC-13-0074-2021 | PCP 6.1 | 112 Dias | 43 dias | The sealing face of the COAMING AC30010 is damaged. | Repair. The same defect was found e treated in NCR-ICN-ESC-12-0225-2020. Follow the steps below: 1) Map the defect; 2) Clean by grinding and take the depth and map the defect; 3) Carry out 100% VT and 100% DP; 4) Stop point to analyse with TA; 5) After analysis open the defect with a good profile (see WPS); 6) Carry out 100%VT; 7) Build up using WPS 141/9-9/RPA2; 8) Carry out 100%Vt and 100%DP; 9) Rework the manual machining using a tool (marble). See tool example in annex of NCR-ICN-ESC-12-0225-2020. | Repair as per description , Annex the inspections before the stop point wtih TA naval-group. | - | FALSE
182 | NCR-ICN-ESC-13-0030-2021 | TA 2.2 Specialist | 246 Dias | 71 dias | For the equipment described in "list of products impacted" attached, we found on board the lack of a functional identification plate and (or) voltage and electrical risk label. | Rework | - | - | FALSE
183 | NCR-ICN-ESC-13-0032-2021 | Closed | 246 Dias | 0 dias | Due to problems in the verticality of the S1 / S2A joint, and also to attend the ceremony, ICN needed to weld the S2A / S2B joint before the S1 / S2A joint, changing the construction logic sequence. (SMB-327699, SMB-327700, SMB-327701, SMB-327702, SMB-327703, SMB-327704, SMB-327705) | NCR opened due TA hull specialist Fabien BRIS request. Accept as it is. | The deviation of SMB-327699 can be Accepted as it is ICN must take care about the conical junction . | - | FALSE
184 | NCR-ICN-ESC-13-0033-2021 | CEDOC Closure | 245 Dias | 194 dias | Pump DA00004 was assembled without A02 inspection on the seating. | I agree with item 1.2. Disassemble the DA00004 pump to perform the A02 inspection test on the seats. After inspection A02, assemble the DA00004 pump with new steel washers, according to the procedure. See note 2.2 of the Doc. DEI-000000-80500-13-007. | REWORK Rework as per original process | - | FALSE
185 | NCR-ICN-ESC-13-0031-2021 | CEDOC Closure/Unfounded | 246 Dias | 245 dias | During the hydrostatic test, the equipment leaked during the test between 0-5 bar rising and 0-8 bar lowering the pressure. | Regarding the shaft line stern gland (MB00003, CMD 15PE000D00001) delivered for SBR3 (AP419848) and assembled in SBR2. During the hydrostatic resistance test (70 bar) and the water tightness test (52,5 bar) a leakage was detected between 0 – 5 bar. To reach the test, It was necessary to open and close the cam holder (MAT422-0109, position 30), when the pressure overtaken 5 bar, the pressure remains constant without any leakage, the pressure was increased step by step until the maximum pressures requested in each test. Decreasing pressure, around 8 bar the leakage appear again, the leakage was quantified around one liter per hour. This phenomenal does not happen in the SBR1 tests. | - | - | FALSE
186 | NCR-ICN-ESC-13-0034-2021 | Closed | 244 Dias | 0 dias | During inspection D36B_1 - Joint Cold Clearance, a root opening of 6.5 mm from position 588T to 595T was detected with a total of 70mm. WPS: 111 / 3B-3B / 30 / A32 Tolerance from 4 to 6mm CLASS 1/1 – 80 HLES – Thickness 30 mm See CTE00862808_D36B_1 attached. | For NG analysis. | Accepted as it is Accepted as it, is and wait the hot clearance inspection. If the gap not reduce open an NCR/RO to build up during the junction. | - | FALSE
187 | NCR-ICN-ESC-13-0035-2021 | PROD 6.1 | 243 Dias | 236 dias | Interference in mounting the P4019890 rail in the battery room FWD After the rail was assembled, it was verified that it was not lined up the structure detached in blue in the annex. Comparing the Y of the rail and the structure in 3D, the two are lined up, and detached in red in the summary, is the nominal Y and the real one | Do as mentioned in 1.2. Use CTE´s annexed. | Rework ajust the inside starboard rail with the maximum tolerance to aign with the structure | - | FALSE
188 | NCR-ICN-ESC-13-0036-2021 | PROD 6.1 | 239 Dias | 99 dias | It was not possible to mount the antenna of the RADAR mast, the antenna did not fit into the mounting housing. Checked the internal diameter and the housing is smaller than the antenna axis. RM00003 | During the assembly of the RADAR mast (53C-RM00003 - P0118608 – CMx 09EP000D00014 NAVIGATION RADAR MAST ASSEMBLY) on the SBR2 submarine, the mast antenna 53C-RD02504 - P0123648 CMx 62AB000D00049 RADAR ANTENNA MAST RESET DEVICE did not fit, checking the internal measurements it was identified that the internal diameter does not conform to the design drawing. The mast of the SBR4 was requested for possible assembly, before assembly the measurements were checked, then it was identified that the internal diameter is not in accordance with the design drawing. For this situation, it is suggested that the internal diameters are machined on the mast of SBR3 and SBR4. Machining the mast 53D-RM00003 internal diameter 162.00 mm, mounting area RADAR POD antenna. See annex 1. | The beam of the RADAR mast must be machined in accordance with the attached drawing: -The internal diameter: 162mm 0/+1 -The depth: 487mm 0/+0,5 A dimensional report should be appended to the NCR. A coat of gray anti-corrosion paint should be applied after machining in the diameter 162mm only, following the process of document SMB-002345. | - | FALSE
189 | NCR-ICN-ESC-13-0042-2021 | Tratamento 6.1 (FS) | 232 Dias | 173 dias | Face of the sealing area is damaged, according to the attachment. | -Open a cavity to remove the defetc and to have a good shape with ''spoon'' on each side ( as per WPS). -Carry out 100% VT and 100% DP. - if the depth is less than 2mm,Build up using WPS 141/9-6/5RP.A1. - if the depth is more than 2mm, stop point. -The welder must be qualified as per SMB-030502-B para.15.4 -Carry out 100%VT and 100% DP. -smooth grinding with sand paper and JIG ( anel) to ajust the good shape. -Carry out flatness inspection on the coaming face | REWORK Build up as described in para.2.1 | - | FALSE
190 | NCR-ICN-ESC-13-0037-2021 | Tratamento 6.1 (FS) | 238 Dias | 230 dias | Flexible shims paid for DA02000 equipment did not support the torque predicted in the CTEPROV31972120 (383 N.m), deforming after the torque. | It is necessary to replace the flexible shims with new ones (14SE200D00008 - FLEXIBLE BUSHING TYPE MN03-125) DA02000 equipment. To apply the torque provided for in the CTE (383 N.m) it is necessary to use the washer locking key during torque so that the washer does not turn with the screw, according to procedure SMB-200949 (See FL 29/115). See annex 1. | Agree with level 1. Open one NCR-MAT in order to supply new flexible shims. | - | FALSE
191 | NCR-ICN-ESC-13-0041-2021 | DELIN 5.1 | 236 Dias | 8 dias | FH duct P4176940 with a problem when opening the flap of the FH00017. A modification was made to the P4176940 duct, as shown in the annex, to completely open the flap FH00017. Duct assembled according to the project. | NG, please analyze the solution given by ICN. | Agree with the modification carried out on the duct P4176940. This modification has to be taken into account on the drawing of manufacture and installation. | Modification has been taken into account on drawings of manufacture and installation. See SMB-TDP-PR-6820371 and See SMB-TDP-PR-6820372 loaded in TDP/IS. | FALSE
192 | NCR-ICN-ESC-13-0038-2021 | PROD 6.1 | 238 Dias | 233 dias | It is not possible to check the equipment identification plate, because this plate is located behind the seating and it is impossible to view the DA00002 traceability information. | Remove and Rework According to the description, the equipment data plate must be fixed in a visible place. | NCR LEVEL 1 | - | FALSE
193 | NCR-ICN-ESC-13-0040-2021 | CEDOC Closure | 237 Dias | 162 dias | Correction of the verticality of the front bulkhead of the AFT battery room is necessary. | Follow 1.2 proposal. | REPAIR Due to the wrong mounting of tank EG3 , the forward bulkhead of battery compartment is not vertical. Consequently the seating are also in wrong position . Correct the defect with shim . 10 mm mm for the small one and 15 mm for the big one. | - | FALSE
194 | NCR-ICN-ESC-13-0039-2021 | PCP 6.1 | 237 Dias | 211 dias | According to COR-2021-901189 (see attached), due to manufacturing problems, the flanges of spools P4167471/P4167473 need to be discarded. | Disassemble the spools, remove and discard the wrong flanges, install the new ones and update M01 inspection. Open an NCR MAT. No tests were performed for this line, so there will be no regression. | In accordance with the COR-2021-901189: The flange with NGD 4730145171318 CMD 18RO110D00077 must to be replace with the CMX 18RO110F00411. On the SBR 3 there are 4 flanges identified with the wrong CMD on the system FQ . The pipes concerned are P4167471 and P4167473 ( annex) Make the change of flanges on templating. Realize all the necessary tests for M01 and send the pipe to the galvanization | - | FALSE
195 | NCR-ICN-ESC-13-0084-2021 | Especialista ICN | 95 Dias | 82 dias | Connectors applied only to the connection part, therefore we are unable to carry out the connection activity of the mentioned equipment. | Provide new complete connectors. | - | - | FALSE
196 | NCR-ICN-ESC-13-0043-2021 | Comissionamento 6.1 | 224 Dias | 78 dias | Regarding Sonar System, bigram UA. The TAF-TA-2021-1218 requested 2 PSU MICROFEC boards from Sonar Cabinet 1 and 2 from SBR3 to be send back to France for retrofit. As requested, here follow the equipment description: FM: UA04000 / UA05000 (Sonar Cabinet) SN: 00049 / 00042 (board Serial Number) PN: 62125891AB (board Part Number) Description: PSU MICROFEC C2 (Rack IAAR) | Remove the boards to retrofit in France. | Please provide the boards as ask in the TAF-TA-2021-1218 and create a NCR MAT to follow the delivery in France and the delivery of the updated board in Brazil reminder : the 2 PSU MICROFEC boards from Sonar Cabinet 1 and 2 from SBR3 wil be send back to France for retrofit. Boards description : FM: UA04000 / UA05000 (Sonar Cabinet) SN: 00049 / 00042 (board Serial Number) PN: 62125891AB (board Part Number) Description: PSU MICROFEC C2 (Rack IAAR) | - | FALSE
197 | NCR-ICN-ESC-13-0044-2021 | PCP 6.1 PEND MATERIAL | 222 Dias | 133 dias | A problem has been identified in the serial coupling of the BC02500 panel, as reported in SBR1's NCR-ICN-ESC-11-1297-2021. The auxiliary power supply U2 for the RXDC Dm1, Dm2 and Dt1 circuit breakers is not correctly wired: - according to Schneider's plans, it must be connected to a 500V bus, during inspection of the panel cabling, it was verified that it is connected to a 1000V bus. This problem extends to the BC02500 panel of the SBR1, SBR2, SBR3 and SBR4. | A new cable must be supplied, and installed on the BC02500 panel according to the Scheneider plans. Make adequacy. | As for SBR1, the cabling and connection done by the manufacturer Schneider is wrong, for the supply U2 of DM1, DM2, DT1, leading to a burning of the card if serial coupling is activated. At this time, the cards are OK. Schneider will come to correct the problem of connection. This NCR is being sent to level 3(Back Office specialist) It is mandatory that ICN blocks the serial coupling, in order to prevent another burning of card, until the manufacturer has corrected the problem. | Prohibit the serial coupling of the BC02500 cabinet. The manufacturer (Schneider) will come to correct the wiring of the BC02500. | FALSE
198 | NCR-ICN-ESC-13-0045-2021 | TA 7.2 | 218 Dias | 26 dias | "The Preservation team, in agreement with the Quality team, opted to open this NCR (processed by the NCR-CQ system) to replace the NCR-ICN-Preserv-035 (which was being processed physically). Please see the original NCR attached." On March 28, 2019, TAF-TA-2019-0974 was issued requiring a change in the EPMs Preservation routine. Through this document, the Preservation team was instructed to perform the borescope inspection task on EPM bearings in the MT2 phase (equipment installed on board), thus replacing the previously defined shaft rotation activities. This change was consolidated in a new version of PHST (SMB-32221-G), which defines a periodicity of 3 months. Facts in EPM - 03: •On May 28, 2019, August 30, 2019 and December 04, 2019, the rotation activities of the MEP-3 and MEP-4 Axis were performed. • On October 18, 2019 a borescope inspection of the MEP-03 was performed, where we found signs of oxidation in the axis according to report RAP-ME-2019-11. | Our suggestion, is to create a flushing system outside of the motors according to the reference document DCNS - BRESIL - NSY - DNA - 8460 Revision-A, putting the lubrication oil on constant movement, thus keeping the engine always lubricated. | Refer to proposed solution by expert Level 1; To be forwarded to level 3 for analysis. (Yann Jaouen) | -Schedule a Jeumont intervention - under the warranty - to bring MEP 2-3-4 back into compliance. - Need FO support to prepare the intervention procedure on board MEP 2 (Dismantling of the environment for accessibility to the landing on the NDE side). - Update documentary 6EM21228: The documentation must indicate to add preservation grease during reassembly, to give details on the rinsing of the casings and to integrate the descriptive sheet of preservation grease "Shell Ensis engine 30" (End Sept 2020). - ICN need to propose an adequate solution for storage of MEP under optimized conditions (Oct 2020). - A awareness of ICN according to the update of documentation will be done (Dec 2020). (LEPESANT M.) | FALSE
199 | NCR-ICN-ESC-13-0046-2021 | CQ 7.1 | 218 Dias | 46 dias | "The Preservation team, in agreement with the Quality team, opted to open this NCR (processed by the NCR-CQ system) to replace the NCR-ICN-Preserv-038/2020 (which was being processed physically). Please see the original NCR attached." On each side of the EPM there are two heating resistors of 750W each, connected in parallel (1500W in total) and connected at 115V, therefore, the current must be around 13A. During the month of January, 2020, the Preservation team observed in the EPM of the SBR-3(starboard side) that the current measurements presented approximately half of the value, 6.5A. (see the attached report) After some tests, we found that one of the resistors is open, burned. | The Preservation team requests a spare heating resistor in order to proceed the replacement. Preservation team will use the instructions presented in activity D7 of document 6EM21228 Ver: J. (SBR-ETM-000MEM0001_B) If Naval Group has any further information, instructions, comments, please let us know. | After analyse, the resistor E3 is defective. Send for level 3 for decision. See attached file. (Thomas Le Corre) | Resistance Replenishment (NGD: 5905930206162). Recommendation to carry out this intervention during a phase of work already planned (MEP deflating for example: see FA 249756). When reassembling the connection terminais, apply the VonRoll resin recommended by ICN for the replacement of the M13 alternator heating resistor on SBR1. Then carry out lhe following checks on lhe replaced element to ensure lhe efficiency of lhe repair: - Resistance measurement (before switching on) expected value = approx. 17 ohms - Insulation test according to the procedure described in § 4.2.10.2 of document 6EM21228 (before powering up) expected value > 10 Mohms - Voltage measurement (after switching on) expected value = approx. 115 Vac - Current measurement (after switching on) expected value = approx. 6.5 A - Finally, check that the engine temperature is + 5 °C compared to the outside temperalure. cf PHST SMB-322221_G . (EUSTACHE J.) | FALSE
200 | NCR-ICN-ESC-13-0047-2021 | PROD 6.1 | 217 Dias | 98 dias | According to endoscopy inspection reports attached, it was identified dust particles inside valves DW01110-P0132772, DW01120-P0132886, DW01210-P0132777 and DW01220-P0132885. | Cleaning the valves using an appropriate tool as a cotton swab ensuring no internals damages with this process. | It's necessary: -cleaning for removing dust inside (make sure of not let of fibers during cleaning) -mounting of all ruch fittings with o-ring and carry out pressure test of the fitting (M09) -A protection on each orifice should be added. | In accordance with proposal of cleaning. Nevertheless the reference of these NCR has to be mentioned in the traceability folder of each equipment. Davide BERNEDE - ISSP | FALSE
201 | NCR-ICN-ESC-13-0048-2021 | CEDOC Closure/Unfounded | 217 Dias | 184 dias | While perfoming the Preventive maintenance activity "Inspect the Stowage" (SBR-MRC-000KFM0000-T005) of KF00043, the Preservation Team detected that the grease nipple in the stowage cover is missing. Please see the attached photo. | Please send a new grease nipple. | - | - | FALSE
202 | NCR-ICN-ESC-13-0049-2021 | CEDOC Closure | 210 Dias | 160 dias | The distance between 2M line and the floor is out of tolerance, as shown in scheme attached (annex 1) The floor height was measured by Laser tracker and it was found deviation, at a maximum of - 7 mm, which means the floor has some points within 7 mm higher ( - 7 mm) than it should be. The tolerance of this measure is +3 / 0 | Follow 1.2 proposition. | REPAIR, trace a new reference line 5mm above. thise new reference will be used to fill the resin and will garantee the good alignment between all the degree. the rest of the defect will be corrected during the resin filling. After welding a new inspection must be done. ICN must inform the mechanical and electric team. | - | FALSE
203 | NCR-ICN-ESC-13-0050-2021 | DA 3.2 | 209 Dias | 34 dias | It was identified a HALAR coating damage in the valve BM00010-P01359 that was dismounted in trial to be sent to SBR2 which also had the same problem in it same valve as seen in NCR-ICN-ESC-12-0487-2021. And how can see in the attachment, the damage didn't occur due the dismounting process cause the damage is old, even is rusted. This matter is related to hull integrity in AC32009. | 1. It's needed remounting a new one valve BM00010-P0135969 on SBR3, it's important remember that if the new hidraulic actuator be installed the CMD will evolve from 18SC011D00166 to 18SC011D00255, paying-attention with the coating protection during the transportation and mounting process. Take care in new F06 that have to be done in imminence of mounting. 2. The valve BM00010-P0135969 of SBR3 that was dismounted 18SC011D00166 /SN:019/SMB3-MU18B-DB8/DOC-2018-905672/Contract-Nº:40000-2009-005-00 should be sent to repair through a NCR-MAT. 3. Open NCR-REGRESS to register the inspections and tests which was carried out. | Agree with proposal | - | FALSE
204 | NCR-ICN-ESC-13-0051-2021 | CEDOC Closure/Unfounded | 203 Dias | 149 dias | Change in seating welding configuration P4181964 e P4171824. It’s not possible to weld and to install the preheating devices of the seating P4181964 e P4171824. (See annex 1). | Agree with 1.2. Weld using austenitic. | - | - | FALSE
205 | NCR-ICN-ESC-13-0052-2021 | PCP 6.1 | 196 Dias | 133 dias | There is an incoherence between the pipe P4127221 connection with hose P0107649, due to the fact that the male connection is smaller than the hose female. For SBR1 this subject was solved by NCR-ICN-ESC-11-0512-2019, according to FTG-7187 made by GIR NG team. | ICN waits NVG orientation. | HP20001 has to be replaced with a new CMD 18FH101D00997. Please refer to OM-121751-B. Hose has been delivered through batch SMB-RAW-DB508 | - | FALSE
206 | NCR-ICN-ESC-13-0053-2021 | PCP 6.1 | 195 Dias | 111 dias | Modify spool EZ51023 (P4178063 and P4177025) according to FTG-5193 which has interference with the EW0001 tank. See NCR-ICN-ESC-12-0054-2020 the same interference was found in SBR3. | ICN waits NVG orientation. | Apply the FTG - 5193 for the modification pipes EZ | - | FALSE
207 | NCR-ICN-ESC-13-0054-2021 | CQ 7.1 | 195 Dias | 34 dias | The equipment (EF00012) was installed on board and found lost by the construction process, not found on board. | Perform the installation of new EF00012 equipment on board to attend the construction process of the SBR3. Open NCR MAT. | REWORK Open a NCR MAT if necessary | - | FALSE
208 | NCR-ICN-ESC-13-0055-2021 | CEDOC Closure/Unfounded | 195 Dias | 184 dias | Regarding SONAR subsystem (bigram UA), during sea out of SBR1, after diving the CA PANEL 27 and 31 stop working. It was identified that the fuse of the specific channel on CXETH board (IAAR rack of SC1 UA04000) was burned. ICN replaced the fuse 2 times already but the issue persist after every sea out. ICN request technical information regarding the issue. | ICN request information | - | - | FALSE
209 | NCR-ICN-UFEM-13-0226-2021 | PCP 6.1 PEND MATERIAL | 194 Dias | 98 dias | The Gasket (MAT424-0813_REP 6) was delivered installed in the Vent Valve (CMD 18PA000D00038) without packaging and traceability. The material described in the part list is the "Latty Gold" brand is not used anymore by NG. AG00013 - SMB-330725 - MANUFACTURING OF THE ESCAPE TRUNK HATCHES AG00017 - SMB-330724 - MANUFACTURING OF THE NAVIGATION BRIDGE ACCESS TRUNK HATCHES | Replace the non-conform gasket by NGD 5330145107997 - FLAT GASKET 60 X 79 X 3 FIBER / NBR; Raise a NCR-MAT to supply new parts (minimum 2 units). | Agree with level 1.2 NCR MAT should be raise to purchase new flat gaskets and the nomenclature (MAT424-0814) should be updated. | Replace seals by seals according to STF33-07-02/002E. MAT424-0814 will be updated. | FALSE
210 | NCR-ICN-ESC-13-0057-2021 | PCP 6.1 | 189 Dias | 50 dias | BC02660 + D1A -P3 panel ammeter damaged the protective acrylic. BC02550 + D1A -P3 panel ammeter damaged the protective acrylic. The ammeter + D2A -P1 (Shore Current) of the BC02550 panel damaged the protective acrylic. Here is an attached file with the photos of the damaged ammeters. | Replace ammeters with new ones. Send to level 2 NG specialist. | Due of no protection, replace and take on sbr4 in : BC02550 P1: DEIF AMMETER 72x72 CAL. 0-100mV ECH. 0-250A Cl1,5 Ref fabricant: DQ72-xc (=S= N°2988503 §8). P3: DEIF AMMETER 72x72 CAL. +/-20mA ECH. -7000/0/+2700A Cl1,5 Ref fabricant: DQ72-xv (=S= N°2988503 §7) BC02660 P3: DEIF AMMETER 72x72 CAL. +/-20mA ECH. -7000/0/+2700A Cl1,5 Ref fabricant: DQ72-xv (=S= N°2988503 §7) Open NCR MAT to refund items After the standard exchanhe, please put a protection on the devices | - | FALSE
211 | NCR-ICN-ESC-13-0058-2021 | PROD 6.1 | 176 Dias | 175 dias | During assembly interference has been detected that impossibilities the correct positioning of the plate ST300. | Do the propose in 1.2 as accorded with TA. After the positioning of ST300 weld again the piece that was cutted and inspect 100% VT ,100% PT or MT. NCR level 1 according NCR-ICN-ESC-12-0045-2020. | NCR LEVEL 1 | - | FALSE
212 | NCR-ICN-ESC-13-0060-2021 | Especialista ICN | 173 Dias | 145 dias | It was applied a torque of 30 Nm conform NAVAL GROUP orientation, once in BDM-00075364 guide one application of torque equal 15±2Nm. | Apply torque as directed in the reference document. | A -Several problems occurred on the Forward BS battery cells of the SBR3 (see appendix) 1 - Some SBR3 battery elements have arrived at production with the nuts locked at the terminal head, traces of sulphation, oxidation. Complicated disassembly. 2 - Out of 20 elements 7 had negative voltages, 3 close to zero and 5 less than 1 volt 3 - inconsistency of the tightening torque in BDM-00075364 between sheet 08 which recommends a torque of 29N.m for M12 copper and sheet 16 which recommends a torque of 15N.m for the battery terminals in M12. NG notified ICN as soon as this inconsistency was identified. Sensible task (cleaning, torque ...) to be manage properly in the futur Open an NCR-MAT to supply new spare for Forward battery B - NG is not aware of the same tightening torque problem on the AFT battery unit | - ICN must specify the conditions under which the batteries were stored(in a sealed bag, in a controlled air-conditioned room, etc.). - ICN must open a NCR by points. Even if it is the same material,the 3 anomalies are quite different and therefore need to be treated as a unit. | FALSE
213 | NCR-ICN-ESC-13-0059-2021 | DA 3.2 | 173 Dias | 169 dias | During assembly of Bow Hydroplane Holes 53C-SC3-DP00355 and 53C-SC3-DP00356 folowing the center of sleeve AC34027 according NCR-ICN-ESC-13-0026-2021, differences were identified in relation the Bridge Fin sctruture and positioning of the Acess Trunk. See measurement report attached. | Accept the positioning of the Rudder Holes DP00355 and DP00356 as it is. The Bow Hydroplane Steering Gear will operate normally through the center of the sleeve AC34027. | The mechanical assembly is possible but the acceptation of the difference of position need to be validate by the BO. 7 mm for the position of the center will create a difference of 14 mm of the final position of the hydroplane. The good way is to moove the hull passage at the right position. Send to level 3 in order to take the decision if accept as is or if modify the position of the hull passage. | - | FALSE
214 | NCR-ICN-ESC-13-0061-2021 | DELIN 5.1 | 169 Dias | 34 dias | Before starting the mounting aboard, the 13 NRVs valves that arrived in the batch SMB-RAW-DB404/01 for SBR3 (18CR000D00002) came with the lock tab washer disaligned and already bent in a incorrect position, like can be seen in the photo attached, and in a trial of solving the problem, this tab bent of one these valves was cut. These valves got in warehouse with NEM-21/00374 and the following serial numbers: 18/014; 18/015; 18/016; 18/017; 18/018; 18/019; 18/020; 18/021; 18/022; 18/023; 18/024; 18/025; 18/026. This matter is related to the materials for hull integrity in AC32005; AC32007; AC32009; AC32011; AC32012; AC32013; AC32052; AC33000; AC33002; AC33003; AC33024; AC34024; AC34025. This NCR is about repair the material, so the serial numbers weren't associated with any industrial mark yet. | The material was incorrectly supplied, but it could not be changed its configuration of the supply, cuting, without a NCR to analyse the case. For this problem it's needed dismounting the incorrect washers and the one cut, item 5 (STOP), indicated in MAT177-0297_EXP, and remounting using a new lock tab washer, item 8 of the same document, that should be manufactured following the drawing specifications, accessible in folio 8, if it's not available in warehouse. It's important to pay attention that the smallest tab washer should be aligned with the protuberance in body valve that fit in passage keyway and the largest one should be bent to lock the hexagonal stop part, item 5. After remouting, do a workshop test to granted the clogging-free and the watertightness for each valve, and so, the material will be available to return to stock or to mount on board. In case of mouting on board and if the material is manufactured or not, the material declaration of conformity used to manufacture the news lock washer should be attached in B11.19 of each valves, and the serial number write in this CTE too, on time that there's no B07 for this type of valve. | Agree with proposal | - | FALSE
215 | NCR-ICN-ESC-13-0062-2021 | PROD 6.1 | 165 Dias | 97 dias | ICN requests to use the PELA SBR4 (AP435534) to assembly in SBR3. The CAM HOLDER (MAT422-0109_Ref. 30) of the PELA SBR4 (AP435534) were used in the PELA SBR2 (AP402618) according to NCR-ICN-ESC-12-0215-2020. The LOCATING PIN (MAT422–0109_Ref. 31), were lost during the construction process. 3 units of the STUD ROD M20x120 (MAT422-0109_Ref. 12) were damaged during assembly. See evidences attached. | 1. Take the PELA (AP435534) initially planned for SBR4 and assembly in SBR3; 2. Remove the parts (MAT422-0109_Ref. 12, 30 and 31) from PELA SBR2 (AP402618) and install on PELA (AP435534); 3. Replace all items listed in Annex 1 and open NCR-MAT to supply new parts; | Agree with level 1. Use the material of the list. One test of the material need to be done in order to validate the compatibility of the replaced items. | - | FALSE
216 | NCR-ICN-ESC-13-0063-2021 | CEDOC Closure/Unfounded | 162 Dias | 159 dias | The correct orientation of the mobile AC41019-P0151127 (01PM100D00052-6227186-2015-01) was not done properly in the NCR-ICN-ESC-12-0269-2020 and it occoured cause the ICN production team used the version B of the construction book DEI-331842-80500-12-001 which don't orient well the position of the conections ruch. How is seen in the MAT425-0609 and in the SBH.1A10.TUY.004136_H the DN14 ruchs are for port side and the DN10 ruchs are for starboard side. This matter is related to hull integrity in AC31019. | - | - | - | FALSE
217 | NCR-ICN-ESC-13-0064-2021 | PCP 6.1 | 155 Dias | 33 dias | In the HE Mock Up 3D, the valves HE00180, HE00181 and HE00162 are with the flow direction inverted. Abord the SBR 3, valve HE00162 is inverted and has the wrong CMD: 18RT150D00008 instead of 18RT150D00014 wich is the correct one). Please, change the Valve and install in the right direction, as per MPE diagram ( SMB- 000648_L) | Reinstall the correct HE00162 valve (CMD:18RT150D00014) in the correct direction. | FTG-9514 - Please see SBH.3B22.SMD.004474_I. The seating already updated. If necessary ICN can perform the modification on board. | - | FALSE
218 | NCR-ICN-ESC-13-0065-2021 | Tratamento 6.1 (FS) | 154 Dias | 99 dias | During MS01 inspection on Electric Plant Cradle AM00002 was checked that mounts 7 and 8 (starboard aft) were not attached to the support. The starboard aft portion of the cradle is supported by a jack. It was not possible to correctly measure the compression of the mounts. See attached MS01-1 and MS01-2 (torque of all screws). | Rework of torque and compression control according to DEI-319733-80500-13-001 | NCR LEVEL 1 | - | FALSE
219 | NCR-ICN-ESC-13-0066-2021 | PCP 6.1 | 152 Dias | 62 dias | The FH10101P equipment was lost during the construction process. | Take a new one from SBR4 equipment 53D-FH10101P - P0124035 - CMD 50MD200D00080_3002 INSTALLATION KIT and install in SBR3. Open NCRMAT for SBR4. | Agree with the ICN Decision. | - | FALSE
220 | NCR-ICN-ESC-13-0067-2021 | PCP 6.1 PEND MATERIAL | 148 Dias | 76 dias | Performing the on-board inspection, the damage of "cracked" glass in the UA04000 equipment was verified. | USE FROM ANOTHER SUBMARINE AND OPEN AN "NCR-MAT" FOR NEW SUPPLY. | NG TA confirm, that the creen is damaged and it is necessary to change it. It is always the same issue, ther are not protection on the equipments, and du to that the equipement are dusty, scratches and finally damged. Look the picture (in annexure) take on 11 august 2021, none protection on all UA cabinets. Raise a NCR MAT to re-order a new screen, The ole, damaged screen will be change only when a new screen will be available, And protect thes Equipment with scrutiny and efficience... 02-09-2021: ICN should now the CMD/NGD of equipments. | - | FALSE
221 | NCR-ICN-ESC-13-0068-2021 | Especialista ICN | 140 Dias | 110 dias | Swivel Hose DM20002 was installed with the storage deadline exceeded. | Wait for NG orientation. | - | - | FALSE
222 | NCR-ICN-ESC-13-0069-2021 | PROD 6.1 | 120 Dias | 106 dias | During the assembly of the KT23371 panel, there was an interference with the seating of the ventilation duct. Seating P4023966 was mounted out of coordinate, as identified in the annex 3D. | Remove the seating and install again according to the drawning and CTE´s annexed. | remove the seating , proceed to nital attack to remove completly austenitic welding, US inspection to check the thickness and perform NCR/RO to build up if necessary in order to respect nominal thickness. re-install new seating in accordance with correct coordonate. carrry out of NDT. | - | FALSE
223 | NCR-ICN-UFEM-13-0227-2021 | DA 3.2 | 118 Dias | 34 dias | 1) The Recess for Lock of Threaded Ring (NGD REP0000005309 - MAT424-1054_Ref. 1) was not completely machined in the manufacturing phase. See picture in Annex A and MAT424-0704 (section C-C); 2) The Hatch Cover (MAT424-1054_Ref. 2) doesn’t have traceability, not visible on the hatch and nothing on the label delivered. 3) The dimensions of SMAC Lip Seal (NGD 5330930186238 / CMD 44JO320D00002) are not conform to MAT424-1296_B. See report attached as requested by TA-NG. 53C-SC2A-AG00013. | 1) The recess for lock of Threaded Ring must be redone to achieve the final measurements according MAT424-0704 (section C-C). A G06 inspection sheet must be done to validate the rework; 2) Waiting for serial number from Naval Group; 3) Continue the hatch assembly with SMAC lip seal and perform the Resistance Test at PEH (70 bar) in the Hyperbaric Chamber. Open a NCR-MAT to supply new seal manufactured according MAT424-1296_B. The Leak Test (PEE) will be validate after vacuum test with the new seal. The non-conform seals must be send to Naval Group analysis. | Agree with proposal: 1) finish the machining 2) Hatch cover was manufacture by CRONOS and serial number is: 41SBR03-01-1/1 3) Continue with SMAC all of pressure tests. The seal will stay on the panel until decision of NG to accept as it is or not. | - | FALSE
224 | NCR-ICN-ESC-13-0070-2021 | PCP 6.1 | 118 Dias | 118 dias | It was identified a damaged on pipe P4149781, creating a final thickness less the minimum authorized. We ask authorization for a simple remanufacture of the pipe. | Manufacture the Spool according to project definition. | NCR LEVEL 1 | - | FALSE
225 | NCR-ICN-ESC-13-0071-2021 | CQ 7.1 | 118 Dias | 74 dias | To make possible the assembly of pipes P4167453 and P4183895 it was necessary to change the position of the straub between this two itens as presented in the attached files. We ask to accept as it is. | ICN ask to accept as it is. | Accept as it is, according to FTG-9522 attached | - | FALSE
226 | NCR-ICN-ESC-13-0072-2021 | PCP 6.1 PEND MATERIAL | 116 Dias | 89 dias | In compliance with OM-120973 (RAI-SBR1-04350-200560) referring to SBR1, internal conductors number 73 of panels BF02504 and BF02505 of SBR3 were removed to be installed in SBR1. | Open NCR MAT to supply replacement material in SBR3. | Remount the cables dismounted on sbr1 into the sbr3 and wait the pins missing to realize the OM-120973. This NCR can be closed only after the OM done. | - | FALSE
227 | NCR-ICN-ESC-13-0073-2021 | CQ 7.1 | 112 Dias | 71 dias | EV63624R cable connector belonging to EV13503N equipment was lost during the construction process. | Provide a new connector. | Take on SBR4 if available Open a NCR-MAT to supply the lost connector (FED F 10M T03-14 E123) | - | FALSE
228 | NCR-ICN-ESC-13-0075-2021 | PCP 6.1 | 106 Dias | 63 dias | During the final assembly of EJ00132 it was identified that the flange rotation was not in agreement with what was done, now we need to disassembly the lower pipe (EJ50048E2) and rotate the flange. Today is impossible to remove the pipe without cutting it, there is no room for disassembly. Also another interference was found, it is impossible to perform the assembly of EJ50048E2 and EJ00132 with the clamp P4126696 welded in final position. To adjust the pipe to the new condition it was necessary to add a straub union on P4126686 as presented in the drawing (annex 1). | ICN suggests adjusting the pipe to the new condition, it being necessary to add a straub union on the P4126686 as there is not enough space to remove the spool as shown in the drawing (see annex 1). | Remove the pipe P4126686 to put the flange in the correct position . Realize the inspection N01. NG autorize the addition of a Straub to make possible the mounting of the pipe P4126686 because it is a circuit without pressure (0.5 b). | - | FALSE
229 | NCR-ICN-ESC-13-0079-2021 | Especialista ICN | 97 Dias | 82 dias | Cable connectors OO64010B and OO64001B belonging to the DT04310 equipment were damaged. | Use the supplied connectors for the OO64010B and OO64001B cables supplied for the equipment "DT04310" (SBR4) and open an "NCR-MAT" for a new supply. | - | - | FALSE
230 | NCR-ICN-ESC-13-0078-2021 | DA 3.2 | 97 Dias | 50 dias | When starting the connection of the FC00520 equipment to the SBR3, the connection of the FC62620I cable to the terminal block TB01 in numbers 23/24/25, it was verified that the terminal block is smaller than the diameter of the cable whose nature is FZH CABLE 3X10MM2. I emphasize that due to the nature of the cable being FZH the terminal block needs to be a number above, so the 10MM2 cable needs a 16 MM2 terminal block. | This inconsistency needs to be analyzed by the NAVAL GROUP so that a "modification order" is created to solve the problem. | Send to level 3 to analize Wait for BO orientation | - | FALSE
231 | NCR-ICN-ESC-13-0076-2021 | PCP 6.1 | 98 Dias | 43 dias | According to the attached image, the shim provided for the equipment (14SE300D00084 - SHOCK CABLE TYPE 20-15-10_2) is not suitable, not supporting the weight of the equipment. | Rework. Perform the assemble of the 53C-DB02501 equipment with the new item 53C-DB02501S - 53C-P4124785 - CMD 14SE300D00084 - CABLE SHOCK ABSORBERS HELICAL-TYPE 20-15 as specified. NG Please check the project specifications if it changes. | Agree with level 1. Perform the assemble of the 53C-DB02501 equipment with the new item 53C-DB02501S - 53C-P4124785 - CMD 14SE300D00084 - CABLE SHOCK ABSORBERS HELICAL-TYPE 20-15 as specified | - | FALSE
232 | NCR-ICN-ESC-13-0097-2021 | DELIN 5.1 | 62 Dias | 1 dias | Shock absorber with the description "CABLE SHOCK ABSORBERS HELICAL-TYPE 20-15" and CMD 14SE300D00084 applied to the equipment DB02501 is not suitable for the equipment. Attached are images of the equipment installed with the supplied shock absorber. | It is necessary to update the technical specifications of the shims to be used in the installation of the "DB02501" equipment. | Apply the SBR1 solution, use CABLE SHOCK ABSORBERS 14SE300D00006 | - | FALSE
233 | NCR-ICN-ESC-13-0077-2021 | CQ 7.1 | 98 Dias | 82 dias | The base AM00004 of compartment B202 has been painted in accordance with Construction Book DEI-319315-63110-11-001 Revision A with C3 (top) paint system and D3 (bottom) paint system. In revision B of the Construction booklet DEI-319315-63110-12-001, Base AM00004 is treated as a support above the 500 mm line painted with scheme D1, in DEI-319315-63110-11-001 Revision A, Base AM00004 is treated as an access platform. | The applied schene paint is enough for the integrity of the anti-corrosive protection as it is not a critical area according to SMB-002345 | Accept as it is | - | FALSE
234 | NCR-ICN-ESC-13-0080-2021 | PCP 6.1 | 97 Dias | 9 dias | There was a mistake in the connecting piece welded to EV20259 (making impossible to assembly EV12500T) and EV22021(making impossible to assembly EV13500T). Instead of welding the To solve we propose the following actions. Forecasted item: • EV22021 (EV13500T) Remove the pipe from board, cut the connection and weld the correct one. Rework. • EV200259 (EV12500T) Machine from 316L hexagon bar a connecting piece and assembly to tee. We cannot remove the pipe from its position. Attached proposed connector. | NG, please analyze the problem found on board. | Regarding this NCR of SBR3, it is requested to provide an analysis/comparison of the same products on SBR1 and SBR2, to help defining if it is an issue related to construction or definition and to decide on associated action . ICN should provide this analysis | - | FALSE
235 | NCR-ICN-ESC-13-0081-2021 | PCP 6.1 | 97 Dias | 97 dias | During M05 it was identified weld material deposition on the surface of pipe P4128083. After cleaning it was detected a 1,2mm depth defect, that represents 37% of the thickness. We ask to remanufacture the part. To do so it is necessary a new bended weld (18LT3000D00674) a straight part pipe (18LT100D00145, 250mm) and two new weld on the same place as the forecasted ones. | Remanufacture the spool according to the project. | NCR LEVEL 1 | - | FALSE
236 | NCR-ICN-ESC-13-0082-2021 | PROD 6.1 | 97 Dias | 77 dias | Change in seating welding configuration P4181964 e P4171824. It’s not possible to weld and to install the preheating devices of the seating P4181964 e P4171824. (See annex 1). | Use austenitic weld to weld the seating without preheating. Use CTE´s from the job order. | accepted as it is Due to the late delivery of equipment and the location of the welding ( bulkhead with insulation) NG/TA agrees to weld with austenitic process Carry out NDT associated | - | FALSE
237 | NCR-ICN-ESC-13-0083-2021 | Especialista ICN | 95 Dias | 76 dias | Attached is the image of the material that was applied to the cmd 11AC500D00052 for the equipment (amendment) BK22500 and BK22501 of the SBR3, their kits did not come complete. For better understanding, the items that were applied are attached. F1 RD K 20MSH 3-6 07 P1 SOURIAU – 1 unit E44 RD M20 MSH 3-6 H07 P1 F0225 SOURIAU – 1 unit What we need: F1 RD K 20MSH 3-6 07 P1 SOURIAU – 2 units E44 RD M20 MSH 3-6 H07 P1 F0225 SOURIAU – 2 unit | Supply two new complete splice kits and open an "NCR-MAT" for a new supply. | - | - | FALSE
238 | NCR-ICN-ESC-13-0085-2021 | Especialista ICN | 89 Dias | 54 dias | UA66000I cable lost during the construction process. | Supply 16m of cable "ARMORED CABLE SHF2 CLASS 2 - 2 X 4 MM² " to meet the need for loss of cable "UA66000I" and open an "NCR-MAT" for a new supply. | - | - | FALSE
239 | NCR-ICN-ESC-13-0086-2021 | CQ 7.1 | 89 Dias | 53 dias | UA66100I cable connector belonging to the UA06000 equipment was applied incomplete, the same shaft without the pins to make the connection. | Use a new connector (FEDM14TPTTX50J4C46) supplied for another Submarine and open an "NCR-MAT" for a new supply. | Use a connector (FEDM14TPTTX50J4C46) supplied for another Submarine. Open an "NCR-MAT" to supply the lost connector. | - | FALSE
240 | NCR-ICN-ESC-13-0094-2021 | PROD 6.1 | 77 Dias | 11 dias | Optical fiber connectors of the equipment listed below applied with the covers missing, an image of the missing part is attached. Equipment: OO02536 Cables: OO62504B - 4 conductors / OO62505B - ​​4 conductors Equipment: OO02532 Cables: OO62507B - 4 conductors / OO62510B - 4 conductors Equipment: OO02534 Cables: OO62503B - 4 conductors / OO62505B - ​​4 conductors Equipment: OO02531 Cables: OO62508B - 4 conductors / OO62509B - 4 conductors Equipment: OO02530 Cables: OO62508B - 4 conductors / OO62506B - 4 conductors Equipment: OO02533 Cables: OO62509B - 4 conductors / OO62510B - 4 conductors | Provide the missing item or a new set to continue the construction process. | -NG FO agreeds with ICN quality team. The connector housing has to be fitted on the SC connector to have a correct connector. -NG has provided the complete quantity of connectors for OO system. -The connector housing shown on the annex is not what has been delivered by NG to ICN. -ICN has already purchased connectors SC and ST on the local market to replace damaged optical connectors. | - | FALSE
241 | NCR-ICN-ESC-13-0087-2021 | CQ 7.1 | 84 Dias | 76 dias | As CMD 11CD300D00009 is tracked, ICN requests authorization to use EV03501 SERIAL NUMBER: 1/19/013 of SBR4 in SBR3. | Agree with the description. In order to meet the SBR3 assembly process. The as per CMD 11CD300D00009 tracked, ICN requests authorization to use EV03501 SERIAL NUMBER: 1/19/013 of SBR4 in SBR3. See list of CMD in annex. Send to TA NG analysis. | Agree with lv2, use the SBR4. The SBR1 was sent for repair to the supplier under the RTE2020-07-049 | - | FALSE
242 | NCR-ICN-ESC-13-0088-2021 | Tratamento 6.1 (FS) | 83 Dias | 82 dias | The spools below were taken from SBR03 for use in SBR01: P4129698, P4130267, P0105314 and P0105315. | This NCR is to keep the traceability and manufacture of a new one Spool to SBR3. | NCR LEVEL 1 | - | FALSE
243 | NCR-ICN-ESC-13-0089-2021 | Comissionamento 6.1 | 83 Dias | 32 dias | The BC02500 panel U1 power supply failed. We do not have voltage (24Vdc) at the power supply output (U1), the input voltage at the power supply is 115Vac, and at the output it is 0Vdc. | Submit for analysis by the NG L2 specialist; Replace power supply. | The damaged power supply was checked at workshop and we can conclude that it can't be repaired. Take new one in BC02500 on sbr4. Open NCR MAT to refund it and scrap the damaged one. SUPPLY AC/DC 28VDC 40A PHOENIX CONTACT Manufacturer Ref: 2866789 | - | FALSE
244 | NCR-ICN-ESC-13-0090-2021 | CQ 7.1 | 82 Dias | 72 dias | As declared in NCR-ICN-UFEM-12-0409-2019 The design of the spools P4153061, P4153059, P4156293 And P4156292 do not respect the rule of minimum distance between welds (IT-33-04-13E G, item 10.8.6). | To resolve the issue, ICN proposes to accept it as is, as described in NCR-ICN-UFEM-12-0409-2019. and perform the radiographic inspection procedure as if they were category "A" tubes, for products P4153061, P4153059, P4156293, P4128926 and P4156292 see attached list | ACCEPT AS IS Agree with the ICN decision | - | FALSE
245 | NCR-ICN-ESC-13-0092-2021 | PCP 6.1 | 78 Dias | 70 dias | Due to the job sequence is necessary to weld the nuts on the flange before the assembly of the pipe, otherwise it is not possible to assembly with the EW tank on final position. | NG, it is necessary to weld the nuts on the flange before assembling the pipe, please validate the solution found. | Follow the direction of the FTG 8870 in appendix. 4-Actions for option 4-step 2 ( page 6/6) | - | FALSE
246 | NCR-ICN-ESC-13-0093-2021 | TA 7.2 Unfounded | 78 Dias | 75 dias | During the rework forecasted on NCR-ICN-ESC-13-0075-2021 it was necessary to cut the bottle seating P4029629, we ask authorization to do that. | ICN ask authorization to cut the bottle seating P4029629. | - | - | FALSE
247 | NCR-ICN-ESC-13-0091-2021 | CQ 7.1 | 78 Dias | 78 dias | By request of NG the DJ0002 valve - 4 WAYS - 2 POSITIONS MOTORIZED VALVE DN50 - 18SC013D00103 has been tested before being applied to identify a possible problem. The test was performed with the presence of NG, the valve manufacturer (AZ armaturen) and ICN. It was identified that the valve has an opening and closing problem and a force greater than that specified must be applied to perform the work. A valve must be sent to AZ armaturem for solution. | A válvula deve ser entregue a NG, para envio imediato para a fabricante para a solução do problema identificado. | The valve will be repaired by the supplier. Naval group has already started to organize the shipment. Open a NCR-MAT to follow the repair. | - | FALSE
248 | NCR-ICN-UFEM-13-0228-2021 | PCP 6.1 | 77 Dias | 62 dias | Alloy X2 CrNiMo 17 12 03 indicated in MAT 442-0003 is not available for use in item 04, 840 x 110 x 5 plate. ICN requests authorization for replacement, to use alloy X6CrNiTi 18-10. The appendix shows the correlations between the materials. The same problem occurred in SBR2, SBR3 and SBR4. CMD: 01PE200D00093. | Do the change in the material as accorded in the email annexed. | REPAIR Agree to exchange the material like proposed in annex | - | FALSE
249 | NCR-ICN-ESC-13-0095-2021 | Especialista ICN | 67 Dias | 51 dias | The equipment KT08371 and KT08373 was lost from the construction process (limit switch). | Perform the supply new one equipment to attend the SBR3 construction process. 1) For the equipment 53C-KT03121 - 53C-P0132873 - CMD 01PE000D00058 - EXTERNAL DOOR SAFETY ASSEMBLY. Supply new one of 53C-KT08371 (limit switch). 2) For the equipment 53C-KT03123 - 53C-P0132881 - CMD 01PE000D00058 - EXTERNAL DOOR SAFETY ASSEMBLY. Supply new one of 53C-KT08373 (limit switch). Open NCR MAT. | - | - | FALSE
250 | NCR-ICN-ESC-13-0096-2021 | PROD 6.1 | 64 Dias | 40 dias | During the visit of NG's light materials specialist, severe cracks were observed between the glue and the cork fixed to the hull. | Probable retraction of mastic CLR. We suggest don't use of manual CLR. | remove the damaged joint , carry out new joint with CLR mastic ( cartoucha) | - | FALSE
251 | NCR-ICN-ESC-13-0098-2021 | PCP 6.1 | 61 Dias | 44 dias | The PLC cabinet OO02534 (AUX 1/2/3) of the S-BR03 has two power supply QUINT 24VDC/10A Output (Ref. Manufacture: 2866763) missing applied on S-BR02 due to the actions declared on the NCR-ICN-ESC-12-0066-2020. | ICN proposes to use the power supply from S-BR04 (cabinet OO02534). Forward to Naval Group. | Naval Group agrees with ICN proposal. Naval Group will check the progress of new material delivery regarding the NCR-MATs (NCR-MAT-000596-2019 and NCR-MAT-000600-2019). | - | FALSE
252 | NCR-ICN-ESC-13-0099-2021 | DELIN 5.1 | 60 Dias | 1 dias | In 2020, ICN acquired a bicomponent resin, as a free sample, to replace the insulation of the heating resistance terminals of one of the diesel generators of the SBR-1 that needed to be replaced. Now, it is necessary to change the heating resistance of the SBR-3 MEP and we will need to use the same resin to insulate its terminals. Component 1: VonRoll Damival 15120, RM-0060018334, CMD 140745, NEM-20/00657, 0.500 Kg - Lot No: 0000375909 - Validity: 12/2021 - The cans have the same lot. Component 2: VonRoll Damival 15174, RM-0060018334, CMD 141448, NEM-20/00657, 0.275 Kg - Lot No: 0000388917 - Validity: 02/2021 - The cans have the same lot | After analyzing the report, we suggest revalidating this resin for 6 months. | Com already align in regard o inspection result test , the resin can be revalidated for 6 Month | - | FALSE
253 | NCR-ICN-ESC-13-0101-2021 | PCP 6.1 | 53 Dias | 43 dias | During MS02 inspection on FC00528 it was checked that the compression of the resilient mounts was out of tolerance in disagreement with SMB-200949_E. See attached CTE. | NCR Level 1 According to the description it is necessary to adjust the compression of the mounts. | NCR LEVEL 1 | - | FALSE
254 | NCR-ICN-ESC-13-0100-2021 | TA 2.2 Specialist | 53 Dias | 29 dias | Follow the same did at NCR-ICN-ESC-11-1264-2020: "As discussed with Frédéric Guevel, it would be interesting and necessary to intervention in the drains FA22004, FA22005, FA22006, FA22007, which receive oily water from the DAR, due to the accumulation of dirt in the FA50097A junction line. One idea would be to place a protective drain screen type. | Proceed as the same in SBR1. | - | - | FALSE
255 | NCR-ICN-ESC-13-0102-2021 | PCP 6.1 | 51 Dias | 43 dias | During MS01 inspection on EV00010S it was checked the following non conformities: 1- Compression of the resilient mount was out of tolerance. See attached CTE (Annex 1); 2- Due to excessive compression only in aft mounts, there is an unevenness of the upper frame in relation to seating. See photos in Annex 2. | NCR LEVEL 1 Rework according to description and proceed according to SMB-200965. | NCR LEVEL 1 | - | FALSE
256 | NCR-ICN-ESC-13-0104-2021 | CQ 7.1 | 48 Dias | 1 dias | During the construction of SMB-TDP-PR-6748406 and 6748407 for SBR2 was necessary some adaptations as per NCR-ICN-ESC-12-0640-2021. For SBR03 it is necessary to take the same actions to be conform. Please consider the update to according to attached isometric drawings. | ICN requests that NG accept the modifications, so that the modifications can be updated via NCR or update the project again, as without one of these options we cannot reissue the CTE's of unofficial documents. see attached. | AT accept the pipe isometry modification because technically the PR is difficult to apply in the Y axis. Only the Y will not be respected, the X and Z axes will conform to the PR. The 2 important dimensions Z =5,785 and Z=5,741 are respected. Send to the level 3 for aprobation. | As long as the Z-axis dimension is respected (compression time) and the X- and Y-axis dimensions allow for clearance. BO accepts the solution presented by ICN. | FALSE
257 | NCR-ICN-ESC-13-0103-2021 | TA 2.2 Specialist | 50 Dias | 50 dias | The materials of the Snorkel Mast SBR03 was used on SBR01. The ICN mechanics team needs to use the SBR04 items. | Take the parts from SBR 4 and install in SBR 3. See part list in attachment. Open a NCR-MAT to supply new items for SBR 4. | - | - | FALSE
258 | NCR-ICN-ESC-13-0105-2021 | TA 7.2 Unfounded | 44 Dias | 44 dias | The PLC cabinet OO02534 (AUX 1/2/3) of the S-BR03 has two power supply QUINT 24VDC/10A Output (Ref. Manufacture: 2866763) missing applied on S-BR02 due to the problems declared on the NCR-ICN-ESC-12-0066-2020. | Forward to Naval Group. | - | - | FALSE
259 | NCR-ICN-ESC-13-0109-2021 | DELIN 5.1 | 34 Dias | 1 dias | Substitution of rivets. According annex, CMD rivets were provided: 31FR000D00031. P4165625, P4164779, P4165606, P4165608, P4165616, P4165696, P4165609, P4165610, P4165617 e P4165618. | ICN requests the replacement of the rivet provided for the products listed in the annex, by the hermetic stainless steel rivet. | Repair, Change the rivets , use hermetic stainless rivet | - | FALSE
260 | NCR-ICN-ESC-13-0106-2021 | DA 3.2 | 42 Dias | 34 dias | The mobile part AC32085-01PM200D00001-20CH1066129-AP424235 was supplied without the key, item 4 of the MAT426-0578_A F.7, to lock the mobile rotation. | Take the item 4 of the MAT426-0577_B CMD: 01PM200D00002_4001 that was supplied for SBR4 and use on AC32085 of the SBR3. To solve the pending of SBR4 ICN suggest to manufacture a new one key, item 4 MAT426-0577_B using the CMD 01BA110D00159 and do a G06 for dimensional inspection of machining. | Agree with proposal, it's necessary to respect the STF 22-52/B043E and to attach the material certificate | - | FALSE
261 | NCR-ICN-ESC-13-0107-2021 | DELIN 5.1 | 42 Dias | 7 dias | Removal of seatings P4156741 and P4156742 from SBR3 to SBR1. Request the fabrication of seatings for mounting on the SBR3. | Correct the reference for SBR1 and manufacture new seating for sbr3 as per job order. | Rework Rework a new seating as per original | - | FALSE
262 | NCR-ICN-ESC-13-0108-2021 | Comissionamento 6.1 | 34 Dias | 14 dias | NCR-ICN-ESC-11-1450-2021 foi aberto para resolver um problema no conector CN3 de BS02507 de SBR1. Para resolver esse problema, o conector CN3 de BS02507 para SBR3 foi removido e instalado no SBR1. Devido aos avanços nos testes do SBR3, solicito que a NG autorize o uso do conector CN3 do BS02507 do SBR4 no SBR3. | Submit for analysis of TA NG L2; Use connector CN3 from BS02507 from SBR4 to SBR3; When the NCR-MAT connector (NCR-ICN-ESC-11-1450-2021) is provided, it will be installed on the SBR4. | Agree with deliberacao N1 NCR-MAT-001692-2021 is treating the refund of the connector for sbr 4 now | - | FALSE
263 | NCR-ICN-ESC-13-0110-2021 | DA 3.2 | 30 Dias | 0 dias | During the presentation phase was identified an impossibility to mount the pipe P4161492 (DV50064Y1) in a single part. So we kindly request authorization to cut and add a new connection point, as performed in NCR-ICN-ESC-12-0350-2021. | ICN request authorization to cut and add a new connection point, as performed in NCR-ICN-ESC-12-0350-2021. | The current state of assembly in this area (cl89) no longer allows assembly of the pipe P4161492 in a single section. The disassemblies necessary to have access are important and risky in view of the J01 / J03. AT proposes to add an additional connection on the pipe to allow its assembly, same solution applied on sbr 2 (NCR-12-0350) Send to the level 3 for decision. | - | FALSE
264 | NCR-ICN-ESC-13-0111-2021 | DELIN 5.1 | 29 Dias | 2 dias | During the check to make the connection of the FC62550D cable to the FC12550T equipment, it was verified that it was damaged. | Supply a new cable and open an "NCR-MAT" to fill the need. | This cable, burned by coactivity, has to be replaced. Before opening an NCR MAT, check the quantity of cable available in the warehouse. | - | FALSE
265 | NCR-ICN-ESC-13-0113-2021 | DELIN 5.1 | 26 Dias | 7 dias | Seating adjustment P4168967 on board, mounted out of coordinates. It has been checked on board that the detail detached seatings in yellow in the annex have been mounted with the degree inverted. | Remove the seating and install in the correct position. | Rework, After removing the wrong support , carry out a nittal attack and open a HRO if required. After installation of new one carry out a G02 inspection. | - | FALSE
266 | NCR-ICN-ESC-13-0112-2021 | PCP 6.1 | 26 Dias | 1 dias | NCR-ICN-ESC-11-0179-2018 was opened to resolve an issue in the power supply -U3 + P3D (Market power ACR750) on the BC02500 panel of the SBR1. To solve this problem, a power supply -U3 + P3D (Market power ACR750) from BC02500 panel was removed from SBR2 and installed in SBR1. With the tests in progress on the SBR2, it was necessary to remove the power supply -U3 + P3D (Market power ACR750) from the BC02500 panel of the SBR3 and install it on the SBR2. For test sequences on SBR3, I request that NG authorize the use of the power supply -U3 + P3D (Market power ACR750), we have one available in the warehouse with NGD 0930930255329 and another power supply that is installed in the BC02660 panel of the SBR4. | Submit for analysis of TA NG L2; Use the font that is available in the warehouse NGD 0930930255329 or the font that is available in the BC02660 panel of the SBR4; | Naval Group front Office authorizes to take Martek power from the warehouse in order that ICN is able to perform the tests. Dont open NCR MAT | - | FALSE
267 | NCR-ICN-ESC-13-0120-2021 | DELIN 5.1 | 12 Dias | 2 dias | RH62603D cable belonging to RH04310 and RF00001 equipment was lost during the construction process. | Provide a new cable and open an "NCR-MAT" for it. | New cable has to be provided. Before opening an NCR mat, check the availability of this type of cable in the warehouse. | - | FALSE
268 | NCR-ICN-ESC-13-0114-2021 | Comissionamento 5.1 | 21 Dias | 18 dias | During OJT17, while performing an activity on BC02500 with Schneider Team, the Preservation Team detected that a silica gel bag tore inside compartment DG1(P2B) blocking the circuit-breaker extraction device. This NCR is being opened due to requests from TA Benoit. | Preservation Team suggests to clean these compartments. | Naval Group requested that Dg1 (P2B), Dg3 (P2C) and DM1 (P2D) compartments be inspected and vacuumed. A check of the well working of the slides will have to be carried out at the end in the presence of Naval Group. | - | FALSE
269 | NCR-ICN-ESC-13-0115-2021 | Especialista ICN | 15 Dias | 15 dias | It was noticed that some welding arcs were opened on the internal sleeve face AC32003, a hull passage where goes mounted the valve EG00202. | - | - | - | FALSE
270 | NCR-ICN-ESC-13-0116-2021 | Especialista ICN | 15 Dias | 15 dias | It was noticed that some welding arcs were opened on the internal sleeve face AC31014, a hull passage where goes mounted the valve EL00007. | - | - | - | FALSE
271 | NCR-ICN-ESC-13-0117-2021 | DELIN 5.1 | 14 Dias | 2 dias | After applying the resin and demolding the floor in the forward battery compartment, a dimensional inspection of the height and flatness was carried out in accordance with TAF-TA-2018-0884, and deviations were detected in disagreement with the flatness tolerance specified in the TAF- TA-2018-0884. | Repair. Carry out ajust of the planeity one by one with appropriate tools, same like in NCR-ICN-ESC-12-0139-2020. According to the results in annex the floor is not aceptable as it is. The solution to repair: 1 - Perform mark on the ground each position of the batterie; 2 - Carry out check the planeity one by one with a steel plate (500x360); 3 - With the jig plate, carry out ajust the horizontability; The area to be reworked will be a gap >1mm compared to the nominal high of each floors . Upon rework done, the measurements have be take and reported After repair, accept as it is. | Agree with proposal level1. Make a inspection after adjusting the floor and made a report to show if it will be possible to connect the battery like done in SBR2. When this report will be done please update this NCR to check if it is acceptable or not. | - | FALSE
272 | NCR-ICN-ESC-13-0118-2021 | DELIN 5.1 | 14 Dias | 2 dias | After applying the resin and demolding the floor in the aft battery compartment, a dimensional inspection of the height and flatness was carried out in accordance with TAF-TA-2018-0884, and deviations were detected in disagreement with the flatness tolerance specified in the TAF-TA -2018-0884. | Repair. Carry out ajust of the planeity one by one with appropriate tools, same like in NCR-ICN-ESC-12-0139-2020. According to the results in annex the floor is not aceptable as it is. The solution to repair: 1 - Perform mark on the ground each position of the batterie; 2 - Carry out check the planeity one by one with a steel plate (500x360); 3 - With the jig plate, carry out ajust the horizontability; The area to be reworked will be a gap >1mm compared to the nominal high of each floors . Upon rework done, the measurements have be take and reported After repair, accept as it is. | Agree with proposal level1. Make a inspection after adjusting the floor and made a report to show if it will be possible to connect the battery like done in SBR2. When this report will be done please update this NCR to check if it is acceptable or not. | - | FALSE
273 | NCR-ICN-ESC-13-0119-2021 | PCP 6.1 | 14 Dias | 8 dias | O make CMD evolution of the EV13502P low pressure detector official. According to COSRIDA-07844 we had an evolution from CMD 50DD200D00041 to 50DD200D00042. “Need to update the doc SMB-002989 (catalogue of measuring chains EV) by NG BO with the new values: High pressure detector EV13501P to calibrate at 1.7 bar Low pressure detector EV13502P to calibrate at 0.7 bar It’s also necessary to update the doc SMB-000616 to modify the CMX of the sensor EV13502P. The CMX 50DD200D00041 concerns a sensor with a adjusting range from 1 to 10 bars. For the EV13502P, we need to change the CMX. A sensor 50DD200D00042 will be in the good adjusting range (from 0.5 to 10 bars).” | Perform the replacement of CMD 50DD200D00041 to 50DD200D00042. | Mount on the SBR3 the sensor EV13501P, CMD: 50DD200D00041 calibrated at 1.7 bar, and the sensor EV13502P, CMD: 50DD200D00042 calibrated at 0.7 bar. The documentations SMB-000616 and SMB-002989 will be update by Naval Group Back Office. | - | FALSE
274 | NCR-ICN-ESC-13-0121-2021 | TA 2.2 Qualité | 1 Dias | 1 dias | The equipment AF31571 was lost during the SBR3 construction process. Doc.: CC-200773-22310-13-001 | Carry out the assembly of a new passage AF31571 - P4138144 - 18PP100D00002. Take this passage from warehouse to SBR3. Open NCR MAT. | - | - | FALSE
275 | NCR-ICN-ESC-13-0122-2021 | TA 2.2 Specialist | 1 Dias | 1 dias | As it is described on e-mail attached, facing the need for SBR1, it was suggested take the valve FQ00103-18RT010D00851-SN.009-MICROMAZZA from SBR3. But after the disassembly it was noticed that the HALAR coating is damaged. | 1. Remount a new one valve, taking care to protect the coating during mounting process. 2. Remember to do the F06 before remounting. 3. Raise a NCR-REGRESS for SBR3 tests carried out. 4. Raise a NCR-MAT to send the damaged valve to repair. | - | - | FALSE
276 | NCR-ICN-ESC-13-0123-2021 | TA 2.2 Specialist | 1 Dias | 0 dias | It was not possible to mount the DA00101 equipment with the supplied fastening elements CMD 32VI120D00775 - SCREW H M14X60X60 A4L-80, the hex head of the screw does not provide an angle for mounting. See attached. It is necessary to modify the fastening elements of screws for cases. | For the equipment 53C-DA00101 - P0102956 – CMD 18CR000D00240 - FOOT VALVE ND32 WITH STRAINER MN FL , it is suggested to change the elements of mounting: 1) The CMD 32VI120D00775 - SCREW H M14X60X60 A4L-80 and CMD 32VI320D00065 - NUT H M14 A4L-80 - 08 Units, will be change by CMD 32VI220D00314 - PITCH DIAM ROD M14X75 EQ NUT X2CRNIMOCUN25-6 (52N) - 4 Units. 2) The CMD 32VI410D00101 - STEEL WASHER N-L ND14 DELTA-PROTEKT - 08 Units, will be change by CMD 32VI420D00083 - INOX SAFETY WASHER STAINLESS NL14SS-23,0-3,0 - 08 Units. | - | - | FALSE
277 | NCR-ICN-ESC-13-0124-2021 | TA 2.2 Qualité | 0 Dias | 0 dias | Equipment lost during the construction process. | USE O EQUIPAMENTO "EF12500B / EF12507B / EF12528B / EF12529B" FORNECIDO PARA O "SBR4" E ABRA UM "NCR-MAT" PARA ATENDER A NECESSIDADE CRIADA NO "SBR4". | - | - | FALSE
278 | NCR-ICN-ESC-13-0125-2021 | TA 2.2 Specialist | 0 Dias | 0 dias | DM00001 and DM00002 equipment connectors were not supplied with the equipment as stated in SMB-351402. | USE THE SUPPLIED CONNECTORS FOR THE "DM0001 AND DM00002 (SBR4)" EQUIPMENT AND OPEN AN "NCR-MAT" TO MEET THE NEED CREATED IN THE "SBR4". | - | - | FALSE
279 | NCR-ICN-ESC-13-0126-2021 | TA 2.2 Specialist | 0 Dias | 0 dias | The NCR-MAT-000895-2020 was opened to solve a problem in the PCB08 and PCB09 power supply boards in the BF02501 (CVT1) board of the SBR1. To solve this problem, the source boards PCB08 and PCB09 from panel BF02501 was removed from SBR3 and installed in SBR1. For test sequences on SBR3, I request that NG authorize the use of two source cards (DU102) PCB08 and PCB09, of which we have two available in the warehouse with NGD 9980000078270 (CARD SUPPLY DU102). | Use two source boards DU102 PCB08 and PCB09 that we have available in the warehouse with NGD 9980000078270 (CARD SUPPLY DU102); Perform inspections F01_BFZ0052, F01_BFZ0026 and F01_BFZ0048. | - | - | FALSE